## Input_Data
No. | Min (day) | Most likely (day) | Max (day) | Predecessor | Type | Lag (day) | Duration and Dependency of Activities_Activity Master Table | No. | Failure name | Probability (%) | Relative delay (%) | Fixed cost increase ($) | EMV ($) | Failure Mode and Effect_Risk Register
A | 76 | 85.5 | 95 | - | - | - |  | A1 | Lack of skilled workers | 20 | 0 | 826 | 165.2
B | 62 | 69 | 76 | A | SS | 45 |  | A2 | Inappropriate regulations | 80 | 45 | 806 | 644.8
C | 27 | 30 | 33 | B | SS | 10 |  | B1 | Unavailability of materials | 20 | 50 | 2348 | 469.6
D | 39 | 45 | 51 | C | SS | 10 |  | C1 | Lack of infrastructure | 40 | 20 | 851 | 340.4
E | 59 | 66 | 73 | D | SS | 10 |  | C2 | Equipment breakdown | 30 | 0 | 980 | 294
F | 49 | 59 | 69 | E | SS | 10 |  | D1 | Lack of infrastructure | 40 | 20 | 851 | 340.4
G | 3 | 3 | 3 | D | FS | 0 |  | D2 | Equipment breakdown | 30 | 0 | 980 | 294
H | 6 | 9 | 12 | G | FS | 0 |  | E1 | Unavailability of materials | 30 | 40 | 5935 | 1780.5
I | 1 | 1 | 1 | H | FS | 0 |  | F1 | Lack of skilled workers | 10 | 30 | 930 | 93
J | 27 | 35.5 | 44 | I | FS | 28 |  | G1 | Lack of infrastructure | 30 | 0 | 851 | 255.3
K | 28 | 30 | 32 | I | FS | 28 |  | H1 | Physical or chemical failure of materials | 25 | 80 | 1755 | 438.75
L | 25 | 30 | 35 | K | SS | 10 |  | I1 | Unavailability of materials | 10 | 15 | 930 | 93
M | 14 | 16 | 18 | L | SS | 15 |  | J1 | Unavailability of materials | 30 | 25 | 2736 | 820.8
N | 14 | 20 | 26 | M | FS | 0 |  | K1 | Physical or chemical failure of materials | 15 | 45 | 2186 | 327.9
O | 43 | 60 | 77 | N | SS | 9 |  | K2 | Unavailability of materials | 5 | 0 | 173 | 8.65
P | 37 | 40 | 43 | O | SS | 40 |  | L1 | Physical or chemical failure of materials | 15 | 45 | 2186 | 327.9
[8 empty] | L2 | Unavailability of materials | 5 | 0 | 173 | 8.65
Project Values | [7 empty] | O1 | Equipment breakdown | 60 | 30 | 893 | 535.8
Project_Start | 2017-03-13 | [6 empty] | P1 | Unavailability of materials | 15 | 10 | 334 | 50.1
Iterations | 50000

## Simulation_Engine
Activity | Random_Seed | Base_Duration | Notes | Risk1_Occur | Risk1_Dly% | Risk1_Dur_Impact | Risk1_Cost | Risk2_Occur | Risk2_Dly% | Risk2_Dur_Impact | Risk2_Cost | Final_Dur | Start_Date | Finish_Date | Pred | Pred_Type | Lag | Total_Cost | Cumulative_Cost
A | 0.27677 | 82.5805 | Beta4(2,2,76,95) | 1 | 0 | 0 | 826 | 1 | 45 | 37.1612 | 806 | 119.7417 | 2017-03-13 | 2017-07-10 17:48 | - | - | - | 1632 | 1632
B | 0.70792 | 70.9946 | Beta4(2,2,62,76) | 1 | 50 | 35.4973 | 2348 | 0 | 0 | 0 | 0 | 106.4919 | 2017-04-27 | 2017-08-11 11:48 | A | SS | 45 | 2348 | 3980
C | 0.59511 | 30.3825 | Beta4(2,2,27,33) | 1 | 20 | 6.0765 | 851 | 1 | 0 | 0 | 980 | 36.459 | 2017-05-07 | 2017-06-12 11:01 | B | SS | 10 | 1831 | 5811
D | 0.40179 | 44.2097 | Beta4(2,2,39,51) | 1 | 20 | 8.8419 | 851 | 1 | 0 | 0 | 980 | 53.0517 | 2017-05-17 | 2017-07-09 01:14 | C | SS | 10 | 1831 | 7642
E | 0.93949 | 70.9045 | Beta4(2,2,59,73) | 1 | 40 | 28.3618 | 5935 | 0 | 0 | 0 | 0 | 99.2662 | 2017-05-27 | 2017-09-03 06:23 | D | SS | 10 | 5935 | 13577
F | 0.31173 | 56.4333 | Beta4(2,2,49,69) | 1 | 30 | 16.93 | 930 | 0 | 0 | 0 | 0 | 73.3633 | 2017-06-06 | 2017-08-18 08:43 | E | SS | 10 | 930 | 14507
G | 0.17981 | 3 | Beta4(2,2,3,3) | 1 | 0 | 0 | 851 | 0 | 0 | 0 | 0 | 3 | 2017-08-18 08:43 | 2017-08-21 08:43 | D | FS | 0 | 851 | 15358
H | 0.5049 | 9.0196 | Beta4(2,2,6,12) | 1 | 80 | 7.2157 | 1755 | 0 | 0 | 0 | 0 | 16.2353 | 2017-08-21 08:43 | 2017-09-06 14:22 | G | FS | 0 | 1755 | 17113
I | 0.46629 | 1 | Beta4(2,2,1,1) | 1 | 15 | 0.15 | 930 | 0 | 0 | 0 | 0 | 1.15 | 2017-09-06 14:22 | 2017-09-07 17:58 | H | FS | 0 | 930 | 18043
J | 0.29958 | 33.1702 | Beta4(2,2,27,44) | 1 | 25 | 8.2925 | 2736 | 0 | 0 | 0 | 0 | 41.4627 | 2017-10-05 17:58 | 2017-11-16 05:04 | I | FS | 28 | 2736 | 20779
K | 0.6518 | 30.4106 | Beta4(2,2,28,32) | 1 | 45 | 13.6848 | 2186 | 1 | 0 | 0 | 173 | 44.0953 | 2017-12-14 05:04 | 2018-01-27 07:22 | I | FS | 28 | 2359 | 23138
L | 0.88655 | 32.9033 | Beta4(2,2,25,35) | 1 | 45 | 14.8065 | 2186 | 1 | 0 | 0 | 173 | 47.7097 | 2017-12-24 05:04 | 2018-02-09 22:06 | K | SS | 10 | 2359 | 25497
M | 0.98916 | 17.7545 | Beta4(2,2,14,18) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.7545 | 2018-01-08 05:04 | 2018-01-25 23:11 | L | SS | 15 | 0 | 25497
N | 0.98556 | 25.1469 | Beta4(2,2,14,26) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.1469 | 2018-01-25 23:11 | 2018-02-20 02:42 | M | FS | 0 | 0 | 25497
O | 0.73412 | 65.4985 | Beta4(2,2,43,77) | 1 | 30 | 19.6495 | 893 | 0 | 0 | 0 | 0 | 85.148 | 2018-02-03 23:11 | 2018-04-30 02:44 | N | SS | 9 | 893 | 26390
P | 0.34476 | 39.3698 | Beta4(2,2,37,43) | 1 | 10 | 3.937 | 334 | 0 | 0 | 0 | 0 | 43.3067 | 2018-03-15 23:11 | 2018-04-28 06:32 | O | SS | 40 | 334 | 26724
Project Summary | Total Duration | 411.2725 | days
| Total Cost | 26724 | $
Formulas:
Start_Date = IF([Pred_Type]="SS",[Start_Date, row above]+[Lag],IF([Pred_Type]="FS",[Finish_Date, row above]+[Lag],[Start_Date, row above]))
Finish_Date = [Start_Date]+[Final_Dur]

## Results
Iteration | Duration | Cost | Duration Statistics |  | Cost Statistics |  | Deterministic Comparison |  | Confidence Levels
1 | 436.2644 | 26724 | Mean | 416.3868 | Mean | 26724 | Duration | 281 | 80% | 423.4308
2 | 409.4155 | 26724 | Standard Deviation | 8.0559 | Standard Deviation | 0 | Cost | 0 | 85% | 425.0101
3 | 407.7462 | 26724 | Minimum | 389.802 | Minimum | 26724 | Mean Difference (Days) | 135.3868 | 90% | 426.8994
4 | 431.2116 | 26724 | Maximum | 442.6626 | Maximum | 26724 | Cost Overrun Expected | 26724 | 95% | 429.6535
5 | 414.7429 | 26724 | 10th Percentile | 405.9106 | Probability>$20000 | 1 | P(Finish on Time) | 0
6 | 420.7681 | 26724 | 50th Percentile | 416.3715 | Probability>$25000 | 1 | P(On Budget) | 0
7 | 424.2017 | 26724 | 90th Percentile | 426.8994 | Probability>$30000 | 0
8 | 401.8886 | 26724 | Probability>281 days | 1
9 | 436.6023 | 26724 | Probability>300 days | 1
10 | 408.7547 | 26724 | Probability>350 days | 1
11 | 419.4891 | 26724 | Probability>450 days | 0
12 | 403.1958 | 26724
13 | 419.9162 | 26724
14 | 411.8518 | 26724
15 | 410.6093 | 26724
16 | 412.0112 | 26724
17 | 401.3338 | 26724
18 | 412.7956 | 26724
19 | 427.6916 | 26724
20 | 416.909 | 26724
21 | 410.3166 | 26724
22 | 413.65 | 26724
23 | 418.6939 | 26724
24 | 400.5793 | 26724
25 | 412.9864 | 26724
26 | 405.542 | 26724
27 | 410.7871 | 26724
28 | 409.1292 | 26724
29 | 421.7062 | 26724
30 | 433.9945 | 26724
31 | 429.4237 | 26724
32 | 429.0761 | 26724
33 | 411.6674 | 26724
34 | 415.7771 | 26724
35 | 417.6801 | 26724
36 | 411.5172 | 26724
37 | 424.6597 | 26724
38 | 410.2798 | 26724
39 | 411.0159 | 26724
40 | 415.9475 | 26724
41 | 425.9643 | 26724
42 | 420.7792 | 26724
43 | 432.5571 | 26724
44 | 420.617 | 26724
45 | 422.1973 | 26724
46 | 419.1979 | 26724
47 | 418.452 | 26724
48 | 413.0475 | 26724
49 | 417.9058 | 26724
50 | 426.6543 | 26724
51 | 410.8532 | 26724
52 | 401.7715 | 26724
53 | 397.3118 | 26724
54 | 419.563 | 26724
55 | 411.9667 | 26724
56 | 420.1987 | 26724
57 | 416.3201 | 26724
58 | 411.964 | 26724
59 | 412.2795 | 26724
60 | 413.1484 | 26724
61 | 406.3759 | 26724
62 | 407.7067 | 26724
63 | 416.9796 | 26724
64 | 415.8044 | 26724
65 | 421.9557 | 26724
66 | 426.4546 | 26724
67 | 420.4198 | 26724
68 | 404.4941 | 26724
69 | 426.2689 | 26724
70 | 415.937 | 26724
71 | 418.3316 | 26724
72 | 430.7991 | 26724
73 | 415.8102 | 26724
74 | 405.6292 | 26724
75 | 415.1496 | 26724
76 | 418.889 | 26724
77 | 414.0035 | 26724
78 | 412.5137 | 26724
79 | 419.3947 | 26724
80 | 414.0675 | 26724
81 | 423.0758 | 26724
82 | 414.4352 | 26724
83 | 433.3626 | 26724
84 | 411.5417 | 26724
85 | 410.604 | 26724
86 | 401.0166 | 26724
87 | 433.4749 | 26724
88 | 409.2886 | 26724
89 | 405.8878 | 26724
90 | 408.5864 | 26724
91 | 422.8831 | 26724
92 | 413.9506 | 26724
93 | 402.7094 | 26724
94 | 418.8202 | 26724
95 | 430.0417 | 26724
96 | 415.6684 | 26724
97 | 413.7827 | 26724
98 | 416.3786 | 26724
99 | 400.697 | 26724
100 | 407.7681 | 26724
101 | 430.5692 | 26724
102 | 404.8326 | 26724
103 | 409.5079 | 26724
104 | 407.3997 | 26724
105 | 413.4377 | 26724
106 | 431.0155 | 26724
107 | 406.3358 | 26724
108 | 418.0114 | 26724
109 | 420.2502 | 26724
110 | 414.6871 | 26724
111 | 401.2644 | 26724
112 | 430.6716 | 26724
113 | 429.3034 | 26724
114 | 415.3948 | 26724
115 | 400.875 | 26724
116 | 423.7738 | 26724
117 | 408.8726 | 26724
118 | 407.286 | 26724
119 | 420.0744 | 26724
120 | 408.0948 | 26724
121 | 420.3984 | 26724
122 | 419.1937 | 26724
123 | 425.1148 | 26724
124 | 432.2811 | 26724
125 | 406.3712 | 26724
126 | 414.4756 | 26724
127 | 419.1225 | 26724
128 | 419.8386 | 26724
129 | 419.1882 | 26724
130 | 421.1289 | 26724
131 | 409.3038 | 26724
132 | 424.0961 | 26724
133 | 418.1803 | 26724
134 | 422.9226 | 26724
135 | 411.5117 | 26724
136 | 425.9899 | 26724
137 | 427.2581 | 26724
138 | 407.1098 | 26724
139 | 418.6146 | 26724
140 | 408.1044 | 26724
141 | 418.5007 | 26724
142 | 411.2816 | 26724
143 | 393.7654 | 26724
144 | 402.1795 | 26724
145 | 420.2662 | 26724
146 | 424.6637 | 26724
147 | 414.5002 | 26724
148 | 414.4277 | 26724
149 | 417.0216 | 26724
150 | 429.4971 | 26724
151 | 428.6093 | 26724
152 | 415.1354 | 26724
153 | 415.9435 | 26724
154 | 413.0137 | 26724
155 | 426.1735 | 26724
156 | 414.5839 | 26724
157 | 429.3223 | 26724
158 | 419.1398 | 26724
159 | 429.6848 | 26724
160 | 425.5037 | 26724
161 | 420.8547 | 26724
162 | 411.9707 | 26724
163 | 403.5897 | 26724
164 | 415.2274 | 26724
165 | 411.3467 | 26724
166 | 421.7174 | 26724
167 | 397.2727 | 26724
168 | 409.4045 | 26724
169 | 415.8881 | 26724
170 | 419.8511 | 26724
171 | 425.8849 | 26724
172 | 425.2835 | 26724
173 | 418.694 | 26724
174 | 415.6889 | 26724
175 | 407.8582 | 26724
176 | 413.1924 | 26724
177 | 407.3132 | 26724
178 | 410.7156 | 26724
179 | 411.7852 | 26724
180 | 420.9136 | 26724
181 | 419.5832 | 26724
182 | 410.1365 | 26724
183 | 416.4943 | 26724
184 | 407.2127 | 26724
185 | 417.4196 | 26724
186 | 410.0838 | 26724
187 | 412.924 | 26724
188 | 412.5198 | 26724
189 | 434.4662 | 26724
190 | 413.7784 | 26724
191 | 400.7701 | 26724
192 | 418.8045 | 26724
193 | 424.8052 | 26724
194 | 431.5617 | 26724
195 | 407.9452 | 26724
196 | 417.927 | 26724
197 | 414.4005 | 26724
198 | 424.093 | 26724
199 | 418.6945 | 26724
200 | 408.0757 | 26724
201 | 414.9123 | 26724
202 | 421.9296 | 26724
203 | 432.4665 | 26724
204 | 437.2226 | 26724
205 | 409.5146 | 26724
206 | 399.7613 | 26724
207 | 421.0877 | 26724
208 | 417.1237 | 26724
209 | 412.8977 | 26724
210 | 410.6456 | 26724
211 | 410.0469 | 26724
212 | 417.7313 | 26724
213 | 425.6919 | 26724
214 | 420.9094 | 26724
215 | 428.416 | 26724
216 | 429.2022 | 26724
217 | 427.0237 | 26724
218 | 433.7566 | 26724
219 | 412.4623 | 26724
220 | 420.4277 | 26724
221 | 421.6944 | 26724
222 | 414.0336 | 26724
223 | 417.9798 | 26724
224 | 414.0356 | 26724
225 | 403.042 | 26724
226 | 409.6641 | 26724
227 | 404.7311 | 26724
228 | 407.9099 | 26724
229 | 415.09 | 26724
230 | 423.4471 | 26724
231 | 417.8395 | 26724
232 | 414.3266 | 26724
233 | 409.069 | 26724
234 | 416.2279 | 26724
235 | 425.6974 | 26724
236 | 415.3601 | 26724
237 | 419.0293 | 26724
238 | 431.631 | 26724
239 | 415.617 | 26724
240 | 421.8004 | 26724
241 | 405.1469 | 26724
242 | 416.005 | 26724
243 | 422.362 | 26724
244 | 411.7383 | 26724
245 | 418.5972 | 26724
246 | 418.6947 | 26724
247 | 422.689 | 26724
248 | 410.9772 | 26724
249 | 417.6274 | 26724
250 | 426.3296 | 26724
251 | 432.0844 | 26724
252 | 413.9292 | 26724
253 | 412.333 | 26724
254 | 415.0834 | 26724
255 | 421.5941 | 26724
256 | 404.0334 | 26724
257 | 410.9681 | 26724
258 | 429.2091 | 26724
259 | 424.3546 | 26724
260 | 405.196 | 26724
261 | 410.9559 | 26724
262 | 410.3614 | 26724
263 | 423.1423 | 26724
264 | 426.8985 | 26724
265 | 404.4567 | 26724
266 | 424.7768 | 26724
267 | 410.0666 | 26724
268 | 426.8975 | 26724
269 | 421.2555 | 26724
270 | 425.5867 | 26724
271 | 429.3957 | 26724
272 | 421.8484 | 26724
273 | 421.1904 | 26724
274 | 418.0092 | 26724
275 | 410.0714 | 26724
276 | 414.9351 | 26724
277 | 418.5588 | 26724
278 | 425.0399 | 26724
279 | 412.0704 | 26724
280 | 407.3576 | 26724
281 | 414.918 | 26724
282 | 416.2313 | 26724
283 | 413.2461 | 26724
284 | 402.648 | 26724
285 | 413.2478 | 26724
286 | 420.8765 | 26724
287 | 413.6345 | 26724
288 | 415.9396 | 26724
289 | 417.7817 | 26724
290 | 425.4981 | 26724
291 | 409.4599 | 26724
292 | 417.5209 | 26724
293 | 412.1449 | 26724
294 | 405.8856 | 26724
295 | 418.7393 | 26724
296 | 430.1961 | 26724
297 | 431.815 | 26724
298 | 411.9913 | 26724
299 | 411.6155 | 26724
300 | 425.3423 | 26724
301 | 418.289 | 26724
302 | 413.7869 | 26724
303 | 423.7304 | 26724
304 | 412.9576 | 26724
305 | 419.7154 | 26724
306 | 420.7908 | 26724
307 | 424.233 | 26724
308 | 427.8057 | 26724
309 | 422.6949 | 26724
310 | 396.2154 | 26724
311 | 410.1426 | 26724
312 | 416.7088 | 26724
313 | 409.9094 | 26724
314 | 420.1632 | 26724
315 | 407.5051 | 26724
316 | 405.5907 | 26724
317 | 413.4047 | 26724
318 | 412.2634 | 26724
319 | 405.9745 | 26724
320 | 419.9717 | 26724
321 | 405.8085 | 26724
322 | 430.2839 | 26724
323 | 427.0581 | 26724
324 | 404.3606 | 26724
325 | 420.472 | 26724
326 | 416.5482 | 26724
327 | 422.4629 | 26724
328 | 423.4739 | 26724
329 | 416.2657 | 26724
330 | 407.5082 | 26724
331 | 410.912 | 26724
332 | 405.1316 | 26724
333 | 418.9807 | 26724
334 | 422.1825 | 26724
335 | 400.5599 | 26724
336 | 416.7885 | 26724
337 | 421.264 | 26724
338 | 412.001 | 26724
339 | 420.6998 | 26724
340 | 410.8271 | 26724
341 | 410.4359 | 26724
342 | 432.8821 | 26724
343 | 417.997 | 26724
344 | 423.5796 | 26724
345 | 420.7741 | 26724
346 | 413.8721 | 26724
347 | 410.8373 | 26724
348 | 415.6745 | 26724
349 | 421.4084 | 26724
350 | 412.2996 | 26724
351 | 422.3751 | 26724
352 | 405.5638 | 26724
353 | 425.7872 | 26724
354 | 406.5561 | 26724
355 | 420.8077 | 26724
356 | 411.305 | 26724
357 | 421.6712 | 26724
358 | 415.1023 | 26724
359 | 415.9099 | 26724
360 | 433.5309 | 26724
361 | 425.875 | 26724
362 | 425.0251 | 26724
363 | 413.4522 | 26724
364 | 418.5789 | 26724
365 | 424.6731 | 26724
366 | 427.4343 | 26724
367 | 409.1641 | 26724
368 | 417.7009 | 26724
369 | 401.8319 | 26724
370 | 424.2602 | 26724
371 | 415.5932 | 26724
372 | 413.06 | 26724
373 | 409.4218 | 26724
374 | 417.1089 | 26724
375 | 408.0362 | 26724
376 | 415.3697 | 26724
377 | 419.6941 | 26724
378 | 410.0598 | 26724
379 | 413.6197 | 26724
380 | 411.6547 | 26724
381 | 419.9869 | 26724
382 | 400.5034 | 26724
383 | 395.1004 | 26724
384 | 410.0799 | 26724
385 | 402.4596 | 26724
386 | 409.0642 | 26724
387 | 419.2252 | 26724
388 | 418.2071 | 26724
389 | 413.8796 | 26724
390 | 426.2709 | 26724
391 | 420.1394 | 26724
392 | 407.4076 | 26724
393 | 421.0526 | 26724
394 | 419.1659 | 26724
395 | 399.943 | 26724
396 | 421.9436 | 26724
397 | 416.5193 | 26724
398 | 427.6718 | 26724
399 | 412.7923 | 26724
400 | 414.1795 | 26724
401 | 410.7296 | 26724
402 | 413.0185 | 26724
403 | 424.6804 | 26724
404 | 405.3552 | 26724
405 | 416.3597 | 26724
406 | 431.638 | 26724
407 | 406.872 | 26724
408 | 403.5826 | 26724
409 | 407.442 | 26724
410 | 415.6603 | 26724
411 | 419.6386 | 26724
412 | 415.1544 | 26724
413 | 413.4159 | 26724
414 | 416.2492 | 26724
415 | 427.4925 | 26724
416 | 434.1254 | 26724
417 | 421.4013 | 26724
418 | 412.5662 | 26724
419 | 413.0202 | 26724
420 | 412.8186 | 26724
421 | 414.3067 | 26724
422 | 421.5828 | 26724
423 | 421.7004 | 26724
424 | 421.7265 | 26724
425 | 404.248 | 26724
426 | 401.4917 | 26724
427 | 419.3851 | 26724
428 | 421.4964 | 26724
429 | 413.7361 | 26724
430 | 403.5093 | 26724
431 | 405.3438 | 26724
432 | 415.7092 | 26724
433 | 407.4032 | 26724
434 | 432.8198 | 26724
435 | 432.1021 | 26724
436 | 404.1714 | 26724
437 | 405.4381 | 26724
438 | 416.6307 | 26724
439 | 426.7628 | 26724
440 | 402.8428 | 26724
441 | 411.2717 | 26724
442 | 409.5801 | 26724
443 | 424.6208 | 26724
444 | 435.477 | 26724
445 | 423.9745 | 26724
446 | 412.554 | 26724
447 | 415.5958 | 26724
448 | 425.7884 | 26724
449 | 411.2995 | 26724
450 | 406.8201 | 26724
451 | 416.6188 | 26724
452 | 417.8036 | 26724
453 | 422.4875 | 26724
454 | 428.9045 | 26724
455 | 418.7559 | 26724
456 | 408.0314 | 26724
457 | 429.834 | 26724
458 | 410.5277 | 26724
459 | 425.6422 | 26724
460 | 410.588 | 26724
461 | 404.0751 | 26724
462 | 422.5785 | 26724
463 | 425.5319 | 26724
464 | 427.1349 | 26724
465 | 406.0918 | 26724
466 | 430.0877 | 26724
467 | 412.5741 | 26724
468 | 414.7316 | 26724
469 | 420.9474 | 26724
470 | 406.7524 | 26724
471 | 435.2375 | 26724
472 | 431.7516 | 26724
473 | 417.2046 | 26724
474 | 413.5663 | 26724
475 | 401.4092 | 26724
476 | 420.0284 | 26724
477 | 402.2401 | 26724
478 | 410.0078 | 26724
479 | 420.7192 | 26724
480 | 423.1335 | 26724
481 | 421.2141 | 26724
482 | 409.0264 | 26724
483 | 423.2386 | 26724
484 | 420.5325 | 26724
485 | 416.8493 | 26724
486 | 416.9524 | 26724
487 | 408.1392 | 26724
488 | 413.1735 | 26724
489 | 439.504 | 26724
490 | 404.6659 | 26724
491 | 421.7887 | 26724
492 | 419.65 | 26724
493 | 435.0156 | 26724
494 | 422.0929 | 26724
495 | 425.6957 | 26724
496 | 411.7264 | 26724
497 | 407.9454 | 26724
498 | 427.2709 | 26724
499 | 420.5454 | 26724
500 | 418.5312 | 26724
501 | 410.4275 | 26724
502 | 418.6063 | 26724
503 | 412.9001 | 26724
504 | 413.2134 | 26724
505 | 410.8477 | 26724
506 | 422.6829 | 26724
507 | 413.3961 | 26724
508 | 425.2592 | 26724
509 | 415.5417 | 26724
510 | 411.588 | 26724
511 | 422.8771 | 26724
512 | 419.1652 | 26724
513 | 401.9683 | 26724
514 | 410.4432 | 26724
515 | 418.9618 | 26724
516 | 412.9664 | 26724
517 | 416.316 | 26724
518 | 415.352 | 26724
519 | 410.6811 | 26724
520 | 407.8245 | 26724
521 | 417.8744 | 26724
522 | 428.5988 | 26724
523 | 420.6648 | 26724
524 | 405.6454 | 26724
525 | 409.9014 | 26724
526 | 412.764 | 26724
527 | 415.3551 | 26724
528 | 417.6005 | 26724
529 | 426.3631 | 26724
530 | 410.9905 | 26724
531 | 426.5747 | 26724
532 | 412.0941 | 26724
533 | 427.9179 | 26724
534 | 405.1858 | 26724
535 | 431.6063 | 26724
536 | 408.963 | 26724
537 | 400.5963 | 26724
538 | 405.5033 | 26724
539 | 424.1603 | 26724
540 | 415.5373 | 26724
541 | 428.3963 | 26724
542 | 417.01 | 26724
543 | 420.7711 | 26724
544 | 417.8745 | 26724
545 | 402.2282 | 26724
546 | 420.256 | 26724
547 | 421.3518 | 26724
548 | 406.7369 | 26724
549 | 413.3926 | 26724
550 | 418.3399 | 26724
551 | 413.9147 | 26724
552 | 413.4088 | 26724
553 | 401.2821 | 26724
554 | 405.6864 | 26724
555 | 411.1214 | 26724
556 | 397.4188 | 26724
557 | 409.4971 | 26724
558 | 418.1109 | 26724
559 | 427.5268 | 26724
560 | 423.5062 | 26724
561 | 417.2492 | 26724
562 | 417.5958 | 26724
563 | 420.145 | 26724
564 | 405.101 | 26724
565 | 409.5939 | 26724
566 | 420.4106 | 26724
567 | 416.2366 | 26724
568 | 417.9845 | 26724
569 | 405.9801 | 26724
570 | 407.1098 | 26724
571 | 422.7113 | 26724
572 | 404.2439 | 26724
573 | 419.066 | 26724
574 | 424.3342 | 26724
575 | 420.9407 | 26724
576 | 420.6745 | 26724
577 | 406.7524 | 26724
578 | 424.4089 | 26724
579 | 415.4516 | 26724
580 | 425.9341 | 26724
581 | 411.4789 | 26724
582 | 411.5586 | 26724
583 | 421.2492 | 26724
584 | 400.2548 | 26724
585 | 411.2909 | 26724
586 | 415.3923 | 26724
587 | 407.1016 | 26724
588 | 418.9545 | 26724
589 | 428.3372 | 26724
590 | 410.7059 | 26724
591 | 406.3948 | 26724
592 | 426.0623 | 26724
593 | 401.8952 | 26724
594 | 415.114 | 26724
595 | 422.8859 | 26724
596 | 413.067 | 26724
597 | 409.6134 | 26724
598 | 418.091 | 26724
599 | 422.0777 | 26724
600 | 417.2932 | 26724
601 | 408.6069 | 26724
602 | 399.3182 | 26724
603 | 403.9358 | 26724
604 | 409.128 | 26724
605 | 418.7662 | 26724
606 | 424.0229 | 26724
607 | 426.0828 | 26724
608 | 421.4722 | 26724
609 | 420.932 | 26724
610 | 430.9147 | 26724
611 | 420.2889 | 26724
612 | 409.2095 | 26724
613 | 425.7197 | 26724
614 | 415.5152 | 26724
615 | 420.0326 | 26724
616 | 418.3553 | 26724
617 | 419.8474 | 26724
618 | 412.2148 | 26724
619 | 424.9143 | 26724
620 | 405.5367 | 26724
621 | 408.5053 | 26724
622 | 400.7078 | 26724
623 | 422.4315 | 26724
624 | 415.3502 | 26724
625 | 402.8563 | 26724
626 | 425.023 | 26724
627 | 418.3834 | 26724
628 | 421.846 | 26724
629 | 405.4153 | 26724
630 | 420.8652 | 26724
631 | 415.2227 | 26724
632 | 408.131 | 26724
633 | 422.1537 | 26724
634 | 419.5549 | 26724
635 | 409.9141 | 26724
636 | 419.838 | 26724
637 | 423.3644 | 26724
638 | 425.3895 | 26724
639 | 411.5784 | 26724
640 | 413.9124 | 26724
641 | 427.6641 | 26724
642 | 412.677 | 26724
643 | 413.6556 | 26724
644 | 419.1494 | 26724
645 | 414.0714 | 26724
646 | 411.8118 | 26724
647 | 406.6108 | 26724
648 | 420.6513 | 26724
649 | 419.9033 | 26724
650 | 408.7318 | 26724
651 | 416.7982 | 26724
652 | 412.3607 | 26724
653 | 412.8858 | 26724
654 | 419.7504 | 26724
655 | 412.3185 | 26724
656 | 406.6341 | 26724
657 | 426.9213 | 26724
658 | 421.8321 | 26724
659 | 419.4387 | 26724
660 | 419.8414 | 26724
661 | 422.7842 | 26724
662 | 414.6736 | 26724
663 | 408.086 | 26724
664 | 427.5109 | 26724
665 | 421.7624 | 26724
666 | 411.3276 | 26724
667 | 415.2665 | 26724
668 | 412.4813 | 26724
669 | 416.6953 | 26724
670 | 425.9097 | 26724
671 | 414.5426 | 26724
672 | 404.9888 | 26724
673 | 419.6467 | 26724
674 | 414.9509 | 26724
675 | 412.3414 | 26724
676 | 423.2129 | 26724
677 | 413.2401 | 26724
678 | 420.0209 | 26724
679 | 408.6934 | 26724
680 | 417.6663 | 26724
681 | 412.8667 | 26724
682 | 410.4195 | 26724
683 | 409.4797 | 26724
684 | 406.3992 | 26724
685 | 400.4368 | 26724
686 | 416.2872 | 26724
687 | 418.4077 | 26724
688 | 417.6787 | 26724
689 | 411.9941 | 26724
690 | 398.5707 | 26724
691 | 412.755 | 26724
692 | 431.1431 | 26724
693 | 416.4767 | 26724
694 | 414.3924 | 26724
695 | 426.637 | 26724
696 | 421.0033 | 26724
697 | 425.5081 | 26724
698 | 409.6322 | 26724
699 | 420.4229 | 26724
700 | 412.8518 | 26724
701 | 426.3737 | 26724
702 | 409.9517 | 26724
703 | 425.9702 | 26724
704 | 402.1109 | 26724
705 | 436.947 | 26724
706 | 424.4163 | 26724
707 | 420.9726 | 26724
708 | 421.0865 | 26724
709 | 407.0182 | 26724
710 | 428.2002 | 26724
711 | 422.251 | 26724
712 | 419.7906 | 26724
713 | 429.21 | 26724
714 | 423.6546 | 26724
715 | 423.9201 | 26724
716 | 407.4135 | 26724
717 | 423.8078 | 26724
718 | 412.9894 | 26724
719 | 424.862 | 26724
720 | 422.4824 | 26724
721 | 419.8931 | 26724
722 | 407.1168 | 26724
723 | 419.911 | 26724
724 | 400.7379 | 26724
725 | 411.4402 | 26724
726 | 426.021 | 26724
727 | 408.8476 | 26724
728 | 415.4351 | 26724
729 | 425.8887 | 26724
730 | 415.2525 | 26724
731 | 409.1688 | 26724
732 | 409.3748 | 26724
733 | 409.7474 | 26724
734 | 400.9706 | 26724
735 | 417.4804 | 26724
736 | 416.8118 | 26724
737 | 432.2603 | 26724
738 | 424.7788 | 26724
739 | 415.8512 | 26724
740 | 425.7579 | 26724
741 | 405.6595 | 26724
742 | 408.3158 | 26724
743 | 413.5877 | 26724
744 | 408.5543 | 26724
745 | 410.8125 | 26724
746 | 402.846 | 26724
747 | 412.0461 | 26724
748 | 418.9537 | 26724
749 | 418.4565 | 26724
750 | 410.7356 | 26724
751 | 420.8729 | 26724
752 | 412.9927 | 26724
753 | 409.3453 | 26724
754 | 408.5003 | 26724
755 | 417.1515 | 26724
756 | 413.1982 | 26724
757 | 410.4625 | 26724
758 | 407.5418 | 26724
759 | 415.393 | 26724
760 | 421.1401 | 26724
761 | 432.6003 | 26724
762 | 408.4445 | 26724
763 | 410.4839 | 26724
764 | 411.9887 | 26724
765 | 411.9235 | 26724
766 | 423.2861 | 26724
767 | 419.4509 | 26724
768 | 419.0254 | 26724
769 | 418.9487 | 26724
770 | 419.4373 | 26724
771 | 406.5274 | 26724
772 | 412.2766 | 26724
773 | 406.0465 | 26724
774 | 416.8941 | 26724
775 | 415.193 | 26724
776 | 412.0974 | 26724
777 | 411.0745 | 26724
778 | 430.4974 | 26724
779 | 428.8623 | 26724
780 | 403.3958 | 26724
781 | 420.9155 | 26724
782 | 419.5398 | 26724
783 | 422.298 | 26724
784 | 409.6104 | 26724
785 | 403.2393 | 26724
786 | 404.2735 | 26724
787 | 414.3158 | 26724
788 | 411.683 | 26724
789 | 419.1867 | 26724
790 | 400.3138 | 26724
791 | 416.3807 | 26724
792 | 419.005 | 26724
793 | 410.93 | 26724
794 | 409.3067 | 26724
795 | 417.5734 | 26724
796 | 431.8951 | 26724
797 | 419.3548 | 26724
798 | 409.9825 | 26724
799 | 432.9106 | 26724
800 | 423.5781 | 26724
801 | 414.346 | 26724
802 | 418.7901 | 26724
803 | 431.511 | 26724
804 | 420.8874 | 26724
805 | 407.1314 | 26724
806 | 428.6545 | 26724
807 | 417.1793 | 26724
808 | 420.688 | 26724
809 | 419.8198 | 26724
810 | 432.6624 | 26724
811 | 421.9402 | 26724
812 | 417.4723 | 26724
813 | 419.4889 | 26724
814 | 411.5193 | 26724
815 | 404.2996 | 26724
816 | 412.6839 | 26724
817 | 414.5401 | 26724
818 | 420.2225 | 26724
819 | 423.12 | 26724
820 | 410.3978 | 26724
821 | 419.4277 | 26724
822 | 417.3424 | 26724
823 | 406.7332 | 26724
824 | 423.9333 | 26724
825 | 418.6114 | 26724
826 | 432.9657 | 26724
827 | 413.0869 | 26724
828 | 422.2538 | 26724
829 | 422.7839 | 26724
830 | 413.1493 | 26724
831 | 409.2648 | 26724
832 | 408.7762 | 26724
833 | 423.4228 | 26724
834 | 413.4482 | 26724
835 | 410.4804 | 26724
836 | 411.393 | 26724
837 | 414.0342 | 26724
838 | 415.2035 | 26724
839 | 423.3946 | 26724
840 | 417.6525 | 26724
841 | 413.4561 | 26724
842 | 426.2307 | 26724
843 | 410.3648 | 26724
844 | 418.0579 | 26724
845 | 420.5765 | 26724
846 | 417.4048 | 26724
847 | 414.3298 | 26724
848 | 420.5767 | 26724
849 | 414.2108 | 26724
850 | 422.7288 | 26724
851 | 419.2728 | 26724
852 | 412.2254 | 26724
853 | 410.1361 | 26724
854 | 411.2632 | 26724
855 | 425.0676 | 26724
856 | 419.8435 | 26724
857 | 419.9548 | 26724
858 | 399.1045 | 26724
859 | 420.6916 | 26724
860 | 412.6829 | 26724
861 | 422.453 | 26724
862 | 409.5725 | 26724
863 | 427.2845 | 26724
864 | 419.6625 | 26724
865 | 404.7421 | 26724
866 | 406.8616 | 26724
867 | 404.2121 | 26724
868 | 430.9593 | 26724
869 | 418.2376 | 26724
870 | 421.9813 | 26724
871 | 427.4275 | 26724
872 | 406.9064 | 26724
873 | 434.1633 | 26724
874 | 423.7071 | 26724
875 | 416.7218 | 26724
876 | 418.1727 | 26724
877 | 413.5509 | 26724
878 | 396.2974 | 26724
879 | 400.7002 | 26724
880 | 407.1549 | 26724
881 | 427.2699 | 26724
882 | 422.2336 | 26724
883 | 400.8731 | 26724
884 | 410.0468 | 26724
885 | 421.8113 | 26724
886 | 410.7925 | 26724
887 | 409.3515 | 26724
888 | 415.8381 | 26724
889 | 435.3836 | 26724
890 | 415.2468 | 26724
891 | 422.4868 | 26724
892 | 429.2534 | 26724
893 | 414.5978 | 26724
894 | 416.8775 | 26724
895 | 428.8563 | 26724
896 | 411.2619 | 26724
897 | 420.7263 | 26724
898 | 403.4471 | 26724
899 | 415.076 | 26724
900 | 431.292 | 26724
901 | 424.5151 | 26724
902 | 432.973 | 26724
903 | 426.6202 | 26724
904 | 414.1952 | 26724
905 | 410.5163 | 26724
906 | 426.1702 | 26724
907 | 428.7397 | 26724
908 | 410.5038 | 26724
909 | 415.8213 | 26724
910 | 415.4804 | 26724
911 | 410.1535 | 26724
912 | 424.5563 | 26724
913 | 409.7642 | 26724
914 | 410.8173 | 26724
915 | 417.495 | 26724
916 | 417.705 | 26724
917 | 412.6333 | 26724
918 | 410.7577 | 26724
919 | 422.7736 | 26724
920 | 422.0083 | 26724
921 | 400.355 | 26724
922 | 408.2507 | 26724
923 | 423.8128 | 26724
924 | 405.8047 | 26724
925 | 422.5788 | 26724
926 | 415.7998 | 26724
927 | 422.393 | 26724
928 | 407.1067 | 26724
929 | 417.9094 | 26724
930 | 417.4008 | 26724
931 | 419.8903 | 26724
932 | 417.9182 | 26724
933 | 410.8137 | 26724
934 | 415.628 | 26724
935 | 405.2089 | 26724
936 | 410.4882 | 26724
937 | 416.6407 | 26724
938 | 406.8907 | 26724
939 | 413.1425 | 26724
940 | 413.9899 | 26724
941 | 428.5772 | 26724
942 | 420.7532 | 26724
943 | 407.0863 | 26724
944 | 428.8019 | 26724
945 | 402.3887 | 26724
946 | 400.2375 | 26724
947 | 410.9599 | 26724
948 | 421.3726 | 26724
949 | 415.0471 | 26724
950 | 419.0408 | 26724
951 | 416.9919 | 26724
952 | 421.4894 | 26724
953 | 419.1371 | 26724
954 | 418.1517 | 26724
955 | 397.2503 | 26724
956 | 421.3888 | 26724
957 | 414.4598 | 26724
958 | 416.6752 | 26724
959 | 422.0595 | 26724
960 | 410.2038 | 26724
961 | 421.9615 | 26724
962 | 417.2054 | 26724
963 | 408.948 | 26724
964 | 415.8134 | 26724
965 | 428.9662 | 26724
966 | 425.164 | 26724
967 | 409.6942 | 26724
968 | 417.2656 | 26724
969 | 423.3939 | 26724
970 | 420.3116 | 26724
971 | 421.656 | 26724
972 | 422.4689 | 26724
973 | 415.5652 | 26724
974 | 413.9497 | 26724
975 | 418.7337 | 26724
976 | 415.3927 | 26724
977 | 411.6187 | 26724
978 | 418.8389 | 26724
979 | 420.5011 | 26724
980 | 425.3803 | 26724
981 | 409.5387 | 26724
982 | 410.2745 | 26724
983 | 429.4493 | 26724
984 | 424.6099 | 26724
985 | 412.2012 | 26724
986 | 416.4097 | 26724
987 | 419.9623 | 26724
988 | 407.1579 | 26724
989 | 421.7603 | 26724
990 | 409.0451 | 26724
991 | 416.5721 | 26724
992 | 422.4558 | 26724
993 | 401.9204 | 26724
994 | 417.6543 | 26724
995 | 415.5047 | 26724
996 | 426.9596 | 26724
997 | 415.4508 | 26724
998 | 419.3843 | 26724
999 | 421.1277 | 26724
1000 | 416.5678 | 26724
1001 | 410.8646 | 26724
1002 | 421.9937 | 26724
1003 | 420.2902 | 26724
1004 | 422.4463 | 26724
1005 | 417.2335 | 26724
1006 | 404.7984 | 26724
1007 | 430.1241 | 26724
1008 | 416.7679 | 26724
1009 | 416.2584 | 26724
1010 | 414.9164 | 26724
1011 | 405.9723 | 26724
1012 | 406.7305 | 26724
1013 | 406.247 | 26724
1014 | 414.6399 | 26724
1015 | 422.9724 | 26724
1016 | 417.3096 | 26724
1017 | 418.5979 | 26724
1018 | 416.6108 | 26724
1019 | 424.8832 | 26724
1020 | 425.8082 | 26724
1021 | 423.007 | 26724
1022 | 432.173 | 26724
1023 | 427.8815 | 26724
1024 | 417.5659 | 26724
1025 | 425.9837 | 26724
1026 | 400.7694 | 26724
1027 | 405.4319 | 26724
1028 | 427.6556 | 26724
1029 | 412.6685 | 26724
1030 | 400.8293 | 26724
1031 | 419.8746 | 26724
1032 | 407.8556 | 26724
1033 | 413.7756 | 26724
1034 | 423.828 | 26724
1035 | 413.4854 | 26724
1036 | 422.1645 | 26724
1037 | 417.9266 | 26724
1038 | 421.6828 | 26724
1039 | 403.3904 | 26724
1040 | 416.5988 | 26724
1041 | 413.0791 | 26724
1042 | 429.3202 | 26724
1043 | 413.6787 | 26724
1044 | 426.5465 | 26724
1045 | 414.3361 | 26724
1046 | 413.1364 | 26724
1047 | 415.5824 | 26724
1048 | 398.7863 | 26724
1049 | 409.8594 | 26724
1050 | 420.4451 | 26724
1051 | 424.378 | 26724
1052 | 414.4357 | 26724
1053 | 411.097 | 26724
1054 | 412.4363 | 26724
1055 | 414.4838 | 26724
1056 | 417.0414 | 26724
1057 | 423.4801 | 26724
1058 | 424.9768 | 26724
1059 | 422.1462 | 26724
1060 | 409.8615 | 26724
1061 | 418.4444 | 26724
1062 | 409.5671 | 26724
1063 | 420.6318 | 26724
1064 | 414.1139 | 26724
1065 | 416.1231 | 26724
1066 | 423.4082 | 26724
1067 | 406.8057 | 26724
1068 | 418.3377 | 26724
1069 | 412.1492 | 26724
1070 | 429.0782 | 26724
1071 | 405.102 | 26724
1072 | 412.3142 | 26724
1073 | 427.6682 | 26724
1074 | 406.7025 | 26724
1075 | 427.9156 | 26724
1076 | 410.2383 | 26724
1077 | 413.3125 | 26724
1078 | 413.9576 | 26724
1079 | 415.3463 | 26724
1080 | 415.7248 | 26724
1081 | 425.8166 | 26724
1082 | 407.4501 | 26724
1083 | 430.4388 | 26724
1084 | 416.3933 | 26724
1085 | 410.1575 | 26724
1086 | 407.7493 | 26724
1087 | 417.8107 | 26724
1088 | 414.5935 | 26724
1089 | 401.5888 | 26724
1090 | 429.0438 | 26724
1091 | 423.8359 | 26724
1092 | 415.0986 | 26724
1093 | 428.9061 | 26724
1094 | 404.5364 | 26724
1095 | 410.0409 | 26724
1096 | 410.7215 | 26724
1097 | 425.5078 | 26724
1098 | 425.8213 | 26724
1099 | 424.3749 | 26724
1100 | 418.4075 | 26724
1101 | 414.6349 | 26724
1102 | 413.683 | 26724
1103 | 419.2314 | 26724
1104 | 401.708 | 26724
1105 | 410.9487 | 26724
1106 | 405.4608 | 26724
1107 | 411.2877 | 26724
1108 | 417.7432 | 26724
1109 | 423.9425 | 26724
1110 | 409.0433 | 26724
1111 | 427.7096 | 26724
1112 | 406.8079 | 26724
1113 | 415.7924 | 26724
1114 | 396.6545 | 26724
1115 | 429.0207 | 26724
1116 | 421.4327 | 26724
1117 | 414.6277 | 26724
1118 | 413.0359 | 26724
1119 | 417.243 | 26724
1120 | 425.8934 | 26724
1121 | 434.8882 | 26724
1122 | 418.3104 | 26724
1123 | 428.8631 | 26724
1124 | 416.6368 | 26724
1125 | 418.2717 | 26724
1126 | 418.3845 | 26724
1127 | 424.321 | 26724
1128 | 399.6684 | 26724
1129 | 432.8699 | 26724
1130 | 419.2198 | 26724
1131 | 411.4455 | 26724
1132 | 420.4726 | 26724
1133 | 425.3657 | 26724
1134 | 421.1532 | 26724
1135 | 413.0758 | 26724
1136 | 423.1231 | 26724
1137 | 405.1382 | 26724
1138 | 424.1171 | 26724
1139 | 412.0707 | 26724
1140 | 422.2043 | 26724
1141 | 408.0816 | 26724
1142 | 411.6598 | 26724
1143 | 409.2299 | 26724
1144 | 406.2311 | 26724
1145 | 430.0726 | 26724
1146 | 406.4099 | 26724
1147 | 409.493 | 26724
1148 | 416.5333 | 26724
1149 | 403.0843 | 26724
1150 | 413.214 | 26724
1151 | 409.9873 | 26724
1152 | 419.3825 | 26724
1153 | 417.8379 | 26724
1154 | 423.9637 | 26724
1155 | 414.481 | 26724
1156 | 424.0629 | 26724
1157 | 432.0151 | 26724
1158 | 424.3377 | 26724
1159 | 416.4202 | 26724
1160 | 422.8226 | 26724
1161 | 402.3844 | 26724
1162 | 411.6229 | 26724
1163 | 423.2476 | 26724
1164 | 432.2337 | 26724
1165 | 411.8757 | 26724
1166 | 415.3937 | 26724
1167 | 407.4072 | 26724
1168 | 411.0144 | 26724
1169 | 428.6277 | 26724
1170 | 410.8992 | 26724
1171 | 405.5864 | 26724
1172 | 403.6195 | 26724
1173 | 407.8858 | 26724
1174 | 409.5657 | 26724
1175 | 402.6646 | 26724
1176 | 422.6681 | 26724
1177 | 416.8535 | 26724
1178 | 426.6941 | 26724
1179 | 431.0539 | 26724
1180 | 417.4154 | 26724
1181 | 406.6411 | 26724
1182 | 419.6938 | 26724
1183 | 400.8529 | 26724
1184 | 414.3437 | 26724
1185 | 427.5932 | 26724
1186 | 410.5553 | 26724
1187 | 421.3911 | 26724
1188 | 413.4575 | 26724
1189 | 425.3446 | 26724
1190 | 425.3993 | 26724
1191 | 405.9724 | 26724
1192 | 414.4667 | 26724
1193 | 424.2527 | 26724
1194 | 410.5518 | 26724
1195 | 424.6546 | 26724
1196 | 427.6806 | 26724
1197 | 393.5721 | 26724
1198 | 416.865 | 26724
1199 | 417.3725 | 26724
1200 | 414.5991 | 26724
1201 | 424.1423 | 26724
1202 | 422.1958 | 26724
1203 | 419.0708 | 26724
1204 | 415.7817 | 26724
1205 | 417.5978 | 26724
1206 | 410.338 | 26724
1207 | 434.5888 | 26724
1208 | 417.9586 | 26724
1209 | 418.246 | 26724
1210 | 426.5189 | 26724
1211 | 420.3442 | 26724
1212 | 431.3148 | 26724
1213 | 425.6475 | 26724
1214 | 414.5021 | 26724
1215 | 418.6774 | 26724
1216 | 414.5136 | 26724
1217 | 405.7696 | 26724
1218 | 427.5102 | 26724
1219 | 415.1013 | 26724
1220 | 413.722 | 26724
1221 | 414.7977 | 26724
1222 | 413.3456 | 26724
1223 | 407.8554 | 26724
1224 | 421.2845 | 26724
1225 | 414.2332 | 26724
1226 | 409.5815 | 26724
1227 | 416.3058 | 26724
1228 | 405.6482 | 26724
1229 | 409.7447 | 26724
1230 | 414.477 | 26724
1231 | 426.7476 | 26724
1232 | 406.853 | 26724
1233 | 410.3199 | 26724
1234 | 418.4623 | 26724
1235 | 415.4112 | 26724
1236 | 431.0058 | 26724
1237 | 417.8032 | 26724
1238 | 411.7932 | 26724
1239 | 399.5585 | 26724
1240 | 405.8845 | 26724
1241 | 413.5854 | 26724
1242 | 411.6492 | 26724
1243 | 409.2363 | 26724
1244 | 407.0836 | 26724
1245 | 432.0296 | 26724
1246 | 415.569 | 26724
1247 | 408.4917 | 26724
1248 | 420.6853 | 26724
1249 | 419.2287 | 26724
1250 | 411.8562 | 26724
1251 | 431.475 | 26724
1252 | 422.0455 | 26724
1253 | 410.1671 | 26724
1254 | 410.3867 | 26724
1255 | 405.4818 | 26724
1256 | 416.4461 | 26724
1257 | 421.5616 | 26724
1258 | 410.5322 | 26724
1259 | 425.3096 | 26724
1260 | 424.0891 | 26724
1261 | 425.2301 | 26724
1262 | 413.1433 | 26724
1263 | 416.2067 | 26724
1264 | 404.5956 | 26724
1265 | 419.8038 | 26724
1266 | 410.2532 | 26724
1267 | 411.4633 | 26724
1268 | 419.1726 | 26724
1269 | 412.2202 | 26724
1270 | 422.6236 | 26724
1271 | 430.1622 | 26724
1272 | 402.2675 | 26724
1273 | 413.1635 | 26724
1274 | 401.8329 | 26724
1275 | 424.6756 | 26724
1276 | 410.6138 | 26724
1277 | 419.2837 | 26724
1278 | 412.0638 | 26724
1279 | 414.51 | 26724
1280 | 417.0864 | 26724
1281 | 421.8176 | 26724
1282 | 406.9765 | 26724
1283 | 420.5327 | 26724
1284 | 413.692 | 26724
1285 | 417.1778 | 26724
1286 | 398.4032 | 26724
1287 | 426.2778 | 26724
1288 | 424.1387 | 26724
1289 | 416.5982 | 26724
1290 | 420.947 | 26724
1291 | 416.8143 | 26724
1292 | 416.7664 | 26724
1293 | 405.6882 | 26724
1294 | 404.4863 | 26724
1295 | 414.9192 | 26724
1296 | 414.0794 | 26724
1297 | 416.8721 | 26724
1298 | 426.0115 | 26724
1299 | 403.9476 | 26724
1300 | 435.1041 | 26724
1301 | 419.3809 | 26724
1302 | 428.0809 | 26724
1303 | 401.3331 | 26724
1304 | 420.9084 | 26724
1305 | 405.1528 | 26724
1306 | 408.4281 | 26724
1307 | 410.6592 | 26724
1308 | 423.7218 | 26724
1309 | 414.593 | 26724
1310 | 419.4008 | 26724
1311 | 425.3474 | 26724
1312 | 421.0002 | 26724
1313 | 408.6097 | 26724
1314 | 415.9311 | 26724
1315 | 398.695 | 26724
1316 | 415.4618 | 26724
1317 | 409.6339 | 26724
1318 | 409.1952 | 26724
1319 | 418.5337 | 26724
1320 | 418.0319 | 26724
1321 | 407.2492 | 26724
1322 | 419.9067 | 26724
1323 | 397.6531 | 26724
1324 | 416.2164 | 26724
1325 | 415.7983 | 26724
1326 | 419.5784 | 26724
1327 | 418.4267 | 26724
1328 | 410.2069 | 26724
1329 | 416.5701 | 26724
1330 | 424.8279 | 26724
1331 | 417.6126 | 26724
1332 | 414.5065 | 26724
1333 | 417.1845 | 26724
1334 | 389.802 | 26724
1335 | 410.9799 | 26724
1336 | 414.0991 | 26724
1337 | 406.3426 | 26724
1338 | 431.8127 | 26724
1339 | 412.3022 | 26724
1340 | 417.6085 | 26724
1341 | 431.953 | 26724
1342 | 405.1851 | 26724
1343 | 422.9982 | 26724
1344 | 423.0147 | 26724
1345 | 419.1591 | 26724
1346 | 427.9648 | 26724
1347 | 406.4373 | 26724
1348 | 417.8873 | 26724
1349 | 411.6446 | 26724
1350 | 412.7576 | 26724
1351 | 415.005 | 26724
1352 | 399.061 | 26724
1353 | 410.2166 | 26724
1354 | 412.3996 | 26724
1355 | 401.5533 | 26724
1356 | 417.279 | 26724
1357 | 416.1983 | 26724
1358 | 408.18 | 26724
1359 | 420.1995 | 26724
1360 | 418.9005 | 26724
1361 | 421.417 | 26724
1362 | 432.0637 | 26724
1363 | 425.5706 | 26724
1364 | 424.1032 | 26724
1365 | 410.0717 | 26724
1366 | 413.6253 | 26724
1367 | 420.1383 | 26724
1368 | 414.7513 | 26724
1369 | 419.789 | 26724
1370 | 425.717 | 26724
1371 | 420.9849 | 26724
1372 | 421.919 | 26724
1373 | 413.6896 | 26724
1374 | 418.5783 | 26724
1375 | 418.933 | 26724
1376 | 426.8464 | 26724
1377 | 408.7137 | 26724
1378 | 407.369 | 26724
1379 | 424.087 | 26724
1380 | 431.1442 | 26724
1381 | 420.2278 | 26724
1382 | 413.1892 | 26724
1383 | 416.6674 | 26724
1384 | 415.6611 | 26724
1385 | 411.976 | 26724
1386 | 418.1695 | 26724
1387 | 412.3803 | 26724
1388 | 412.1542 | 26724
1389 | 423.8323 | 26724
1390 | 418.0954 | 26724
1391 | 421.7571 | 26724
1392 | 402.9326 | 26724
1393 | 413.3276 | 26724
1394 | 410.1345 | 26724
1395 | 422.1106 | 26724
1396 | 428.9714 | 26724
1397 | 402.007 | 26724
1398 | 428.8747 | 26724
1399 | 413.6251 | 26724
1400 | 414.4533 | 26724
1401 | 410.4568 | 26724
1402 | 410.4657 | 26724
1403 | 429.064 | 26724
1404 | 419.8695 | 26724
1405 | 420.3109 | 26724
1406 | 413.2869 | 26724
1407 | 405.2238 | 26724
1408 | 417.7016 | 26724
1409 | 407.7504 | 26724
1410 | 421.714 | 26724
1411 | 417.0944 | 26724
1412 | 406.4584 | 26724
1413 | 420.7143 | 26724
1414 | 431.9375 | 26724
1415 | 418.6153 | 26724
1416 | 419.968 | 26724
1417 | 426.2863 | 26724
1418 | 414.9013 | 26724
1419 | 413.7525 | 26724
1420 | 421.2849 | 26724
1421 | 420.6622 | 26724
1422 | 414.1301 | 26724
1423 | 422.0657 | 26724
1424 | 428.184 | 26724
1425 | 426.412 | 26724
1426 | 421.6292 | 26724
1427 | 418.3962 | 26724
1428 | 415.1855 | 26724
1429 | 426.0911 | 26724
1430 | 415.9749 | 26724
1431 | 415.6904 | 26724
1432 | 428.0111 | 26724
1433 | 423.9459 | 26724
1434 | 398.0247 | 26724
1435 | 432.1266 | 26724
1436 | 422.7556 | 26724
1437 | 404.2171 | 26724
1438 | 405.9152 | 26724
1439 | 416.0389 | 26724
1440 | 431.6782 | 26724
1441 | 422.6377 | 26724
1442 | 422.2938 | 26724
1443 | 407.7652 | 26724
1444 | 420.5435 | 26724
1445 | 412.3725 | 26724
1446 | 427.2654 | 26724
1447 | 423.4686 | 26724
1448 | 428.0152 | 26724
1449 | 420.8354 | 26724
1450 | 414.351 | 26724
1451 | 413.5353 | 26724
1452 | 418.5594 | 26724
1453 | 423.9514 | 26724
1454 | 435.0691 | 26724
1455 | 414.1468 | 26724
1456 | 435.7429 | 26724
1457 | 411.1402 | 26724
1458 | 413.6566 | 26724
1459 | 410.8794 | 26724
1460 | 404.2821 | 26724
1461 | 417.9776 | 26724
1462 | 411.9629 | 26724
1463 | 414.2819 | 26724
1464 | 418.682 | 26724
1465 | 406.1466 | 26724
1466 | 413.8844 | 26724
1467 | 404.985 | 26724
1468 | 416.0462 | 26724
1469 | 423.9255 | 26724
1470 | 400.0774 | 26724
1471 | 418.6983 | 26724
1472 | 411.1697 | 26724
1473 | 422.2535 | 26724
1474 | 412.6447 | 26724
1475 | 425.7768 | 26724
1476 | 415.1396 | 26724
1477 | 421.0332 | 26724
1478 | 415.3366 | 26724
1479 | 411.9285 | 26724
1480 | 421.2244 | 26724
1481 | 424.7385 | 26724
1482 | 420.5706 | 26724
1483 | 416.9267 | 26724
1484 | 405.8718 | 26724
1485 | 417.913 | 26724
1486 | 407.7948 | 26724
1487 | 417.9883 | 26724
1488 | 422.6908 | 26724
1489 | 418.9067 | 26724
1490 | 417.1085 | 26724
1491 | 413.2218 | 26724
1492 | 428.5403 | 26724
1493 | 416.9566 | 26724
1494 | 422.1961 | 26724
1495 | 418.1279 | 26724
1496 | 410.3403 | 26724
1497 | 408.2824 | 26724
1498 | 415.4877 | 26724
1499 | 412.7963 | 26724
1500 | 415.7738 | 26724
1501 | 412.5959 | 26724
1502 | 409.8427 | 26724
1503 | 415.2595 | 26724
1504 | 417.0256 | 26724
1505 | 431.3027 | 26724
1506 | 407.3989 | 26724
1507 | 410.3142 | 26724
1508 | 423.4473 | 26724
1509 | 418.8023 | 26724
1510 | 429.0464 | 26724
1511 | 413.493 | 26724
1512 | 420.4249 | 26724
1513 | 403.7213 | 26724
1514 | 413.1168 | 26724
1515 | 414.6746 | 26724
1516 | 414.7959 | 26724
1517 | 420.7043 | 26724
1518 | 409.9419 | 26724
1519 | 421.9335 | 26724
1520 | 412.7012 | 26724
1521 | 435.3458 | 26724
1522 | 427.4294 | 26724
1523 | 418.952 | 26724
1524 | 412.4336 | 26724
1525 | 400.376 | 26724
1526 | 416.9154 | 26724
1527 | 419.8398 | 26724
1528 | 428.1857 | 26724
1529 | 404.3427 | 26724
1530 | 422.7282 | 26724
1531 | 427.6278 | 26724
1532 | 407.112 | 26724
1533 | 416.0219 | 26724
1534 | 417.0778 | 26724
1535 | 415.1832 | 26724
1536 | 405.6216 | 26724
1537 | 428.3617 | 26724
1538 | 414.0684 | 26724
1539 | 410.0233 | 26724
1540 | 426.2544 | 26724
1541 | 417.1887 | 26724
1542 | 423.212 | 26724
1543 | 426.3199 | 26724
1544 | 426.0668 | 26724
1545 | 401.5593 | 26724
1546 | 419.8666 | 26724
1547 | 408.3236 | 26724
1548 | 403.1595 | 26724
1549 | 420.5765 | 26724
1550 | 407.9419 | 26724
1551 | 401.2202 | 26724
1552 | 414.1272 | 26724
1553 | 411.3316 | 26724
1554 | 408.4999 | 26724
1555 | 421.9818 | 26724
1556 | 422.3952 | 26724
1557 | 416.0484 | 26724
1558 | 406.3414 | 26724
1559 | 410.6991 | 26724
1560 | 429.0191 | 26724
1561 | 416.5733 | 26724
1562 | 425.5889 | 26724
1563 | 400.1875 | 26724
1564 | 416.2068 | 26724
1565 | 423.4234 | 26724
1566 | 424.1641 | 26724
1567 | 427.6551 | 26724
1568 | 418.5409 | 26724
1569 | 416.5619 | 26724
1570 | 425.6491 | 26724
1571 | 409.2213 | 26724
1572 | 425.6948 | 26724
1573 | 393.1907 | 26724
1574 | 425.1805 | 26724
1575 | 417.0874 | 26724
1576 | 412.6712 | 26724
1577 | 400.958 | 26724
1578 | 423.5747 | 26724
1579 | 402.2316 | 26724
1580 | 422.5412 | 26724
1581 | 405.584 | 26724
1582 | 422.3995 | 26724
1583 | 410.6755 | 26724
1584 | 430.2237 | 26724
1585 | 407.578 | 26724
1586 | 402.6081 | 26724
1587 | 421.78 | 26724
1588 | 416.6277 | 26724
1589 | 405.837 | 26724
1590 | 431.2954 | 26724
1591 | 411.7022 | 26724
1592 | 420.2925 | 26724
1593 | 418.634 | 26724
1594 | 410.2784 | 26724
1595 | 408.5727 | 26724
1596 | 410.0357 | 26724
1597 | 427.5588 | 26724
1598 | 415.2545 | 26724
1599 | 425.8995 | 26724
1600 | 420.9656 | 26724
1601 | 399.3728 | 26724
1602 | 426.6655 | 26724
1603 | 423.2556 | 26724
1604 | 408.0853 | 26724
1605 | 411.6246 | 26724
1606 | 409.0342 | 26724
1607 | 426.5922 | 26724
1608 | 417.9756 | 26724
1609 | 411.4371 | 26724
1610 | 418.5106 | 26724
1611 | 417.8859 | 26724
1612 | 424.789 | 26724
1613 | 420.8595 | 26724
1614 | 405.8942 | 26724
1615 | 420.4918 | 26724
1616 | 405.5092 | 26724
1617 | 410.7242 | 26724
1618 | 414.4356 | 26724
1619 | 419.1602 | 26724
1620 | 428.2321 | 26724
1621 | 414.3068 | 26724
1622 | 426.9748 | 26724
1623 | 415.6705 | 26724
1624 | 418.2981 | 26724
1625 | 424.9038 | 26724
1626 | 411.0945 | 26724
1627 | 421.825 | 26724
1628 | 402.9526 | 26724
1629 | 414.3891 | 26724
1630 | 425.988 | 26724
1631 | 397.8569 | 26724
1632 | 414.7511 | 26724
1633 | 415.7532 | 26724
1634 | 412.2439 | 26724
1635 | 406.8158 | 26724
1636 | 418.3231 | 26724
1637 | 413.8477 | 26724
1638 | 418.8064 | 26724
1639 | 424.0084 | 26724
1640 | 418.5077 | 26724
1641 | 420.6189 | 26724
1642 | 416.412 | 26724
1643 | 395.8688 | 26724
1644 | 425.5816 | 26724
1645 | 432.6674 | 26724
1646 | 415.5548 | 26724
1647 | 424.9237 | 26724
1648 | 395.4668 | 26724
1649 | 427.6964 | 26724
1650 | 431.4654 | 26724
1651 | 419.8389 | 26724
1652 | 413.8513 | 26724
1653 | 416.121 | 26724
1654 | 416.1543 | 26724
1655 | 423.3839 | 26724
1656 | 404.4453 | 26724
1657 | 410.6261 | 26724
1658 | 413.1108 | 26724
1659 | 414.3107 | 26724
1660 | 408.2712 | 26724
1661 | 417.6355 | 26724
1662 | 406.9374 | 26724
1663 | 409.2547 | 26724
1664 | 407.7163 | 26724
1665 | 413.2138 | 26724
1666 | 418.1821 | 26724
1667 | 414.1694 | 26724
1668 | 427.7817 | 26724
1669 | 402.1401 | 26724
1670 | 423.1726 | 26724
1671 | 414.5811 | 26724
1672 | 415.0625 | 26724
1673 | 424.8937 | 26724
1674 | 426.0315 | 26724
1675 | 436.9724 | 26724
1676 | 411.4011 | 26724
1677 | 402.8154 | 26724
1678 | 409.3164 | 26724
1679 | 412.838 | 26724
1680 | 421.8863 | 26724
1681 | 410.3699 | 26724
1682 | 408.4728 | 26724
1683 | 409.9011 | 26724
1684 | 415.6286 | 26724
1685 | 408.7162 | 26724
1686 | 410.0768 | 26724
1687 | 428.2559 | 26724
1688 | 416.458 | 26724
1689 | 437.1664 | 26724
1690 | 414.8809 | 26724
1691 | 424.0407 | 26724
1692 | 410.1291 | 26724
1693 | 424.0009 | 26724
1694 | 432.558 | 26724
1695 | 414.8343 | 26724
1696 | 420.0677 | 26724
1697 | 412.7485 | 26724
1698 | 417.9866 | 26724
1699 | 425.0536 | 26724
1700 | 406.5886 | 26724
1701 | 427.2056 | 26724
1702 | 414.1973 | 26724
1703 | 410.2136 | 26724
1704 | 423.4477 | 26724
1705 | 408.4265 | 26724
1706 | 412.1501 | 26724
1707 | 401.1148 | 26724
1708 | 426.0999 | 26724
1709 | 399.6667 | 26724
1710 | 417.0248 | 26724
1711 | 418.9731 | 26724
1712 | 423.8236 | 26724
1713 | 394.3177 | 26724
1714 | 420.4824 | 26724
1715 | 415.9858 | 26724
1716 | 424.9053 | 26724
1717 | 427.1786 | 26724
1718 | 415.9627 | 26724
1719 | 423.4246 | 26724
1720 | 424.2853 | 26724
1721 | 399.3509 | 26724
1722 | 403.848 | 26724
1723 | 416.1116 | 26724
1724 | 392.3488 | 26724
1725 | 402.9985 | 26724
1726 | 408.8316 | 26724
1727 | 435.8192 | 26724
1728 | 413.92 | 26724
1729 | 415.0636 | 26724
1730 | 407.654 | 26724
1731 | 420.4722 | 26724
1732 | 405.049 | 26724
1733 | 412.6075 | 26724
1734 | 417.1342 | 26724
1735 | 431.8126 | 26724
1736 | 420.0521 | 26724
1737 | 419.8477 | 26724
1738 | 413.9704 | 26724
1739 | 422.7745 | 26724
1740 | 431.3164 | 26724
1741 | 404.2055 | 26724
1742 | 415.9901 | 26724
1743 | 428.2706 | 26724
1744 | 410.0463 | 26724
1745 | 419.3323 | 26724
1746 | 424.5951 | 26724
1747 | 428.4127 | 26724
1748 | 415.3911 | 26724
1749 | 425.143 | 26724
1750 | 407.2483 | 26724
1751 | 395.8028 | 26724
1752 | 408.4971 | 26724
1753 | 416.99 | 26724
1754 | 416.8011 | 26724
1755 | 414.9662 | 26724
1756 | 413.623 | 26724
1757 | 423.1736 | 26724
1758 | 407.9086 | 26724
1759 | 419.7755 | 26724
1760 | 398.2436 | 26724
1761 | 420.4839 | 26724
1762 | 410.5724 | 26724
1763 | 422.7055 | 26724
1764 | 411.9088 | 26724
1765 | 418.6549 | 26724
1766 | 408.4432 | 26724
1767 | 413.7719 | 26724
1768 | 398.2489 | 26724
1769 | 423.4825 | 26724
1770 | 398.9992 | 26724
1771 | 421.4657 | 26724
1772 | 412.149 | 26724
1773 | 419.5447 | 26724
1774 | 415.3404 | 26724
1775 | 414.5159 | 26724
1776 | 414.5212 | 26724
1777 | 406.5991 | 26724
1778 | 408.3658 | 26724
1779 | 408.1674 | 26724
1780 | 432.2645 | 26724
1781 | 416.2018 | 26724
1782 | 411.1865 | 26724
1783 | 422.5794 | 26724
1784 | 432.027 | 26724
1785 | 404.4758 | 26724
1786 | 419.6109 | 26724
1787 | 414.6457 | 26724
1788 | 425.8834 | 26724
1789 | 413.7786 | 26724
1790 | 426.5415 | 26724
1791 | 410.6103 | 26724
1792 | 413.5167 | 26724
1793 | 409.8733 | 26724
1794 | 415.7316 | 26724
1795 | 431.9337 | 26724
1796 | 412.1067 | 26724
1797 | 410.1212 | 26724
1798 | 432.1342 | 26724
1799 | 410.0563 | 26724
1800 | 409.3969 | 26724
1801 | 405.7126 | 26724
1802 | 402.8034 | 26724
1803 | 410.1057 | 26724
1804 | 415.311 | 26724
1805 | 423.7792 | 26724
1806 | 424.7969 | 26724
1807 | 420.4136 | 26724
1808 | 417.1003 | 26724
1809 | 417.2106 | 26724
1810 | 409.3173 | 26724
1811 | 408.0141 | 26724
1812 | 427.0927 | 26724
1813 | 408.0108 | 26724
1814 | 422.7979 | 26724
1815 | 417.1665 | 26724
1816 | 414.0853 | 26724
1817 | 413.9721 | 26724
1818 | 427.8627 | 26724
1819 | 413.729 | 26724
1820 | 410.2376 | 26724
1821 | 422.5011 | 26724
1822 | 416.5818 | 26724
1823 | 404.1647 | 26724
1824 | 419.5051 | 26724
1825 | 415.9292 | 26724
1826 | 417.9332 | 26724
1827 | 417.3756 | 26724
1828 | 425.7365 | 26724
1829 | 409.7619 | 26724
1830 | 420.1984 | 26724
1831 | 414.3818 | 26724
1832 | 407.4669 | 26724
1833 | 421.7066 | 26724
1834 | 409.6755 | 26724
1835 | 407.7896 | 26724
1836 | 407.2417 | 26724
1837 | 431.5828 | 26724
1838 | 409.3601 | 26724
1839 | 402.9188 | 26724
1840 | 415.2642 | 26724
1841 | 410.6916 | 26724
1842 | 406.6261 | 26724
1843 | 408.7031 | 26724
1844 | 423.7311 | 26724
1845 | 409.7875 | 26724
1846 | 418.6018 | 26724
1847 | 424.28 | 26724
1848 | 427.8294 | 26724
1849 | 428.3501 | 26724
1850 | 410.1477 | 26724
1851 | 421.4435 | 26724
1852 | 418.2869 | 26724
1853 | 415.5408 | 26724
1854 | 420.4259 | 26724
1855 | 421.8932 | 26724
1856 | 423.6783 | 26724
1857 | 419.5025 | 26724
1858 | 415.584 | 26724
1859 | 412.0815 | 26724
1860 | 415.9016 | 26724
1861 | 406.2825 | 26724
1862 | 427.6961 | 26724
1863 | 425.9857 | 26724
1864 | 399.9869 | 26724
1865 | 410.4433 | 26724
1866 | 407.0138 | 26724
1867 | 416.9851 | 26724
1868 | 414.3361 | 26724
1869 | 414.677 | 26724
1870 | 419.2776 | 26724
1871 | 406.7052 | 26724
1872 | 425.7635 | 26724
1873 | 413.459 | 26724
1874 | 420.7031 | 26724
1875 | 418.0046 | 26724
1876 | 418.9951 | 26724
1877 | 427.9204 | 26724
1878 | 396.6851 | 26724
1879 | 414.9927 | 26724
1880 | 425.8401 | 26724
1881 | 415.0731 | 26724
1882 | 405.5445 | 26724
1883 | 421.5381 | 26724
1884 | 417.5075 | 26724
1885 | 422.5342 | 26724
1886 | 424.8967 | 26724
1887 | 428.4444 | 26724
1888 | 399.2608 | 26724
1889 | 401.3169 | 26724
1890 | 414.1124 | 26724
1891 | 420.1702 | 26724
1892 | 401.9158 | 26724
1893 | 426.5089 | 26724
1894 | 437.8522 | 26724
1895 | 412.206 | 26724
1896 | 399.9464 | 26724
1897 | 431.7624 | 26724
1898 | 414.9027 | 26724
1899 | 401.8738 | 26724
1900 | 404.0909 | 26724
1901 | 416.213 | 26724
1902 | 415.4454 | 26724
1903 | 411.3842 | 26724
1904 | 402.9999 | 26724
1905 | 414.0838 | 26724
1906 | 424.4656 | 26724
1907 | 408.5783 | 26724
1908 | 414.4217 | 26724
1909 | 403.6086 | 26724
1910 | 415.7062 | 26724
1911 | 414.0178 | 26724
1912 | 408.6394 | 26724
1913 | 409.1157 | 26724
1914 | 423.2334 | 26724
1915 | 422.7975 | 26724
1916 | 413.2829 | 26724
1917 | 427.4126 | 26724
1918 | 418.9735 | 26724
1919 | 419.4837 | 26724
1920 | 415.7259 | 26724
1921 | 421.0142 | 26724
1922 | 419.6073 | 26724
1923 | 406.8364 | 26724
1924 | 422.5546 | 26724
1925 | 397.7369 | 26724
1926 | 412.0936 | 26724
1927 | 411.7859 | 26724
1928 | 416.6546 | 26724
1929 | 413.5585 | 26724
1930 | 416.5988 | 26724
1931 | 423.6678 | 26724
1932 | 408.8958 | 26724
1933 | 414.189 | 26724
1934 | 420.4571 | 26724
1935 | 411.8279 | 26724
1936 | 422.6797 | 26724
1937 | 422.5866 | 26724
1938 | 415.9013 | 26724
1939 | 404.3946 | 26724
1940 | 402.9151 | 26724
1941 | 436.216 | 26724
1942 | 420.2785 | 26724
1943 | 435.8241 | 26724
1944 | 413.2772 | 26724
1945 | 420.6654 | 26724
1946 | 401.0167 | 26724
1947 | 410.7615 | 26724
1948 | 419.9423 | 26724
1949 | 429.6248 | 26724
1950 | 421.7372 | 26724
1951 | 422.3959 | 26724
1952 | 423.6515 | 26724
1953 | 429.2711 | 26724
1954 | 402.329 | 26724
1955 | 404.7186 | 26724
1956 | 416.973 | 26724
1957 | 422.9823 | 26724
1958 | 419.8688 | 26724
1959 | 434.2993 | 26724
1960 | 423.356 | 26724
1961 | 401.0156 | 26724
1962 | 411.1693 | 26724
1963 | 421.8083 | 26724
1964 | 418.8902 | 26724
1965 | 418.8965 | 26724
1966 | 404.2686 | 26724
1967 | 415.5622 | 26724
1968 | 431.0283 | 26724
1969 | 401.3205 | 26724
1970 | 421.7605 | 26724
1971 | 416.2831 | 26724
1972 | 418.3288 | 26724
1973 | 419.8321 | 26724
1974 | 416.7188 | 26724
1975 | 407.4649 | 26724
1976 | 422.0246 | 26724
1977 | 418.7505 | 26724
1978 | 409.6073 | 26724
1979 | 419.9135 | 26724
1980 | 423.1967 | 26724
1981 | 403.9366 | 26724
1982 | 417.4088 | 26724
1983 | 422.4811 | 26724
1984 | 415.2423 | 26724
1985 | 402.6927 | 26724
1986 | 422.7378 | 26724
1987 | 410.7098 | 26724
1988 | 417.198 | 26724
1989 | 420.4278 | 26724
1990 | 420.9645 | 26724
1991 | 407.4173 | 26724
1992 | 410.5231 | 26724
1993 | 415.0822 | 26724
1994 | 400.8794 | 26724
1995 | 405.7772 | 26724
1996 | 413.8852 | 26724
1997 | 407.4462 | 26724
1998 | 408.873 | 26724
1999 | 419.6149 | 26724
2000 | 412.476 | 26724
2001 | 408.3955 | 26724
2002 | 412.8532 | 26724
2003 | 426.5936 | 26724
2004 | 416.5772 | 26724
2005 | 414.5498 | 26724
2006 | 411.1396 | 26724
2007 | 420.506 | 26724
2008 | 404.2894 | 26724
2009 | 408.8819 | 26724
2010 | 414.7125 | 26724
2011 | 426.0086 | 26724
2012 | 409.9226 | 26724
2013 | 427.907 | 26724
2014 | 421.1315 | 26724
2015 | 424.1663 | 26724
2016 | 423.78 | 26724
2017 | 410.3174 | 26724
2018 | 419.8772 | 26724
2019 | 425.6973 | 26724
2020 | 417.3757 | 26724
2021 | 406.4201 | 26724
2022 | 399.9338 | 26724
2023 | 413.6802 | 26724
2024 | 430.321 | 26724
2025 | 428.7009 | 26724
2026 | 429.15 | 26724
2027 | 426.9887 | 26724
2028 | 399.1536 | 26724
2029 | 412.2886 | 26724
2030 | 416.5755 | 26724
2031 | 414.8379 | 26724
2032 | 404.3025 | 26724
2033 | 422.119 | 26724
2034 | 428.9119 | 26724
2035 | 410.7963 | 26724
2036 | 421.6052 | 26724
2037 | 415.5797 | 26724
2038 | 419.9848 | 26724
2039 | 408.3511 | 26724
2040 | 421.8441 | 26724
2041 | 405.953 | 26724
2042 | 423.2819 | 26724
2043 | 412.8361 | 26724
2044 | 421.8211 | 26724
2045 | 431.6452 | 26724
2046 | 414.7309 | 26724
2047 | 418.0161 | 26724
2048 | 416.0655 | 26724
2049 | 423.3034 | 26724
2050 | 416.6534 | 26724
2051 | 418.1909 | 26724
2052 | 416.0973 | 26724
2053 | 416.7006 | 26724
2054 | 419.5272 | 26724
2055 | 416.8697 | 26724
2056 | 416.5263 | 26724
2057 | 420.9428 | 26724
2058 | 417.3595 | 26724
2059 | 416.0844 | 26724
2060 | 415.5061 | 26724
2061 | 405.7453 | 26724
2062 | 426.7219 | 26724
2063 | 414.1501 | 26724
2064 | 411.4215 | 26724
2065 | 433.2583 | 26724
2066 | 417.8426 | 26724
2067 | 421.8536 | 26724
2068 | 402.5631 | 26724
2069 | 402.7283 | 26724
2070 | 421.5069 | 26724
2071 | 419.2957 | 26724
2072 | 407.6773 | 26724
2073 | 418.137 | 26724
2074 | 411.5324 | 26724
2075 | 419.207 | 26724
2076 | 403.834 | 26724
2077 | 401.5868 | 26724
2078 | 421.1829 | 26724
2079 | 418.8629 | 26724
2080 | 422.0867 | 26724
2081 | 419.5993 | 26724
2082 | 420.4013 | 26724
2083 | 413.7202 | 26724
2084 | 408.721 | 26724
2085 | 411.9817 | 26724
2086 | 417.0891 | 26724
2087 | 403.3005 | 26724
2088 | 419.1087 | 26724
2089 | 415.4661 | 26724
2090 | 411.8859 | 26724
2091 | 430.7962 | 26724
2092 | 411.4209 | 26724
2093 | 406.0925 | 26724
2094 | 412.4601 | 26724
2095 | 420.3194 | 26724
2096 | 419.4578 | 26724
2097 | 417.814 | 26724
2098 | 428.3366 | 26724
2099 | 418.8657 | 26724
2100 | 421.4406 | 26724
2101 | 423.8243 | 26724
2102 | 408.4726 | 26724
2103 | 406.2964 | 26724
2104 | 415.8567 | 26724
2105 | 421.3479 | 26724
2106 | 419.0181 | 26724
2107 | 420.0949 | 26724
2108 | 408.6814 | 26724
2109 | 407.838 | 26724
2110 | 398.007 | 26724
2111 | 416.54 | 26724
2112 | 413.1565 | 26724
2113 | 401.6779 | 26724
2114 | 418.7368 | 26724
2115 | 429.8519 | 26724
2116 | 410.6434 | 26724
2117 | 415.6787 | 26724
2118 | 416.7177 | 26724
2119 | 408.2734 | 26724
2120 | 429.2604 | 26724
2121 | 406.6628 | 26724
2122 | 410.3167 | 26724
2123 | 423.3976 | 26724
2124 | 414.6234 | 26724
2125 | 421.4765 | 26724
2126 | 408.4965 | 26724
2127 | 416.5078 | 26724
2128 | 423.272 | 26724
2129 | 429.0238 | 26724
2130 | 416.9369 | 26724
2131 | 422.0586 | 26724
2132 | 409.32 | 26724
2133 | 419.261 | 26724
2134 | 419.4885 | 26724
2135 | 412.7489 | 26724
2136 | 420.0606 | 26724
2137 | 415.4155 | 26724
2138 | 421.7412 | 26724
2139 | 411.6237 | 26724
2140 | 410.8109 | 26724
2141 | 420.6751 | 26724
2142 | 412.712 | 26724
2143 | 424.7646 | 26724
2144 | 420.7535 | 26724
2145 | 417.7865 | 26724
2146 | 410.0087 | 26724
2147 | 414.2577 | 26724
2148 | 406.4922 | 26724
2149 | 408.8736 | 26724
2150 | 411.3366 | 26724
2151 | 417.7998 | 26724
2152 | 420.0672 | 26724
2153 | 412.6394 | 26724
2154 | 409.4996 | 26724
2155 | 422.6426 | 26724
2156 | 419.4962 | 26724
2157 | 424.0888 | 26724
2158 | 410.587 | 26724
2159 | 428.7695 | 26724
2160 | 407.1582 | 26724
2161 | 413.6329 | 26724
2162 | 419.1469 | 26724
2163 | 415.4562 | 26724
2164 | 413.971 | 26724
2165 | 411.0244 | 26724
2166 | 408.6464 | 26724
2167 | 418.6462 | 26724
2168 | 420.0151 | 26724
2169 | 414.6326 | 26724
2170 | 428.6441 | 26724
2171 | 416.9478 | 26724
2172 | 435.9172 | 26724
2173 | 426.5735 | 26724
2174 | 422.1232 | 26724
2175 | 412.0726 | 26724
2176 | 417.6012 | 26724
2177 | 401.1871 | 26724
2178 | 412.8254 | 26724
2179 | 406.7137 | 26724
2180 | 418.4012 | 26724
2181 | 412.8002 | 26724
2182 | 429.6839 | 26724
2183 | 429.6403 | 26724
2184 | 432.5589 | 26724
2185 | 428.9317 | 26724
2186 | 417.9864 | 26724
2187 | 417.77 | 26724
2188 | 402.8816 | 26724
2189 | 405.3848 | 26724
2190 | 419.686 | 26724
2191 | 408.8158 | 26724
2192 | 408.9827 | 26724
2193 | 411.2713 | 26724
2194 | 420.0977 | 26724
2195 | 427.9783 | 26724
2196 | 415.2122 | 26724
2197 | 421.7859 | 26724
2198 | 411.7962 | 26724
2199 | 422.3363 | 26724
2200 | 410.7312 | 26724
2201 | 406.9815 | 26724
2202 | 419.6565 | 26724
2203 | 411.7938 | 26724
2204 | 418.8637 | 26724
2205 | 414.08 | 26724
2206 | 413.9746 | 26724
2207 | 418.6492 | 26724
2208 | 423.3105 | 26724
2209 | 397.4038 | 26724
2210 | 417.5795 | 26724
2211 | 430.1084 | 26724
2212 | 423.6049 | 26724
2213 | 404.8482 | 26724
2214 | 409.5573 | 26724
2215 | 421.9542 | 26724
2216 | 420.3451 | 26724
2217 | 412.5851 | 26724
2218 | 422.5006 | 26724
2219 | 425.9777 | 26724
2220 | 405.5983 | 26724
2221 | 406.9721 | 26724
2222 | 404.9984 | 26724
2223 | 415.9796 | 26724
2224 | 432.9313 | 26724
2225 | 415.4845 | 26724
2226 | 428.0527 | 26724
2227 | 416.3748 | 26724
2228 | 427.3288 | 26724
2229 | 406.2119 | 26724
2230 | 409.9167 | 26724
2231 | 411.5541 | 26724
2232 | 414.3152 | 26724
2233 | 399.7119 | 26724
2234 | 414.4451 | 26724
2235 | 422.4972 | 26724
2236 | 414.2792 | 26724
2237 | 400.3673 | 26724
2238 | 437.4303 | 26724
2239 | 422.1994 | 26724
2240 | 425.1103 | 26724
2241 | 409.3839 | 26724
2242 | 415.837 | 26724
2243 | 416.8984 | 26724
2244 | 413.3438 | 26724
2245 | 424.0525 | 26724
2246 | 421.5521 | 26724
2247 | 414.0034 | 26724
2248 | 404.1313 | 26724
2249 | 398.1348 | 26724
2250 | 419.6757 | 26724
2251 | 417.022 | 26724
2252 | 407.0474 | 26724
2253 | 425.8802 | 26724
2254 | 404.4485 | 26724
2255 | 408.6576 | 26724
2256 | 417.8578 | 26724
2257 | 416.8004 | 26724
2258 | 412.3203 | 26724
2259 | 421.3446 | 26724
2260 | 410.9623 | 26724
2261 | 408.4734 | 26724
2262 | 423.3309 | 26724
2263 | 407.2114 | 26724
2264 | 416.4059 | 26724
2265 | 406.4644 | 26724
2266 | 413.8502 | 26724
2267 | 419.9562 | 26724
2268 | 412.7126 | 26724
2269 | 415.102 | 26724
2270 | 416.6074 | 26724
2271 | 410.092 | 26724
2272 | 426.4084 | 26724
2273 | 429.0176 | 26724
2274 | 408.4537 | 26724
2275 | 430.0509 | 26724
2276 | 400.5778 | 26724
2277 | 432.8986 | 26724
2278 | 410.6919 | 26724
2279 | 432.747 | 26724
2280 | 411.217 | 26724
2281 | 419.5623 | 26724
2282 | 425.2029 | 26724
2283 | 408.3763 | 26724
2284 | 403.331 | 26724
2285 | 399.5759 | 26724
2286 | 434.0852 | 26724
2287 | 426.1532 | 26724
2288 | 409.033 | 26724
2289 | 407.4443 | 26724
2290 | 413.5988 | 26724
2291 | 421.6172 | 26724
2292 | 408.6942 | 26724
2293 | 409.912 | 26724
2294 | 420.6134 | 26724
2295 | 425.5937 | 26724
2296 | 404.9132 | 26724
2297 | 422.3625 | 26724
2298 | 419.8459 | 26724
2299 | 414.8076 | 26724
2300 | 413.6272 | 26724
2301 | 416.2958 | 26724
2302 | 419.1112 | 26724
2303 | 410.6943 | 26724
2304 | 410.9618 | 26724
2305 | 418.3733 | 26724
2306 | 398.3523 | 26724
2307 | 412.2577 | 26724
2308 | 405.715 | 26724
2309 | 402.2746 | 26724
2310 | 427.5396 | 26724
2311 | 425.3012 | 26724
2312 | 411.284 | 26724
2313 | 423.2993 | 26724
2314 | 412.9353 | 26724
2315 | 416.1528 | 26724
2316 | 427.2444 | 26724
2317 | 424.0854 | 26724
2318 | 424.7075 | 26724
2319 | 424.9356 | 26724
2320 | 432.9692 | 26724
2321 | 405.6674 | 26724
2322 | 421.8584 | 26724
2323 | 419.6468 | 26724
2324 | 424.6331 | 26724
2325 | 400.7154 | 26724
2326 | 421.988 | 26724
2327 | 419.501 | 26724
2328 | 411.3929 | 26724
2329 | 426.6043 | 26724
2330 | 421.3921 | 26724
2331 | 411.3313 | 26724
2332 | 417.6639 | 26724
2333 | 430.3263 | 26724
2334 | 418.0689 | 26724
2335 | 427.5149 | 26724
2336 | 421.8116 | 26724
2337 | 422.0391 | 26724
2338 | 422.0294 | 26724
2339 | 404.3068 | 26724
2340 | 416.9679 | 26724
2341 | 424.7814 | 26724
2342 | 414.7395 | 26724
2343 | 402.9283 | 26724
2344 | 413.6927 | 26724
2345 | 415.4903 | 26724
2346 | 430.0142 | 26724
2347 | 411.7225 | 26724
2348 | 401.1 | 26724
2349 | 416.7229 | 26724
2350 | 419.6711 | 26724
2351 | 426.8424 | 26724
2352 | 423.6617 | 26724
2353 | 416.9129 | 26724
2354 | 423.494 | 26724
2355 | 415.0629 | 26724
2356 | 416.0949 | 26724
2357 | 414.5526 | 26724
2358 | 427.7156 | 26724
2359 | 420.1475 | 26724
2360 | 406.1137 | 26724
2361 | 407.1901 | 26724
2362 | 416.7711 | 26724
2363 | 411.7719 | 26724
2364 | 415.4203 | 26724
2365 | 410.7327 | 26724
2366 | 410.9595 | 26724
2367 | 420.6078 | 26724
2368 | 419.4494 | 26724
2369 | 409.6954 | 26724
2370 | 409.9057 | 26724
2371 | 408.6357 | 26724
2372 | 418.3384 | 26724
2373 | 409.7763 | 26724
2374 | 420.8229 | 26724
2375 | 403.4909 | 26724
2376 | 407.5309 | 26724
2377 | 418.9105 | 26724
2378 | 409.7894 | 26724
2379 | 405.8861 | 26724
2380 | 405.7855 | 26724
2381 | 417.5169 | 26724
2382 | 412.5771 | 26724
2383 | 414.3716 | 26724
2384 | 409.6087 | 26724
2385 | 417.7805 | 26724
2386 | 427.5157 | 26724
2387 | 419.0147 | 26724
2388 | 425.9389 | 26724
2389 | 425.2549 | 26724
2390 | 412.829 | 26724
2391 | 399.1225 | 26724
2392 | 418.2663 | 26724
2393 | 422.677 | 26724
2394 | 431.855 | 26724
2395 | 420.1623 | 26724
2396 | 410.7302 | 26724
2397 | 424.5352 | 26724
2398 | 425.5425 | 26724
2399 | 404.9423 | 26724
2400 | 421.533 | 26724
2401 | 423.8138 | 26724
2402 | 420.4478 | 26724
2403 | 417.1461 | 26724
2404 | 410.1702 | 26724
2405 | 410.7107 | 26724
2406 | 413.6072 | 26724
2407 | 404.3734 | 26724
2408 | 438.0824 | 26724
2409 | 396.4193 | 26724
2410 | 428.9925 | 26724
2411 | 415.5559 | 26724
2412 | 412.6055 | 26724
2413 | 415.2695 | 26724
2414 | 411.9316 | 26724
2415 | 417.4721 | 26724
2416 | 417.2878 | 26724
2417 | 408.6119 | 26724
2418 | 419.9107 | 26724
2419 | 425.6518 | 26724
2420 | 406.418 | 26724
2421 | 433.7047 | 26724
2422 | 423.6007 | 26724
2423 | 408.0843 | 26724
2424 | 408.1364 | 26724
2425 | 417.5654 | 26724
2426 | 412.4671 | 26724
2427 | 411.9492 | 26724
2428 | 404.7729 | 26724
2429 | 420.98 | 26724
2430 | 403.5505 | 26724
2431 | 415.8626 | 26724
2432 | 425.7687 | 26724
2433 | 422.8077 | 26724
2434 | 415.7201 | 26724
2435 | 427.9105 | 26724
2436 | 422.1216 | 26724
2437 | 417.2961 | 26724
2438 | 423.925 | 26724
2439 | 426.2747 | 26724
2440 | 436.2563 | 26724
2441 | 422.0607 | 26724
2442 | 401.2081 | 26724
2443 | 404.2457 | 26724
2444 | 412.8346 | 26724
2445 | 405.6753 | 26724
2446 | 421.1128 | 26724
2447 | 437.3604 | 26724
2448 | 408.0913 | 26724
2449 | 424.8379 | 26724
2450 | 429.1665 | 26724
2451 | 415.938 | 26724
2452 | 414.8293 | 26724
2453 | 411.8527 | 26724
2454 | 420.8446 | 26724
2455 | 419.9312 | 26724
2456 | 414.2635 | 26724
2457 | 428.9548 | 26724
2458 | 423.5692 | 26724
2459 | 420.1867 | 26724
2460 | 411.9985 | 26724
2461 | 415.4541 | 26724
2462 | 418.0613 | 26724
2463 | 432.0405 | 26724
2464 | 419.7778 | 26724
2465 | 407.1786 | 26724
2466 | 409.8503 | 26724
2467 | 415.5361 | 26724
2468 | 412.7677 | 26724
2469 | 406.4746 | 26724
2470 | 403.843 | 26724
2471 | 414.8613 | 26724
2472 | 408.5547 | 26724
2473 | 417.8732 | 26724
2474 | 423.9025 | 26724
2475 | 425.6502 | 26724
2476 | 421.3359 | 26724
2477 | 422.3135 | 26724
2478 | 401.5856 | 26724
2479 | 402.9962 | 26724
2480 | 409.6735 | 26724
2481 | 409.4689 | 26724
2482 | 422.9078 | 26724
2483 | 425.4784 | 26724
2484 | 407.4339 | 26724
2485 | 423.278 | 26724
2486 | 400.2693 | 26724
2487 | 411.2451 | 26724
2488 | 415.3018 | 26724
2489 | 417.0405 | 26724
2490 | 410.9737 | 26724
2491 | 414.4293 | 26724
2492 | 416.1636 | 26724
2493 | 418.3683 | 26724
2494 | 417.9954 | 26724
2495 | 408.7807 | 26724
2496 | 404.2707 | 26724
2497 | 411.2892 | 26724
2498 | 424.8596 | 26724
2499 | 421.0961 | 26724
2500 | 415.722 | 26724
2501 | 428.6608 | 26724
2502 | 423.8473 | 26724
2503 | 418.2671 | 26724
2504 | 412.6081 | 26724
2505 | 419.6767 | 26724
2506 | 402.9706 | 26724
2507 | 409.7268 | 26724
2508 | 419.4147 | 26724
2509 | 416.3526 | 26724
2510 | 424.2327 | 26724
2511 | 415.8397 | 26724
2512 | 421.0581 | 26724
2513 | 426.9551 | 26724
2514 | 409.6136 | 26724
2515 | 420.4293 | 26724
2516 | 416.8469 | 26724
2517 | 428.857 | 26724
2518 | 426.2135 | 26724
2519 | 406.9807 | 26724
2520 | 405.1984 | 26724
2521 | 419.8976 | 26724
2522 | 408.5868 | 26724
2523 | 413.5633 | 26724
2524 | 423.4111 | 26724
2525 | 432.968 | 26724
2526 | 423.8977 | 26724
2527 | 423.9978 | 26724
2528 | 409.2902 | 26724
2529 | 409.4366 | 26724
2530 | 418.2344 | 26724
2531 | 403.5233 | 26724
2532 | 408.8657 | 26724
2533 | 425.0689 | 26724
2534 | 402.9212 | 26724
2535 | 423.3641 | 26724
2536 | 404.3218 | 26724
2537 | 411.4408 | 26724
2538 | 420.6128 | 26724
2539 | 418.5289 | 26724
2540 | 401.5205 | 26724
2541 | 423.1321 | 26724
2542 | 414.2565 | 26724
2543 | 421.3644 | 26724
2544 | 423.888 | 26724
2545 | 428.2686 | 26724
2546 | 410.0199 | 26724
2547 | 412.5245 | 26724
2548 | 409.9467 | 26724
2549 | 422.3827 | 26724
2550 | 400.922 | 26724
2551 | 424.5121 | 26724
2552 | 419.3861 | 26724
2553 | 422.9014 | 26724
2554 | 424.7551 | 26724
2555 | 424.23 | 26724
2556 | 414.1827 | 26724
2557 | 419.0363 | 26724
2558 | 409.555 | 26724
2559 | 425.3946 | 26724
2560 | 407.2858 | 26724
2561 | 419.0516 | 26724
2562 | 410.6482 | 26724
2563 | 404.0356 | 26724
2564 | 408.6885 | 26724
2565 | 435.791 | 26724
2566 | 420.8206 | 26724
2567 | 420.5214 | 26724
2568 | 407.6083 | 26724
2569 | 406.5752 | 26724
2570 | 416.1192 | 26724
2571 | 412.2497 | 26724
2572 | 425.1769 | 26724
2573 | 416.5088 | 26724
2574 | 419.5757 | 26724
2575 | 414.6281 | 26724
2576 | 414.7577 | 26724
2577 | 424.8843 | 26724
2578 | 410.2961 | 26724
2579 | 420.4926 | 26724
2580 | 428.4155 | 26724
2581 | 413.2116 | 26724
2582 | 420.3971 | 26724
2583 | 421.2338 | 26724
2584 | 420.3222 | 26724
2585 | 428.9458 | 26724
2586 | 405.6368 | 26724
2587 | 420.7075 | 26724
2588 | 409.3676 | 26724
2589 | 414.4902 | 26724
2590 | 424.1127 | 26724
2591 | 418.5994 | 26724
2592 | 402.9859 | 26724
2593 | 411.2458 | 26724
2594 | 421.6142 | 26724
2595 | 424.7829 | 26724
2596 | 431.4721 | 26724
2597 | 414.352 | 26724
2598 | 417.8047 | 26724
2599 | 414.1557 | 26724
2600 | 423.799 | 26724
2601 | 418.8183 | 26724
2602 | 406.88 | 26724
2603 | 419.6135 | 26724
2604 | 426.123 | 26724
2605 | 422.3889 | 26724
2606 | 425.3398 | 26724
2607 | 421.0689 | 26724
2608 | 411.7871 | 26724
2609 | 412.0785 | 26724
2610 | 421.8489 | 26724
2611 | 417.5818 | 26724
2612 | 408.6283 | 26724
2613 | 402.2299 | 26724
2614 | 414.9177 | 26724
2615 | 398.8735 | 26724
2616 | 417.2266 | 26724
2617 | 413.3722 | 26724
2618 | 406.4198 | 26724
2619 | 415.8494 | 26724
2620 | 412.6261 | 26724
2621 | 421.4131 | 26724
2622 | 401.6419 | 26724
2623 | 405.3751 | 26724
2624 | 429.8668 | 26724
2625 | 416.6974 | 26724
2626 | 408.984 | 26724
2627 | 422.101 | 26724
2628 | 426.1414 | 26724
2629 | 425.6334 | 26724
2630 | 404.2544 | 26724
2631 | 421.9687 | 26724
2632 | 419.2669 | 26724
2633 | 414.6321 | 26724
2634 | 416.9223 | 26724
2635 | 404.9022 | 26724
2636 | 428.8575 | 26724
2637 | 410.3033 | 26724
2638 | 428.5131 | 26724
2639 | 422.6043 | 26724
2640 | 433.7493 | 26724
2641 | 405.5146 | 26724
2642 | 409.3885 | 26724
2643 | 416.9796 | 26724
2644 | 414.5034 | 26724
2645 | 416.3651 | 26724
2646 | 421.4654 | 26724
2647 | 410.2472 | 26724
2648 | 399.2382 | 26724
2649 | 401.722 | 26724
2650 | 418.608 | 26724
2651 | 418.2287 | 26724
2652 | 421.8414 | 26724
2653 | 409.9709 | 26724
2654 | 433.3174 | 26724
2655 | 428.0446 | 26724
2656 | 425.7932 | 26724
2657 | 408.6296 | 26724
2658 | 431.8815 | 26724
2659 | 421.5245 | 26724
2660 | 424.9847 | 26724
2661 | 404.163 | 26724
2662 | 411.2303 | 26724
2663 | 411.9975 | 26724
2664 | 407.9014 | 26724
2665 | 423.0157 | 26724
2666 | 421.0861 | 26724
2667 | 407.49 | 26724
2668 | 426.2044 | 26724
2669 | 434.6773 | 26724
2670 | 418.9878 | 26724
2671 | 409.1855 | 26724
2672 | 421.609 | 26724
2673 | 405.3974 | 26724
2674 | 420.3843 | 26724
2675 | 407.6739 | 26724
2676 | 408.0221 | 26724
2677 | 433.6697 | 26724
2678 | 416.0918 | 26724
2679 | 415.6478 | 26724
2680 | 412.0252 | 26724
2681 | 423.4971 | 26724
2682 | 423.537 | 26724
2683 | 408.8396 | 26724
2684 | 409.2817 | 26724
2685 | 417.9006 | 26724
2686 | 415.4642 | 26724
2687 | 415.5394 | 26724
2688 | 409.5785 | 26724
2689 | 403.6729 | 26724
2690 | 408.1307 | 26724
2691 | 408.5361 | 26724
2692 | 423.6629 | 26724
2693 | 421.2225 | 26724
2694 | 396.4774 | 26724
2695 | 399.9792 | 26724
2696 | 417.1995 | 26724
2697 | 422.3913 | 26724
2698 | 419.3408 | 26724
2699 | 422.5853 | 26724
2700 | 411.0868 | 26724
2701 | 414.6337 | 26724
2702 | 430.3507 | 26724
2703 | 418.1906 | 26724
2704 | 425.51 | 26724
2705 | 409.6685 | 26724
2706 | 417.4571 | 26724
2707 | 421.5825 | 26724
2708 | 419.8956 | 26724
2709 | 420.0553 | 26724
2710 | 425.7273 | 26724
2711 | 417.4816 | 26724
2712 | 420.3078 | 26724
2713 | 413.4496 | 26724
2714 | 409.7011 | 26724
2715 | 416.3359 | 26724
2716 | 418.5453 | 26724
2717 | 424.0452 | 26724
2718 | 415.4045 | 26724
2719 | 423.6804 | 26724
2720 | 418.8891 | 26724
2721 | 411.2216 | 26724
2722 | 402.6582 | 26724
2723 | 410.0542 | 26724
2724 | 427.0571 | 26724
2725 | 416.1857 | 26724
2726 | 428.9574 | 26724
2727 | 430.6431 | 26724
2728 | 429.0136 | 26724
2729 | 409.8226 | 26724
2730 | 409.0247 | 26724
2731 | 409.5538 | 26724
2732 | 415.8945 | 26724
2733 | 407.9903 | 26724
2734 | 408.4004 | 26724
2735 | 402.4877 | 26724
2736 | 424.4523 | 26724
2737 | 431.6982 | 26724
2738 | 413.5798 | 26724
2739 | 414.4772 | 26724
2740 | 412.6964 | 26724
2741 | 417.712 | 26724
2742 | 411.2477 | 26724
2743 | 423.359 | 26724
2744 | 414.6035 | 26724
2745 | 416.4674 | 26724
2746 | 417.7978 | 26724
2747 | 419.8394 | 26724
2748 | 412.9738 | 26724
2749 | 405.6261 | 26724
2750 | 413.8255 | 26724
2751 | 424.1509 | 26724
2752 | 417.2051 | 26724
2753 | 429.6236 | 26724
2754 | 414.8769 | 26724
2755 | 425.7285 | 26724
2756 | 413.5722 | 26724
2757 | 407.7229 | 26724
2758 | 423.2378 | 26724
2759 | 417.4401 | 26724
2760 | 398.1059 | 26724
2761 | 423.9479 | 26724
2762 | 400.2101 | 26724
2763 | 416.9142 | 26724
2764 | 414.6084 | 26724
2765 | 412.2413 | 26724
2766 | 410.6773 | 26724
2767 | 418.0678 | 26724
2768 | 405.1642 | 26724
2769 | 410.739 | 26724
2770 | 420.1725 | 26724
2771 | 418.6287 | 26724
2772 | 412.2242 | 26724
2773 | 418.1092 | 26724
2774 | 412.5176 | 26724
2775 | 408.9014 | 26724
2776 | 421.5546 | 26724
2777 | 414.1761 | 26724
2778 | 408.5606 | 26724
2779 | 411.6106 | 26724
2780 | 422.3443 | 26724
2781 | 408.7075 | 26724
2782 | 401.9298 | 26724
2783 | 421.7579 | 26724
2784 | 406.5126 | 26724
2785 | 416.915 | 26724
2786 | 435.3517 | 26724
2787 | 415.8392 | 26724
2788 | 425.2489 | 26724
2789 | 434.6103 | 26724
2790 | 419.4767 | 26724
2791 | 433.341 | 26724
2792 | 417.9919 | 26724
2793 | 407.9245 | 26724
2794 | 409.1683 | 26724
2795 | 402.8281 | 26724
2796 | 416.8786 | 26724
2797 | 413.1759 | 26724
2798 | 415.6277 | 26724
2799 | 410.4494 | 26724
2800 | 418.3091 | 26724
2801 | 422.8259 | 26724
2802 | 415.4561 | 26724
2803 | 418.7918 | 26724
2804 | 407.5427 | 26724
2805 | 417.4477 | 26724
2806 | 417.5358 | 26724
2807 | 424.7347 | 26724
2808 | 409.5537 | 26724
2809 | 422.6151 | 26724
2810 | 404.2726 | 26724
2811 | 403.5827 | 26724
2812 | 415.2898 | 26724
2813 | 414.8033 | 26724
2814 | 414.5153 | 26724
2815 | 399.547 | 26724
2816 | 431.9953 | 26724
2817 | 429.3362 | 26724
2818 | 412.4785 | 26724
2819 | 423.6948 | 26724
2820 | 420.0857 | 26724
2821 | 425.1416 | 26724
2822 | 424.5891 | 26724
2823 | 413.2467 | 26724
2824 | 432.1044 | 26724
2825 | 423.071 | 26724
2826 | 410.7066 | 26724
2827 | 421.5113 | 26724
2828 | 410.0542 | 26724
2829 | 414.8912 | 26724
2830 | 423.7095 | 26724
2831 | 407.6628 | 26724
2832 | 408.7517 | 26724
2833 | 417.3391 | 26724
2834 | 432.0703 | 26724
2835 | 407.891 | 26724
2836 | 415.2699 | 26724
2837 | 420.2411 | 26724
2838 | 414.968 | 26724
2839 | 418.3655 | 26724
2840 | 414.7114 | 26724
2841 | 411.983 | 26724
2842 | 415.7964 | 26724
2843 | 423.961 | 26724
2844 | 415.5596 | 26724
2845 | 413.1481 | 26724
2846 | 410.0019 | 26724
2847 | 417.0017 | 26724
2848 | 407.4326 | 26724
2849 | 409.9653 | 26724
2850 | 426.9447 | 26724
2851 | 416.8561 | 26724
2852 | 415.1792 | 26724
2853 | 424.6069 | 26724
2854 | 425.7323 | 26724
2855 | 412.5517 | 26724
2856 | 398.9356 | 26724
2857 | 410.0815 | 26724
2858 | 416.4329 | 26724
2859 | 418.1356 | 26724
2860 | 433.8438 | 26724
2861 | 400.1934 | 26724
2862 | 429.9433 | 26724
2863 | 421.5758 | 26724
2864 | 432.7671 | 26724
2865 | 416.701 | 26724
2866 | 413.076 | 26724
2867 | 401.7031 | 26724
2868 | 407.2963 | 26724
2869 | 412.5434 | 26724
2870 | 415.1244 | 26724
2871 | 408.2642 | 26724
2872 | 421.2496 | 26724
2873 | 410.128 | 26724
2874 | 400.6231 | 26724
2875 | 410.3826 | 26724
2876 | 415.4784 | 26724
2877 | 399.6861 | 26724
2878 | 426.306 | 26724
2879 | 400.2449 | 26724
2880 | 412.0011 | 26724
2881 | 421.9236 | 26724
2882 | 418.2083 | 26724
2883 | 421.4395 | 26724
2884 | 431.0386 | 26724
2885 | 422.1189 | 26724
2886 | 404.4841 | 26724
2887 | 418.6649 | 26724
2888 | 412.9965 | 26724
2889 | 409.9733 | 26724
2890 | 417.4456 | 26724
2891 | 429.1259 | 26724
2892 | 416.4351 | 26724
2893 | 406.017 | 26724
2894 | 418.946 | 26724
2895 | 411.9296 | 26724
2896 | 419.0043 | 26724
2897 | 429.592 | 26724
2898 | 418.6024 | 26724
2899 | 416.7164 | 26724
2900 | 418.7047 | 26724
2901 | 418.4786 | 26724
2902 | 400.6266 | 26724
2903 | 403.5603 | 26724
2904 | 422.1122 | 26724
2905 | 416.9447 | 26724
2906 | 426.8655 | 26724
2907 | 421.0687 | 26724
2908 | 416.4252 | 26724
2909 | 416.2595 | 26724
2910 | 416.9587 | 26724
2911 | 416.0599 | 26724
2912 | 420.0053 | 26724
2913 | 421.4853 | 26724
2914 | 418.4412 | 26724
2915 | 403.8905 | 26724
2916 | 427.2226 | 26724
2917 | 408.0154 | 26724
2918 | 413.0247 | 26724
2919 | 413.119 | 26724
2920 | 418.6501 | 26724
2921 | 412.2893 | 26724
2922 | 425.369 | 26724
2923 | 411.6836 | 26724
2924 | 429.4823 | 26724
2925 | 425.6698 | 26724
2926 | 417.4572 | 26724
2927 | 424.7966 | 26724
2928 | 419.2134 | 26724
2929 | 422.7818 | 26724
2930 | 421.5163 | 26724
2931 | 408.7731 | 26724
2932 | 401.7905 | 26724
2933 | 423.6844 | 26724
2934 | 423.716 | 26724
2935 | 414.3398 | 26724
2936 | 399.2314 | 26724
2937 | 408.7377 | 26724
2938 | 413.4081 | 26724
2939 | 395.603 | 26724
2940 | 420.6624 | 26724
2941 | 423.0465 | 26724
2942 | 423.3154 | 26724
2943 | 421.7211 | 26724
2944 | 408.8371 | 26724
2945 | 400.613 | 26724
2946 | 422.8258 | 26724
2947 | 414.77 | 26724
2948 | 418.8254 | 26724
2949 | 401.5585 | 26724
2950 | 427.0515 | 26724
2951 | 424.2087 | 26724
2952 | 431.3193 | 26724
2953 | 403.5583 | 26724
2954 | 426.0431 | 26724
2955 | 415.903 | 26724
2956 | 418.6325 | 26724
2957 | 398.1429 | 26724
2958 | 413.4071 | 26724
2959 | 411.8058 | 26724
2960 | 420.9923 | 26724
2961 | 420.6636 | 26724
2962 | 405.7066 | 26724
2963 | 410.7768 | 26724
2964 | 399.1321 | 26724
2965 | 414.0743 | 26724
2966 | 407.3362 | 26724
2967 | 412.8174 | 26724
2968 | 424.3271 | 26724
2969 | 415.1432 | 26724
2970 | 435.7373 | 26724
2971 | 420.439 | 26724
2972 | 416.442 | 26724
2973 | 429.276 | 26724
2974 | 409.7338 | 26724
2975 | 410.9608 | 26724
2976 | 421.6645 | 26724
2977 | 424.2643 | 26724
2978 | 411.5057 | 26724
2979 | 428.2409 | 26724
2980 | 420.8443 | 26724
2981 | 416.3973 | 26724
2982 | 423.2115 | 26724
2983 | 417.9586 | 26724
2984 | 404.633 | 26724
2985 | 420.6364 | 26724
2986 | 432.2542 | 26724
2987 | 409.7416 | 26724
2988 | 406.5953 | 26724
2989 | 435.8557 | 26724
2990 | 405.177 | 26724
2991 | 400.5815 | 26724
2992 | 398.7144 | 26724
2993 | 420.7625 | 26724
2994 | 409.2495 | 26724
2995 | 416.7125 | 26724
2996 | 422.6846 | 26724
2997 | 408.1975 | 26724
2998 | 407.3199 | 26724
2999 | 416.5043 | 26724
3000 | 408.4988 | 26724
3001 | 426.307 | 26724
3002 | 411.5219 | 26724
3003 | 425.7781 | 26724
3004 | 426.3734 | 26724
3005 | 411.2077 | 26724
3006 | 416.3919 | 26724
3007 | 407.2484 | 26724
3008 | 419.3887 | 26724
3009 | 425.5544 | 26724
3010 | 420.7065 | 26724
3011 | 418.2418 | 26724
3012 | 428.0576 | 26724
3013 | 414.6392 | 26724
3014 | 422.3436 | 26724
3015 | 413.3241 | 26724
3016 | 408.4876 | 26724
3017 | 404.4256 | 26724
3018 | 428.8559 | 26724
3019 | 403.1248 | 26724
3020 | 422.5009 | 26724
3021 | 411.8445 | 26724
3022 | 406.1537 | 26724
3023 | 416.7632 | 26724
3024 | 424.2057 | 26724
3025 | 421.2826 | 26724
3026 | 410.9444 | 26724
3027 | 421.127 | 26724
3028 | 404.3132 | 26724
3029 | 403.7026 | 26724
3030 | 414.5582 | 26724
3031 | 416.6154 | 26724
3032 | 402.6793 | 26724
3033 | 423.0962 | 26724
3034 | 397.1248 | 26724
3035 | 417.2962 | 26724
3036 | 405.367 | 26724
3037 | 419.0989 | 26724
3038 | 414.18 | 26724
3039 | 408.3084 | 26724
3040 | 420.2036 | 26724
3041 | 432.9222 | 26724
3042 | 417.0184 | 26724
3043 | 416.5189 | 26724
3044 | 410.8516 | 26724
3045 | 413.0382 | 26724
3046 | 414.0258 | 26724
3047 | 428.1545 | 26724
3048 | 407.7859 | 26724
3049 | 422.25 | 26724
3050 | 402.239 | 26724
3051 | 424.152 | 26724
3052 | 414.8911 | 26724
3053 | 403.4116 | 26724
3054 | 424.9761 | 26724
3055 | 422.232 | 26724
3056 | 413.9036 | 26724
3057 | 406.7684 | 26724
3058 | 401.4041 | 26724
3059 | 416.7781 | 26724
3060 | 416.8062 | 26724
3061 | 409.2532 | 26724
3062 | 416.9559 | 26724
3063 | 415.5321 | 26724
3064 | 419.4712 | 26724
3065 | 415.2207 | 26724
3066 | 416.6324 | 26724
3067 | 424.48 | 26724
3068 | 414.1078 | 26724
3069 | 410.8876 | 26724
3070 | 411.5012 | 26724
3071 | 425.0065 | 26724
3072 | 410.9405 | 26724
3073 | 429.2254 | 26724
3074 | 429.7993 | 26724
3075 | 408.7393 | 26724
3076 | 415.2048 | 26724
3077 | 418.8231 | 26724
3078 | 404.2126 | 26724
3079 | 422.456 | 26724
3080 | 412.4926 | 26724
3081 | 415.2231 | 26724
3082 | 419.9338 | 26724
3083 | 430.0736 | 26724
3084 | 418.415 | 26724
3085 | 412.178 | 26724
3086 | 402.521 | 26724
3087 | 416.1337 | 26724
3088 | 408.5875 | 26724
3089 | 414.6886 | 26724
3090 | 428.1401 | 26724
3091 | 426.3542 | 26724
3092 | 413.3298 | 26724
3093 | 414.2582 | 26724
3094 | 427.215 | 26724
3095 | 409.7205 | 26724
3096 | 417.3777 | 26724
3097 | 424.4127 | 26724
3098 | 415.9554 | 26724
3099 | 417.4606 | 26724
3100 | 423.6111 | 26724
3101 | 409.7775 | 26724
3102 | 416.7882 | 26724
3103 | 413.8267 | 26724
3104 | 425.2276 | 26724
3105 | 431.6081 | 26724
3106 | 422.5828 | 26724
3107 | 418.1694 | 26724
3108 | 420.3108 | 26724
3109 | 430.1223 | 26724
3110 | 411.2001 | 26724
3111 | 435.3931 | 26724
3112 | 432.7736 | 26724
3113 | 425.5397 | 26724
3114 | 430.9936 | 26724
3115 | 420.9157 | 26724
3116 | 408.989 | 26724
3117 | 416.2818 | 26724
3118 | 416.9674 | 26724
3119 | 396.7775 | 26724
3120 | 411.6315 | 26724
3121 | 408.0981 | 26724
3122 | 405.2846 | 26724
3123 | 414.7808 | 26724
3124 | 426.0684 | 26724
3125 | 397.6209 | 26724
3126 | 404.2386 | 26724
3127 | 416.1324 | 26724
3128 | 429.2715 | 26724
3129 | 417.2257 | 26724
3130 | 418.2762 | 26724
3131 | 421.6606 | 26724
3132 | 419.5507 | 26724
3133 | 415.4243 | 26724
3134 | 413.8989 | 26724
3135 | 420.3396 | 26724
3136 | 404.6386 | 26724
3137 | 420.081 | 26724
3138 | 414.4721 | 26724
3139 | 418.6263 | 26724
3140 | 419.645 | 26724
3141 | 413.0109 | 26724
3142 | 418.691 | 26724
3143 | 421.9544 | 26724
3144 | 414.1016 | 26724
3145 | 416.352 | 26724
3146 | 418.4929 | 26724
3147 | 414.4277 | 26724
3148 | 427.5651 | 26724
3149 | 410.7432 | 26724
3150 | 425.9178 | 26724
3151 | 408.2569 | 26724
3152 | 408.2791 | 26724
3153 | 426.4422 | 26724
3154 | 424.5141 | 26724
3155 | 415.3918 | 26724
3156 | 409.9933 | 26724
3157 | 425.9434 | 26724
3158 | 427.9751 | 26724
3159 | 416.3087 | 26724
3160 | 416.5645 | 26724
3161 | 420.7412 | 26724
3162 | 398.9445 | 26724
3163 | 418.8641 | 26724
3164 | 420.1972 | 26724
3165 | 428.0447 | 26724
3166 | 406.0718 | 26724
3167 | 414.4757 | 26724
3168 | 421.8552 | 26724
3169 | 404.0682 | 26724
3170 | 406.7464 | 26724
3171 | 409.3198 | 26724
3172 | 416.6208 | 26724
3173 | 429.2063 | 26724
3174 | 415.8988 | 26724
3175 | 397.8761 | 26724
3176 | 403.4861 | 26724
3177 | 408.7521 | 26724
3178 | 413.0022 | 26724
3179 | 417.3336 | 26724
3180 | 426.6043 | 26724
3181 | 410.2151 | 26724
3182 | 430.0595 | 26724
3183 | 424.1218 | 26724
3184 | 438.0623 | 26724
3185 | 422.9569 | 26724
3186 | 417.1986 | 26724
3187 | 416.7365 | 26724
3188 | 426.5147 | 26724
3189 | 406.4739 | 26724
3190 | 411.9526 | 26724
3191 | 399.7206 | 26724
3192 | 426.156 | 26724
3193 | 419.4703 | 26724
3194 | 418.8434 | 26724
3195 | 421.337 | 26724
3196 | 406.2554 | 26724
3197 | 398.8798 | 26724
3198 | 411.4808 | 26724
3199 | 415.9604 | 26724
3200 | 412.4368 | 26724
3201 | 413.6933 | 26724
3202 | 413.8123 | 26724
3203 | 418.6055 | 26724
3204 | 423.963 | 26724
3205 | 417.5025 | 26724
3206 | 402.022 | 26724
3207 | 429.3455 | 26724
3208 | 421.2386 | 26724
3209 | 414.0801 | 26724
3210 | 414.1357 | 26724
3211 | 421.0144 | 26724
3212 | 411.2401 | 26724
3213 | 409.4207 | 26724
3214 | 411.2858 | 26724
3215 | 408.1978 | 26724
3216 | 423.296 | 26724
3217 | 426.0342 | 26724
3218 | 421.3071 | 26724
3219 | 420.7604 | 26724
3220 | 420.6946 | 26724
3221 | 405.716 | 26724
3222 | 408.76 | 26724
3223 | 407.5884 | 26724
3224 | 400.7823 | 26724
3225 | 415.5432 | 26724
3226 | 430.0427 | 26724
3227 | 412.5507 | 26724
3228 | 413.7734 | 26724
3229 | 404.468 | 26724
3230 | 409.6399 | 26724
3231 | 412.9063 | 26724
3232 | 425.2926 | 26724
3233 | 422.8824 | 26724
3234 | 416.6682 | 26724
3235 | 408.6541 | 26724
3236 | 411.1409 | 26724
3237 | 417.6168 | 26724
3238 | 414.5444 | 26724
3239 | 407.3547 | 26724
3240 | 412.9577 | 26724
3241 | 418.9067 | 26724
3242 | 411.4091 | 26724
3243 | 410.1808 | 26724
3244 | 411.7657 | 26724
3245 | 411.4559 | 26724
3246 | 422.6828 | 26724
3247 | 415.7846 | 26724
3248 | 435.0243 | 26724
3249 | 414.6195 | 26724
3250 | 427.8968 | 26724
3251 | 420.2772 | 26724
3252 | 415.0855 | 26724
3253 | 423.297 | 26724
3254 | 426.6609 | 26724
3255 | 421.1535 | 26724
3256 | 421.5218 | 26724
3257 | 421.2839 | 26724
3258 | 420.4762 | 26724
3259 | 406.7465 | 26724
3260 | 426.2427 | 26724
3261 | 408.9909 | 26724
3262 | 411.1975 | 26724
3263 | 411.7096 | 26724
3264 | 406.0931 | 26724
3265 | 426.9144 | 26724
3266 | 408.4205 | 26724
3267 | 429.8976 | 26724
3268 | 411.0927 | 26724
3269 | 425.8053 | 26724
3270 | 422.8232 | 26724
3271 | 419.66 | 26724
3272 | 410.8925 | 26724
3273 | 431.6341 | 26724
3274 | 407.8578 | 26724
3275 | 419.0698 | 26724
3276 | 429.3856 | 26724
3277 | 414.1755 | 26724
3278 | 401.4073 | 26724
3279 | 416.065 | 26724
3280 | 424.9756 | 26724
3281 | 414.2654 | 26724
3282 | 407.2976 | 26724
3283 | 418.1883 | 26724
3284 | 422.4598 | 26724
3285 | 421.1122 | 26724
3286 | 418.0455 | 26724
3287 | 418.2413 | 26724
3288 | 416.3004 | 26724
3289 | 420.433 | 26724
3290 | 422.9669 | 26724
3291 | 428.3634 | 26724
3292 | 433.7691 | 26724
3293 | 413.7248 | 26724
3294 | 418.394 | 26724
3295 | 416.497 | 26724
3296 | 430.3495 | 26724
3297 | 417.0492 | 26724
3298 | 416.2402 | 26724
3299 | 398.5543 | 26724
3300 | 407.7551 | 26724
3301 | 411.9565 | 26724
3302 | 411.8996 | 26724
3303 | 415.0576 | 26724
3304 | 421.0443 | 26724
3305 | 410.0113 | 26724
3306 | 427.9683 | 26724
3307 | 412.4458 | 26724
3308 | 421.939 | 26724
3309 | 424.0241 | 26724
3310 | 416.5097 | 26724
3311 | 405.5917 | 26724
3312 | 427.1325 | 26724
3313 | 413.3207 | 26724
3314 | 420.2986 | 26724
3315 | 421.3118 | 26724
3316 | 419.2527 | 26724
3317 | 403.4063 | 26724
3318 | 418.1862 | 26724
3319 | 424.3909 | 26724
3320 | 416.8043 | 26724
3321 | 415.6149 | 26724
3322 | 421.1287 | 26724
3323 | 398.389 | 26724
3324 | 415.1935 | 26724
3325 | 423.9471 | 26724
3326 | 401.9834 | 26724
3327 | 413.9372 | 26724
3328 | 420.0041 | 26724
3329 | 421.2205 | 26724
3330 | 421.9003 | 26724
3331 | 410.137 | 26724
3332 | 429.2997 | 26724
3333 | 408.4443 | 26724
3334 | 402.502 | 26724
3335 | 410.1759 | 26724
3336 | 423.3162 | 26724
3337 | 405.9248 | 26724
3338 | 414.6355 | 26724
3339 | 427.1472 | 26724
3340 | 420.696 | 26724
3341 | 421.1122 | 26724
3342 | 418.9779 | 26724
3343 | 423.4137 | 26724
3344 | 423.9216 | 26724
3345 | 417.6995 | 26724
3346 | 426.7683 | 26724
3347 | 411.7915 | 26724
3348 | 408.1004 | 26724
3349 | 412.3168 | 26724
3350 | 422.6164 | 26724
3351 | 415.4272 | 26724
3352 | 424.3702 | 26724
3353 | 417.2365 | 26724
3354 | 417.4231 | 26724
3355 | 411.015 | 26724
3356 | 405.4923 | 26724
3357 | 420.4048 | 26724
3358 | 418.2692 | 26724
3359 | 401.592 | 26724
3360 | 413.6409 | 26724
3361 | 404.5376 | 26724
3362 | 405.9618 | 26724
3363 | 416.0342 | 26724
3364 | 413.5294 | 26724
3365 | 404.0618 | 26724
3366 | 427.3997 | 26724
3367 | 413.8488 | 26724
3368 | 421.0141 | 26724
3369 | 417.5963 | 26724
3370 | 413.7297 | 26724
3371 | 423.8417 | 26724
3372 | 426.6191 | 26724
3373 | 432.583 | 26724
3374 | 418.1694 | 26724
3375 | 424.1116 | 26724
3376 | 406.9123 | 26724
3377 | 412.8658 | 26724
3378 | 404.79 | 26724
3379 | 415.6975 | 26724
3380 | 422.3562 | 26724
3381 | 421.2054 | 26724
3382 | 416.2333 | 26724
3383 | 408.9211 | 26724
3384 | 420.061 | 26724
3385 | 419.0284 | 26724
3386 | 404.7407 | 26724
3387 | 432.497 | 26724
3388 | 431.4202 | 26724
3389 | 418.4731 | 26724
3390 | 425.0826 | 26724
3391 | 416.5245 | 26724
3392 | 406.0089 | 26724
3393 | 425.2354 | 26724
3394 | 419.356 | 26724
3395 | 410.0465 | 26724
3396 | 424.351 | 26724
3397 | 414.7416 | 26724
3398 | 427.1819 | 26724
3399 | 421.2367 | 26724
3400 | 418.3154 | 26724
3401 | 413.9136 | 26724
3402 | 408.6732 | 26724
3403 | 415.0818 | 26724
3404 | 402.5967 | 26724
3405 | 420.4133 | 26724
3406 | 412.1145 | 26724
3407 | 402.6766 | 26724
3408 | 410.9306 | 26724
3409 | 413.424 | 26724
3410 | 406.2758 | 26724
3411 | 415.6442 | 26724
3412 | 410.2318 | 26724
3413 | 416.0039 | 26724
3414 | 415.2987 | 26724
3415 | 405.3629 | 26724
3416 | 425.5391 | 26724
3417 | 417.5429 | 26724
3418 | 414.996 | 26724
3419 | 407.2046 | 26724
3420 | 417.9283 | 26724
3421 | 419.7634 | 26724
3422 | 406.0247 | 26724
3423 | 414.1688 | 26724
3424 | 403.5749 | 26724
3425 | 409.2723 | 26724
3426 | 421.5218 | 26724
3427 | 404.138 | 26724
3428 | 418.1153 | 26724
3429 | 410.4422 | 26724
3430 | 429.5061 | 26724
3431 | 423.0172 | 26724
3432 | 408.5214 | 26724
3433 | 423.7017 | 26724
3434 | 409.5639 | 26724
3435 | 419.9151 | 26724
3436 | 413.226 | 26724
3437 | 410.3284 | 26724
3438 | 410.7691 | 26724
3439 | 429.6496 | 26724
3440 | 425.0656 | 26724
3441 | 405.5283 | 26724
3442 | 401.1012 | 26724
3443 | 421.6778 | 26724
3444 | 396.3727 | 26724
3445 | 415.0014 | 26724
3446 | 407.1062 | 26724
3447 | 430.9223 | 26724
3448 | 418.2383 | 26724
3449 | 417.6571 | 26724
3450 | 416.7112 | 26724
3451 | 406.3707 | 26724
3452 | 412.3968 | 26724
3453 | 419.7303 | 26724
3454 | 399.8394 | 26724
3455 | 421.181 | 26724
3456 | 417.0364 | 26724
3457 | 418.4388 | 26724
3458 | 423.3849 | 26724
3459 | 420.0295 | 26724
3460 | 411.9782 | 26724
3461 | 417.2622 | 26724
3462 | 401.4734 | 26724
3463 | 419.3498 | 26724
3464 | 418.1282 | 26724
3465 | 397.1267 | 26724
3466 | 417.6277 | 26724
3467 | 428.4965 | 26724
3468 | 416.0463 | 26724
3469 | 423.6309 | 26724
3470 | 406.1611 | 26724
3471 | 404.6216 | 26724
3472 | 414.9173 | 26724
3473 | 416.0538 | 26724
3474 | 403.2895 | 26724
3475 | 405.5008 | 26724
3476 | 425.8503 | 26724
3477 | 397.0517 | 26724
3478 | 423.354 | 26724
3479 | 411.9548 | 26724
3480 | 414.149 | 26724
3481 | 420.0594 | 26724
3482 | 408.0241 | 26724
3483 | 405.376 | 26724
3484 | 408.8849 | 26724
3485 | 414.3791 | 26724
3486 | 416.343 | 26724
3487 | 422.0126 | 26724
3488 | 419.3472 | 26724
3489 | 411.8622 | 26724
3490 | 421.019 | 26724
3491 | 414.0145 | 26724
3492 | 420.758 | 26724
3493 | 412.8137 | 26724
3494 | 412.408 | 26724
3495 | 396.187 | 26724
3496 | 420.1928 | 26724
3497 | 413.2608 | 26724
3498 | 421.4645 | 26724
3499 | 409.9324 | 26724
3500 | 411.9384 | 26724
3501 | 413.6016 | 26724
3502 | 427.968 | 26724
3503 | 407.793 | 26724
3504 | 423.873 | 26724
3505 | 417.2205 | 26724
3506 | 417.8378 | 26724
3507 | 412.6114 | 26724
3508 | 428.7476 | 26724
3509 | 421.1063 | 26724
3510 | 416.2527 | 26724
3511 | 419.4193 | 26724
3512 | 413.0219 | 26724
3513 | 407.6862 | 26724
3514 | 414.6071 | 26724
3515 | 429.8518 | 26724
3516 | 407.2241 | 26724
3517 | 409.4342 | 26724
3518 | 407.7857 | 26724
3519 | 430.6475 | 26724
3520 | 407.5787 | 26724
3521 | 410.8486 | 26724
3522 | 414.3874 | 26724
3523 | 414.2692 | 26724
3524 | 420.7501 | 26724
3525 | 414.8957 | 26724
3526 | 406.0261 | 26724
3527 | 416.3442 | 26724
3528 | 408.8265 | 26724
3529 | 424.6251 | 26724
3530 | 416.8907 | 26724
3531 | 408.5878 | 26724
3532 | 409.2988 | 26724
3533 | 399.8192 | 26724
3534 | 429.6567 | 26724
3535 | 408.42 | 26724
3536 | 417.228 | 26724
3537 | 419.7665 | 26724
3538 | 417.2567 | 26724
3539 | 405.3498 | 26724
3540 | 408.165 | 26724
3541 | 417.7534 | 26724
3542 | 402.3721 | 26724
3543 | 415.5391 | 26724
3544 | 410.1452 | 26724
3545 | 411.9958 | 26724
3546 | 410.1247 | 26724
3547 | 420.562 | 26724
3548 | 411.608 | 26724
3549 | 412.8858 | 26724
3550 | 432.5108 | 26724
3551 | 418.5217 | 26724
3552 | 410.4224 | 26724
3553 | 437.2476 | 26724
3554 | 422.4769 | 26724
3555 | 401.9495 | 26724
3556 | 423.0075 | 26724
3557 | 406.9609 | 26724
3558 | 407.6173 | 26724
3559 | 420.5344 | 26724
3560 | 419.8161 | 26724
3561 | 405.3116 | 26724
3562 | 420.3102 | 26724
3563 | 416.9244 | 26724
3564 | 403.1977 | 26724
3565 | 424.7871 | 26724
3566 | 408.5756 | 26724
3567 | 404.0737 | 26724
3568 | 418.1013 | 26724
3569 | 421.6067 | 26724
3570 | 409.7169 | 26724
3571 | 413.9172 | 26724
3572 | 428.6117 | 26724
3573 | 413.4994 | 26724
3574 | 408.2789 | 26724
3575 | 421.8016 | 26724
3576 | 403.4911 | 26724
3577 | 404.9059 | 26724
3578 | 413.1172 | 26724
3579 | 412.0885 | 26724
3580 | 419.476 | 26724
3581 | 414.7592 | 26724
3582 | 429.1501 | 26724
3583 | 419.8513 | 26724
3584 | 433.2608 | 26724
3585 | 418.8562 | 26724
3586 | 436.1609 | 26724
3587 | 405.8768 | 26724
3588 | 417.7792 | 26724
3589 | 417.2067 | 26724
3590 | 419.5766 | 26724
3591 | 400.81 | 26724
3592 | 416.4729 | 26724
3593 | 425.9158 | 26724
3594 | 412.7748 | 26724
3595 | 425.3694 | 26724
3596 | 415.2702 | 26724
3597 | 412.6296 | 26724
3598 | 414.8095 | 26724
3599 | 410.8604 | 26724
3600 | 413.1121 | 26724
3601 | 428.3599 | 26724
3602 | 416.6767 | 26724
3603 | 411.6359 | 26724
3604 | 408.9402 | 26724
3605 | 408.6285 | 26724
3606 | 416.0496 | 26724
3607 | 410.517 | 26724
3608 | 421.7661 | 26724
3609 | 411.9304 | 26724
3610 | 429.074 | 26724
3611 | 426.412 | 26724
3612 | 413.0619 | 26724
3613 | 405.2799 | 26724
3614 | 411.8501 | 26724
3615 | 417.4748 | 26724
3616 | 412.3363 | 26724
3617 | 423.1322 | 26724
3618 | 404.6102 | 26724
3619 | 427.3386 | 26724
3620 | 414.0064 | 26724
3621 | 429.8727 | 26724
3622 | 416.0788 | 26724
3623 | 411.33 | 26724
3624 | 409.7749 | 26724
3625 | 419.3301 | 26724
3626 | 425.6436 | 26724
3627 | 418.4738 | 26724
3628 | 426.4783 | 26724
3629 | 416.0912 | 26724
3630 | 413.4106 | 26724
3631 | 416.0612 | 26724
3632 | 412.1276 | 26724
3633 | 417.329 | 26724
3634 | 416.7939 | 26724
3635 | 418.2295 | 26724
3636 | 417.6523 | 26724
3637 | 399.3278 | 26724
3638 | 408.5921 | 26724
3639 | 426.1377 | 26724
3640 | 401.5053 | 26724
3641 | 413.0606 | 26724
3642 | 425.7293 | 26724
3643 | 427.2042 | 26724
3644 | 410.7246 | 26724
3645 | 420.3999 | 26724
3646 | 417.1446 | 26724
3647 | 415.4589 | 26724
3648 | 407.2663 | 26724
3649 | 401.7431 | 26724
3650 | 421.5784 | 26724
3651 | 413.4845 | 26724
3652 | 431.1008 | 26724
3653 | 418.718 | 26724
3654 | 409.7217 | 26724
3655 | 414.7952 | 26724
3656 | 414.1949 | 26724
3657 | 422.3341 | 26724
3658 | 424.0004 | 26724
3659 | 417.8729 | 26724
3660 | 403.0973 | 26724
3661 | 427.9027 | 26724
3662 | 411.3586 | 26724
3663 | 414.8885 | 26724
3664 | 417.9479 | 26724
3665 | 416.8104 | 26724
3666 | 417.0853 | 26724
3667 | 421.9302 | 26724
3668 | 410.7996 | 26724
3669 | 415.0472 | 26724
3670 | 409.35 | 26724
3671 | 411.5744 | 26724
3672 | 410.2459 | 26724
3673 | 408.5094 | 26724
3674 | 432.2234 | 26724
3675 | 417.7957 | 26724
3676 | 416.4929 | 26724
3677 | 411.2931 | 26724
3678 | 411.07 | 26724
3679 | 409.7739 | 26724
3680 | 416.5851 | 26724
3681 | 420.1344 | 26724
3682 | 425.1179 | 26724
3683 | 421.1661 | 26724
3684 | 410.8535 | 26724
3685 | 414.628 | 26724
3686 | 426.2735 | 26724
3687 | 415.0781 | 26724
3688 | 404.3598 | 26724
3689 | 405.2848 | 26724
3690 | 421.3006 | 26724
3691 | 420.3062 | 26724
3692 | 418.7563 | 26724
3693 | 410.339 | 26724
3694 | 409.6275 | 26724
3695 | 426.6398 | 26724
3696 | 405.6842 | 26724
3697 | 416.5871 | 26724
3698 | 400.4828 | 26724
3699 | 430.3904 | 26724
3700 | 403.4571 | 26724
3701 | 427.2241 | 26724
3702 | 420.6231 | 26724
3703 | 417.4984 | 26724
3704 | 421.7004 | 26724
3705 | 412.8663 | 26724
3706 | 422.5468 | 26724
3707 | 413.6966 | 26724
3708 | 414.218 | 26724
3709 | 401.4182 | 26724
3710 | 429.5608 | 26724
3711 | 421.7022 | 26724
3712 | 413.8535 | 26724
3713 | 427.4393 | 26724
3714 | 419.6829 | 26724
3715 | 425.2314 | 26724
3716 | 413.0226 | 26724
3717 | 415.4852 | 26724
3718 | 430.39 | 26724
3719 | 412.9896 | 26724
3720 | 412.6359 | 26724
3721 | 423.6508 | 26724
3722 | 422.4724 | 26724
3723 | 421.6515 | 26724
3724 | 426.176 | 26724
3725 | 406.1809 | 26724
3726 | 421.1659 | 26724
3727 | 428.4328 | 26724
3728 | 413.2301 | 26724
3729 | 402.4036 | 26724
3730 | 415.4853 | 26724
3731 | 421.2656 | 26724
3732 | 419.1982 | 26724
3733 | 421.945 | 26724
3734 | 408.1062 | 26724
3735 | 403.1374 | 26724
3736 | 408.133 | 26724
3737 | 415.6548 | 26724
3738 | 420.0838 | 26724
3739 | 413.9041 | 26724
3740 | 419.7407 | 26724
3741 | 412.5056 | 26724
3742 | 406.0105 | 26724
3743 | 411.5843 | 26724
3744 | 411.9608 | 26724
3745 | 425.7168 | 26724
3746 | 429.2742 | 26724
3747 | 419.8261 | 26724
3748 | 428.6058 | 26724
3749 | 416.7277 | 26724
3750 | 413.6309 | 26724
3751 | 410.823 | 26724
3752 | 409.2384 | 26724
3753 | 422.6509 | 26724
3754 | 407.903 | 26724
3755 | 406.1113 | 26724
3756 | 413.9124 | 26724
3757 | 422.4773 | 26724
3758 | 406.7636 | 26724
3759 | 430.0691 | 26724
3760 | 412.7099 | 26724
3761 | 408.9123 | 26724
3762 | 414.1644 | 26724
3763 | 416.1613 | 26724
3764 | 402.1719 | 26724
3765 | 426.8552 | 26724
3766 | 414.1555 | 26724
3767 | 402.7031 | 26724
3768 | 413.4521 | 26724
3769 | 406.6617 | 26724
3770 | 409.7328 | 26724
3771 | 416.5885 | 26724
3772 | 411.9934 | 26724
3773 | 436.8084 | 26724
3774 | 401.3331 | 26724
3775 | 413.8563 | 26724
3776 | 410.8051 | 26724
3777 | 402.5837 | 26724
3778 | 418.0173 | 26724
3779 | 400.0132 | 26724
3780 | 398.0508 | 26724
3781 | 413.1606 | 26724
3782 | 424.5574 | 26724
3783 | 414.396 | 26724
3784 | 423.3989 | 26724
3785 | 410.2911 | 26724
3786 | 407.8743 | 26724
3787 | 416.0216 | 26724
3788 | 401.574 | 26724
3789 | 432.2732 | 26724
3790 | 400.5102 | 26724
3791 | 407.9213 | 26724
3792 | 412.0025 | 26724
3793 | 440.3258 | 26724
3794 | 418.0119 | 26724
3795 | 430.0354 | 26724
3796 | 425.5122 | 26724
3797 | 411.8152 | 26724
3798 | 415.3733 | 26724
3799 | 410.7919 | 26724
3800 | 402.3073 | 26724
3801 | 411.5785 | 26724
3802 | 419.3528 | 26724
3803 | 424.0936 | 26724
3804 | 421.3664 | 26724
3805 | 412.1312 | 26724
3806 | 420.4471 | 26724
3807 | 417.2148 | 26724
3808 | 420.3599 | 26724
3809 | 413.7795 | 26724
3810 | 411.0525 | 26724
3811 | 410.2983 | 26724
3812 | 402.2335 | 26724
3813 | 424.3637 | 26724
3814 | 414.9076 | 26724
3815 | 423.1069 | 26724
3816 | 400.8239 | 26724
3817 | 408.4543 | 26724
3818 | 412.291 | 26724
3819 | 426.2014 | 26724
3820 | 427.9897 | 26724
3821 | 414.7376 | 26724
3822 | 414.4867 | 26724
3823 | 412.5242 | 26724
3824 | 412.3611 | 26724
3825 | 410.9434 | 26724
3826 | 415.7841 | 26724
3827 | 413.8403 | 26724
3828 | 419.8203 | 26724
3829 | 415.1366 | 26724
3830 | 412.7747 | 26724
3831 | 412.0073 | 26724
3832 | 426.2175 | 26724
3833 | 405.3403 | 26724
3834 | 419.6307 | 26724
3835 | 409.524 | 26724
3836 | 419.9991 | 26724
3837 | 435.7038 | 26724
3838 | 407.5335 | 26724
3839 | 413.7613 | 26724
3840 | 416.8101 | 26724
3841 | 420.0082 | 26724
3842 | 419.3058 | 26724
3843 | 413.7392 | 26724
3844 | 415.4445 | 26724
3845 | 425.1197 | 26724
3846 | 407.9431 | 26724
3847 | 415.7649 | 26724
3848 | 422.0902 | 26724
3849 | 423.0513 | 26724
3850 | 424.7052 | 26724
3851 | 435.1119 | 26724
3852 | 418.8697 | 26724
3853 | 411.5512 | 26724
3854 | 411.672 | 26724
3855 | 399.019 | 26724
3856 | 428.8837 | 26724
3857 | 410.519 | 26724
3858 | 427.1057 | 26724
3859 | 423.3342 | 26724
3860 | 409.6883 | 26724
3861 | 411.4132 | 26724
3862 | 424.623 | 26724
3863 | 411.9618 | 26724
3864 | 426.2593 | 26724
3865 | 410.8433 | 26724
3866 | 420.799 | 26724
3867 | 416.8732 | 26724
3868 | 428.8275 | 26724
3869 | 413.3789 | 26724
3870 | 410.6658 | 26724
3871 | 408.2038 | 26724
3872 | 410.1712 | 26724
3873 | 400.6891 | 26724
3874 | 421.4688 | 26724
3875 | 416.4424 | 26724
3876 | 421.4621 | 26724
3877 | 414.6163 | 26724
3878 | 398.451 | 26724
3879 | 416.0812 | 26724
3880 | 412.3079 | 26724
3881 | 400.6969 | 26724
3882 | 410.1714 | 26724
3883 | 413.7951 | 26724
3884 | 418.2897 | 26724
3885 | 415.4067 | 26724
3886 | 409.4938 | 26724
3887 | 411.1961 | 26724
3888 | 420.0973 | 26724
3889 | 402.8462 | 26724
3890 | 412.4408 | 26724
3891 | 406.1516 | 26724
3892 | 411.5639 | 26724
3893 | 413.6768 | 26724
3894 | 403.9774 | 26724
3895 | 402.3637 | 26724
3896 | 410.2727 | 26724
3897 | 414.2034 | 26724
3898 | 426.5065 | 26724
3899 | 403.224 | 26724
3900 | 414.188 | 26724
3901 | 419.6222 | 26724
3902 | 406.6773 | 26724
3903 | 429.4661 | 26724
3904 | 419.9342 | 26724
3905 | 411.7398 | 26724
3906 | 402.9105 | 26724
3907 | 412.4507 | 26724
3908 | 403.948 | 26724
3909 | 415.4792 | 26724
3910 | 426.3157 | 26724
3911 | 403.3288 | 26724
3912 | 418.3738 | 26724
3913 | 418.9935 | 26724
3914 | 424.1905 | 26724
3915 | 416.4009 | 26724
3916 | 435.4877 | 26724
3917 | 414.1452 | 26724
3918 | 416.5937 | 26724
3919 | 422.6653 | 26724
3920 | 409.0354 | 26724
3921 | 417.1527 | 26724
3922 | 416.9573 | 26724
3923 | 418.1917 | 26724
3924 | 424.7545 | 26724
3925 | 411.3575 | 26724
3926 | 432.5658 | 26724
3927 | 415.8733 | 26724
3928 | 418.1324 | 26724
3929 | 411.7195 | 26724
3930 | 415.3619 | 26724
3931 | 405.4373 | 26724
3932 | 416.3189 | 26724
3933 | 413.7707 | 26724
3934 | 414.3286 | 26724
3935 | 413.3693 | 26724
3936 | 408.0227 | 26724
3937 | 398.6571 | 26724
3938 | 420.9261 | 26724
3939 | 419.6695 | 26724
3940 | 402.5467 | 26724
3941 | 417.651 | 26724
3942 | 427.5181 | 26724
3943 | 425.5749 | 26724
3944 | 417.6796 | 26724
3945 | 413.2231 | 26724
3946 | 414.1687 | 26724
3947 | 404.8152 | 26724
3948 | 420.9837 | 26724
3949 | 401.7662 | 26724
3950 | 426.134 | 26724
3951 | 422.3914 | 26724
3952 | 421.9988 | 26724
3953 | 427.0824 | 26724
3954 | 424.507 | 26724
3955 | 419.4742 | 26724
3956 | 402.5818 | 26724
3957 | 422.9387 | 26724
3958 | 423.3733 | 26724
3959 | 429.852 | 26724
3960 | 413.6345 | 26724
3961 | 428.7199 | 26724
3962 | 416.2585 | 26724
3963 | 406.7787 | 26724
3964 | 420.7388 | 26724
3965 | 419.9199 | 26724
3966 | 420.5251 | 26724
3967 | 422.5437 | 26724
3968 | 412.2272 | 26724
3969 | 403.3003 | 26724
3970 | 423.9377 | 26724
3971 | 410.241 | 26724
3972 | 411.2904 | 26724
3973 | 405.0693 | 26724
3974 | 420.9887 | 26724
3975 | 407.8877 | 26724
3976 | 421.0778 | 26724
3977 | 419.8988 | 26724
3978 | 409.4682 | 26724
3979 | 429.7916 | 26724
3980 | 407.5368 | 26724
3981 | 429.1873 | 26724
3982 | 409.0385 | 26724
3983 | 414.4666 | 26724
3984 | 427.3977 | 26724
3985 | 408.1931 | 26724
3986 | 415.8517 | 26724
3987 | 417.1816 | 26724
3988 | 415.4605 | 26724
3989 | 408.8395 | 26724
3990 | 430.8991 | 26724
3991 | 418.5235 | 26724
3992 | 414.1108 | 26724
3993 | 411.7445 | 26724
3994 | 415.2059 | 26724
3995 | 409.5237 | 26724
3996 | 415.8525 | 26724
3997 | 417.537 | 26724
3998 | 438.7648 | 26724
3999 | 400.5605 | 26724
4000 | 417.1659 | 26724
4001 | 411.1584 | 26724
4002 | 418.8376 | 26724
4003 | 410.4483 | 26724
4004 | 419.8467 | 26724
4005 | 400.2595 | 26724
4006 | 425.6423 | 26724
4007 | 416.9329 | 26724
4008 | 403.9453 | 26724
4009 | 404.9443 | 26724
4010 | 413.9446 | 26724
4011 | 416.7439 | 26724
4012 | 417.0939 | 26724
4013 | 415.2681 | 26724
4014 | 414.1723 | 26724
4015 | 412.5981 | 26724
4016 | 420.2096 | 26724
4017 | 415.01 | 26724
4018 | 417.9761 | 26724
4019 | 418.5768 | 26724
4020 | 418.897 | 26724
4021 | 413.0576 | 26724
4022 | 426.3422 | 26724
4023 | 419.8549 | 26724
4024 | 400.0656 | 26724
4025 | 421.4762 | 26724
4026 | 417.0597 | 26724
4027 | 411.7512 | 26724
4028 | 402.7562 | 26724
4029 | 418.8946 | 26724
4030 | 411.75 | 26724
4031 | 412.5252 | 26724
4032 | 409.2962 | 26724
4033 | 422.732 | 26724
4034 | 413.9432 | 26724
4035 | 407.2831 | 26724
4036 | 406.516 | 26724
4037 | 424.2797 | 26724
4038 | 407.656 | 26724
4039 | 422.855 | 26724
4040 | 425.8078 | 26724
4041 | 410.7809 | 26724
4042 | 414.3795 | 26724
4043 | 412.3124 | 26724
4044 | 413.0044 | 26724
4045 | 422.304 | 26724
4046 | 419.7892 | 26724
4047 | 407.3895 | 26724
4048 | 432.5555 | 26724
4049 | 411.288 | 26724
4050 | 414.027 | 26724
4051 | 419.704 | 26724
4052 | 412.3992 | 26724
4053 | 413.6422 | 26724
4054 | 422.0572 | 26724
4055 | 418.2058 | 26724
4056 | 410.2701 | 26724
4057 | 415.8137 | 26724
4058 | 397.1214 | 26724
4059 | 425.1788 | 26724
4060 | 407.3533 | 26724
4061 | 421.3721 | 26724
4062 | 416.4769 | 26724
4063 | 414.1286 | 26724
4064 | 414.3395 | 26724
4065 | 407.6884 | 26724
4066 | 416.7163 | 26724
4067 | 416.3061 | 26724
4068 | 420.2375 | 26724
4069 | 421.596 | 26724
4070 | 412.4604 | 26724
4071 | 419.9097 | 26724
4072 | 419.6579 | 26724
4073 | 399.2987 | 26724
4074 | 432.9146 | 26724
4075 | 419.7443 | 26724
4076 | 418.4365 | 26724
4077 | 417.1549 | 26724
4078 | 411.1358 | 26724
4079 | 410.9345 | 26724
4080 | 408.1873 | 26724
4081 | 404.5511 | 26724
4082 | 421.5287 | 26724
4083 | 411.5832 | 26724
4084 | 416.0824 | 26724
4085 | 421.8047 | 26724
4086 | 425.9282 | 26724
4087 | 412.9679 | 26724
4088 | 431.6726 | 26724
4089 | 408.7731 | 26724
4090 | 432.9852 | 26724
4091 | 426.3389 | 26724
4092 | 425.8784 | 26724
4093 | 423.5813 | 26724
4094 | 407.8014 | 26724
4095 | 425.4074 | 26724
4096 | 427.9698 | 26724
4097 | 419.5465 | 26724
4098 | 422.2848 | 26724
4099 | 418.9055 | 26724
4100 | 411.2078 | 26724
4101 | 417.7866 | 26724
4102 | 416.5765 | 26724
4103 | 416.3287 | 26724
4104 | 406.5768 | 26724
4105 | 436.9055 | 26724
4106 | 411.2564 | 26724
4107 | 409.5379 | 26724
4108 | 410.6627 | 26724
4109 | 433.1098 | 26724
4110 | 413.2549 | 26724
4111 | 433.1958 | 26724
4112 | 405.5414 | 26724
4113 | 418.3842 | 26724
4114 | 418.1156 | 26724
4115 | 418.0534 | 26724
4116 | 422.7081 | 26724
4117 | 412.9845 | 26724
4118 | 418.4005 | 26724
4119 | 414.6931 | 26724
4120 | 419.1987 | 26724
4121 | 414.6663 | 26724
4122 | 416.8803 | 26724
4123 | 397.6844 | 26724
4124 | 412.7001 | 26724
4125 | 419.7271 | 26724
4126 | 418.0004 | 26724
4127 | 395.0557 | 26724
4128 | 400.7991 | 26724
4129 | 428.381 | 26724
4130 | 426.1796 | 26724
4131 | 427.4268 | 26724
4132 | 421.1924 | 26724
4133 | 398.6364 | 26724
4134 | 407.9165 | 26724
4135 | 420.5179 | 26724
4136 | 415.0073 | 26724
4137 | 408.4075 | 26724
4138 | 403.7359 | 26724
4139 | 421.2136 | 26724
4140 | 403.4111 | 26724
4141 | 422.3616 | 26724
4142 | 423.7033 | 26724
4143 | 413.9979 | 26724
4144 | 419.6825 | 26724
4145 | 419.6859 | 26724
4146 | 406.3692 | 26724
4147 | 410.4664 | 26724
4148 | 416.9419 | 26724
4149 | 415.5459 | 26724
4150 | 417.0621 | 26724
4151 | 418.7403 | 26724
4152 | 413.5652 | 26724
4153 | 417.0415 | 26724
4154 | 412.1505 | 26724
4155 | 413.961 | 26724
4156 | 398.2015 | 26724
4157 | 435.7673 | 26724
4158 | 412.5917 | 26724
4159 | 414.1777 | 26724
4160 | 419.4524 | 26724
4161 | 423.6629 | 26724
4162 | 410.3883 | 26724
4163 | 417.7807 | 26724
4164 | 412.941 | 26724
4165 | 418.3685 | 26724
4166 | 418.983 | 26724
4167 | 411.3734 | 26724
4168 | 415.5568 | 26724
4169 | 430.9594 | 26724
4170 | 422.8632 | 26724
4171 | 429.1583 | 26724
4172 | 419.642 | 26724
4173 | 421.4825 | 26724
4174 | 424.3649 | 26724
4175 | 433.4113 | 26724
4176 | 423.9049 | 26724
4177 | 418.2185 | 26724
4178 | 417.0492 | 26724
4179 | 424.6243 | 26724
4180 | 420.8541 | 26724
4181 | 420.5607 | 26724
4182 | 415.5136 | 26724
4183 | 415.1438 | 26724
4184 | 423.5439 | 26724
4185 | 407.752 | 26724
4186 | 414.4504 | 26724
4187 | 414.7746 | 26724
4188 | 421.4871 | 26724
4189 | 410.1767 | 26724
4190 | 422.8911 | 26724
4191 | 430.0875 | 26724
4192 | 417.3716 | 26724
4193 | 421.6305 | 26724
4194 | 405.3508 | 26724
4195 | 420.5323 | 26724
4196 | 423.7001 | 26724
4197 | 420.436 | 26724
4198 | 417.012 | 26724
4199 | 409.1401 | 26724
4200 | 417.1681 | 26724
4201 | 420.212 | 26724
4202 | 416.4922 | 26724
4203 | 410.2502 | 26724
4204 | 409.6671 | 26724
4205 | 409.7259 | 26724
4206 | 410.8046 | 26724
4207 | 423.0511 | 26724
4208 | 410.8458 | 26724
4209 | 412.8862 | 26724
4210 | 411.2535 | 26724
4211 | 418.3022 | 26724
4212 | 400.6838 | 26724
4213 | 411.8356 | 26724
4214 | 428.3558 | 26724
4215 | 429.9745 | 26724
4216 | 418.6624 | 26724
4217 | 415.6962 | 26724
4218 | 424.359 | 26724
4219 | 406.3858 | 26724
4220 | 399.452 | 26724
4221 | 413.7444 | 26724
4222 | 415.6429 | 26724
4223 | 437.6444 | 26724
4224 | 407.4681 | 26724
4225 | 413.5031 | 26724
4226 | 405.1426 | 26724
4227 | 418.3081 | 26724
4228 | 417.2769 | 26724
4229 | 407.4955 | 26724
4230 | 412.047 | 26724
4231 | 409.0651 | 26724
4232 | 401.4615 | 26724
4233 | 413.4523 | 26724
4234 | 424.2517 | 26724
4235 | 411.7661 | 26724
4236 | 419.4264 | 26724
4237 | 422.5239 | 26724
4238 | 400.9972 | 26724
4239 | 403.8117 | 26724
4240 | 431.9787 | 26724
4241 | 415.2964 | 26724
4242 | 416.3983 | 26724
4243 | 422.7404 | 26724
4244 | 424.9509 | 26724
4245 | 415.5341 | 26724
4246 | 419.2413 | 26724
4247 | 420.4143 | 26724
4248 | 414.9809 | 26724
4249 | 408.2567 | 26724
4250 | 410.4191 | 26724
4251 | 420.6962 | 26724
4252 | 430.2844 | 26724
4253 | 431.7959 | 26724
4254 | 414.2392 | 26724
4255 | 412.2162 | 26724
4256 | 412.3515 | 26724
4257 | 412.4454 | 26724
4258 | 414.6538 | 26724
4259 | 420.7623 | 26724
4260 | 425.7591 | 26724
4261 | 415.6199 | 26724
4262 | 411.9547 | 26724
4263 | 426.0418 | 26724
4264 | 419.4346 | 26724
4265 | 410.505 | 26724
4266 | 419.6586 | 26724
4267 | 409.4365 | 26724
4268 | 410.2646 | 26724
4269 | 420.0044 | 26724
4270 | 428.3827 | 26724
4271 | 421.5736 | 26724
4272 | 414.2576 | 26724
4273 | 397.0232 | 26724
4274 | 431.5512 | 26724
4275 | 407.7993 | 26724
4276 | 426.4701 | 26724
4277 | 409.1915 | 26724
4278 | 408.6468 | 26724
4279 | 408.841 | 26724
4280 | 406.5249 | 26724
4281 | 417.0475 | 26724
4282 | 417.5325 | 26724
4283 | 428.4456 | 26724
4284 | 422.7026 | 26724
4285 | 402.3896 | 26724
4286 | 417.7103 | 26724
4287 | 423.901 | 26724
4288 | 413.0324 | 26724
4289 | 401.5174 | 26724
4290 | 405.174 | 26724
4291 | 423.2754 | 26724
4292 | 407.6669 | 26724
4293 | 406.1443 | 26724
4294 | 415.5284 | 26724
4295 | 405.9505 | 26724
4296 | 417.0604 | 26724
4297 | 411.4077 | 26724
4298 | 420.6744 | 26724
4299 | 429.8837 | 26724
4300 | 432.2598 | 26724
4301 | 413.2919 | 26724
4302 | 422.872 | 26724
4303 | 428.5922 | 26724
4304 | 414.7639 | 26724
4305 | 401.9661 | 26724
4306 | 408.427 | 26724
4307 | 414.4627 | 26724
4308 | 421.6122 | 26724
4309 | 411.3951 | 26724
4310 | 399.926 | 26724
4311 | 400.3139 | 26724
4312 | 416.2079 | 26724
4313 | 410.6042 | 26724
4314 | 416.7455 | 26724
4315 | 406.9584 | 26724
4316 | 424.1497 | 26724
4317 | 409.4031 | 26724
4318 | 421.0761 | 26724
4319 | 408.0759 | 26724
4320 | 410.9483 | 26724
4321 | 413.7585 | 26724
4322 | 419.1629 | 26724
4323 | 417.6119 | 26724
4324 | 407.8962 | 26724
4325 | 410.4657 | 26724
4326 | 415.176 | 26724
4327 | 417.3217 | 26724
4328 | 422.1707 | 26724
4329 | 433.1757 | 26724
4330 | 416.4207 | 26724
4331 | 413.7609 | 26724
4332 | 423.8348 | 26724
4333 | 423.6221 | 26724
4334 | 423.3958 | 26724
4335 | 404.3924 | 26724
4336 | 426.0078 | 26724
4337 | 430.5897 | 26724
4338 | 415.9458 | 26724
4339 | 420.9475 | 26724
4340 | 412.4511 | 26724
4341 | 422.9586 | 26724
4342 | 407.155 | 26724
4343 | 427.018 | 26724
4344 | 412.1108 | 26724
4345 | 417.4392 | 26724
4346 | 423.9139 | 26724
4347 | 416.2367 | 26724
4348 | 405.0204 | 26724
4349 | 416.4243 | 26724
4350 | 427.2842 | 26724
4351 | 422.7298 | 26724
4352 | 423.5505 | 26724
4353 | 401.4687 | 26724
4354 | 408.0582 | 26724
4355 | 396.1294 | 26724
4356 | 419.3953 | 26724
4357 | 411.5024 | 26724
4358 | 426.4466 | 26724
4359 | 429.1243 | 26724
4360 | 401.691 | 26724
4361 | 429.1901 | 26724
4362 | 417.9488 | 26724
4363 | 420.3106 | 26724
4364 | 421.72 | 26724
4365 | 422.9681 | 26724
4366 | 414.4093 | 26724
4367 | 414.8809 | 26724
4368 | 406.0548 | 26724
4369 | 428.8427 | 26724
4370 | 415.0096 | 26724
4371 | 412.5971 | 26724
4372 | 415.2553 | 26724
4373 | 416.2918 | 26724
4374 | 417.1245 | 26724
4375 | 414.773 | 26724
4376 | 415.581 | 26724
4377 | 415.5487 | 26724
4378 | 416.9911 | 26724
4379 | 412.9096 | 26724
4380 | 415.8927 | 26724
4381 | 423.6987 | 26724
4382 | 403.7347 | 26724
4383 | 422.0314 | 26724
4384 | 410.0473 | 26724
4385 | 416.6246 | 26724
4386 | 418.3106 | 26724
4387 | 430.7624 | 26724
4388 | 413.8725 | 26724
4389 | 411.0025 | 26724
4390 | 419.5338 | 26724
4391 | 423.9548 | 26724
4392 | 403.05 | 26724
4393 | 406.1317 | 26724
4394 | 417.084 | 26724
4395 | 416.5547 | 26724
4396 | 407.7962 | 26724
4397 | 417.1519 | 26724
4398 | 418.4972 | 26724
4399 | 410.9174 | 26724
4400 | 418.8116 | 26724
4401 | 412.6566 | 26724
4402 | 428.5141 | 26724
4403 | 414.4197 | 26724
4404 | 422.9586 | 26724
4405 | 405.5522 | 26724
4406 | 423.6812 | 26724
4407 | 423.2802 | 26724
4408 | 415.8258 | 26724
4409 | 414.9829 | 26724
4410 | 418.4886 | 26724
4411 | 418.2401 | 26724
4412 | 407.5113 | 26724
4413 | 407.9826 | 26724
4414 | 405.1952 | 26724
4415 | 424.4988 | 26724
4416 | 409.1869 | 26724
4417 | 417.0555 | 26724
4418 | 419.6979 | 26724
4419 | 403.273 | 26724
4420 | 417.226 | 26724
4421 | 418.5023 | 26724
4422 | 417.0061 | 26724
4423 | 409.8802 | 26724
4424 | 423.2096 | 26724
4425 | 417.2126 | 26724
4426 | 408.3176 | 26724
4427 | 416.3625 | 26724
4428 | 419.1791 | 26724
4429 | 414.9023 | 26724
4430 | 416.2638 | 26724
4431 | 416.5334 | 26724
4432 | 421.6204 | 26724
4433 | 411.7243 | 26724
4434 | 419.9975 | 26724
4435 | 412.2033 | 26724
4436 | 408.5467 | 26724
4437 | 421.1402 | 26724
4438 | 408.8619 | 26724
4439 | 409.7364 | 26724
4440 | 419.5147 | 26724
4441 | 422.6616 | 26724
4442 | 421.8502 | 26724
4443 | 413.2317 | 26724
4444 | 414.1927 | 26724
4445 | 415.4637 | 26724
4446 | 420.1911 | 26724
4447 | 415.072 | 26724
4448 | 410.6026 | 26724
4449 | 419.4152 | 26724
4450 | 420.813 | 26724
4451 | 414.6395 | 26724
4452 | 437.7186 | 26724
4453 | 407.7719 | 26724
4454 | 405.2646 | 26724
4455 | 417.038 | 26724
4456 | 412.9669 | 26724
4457 | 407.7477 | 26724
4458 | 425.9735 | 26724
4459 | 420.4571 | 26724
4460 | 422.3975 | 26724
4461 | 427.6623 | 26724
4462 | 421.7924 | 26724
4463 | 412.5863 | 26724
4464 | 415.9042 | 26724
4465 | 413.5515 | 26724
4466 | 426.9374 | 26724
4467 | 415.0397 | 26724
4468 | 413.0459 | 26724
4469 | 425.6435 | 26724
4470 | 414.4448 | 26724
4471 | 416.6999 | 26724
4472 | 407.2461 | 26724
4473 | 417.3903 | 26724
4474 | 410.4065 | 26724
4475 | 413.1149 | 26724
4476 | 408.0462 | 26724
4477 | 416.6442 | 26724
4478 | 416.2998 | 26724
4479 | 406.1073 | 26724
4480 | 407.7064 | 26724
4481 | 420.1709 | 26724
4482 | 400.3048 | 26724
4483 | 421.6424 | 26724
4484 | 405.1682 | 26724
4485 | 410.2062 | 26724
4486 | 419.3638 | 26724
4487 | 422.4329 | 26724
4488 | 427.6179 | 26724
4489 | 403.6972 | 26724
4490 | 432.3708 | 26724
4491 | 409.0863 | 26724
4492 | 416.9861 | 26724
4493 | 417.7339 | 26724
4494 | 420.7858 | 26724
4495 | 414.3974 | 26724
4496 | 393.8913 | 26724
4497 | 429.4201 | 26724
4498 | 420.5275 | 26724
4499 | 420.7636 | 26724
4500 | 416.9773 | 26724
4501 | 404.8699 | 26724
4502 | 408.4534 | 26724
4503 | 416.4252 | 26724
4504 | 416.9129 | 26724
4505 | 408.4309 | 26724
4506 | 400.3413 | 26724
4507 | 406.0877 | 26724
4508 | 429.8082 | 26724
4509 | 417.9008 | 26724
4510 | 424.84 | 26724
4511 | 419.5817 | 26724
4512 | 412.2878 | 26724
4513 | 420.0667 | 26724
4514 | 417.9226 | 26724
4515 | 405.9932 | 26724
4516 | 420.4408 | 26724
4517 | 405.8491 | 26724
4518 | 428.9809 | 26724
4519 | 400.6949 | 26724
4520 | 412.5127 | 26724
4521 | 423.3905 | 26724
4522 | 404.7593 | 26724
4523 | 409.8139 | 26724
4524 | 412.7565 | 26724
4525 | 411.9632 | 26724
4526 | 406.0947 | 26724
4527 | 420.0105 | 26724
4528 | 422.2109 | 26724
4529 | 417.5513 | 26724
4530 | 402.9698 | 26724
4531 | 412.2298 | 26724
4532 | 408.9687 | 26724
4533 | 426.932 | 26724
4534 | 419.5489 | 26724
4535 | 420.6213 | 26724
4536 | 420.6495 | 26724
4537 | 421.2145 | 26724
4538 | 431.1577 | 26724
4539 | 405.8477 | 26724
4540 | 418.1785 | 26724
4541 | 419.2075 | 26724
4542 | 415.0882 | 26724
4543 | 415.9383 | 26724
4544 | 415.0261 | 26724
4545 | 427.6993 | 26724
4546 | 419.3349 | 26724
4547 | 405.6757 | 26724
4548 | 420.0127 | 26724
4549 | 428.3975 | 26724
4550 | 422.6868 | 26724
4551 | 417.4775 | 26724
4552 | 426.8649 | 26724
4553 | 426.1446 | 26724
4554 | 416.859 | 26724
4555 | 415.1087 | 26724
4556 | 425.3366 | 26724
4557 | 405.4679 | 26724
4558 | 424.2443 | 26724
4559 | 425.8069 | 26724
4560 | 406.1086 | 26724
4561 | 402.9678 | 26724
4562 | 420.4858 | 26724
4563 | 418.1749 | 26724
4564 | 399.2858 | 26724
4565 | 411.2634 | 26724
4566 | 420.2022 | 26724
4567 | 420.0217 | 26724
4568 | 415.6639 | 26724
4569 | 409.3768 | 26724
4570 | 416.8039 | 26724
4571 | 408.0867 | 26724
4572 | 421.3733 | 26724
4573 | 411.3037 | 26724
4574 | 414.5005 | 26724
4575 | 411.6478 | 26724
4576 | 417.5151 | 26724
4577 | 419.6304 | 26724
4578 | 411.0101 | 26724
4579 | 425.7364 | 26724
4580 | 414.1934 | 26724
4581 | 416.077 | 26724
4582 | 409.3795 | 26724
4583 | 416.841 | 26724
4584 | 414.3821 | 26724
4585 | 428.7541 | 26724
4586 | 403.8636 | 26724
4587 | 430.4806 | 26724
4588 | 405.5339 | 26724
4589 | 428.7433 | 26724
4590 | 415.3191 | 26724
4591 | 419.4153 | 26724
4592 | 418.9196 | 26724
4593 | 423.3789 | 26724
4594 | 405.0845 | 26724
4595 | 413.4813 | 26724
4596 | 410.3374 | 26724
4597 | 403.2865 | 26724
4598 | 416.0122 | 26724
4599 | 414.5556 | 26724
4600 | 396.7858 | 26724
4601 | 418.8993 | 26724
4602 | 412.3582 | 26724
4603 | 415.2709 | 26724
4604 | 407.902 | 26724
4605 | 405.4748 | 26724
4606 | 418.6092 | 26724
4607 | 406.4534 | 26724
4608 | 414.1556 | 26724
4609 | 407.8342 | 26724
4610 | 428.2381 | 26724
4611 | 404.8092 | 26724
4612 | 412.1671 | 26724
4613 | 411.534 | 26724
4614 | 405.0581 | 26724
4615 | 411.0276 | 26724
4616 | 409.3426 | 26724
4617 | 432.1656 | 26724
4618 | 415.0182 | 26724
4619 | 420.5958 | 26724
4620 | 402.5554 | 26724
4621 | 410.2955 | 26724
4622 | 411.5422 | 26724
4623 | 414.9937 | 26724
4624 | 409.2097 | 26724
4625 | 411.5713 | 26724
4626 | 417.0792 | 26724
4627 | 423.4759 | 26724
4628 | 408.5083 | 26724
4629 | 424.9065 | 26724
4630 | 407.8169 | 26724
4631 | 415.7803 | 26724
4632 | 403.4831 | 26724
4633 | 421.6192 | 26724
4634 | 419.3577 | 26724
4635 | 411.0946 | 26724
4636 | 424.4252 | 26724
4637 | 405.7022 | 26724
4638 | 409.514 | 26724
4639 | 398.0449 | 26724
4640 | 405.5603 | 26724
4641 | 405.0584 | 26724
4642 | 416.1905 | 26724
4643 | 412.0818 | 26724
4644 | 405.856 | 26724
4645 | 409.0504 | 26724
4646 | 418.3738 | 26724
4647 | 424.3815 | 26724
4648 | 412.6789 | 26724
4649 | 423.4799 | 26724
4650 | 402.7782 | 26724
4651 | 415.6079 | 26724
4652 | 417.2178 | 26724
4653 | 408.618 | 26724
4654 | 421.1228 | 26724
4655 | 409.2552 | 26724
4656 | 410.5258 | 26724
4657 | 423.215 | 26724
4658 | 432.9558 | 26724
4659 | 423.5693 | 26724
4660 | 419.5011 | 26724
4661 | 418.0231 | 26724
4662 | 412.289 | 26724
4663 | 430.2482 | 26724
4664 | 428.118 | 26724
4665 | 408.3022 | 26724
4666 | 427.4966 | 26724
4667 | 403.7887 | 26724
4668 | 422.5786 | 26724
4669 | 411.4334 | 26724
4670 | 423.9365 | 26724
4671 | 413.2487 | 26724
4672 | 413.5063 | 26724
4673 | 415.8503 | 26724
4674 | 415.6325 | 26724
4675 | 404.3595 | 26724
4676 | 420.1243 | 26724
4677 | 424.081 | 26724
4678 | 411.8079 | 26724
4679 | 414.4877 | 26724
4680 | 426.8584 | 26724
4681 | 428.6224 | 26724
4682 | 418.99 | 26724
4683 | 421.2089 | 26724
4684 | 411.1021 | 26724
4685 | 410.0679 | 26724
4686 | 406.0317 | 26724
4687 | 422.771 | 26724
4688 | 417.3037 | 26724
4689 | 412.239 | 26724
4690 | 420.8906 | 26724
4691 | 406.8492 | 26724
4692 | 404.7543 | 26724
4693 | 407.6916 | 26724
4694 | 414.9565 | 26724
4695 | 410.7033 | 26724
4696 | 402.7898 | 26724
4697 | 424.9273 | 26724
4698 | 408.9015 | 26724
4699 | 412.4046 | 26724
4700 | 406.2572 | 26724
4701 | 414.1631 | 26724
4702 | 409.245 | 26724
4703 | 418.9873 | 26724
4704 | 417.0639 | 26724
4705 | 425.9128 | 26724
4706 | 416.7913 | 26724
4707 | 417.7015 | 26724
4708 | 406.3847 | 26724
4709 | 416.2824 | 26724
4710 | 412.1459 | 26724
4711 | 420.3853 | 26724
4712 | 422.8306 | 26724
4713 | 420.6032 | 26724
4714 | 415.6565 | 26724
4715 | 412.2134 | 26724
4716 | 427.2067 | 26724
4717 | 409.7193 | 26724
4718 | 413.1673 | 26724
4719 | 413.0829 | 26724
4720 | 431.9173 | 26724
4721 | 415.1209 | 26724
4722 | 418.0889 | 26724
4723 | 401.1713 | 26724
4724 | 426.2267 | 26724
4725 | 411.7863 | 26724
4726 | 415.2817 | 26724
4727 | 418.1073 | 26724
4728 | 410.245 | 26724
4729 | 433.1509 | 26724
4730 | 402.969 | 26724
4731 | 419.7417 | 26724
4732 | 408.4205 | 26724
4733 | 410.6006 | 26724
4734 | 423.238 | 26724
4735 | 424.4437 | 26724
4736 | 406.4774 | 26724
4737 | 404.8692 | 26724
4738 | 418.0058 | 26724
4739 | 408.7815 | 26724
4740 | 409.6377 | 26724
4741 | 400.2907 | 26724
4742 | 404.8263 | 26724
4743 | 415.5074 | 26724
4744 | 411.2601 | 26724
4745 | 433.0492 | 26724
4746 | 417.85 | 26724
4747 | 415.1839 | 26724
4748 | 405.9161 | 26724
4749 | 408.7213 | 26724
4750 | 412.6211 | 26724
4751 | 411.6006 | 26724
4752 | 418.747 | 26724
4753 | 414.476 | 26724
4754 | 428.6564 | 26724
4755 | 416.809 | 26724
4756 | 422.8693 | 26724
4757 | 416.7113 | 26724
4758 | 429.8685 | 26724
4759 | 435.8067 | 26724
4760 | 411.6015 | 26724
4761 | 428.7756 | 26724
4762 | 421.5788 | 26724
4763 | 424.9562 | 26724
4764 | 418.6679 | 26724
4765 | 422.6672 | 26724
4766 | 413.5862 | 26724
4767 | 413.1046 | 26724
4768 | 422.8522 | 26724
4769 | 417.8032 | 26724
4770 | 413.9844 | 26724
4771 | 429.1232 | 26724
4772 | 425.6717 | 26724
4773 | 401.0301 | 26724
4774 | 423.2479 | 26724
4775 | 421.9602 | 26724
4776 | 416.4289 | 26724
4777 | 417.8538 | 26724
4778 | 408.5369 | 26724
4779 | 422.6481 | 26724
4780 | 418.558 | 26724
4781 | 424.8482 | 26724
4782 | 404.3554 | 26724
4783 | 411.527 | 26724
4784 | 413.4308 | 26724
4785 | 421.1289 | 26724
4786 | 427.7991 | 26724
4787 | 416.1957 | 26724
4788 | 430.2982 | 26724
4789 | 417.7015 | 26724
4790 | 408.4653 | 26724
4791 | 425.0434 | 26724
4792 | 423.1633 | 26724
4793 | 418.7573 | 26724
4794 | 411.8016 | 26724
4795 | 419.3961 | 26724
4796 | 418.3785 | 26724
4797 | 410.0211 | 26724
4798 | 415.1012 | 26724
4799 | 414.0298 | 26724
4800 | 425.3614 | 26724
4801 | 414.9233 | 26724
4802 | 420.9965 | 26724
4803 | 432.2006 | 26724
4804 | 425.0647 | 26724
4805 | 427.8273 | 26724
4806 | 418.4724 | 26724
4807 | 408.2755 | 26724
4808 | 412.5399 | 26724
4809 | 412.4463 | 26724
4810 | 414.7485 | 26724
4811 | 404.1696 | 26724
4812 | 415.6993 | 26724
4813 | 419.0525 | 26724
4814 | 406.0862 | 26724
4815 | 406.7757 | 26724
4816 | 423.7047 | 26724
4817 | 417.6361 | 26724
4818 | 402.627 | 26724
4819 | 405.4305 | 26724
4820 | 424.1493 | 26724
4821 | 419.6485 | 26724
4822 | 417.0221 | 26724
4823 | 421.4811 | 26724
4824 | 419.7413 | 26724
4825 | 407.2647 | 26724
4826 | 416.573 | 26724
4827 | 411.7694 | 26724
4828 | 416.0401 | 26724
4829 | 414.1743 | 26724
4830 | 409.019 | 26724
4831 | 409.4653 | 26724
4832 | 412.9139 | 26724
4833 | 421.5174 | 26724
4834 | 416.4258 | 26724
4835 | 407.4363 | 26724
4836 | 405.2344 | 26724
4837 | 419.8826 | 26724
4838 | 404.5068 | 26724
4839 | 422.5093 | 26724
4840 | 427.3736 | 26724
4841 | 419.2246 | 26724
4842 | 413.9763 | 26724
4843 | 423.3283 | 26724
4844 | 408.5667 | 26724
4845 | 400.4978 | 26724
4846 | 419.4703 | 26724
4847 | 399.6971 | 26724
4848 | 417.2781 | 26724
4849 | 409.9802 | 26724
4850 | 414.9125 | 26724
4851 | 407.6327 | 26724
4852 | 415.9788 | 26724
4853 | 409.7254 | 26724
4854 | 394.1866 | 26724
4855 | 427.6651 | 26724
4856 | 420.1832 | 26724
4857 | 420.6002 | 26724
4858 | 424.9869 | 26724
4859 | 423.449 | 26724
4860 | 411.3599 | 26724
4861 | 415.8427 | 26724
4862 | 419.0288 | 26724
4863 | 418.7271 | 26724
4864 | 418.2251 | 26724
4865 | 414.9186 | 26724
4866 | 414.6421 | 26724
4867 | 398.1327 | 26724
4868 | 423.3938 | 26724
4869 | 412.4784 | 26724
4870 | 423.8021 | 26724
4871 | 409.2344 | 26724
4872 | 420.3426 | 26724
4873 | 402.1504 | 26724
4874 | 426.3768 | 26724
4875 | 415.2684 | 26724
4876 | 413.361 | 26724
4877 | 420.4289 | 26724
4878 | 421.2912 | 26724
4879 | 421.9332 | 26724
4880 | 419.0841 | 26724
4881 | 412.423 | 26724
4882 | 407.3865 | 26724
4883 | 421.9207 | 26724
4884 | 418.6955 | 26724
4885 | 401.5355 | 26724
4886 | 406.6747 | 26724
4887 | 415.3507 | 26724
4888 | 409.3111 | 26724
4889 | 401.3779 | 26724
4890 | 408.0937 | 26724
4891 | 424.8357 | 26724
4892 | 404.7285 | 26724
4893 | 413.0946 | 26724
4894 | 406.67 | 26724
4895 | 414.2304 | 26724
4896 | 425.2818 | 26724
4897 | 415.8869 | 26724
4898 | 407.896 | 26724
4899 | 413.9022 | 26724
4900 | 409.4098 | 26724
4901 | 414.7863 | 26724
4902 | 422.8343 | 26724
4903 | 425.9541 | 26724
4904 | 402.987 | 26724
4905 | 421.3847 | 26724
4906 | 425.3986 | 26724
4907 | 415.0739 | 26724
4908 | 434.7147 | 26724
4909 | 407.3651 | 26724
4910 | 413.9732 | 26724
4911 | 413.7876 | 26724
4912 | 422.0194 | 26724
4913 | 416.8602 | 26724
4914 | 416.7346 | 26724
4915 | 403.7677 | 26724
4916 | 408.5992 | 26724
4917 | 402.2276 | 26724
4918 | 403.6068 | 26724
4919 | 413.8934 | 26724
4920 | 429.279 | 26724
4921 | 414.8634 | 26724
4922 | 418.4045 | 26724
4923 | 415.1418 | 26724
4924 | 404.9706 | 26724
4925 | 418.7062 | 26724
4926 | 407.5514 | 26724
4927 | 424.2575 | 26724
4928 | 418.0986 | 26724
4929 | 405.0178 | 26724
4930 | 415.3826 | 26724
4931 | 416.0546 | 26724
4932 | 416.2143 | 26724
4933 | 407.706 | 26724
4934 | 427.7676 | 26724
4935 | 421.9436 | 26724
4936 | 416.2609 | 26724
4937 | 433.5913 | 26724
4938 | 424.1718 | 26724
4939 | 406.1337 | 26724
4940 | 422.1068 | 26724
4941 | 417.1788 | 26724
4942 | 422.5152 | 26724
4943 | 414.4071 | 26724
4944 | 432.7975 | 26724
4945 | 417.3612 | 26724
4946 | 410.1362 | 26724
4947 | 415.0988 | 26724
4948 | 426.0988 | 26724
4949 | 407.0738 | 26724
4950 | 424.7807 | 26724
4951 | 430.6033 | 26724
4952 | 421.0683 | 26724
4953 | 410.2045 | 26724
4954 | 422.9006 | 26724
4955 | 426.4782 | 26724
4956 | 420.2096 | 26724
4957 | 418.2317 | 26724
4958 | 422.6874 | 26724
4959 | 422.2704 | 26724
4960 | 422.0321 | 26724
4961 | 405.7559 | 26724
4962 | 414.0822 | 26724
4963 | 414.0844 | 26724
4964 | 396.4356 | 26724
4965 | 408.476 | 26724
4966 | 421.1021 | 26724
4967 | 401.9901 | 26724
4968 | 416.6262 | 26724
4969 | 419.3478 | 26724
4970 | 418.2042 | 26724
4971 | 407.915 | 26724
4972 | 417.7522 | 26724
4973 | 434.6208 | 26724
4974 | 411.7863 | 26724
4975 | 416.5644 | 26724
4976 | 413.0153 | 26724
4977 | 411.6443 | 26724
4978 | 423.6737 | 26724
4979 | 419.3846 | 26724
4980 | 426.6897 | 26724
4981 | 403.47 | 26724
4982 | 407.8371 | 26724
4983 | 418.6482 | 26724
4984 | 414.3593 | 26724
4985 | 415.2563 | 26724
4986 | 422.6716 | 26724
4987 | 410.0758 | 26724
4988 | 416.3956 | 26724
4989 | 410.274 | 26724
4990 | 432.1552 | 26724
4991 | 420.572 | 26724
4992 | 401.2047 | 26724
4993 | 420.9919 | 26724
4994 | 419.409 | 26724
4995 | 411.9167 | 26724
4996 | 431.9417 | 26724
4997 | 427.0054 | 26724
4998 | 413.8497 | 26724
4999 | 401.9872 | 26724
5000 | 412.8748 | 26724
5001 | 421.7506 | 26724
5002 | 408.9545 | 26724
5003 | 409.6599 | 26724
5004 | 420.3691 | 26724
5005 | 411.2272 | 26724
5006 | 420.1008 | 26724
5007 | 420.9015 | 26724
5008 | 410.6878 | 26724
5009 | 409.0884 | 26724
5010 | 416.5015 | 26724
5011 | 423.3348 | 26724
5012 | 426.5767 | 26724
5013 | 413.2945 | 26724
5014 | 425.8397 | 26724
5015 | 421.291 | 26724
5016 | 409.1225 | 26724
5017 | 410.4041 | 26724
5018 | 412.7571 | 26724
5019 | 424.026 | 26724
5020 | 418.5497 | 26724
5021 | 428.4225 | 26724
5022 | 408.4753 | 26724
5023 | 421.9942 | 26724
5024 | 424.5746 | 26724
5025 | 406.9381 | 26724
5026 | 400.2387 | 26724
5027 | 419.856 | 26724
5028 | 417.8483 | 26724
5029 | 414.0326 | 26724
5030 | 404.6285 | 26724
5031 | 408.3983 | 26724
5032 | 411.8168 | 26724
5033 | 414.6504 | 26724
5034 | 407.5059 | 26724
5035 | 413.4624 | 26724
5036 | 428.0043 | 26724
5037 | 426.8452 | 26724
5038 | 416.6852 | 26724
5039 | 406.8361 | 26724
5040 | 410.9883 | 26724
5041 | 420.6426 | 26724
5042 | 413.2135 | 26724
5043 | 428.9508 | 26724
5044 | 417.9586 | 26724
5045 | 428.5622 | 26724
5046 | 432.1516 | 26724
5047 | 410.411 | 26724
5048 | 427.1048 | 26724
5049 | 420.2925 | 26724
5050 | 429.1142 | 26724
5051 | 415.0906 | 26724
5052 | 414.2113 | 26724
5053 | 406.7359 | 26724
5054 | 411.2532 | 26724
5055 | 418.0887 | 26724
5056 | 412.7829 | 26724
5057 | 406.8332 | 26724
5058 | 418.6066 | 26724
5059 | 413.0024 | 26724
5060 | 414.0098 | 26724
5061 | 402.94 | 26724
5062 | 426.9354 | 26724
5063 | 408.8596 | 26724
5064 | 415.0956 | 26724
5065 | 424.6829 | 26724
5066 | 404.0702 | 26724
5067 | 417.0294 | 26724
5068 | 405.2811 | 26724
5069 | 404.1477 | 26724
5070 | 410.6663 | 26724
5071 | 418.2991 | 26724
5072 | 411.8439 | 26724
5073 | 404.3911 | 26724
5074 | 401.6349 | 26724
5075 | 417.6992 | 26724
5076 | 402.4097 | 26724
5077 | 418.3637 | 26724
5078 | 407.2779 | 26724
5079 | 410.0447 | 26724
5080 | 412.974 | 26724
5081 | 420.0786 | 26724
5082 | 427.0506 | 26724
5083 | 404.7157 | 26724
5084 | 402.9889 | 26724
5085 | 429.9093 | 26724
5086 | 438.461 | 26724
5087 | 425.5472 | 26724
5088 | 413.0618 | 26724
5089 | 406.9142 | 26724
5090 | 412.6881 | 26724
5091 | 425.0171 | 26724
5092 | 426.7243 | 26724
5093 | 417.011 | 26724
5094 | 433.2139 | 26724
5095 | 414.8769 | 26724
5096 | 415.9572 | 26724
5097 | 404.5717 | 26724
5098 | 420.4526 | 26724
5099 | 397.5535 | 26724
5100 | 417.214 | 26724
5101 | 415.5983 | 26724
5102 | 414.3952 | 26724
5103 | 408.3564 | 26724
5104 | 415.6854 | 26724
5105 | 426.8295 | 26724
5106 | 413.4766 | 26724
5107 | 419.9242 | 26724
5108 | 409.5405 | 26724
5109 | 412.4669 | 26724
5110 | 429.3376 | 26724
5111 | 424.3773 | 26724
5112 | 419.9173 | 26724
5113 | 417.7404 | 26724
5114 | 415.3174 | 26724
5115 | 402.9579 | 26724
5116 | 425.0994 | 26724
5117 | 403.7012 | 26724
5118 | 411.4913 | 26724
5119 | 421.0951 | 26724
5120 | 412.4016 | 26724
5121 | 406.7333 | 26724
5122 | 420.979 | 26724
5123 | 411.5229 | 26724
5124 | 411.6761 | 26724
5125 | 420.084 | 26724
5126 | 409.4995 | 26724
5127 | 427.0684 | 26724
5128 | 416.8739 | 26724
5129 | 419.2389 | 26724
5130 | 410.2451 | 26724
5131 | 425.5092 | 26724
5132 | 403.8565 | 26724
5133 | 417.9041 | 26724
5134 | 424.3205 | 26724
5135 | 417.5058 | 26724
5136 | 408.4275 | 26724
5137 | 407.3116 | 26724
5138 | 417.5272 | 26724
5139 | 409.4646 | 26724
5140 | 409.4195 | 26724
5141 | 418.7082 | 26724
5142 | 405.67 | 26724
5143 | 406.2615 | 26724
5144 | 418.6182 | 26724
5145 | 418.6045 | 26724
5146 | 415.8544 | 26724
5147 | 408.9972 | 26724
5148 | 403.5098 | 26724
5149 | 425.5734 | 26724
5150 | 413.224 | 26724
5151 | 427.1991 | 26724
5152 | 407.9458 | 26724
5153 | 427.0853 | 26724
5154 | 408.4487 | 26724
5155 | 411.5914 | 26724
5156 | 417.4687 | 26724
5157 | 418.1953 | 26724
5158 | 405.4833 | 26724
5159 | 423.1212 | 26724
5160 | 408.6494 | 26724
5161 | 419.036 | 26724
5162 | 426.7413 | 26724
5163 | 413.9971 | 26724
5164 | 415.0761 | 26724
5165 | 414.9074 | 26724
5166 | 400.8163 | 26724
5167 | 411.9707 | 26724
5168 | 403.1511 | 26724
5169 | 416.8065 | 26724
5170 | 412.939 | 26724
5171 | 420.024 | 26724
5172 | 417.0527 | 26724
5173 | 429.0352 | 26724
5174 | 416.6136 | 26724
5175 | 410.1051 | 26724
5176 | 428.7732 | 26724
5177 | 420.2322 | 26724
5178 | 413.5203 | 26724
5179 | 411.8091 | 26724
5180 | 411.6222 | 26724
5181 | 417.2425 | 26724
5182 | 411.6373 | 26724
5183 | 423.8615 | 26724
5184 | 410.8798 | 26724
5185 | 425.075 | 26724
5186 | 416.8569 | 26724
5187 | 414.03 | 26724
5188 | 406.5826 | 26724
5189 | 423.9552 | 26724
5190 | 411.4794 | 26724
5191 | 412.6881 | 26724
5192 | 420.2882 | 26724
5193 | 415.2932 | 26724
5194 | 411.8395 | 26724
5195 | 420.2062 | 26724
5196 | 413.1788 | 26724
5197 | 410.1417 | 26724
5198 | 424.0371 | 26724
5199 | 416.0734 | 26724
5200 | 425.7474 | 26724
5201 | 406.6577 | 26724
5202 | 410.5622 | 26724
5203 | 421.3025 | 26724
5204 | 406.8686 | 26724
5205 | 405.5909 | 26724
5206 | 423.4182 | 26724
5207 | 411.0228 | 26724
5208 | 417.5421 | 26724
5209 | 410.0012 | 26724
5210 | 424.3661 | 26724
5211 | 414.1384 | 26724
5212 | 429.6251 | 26724
5213 | 421.4241 | 26724
5214 | 421.9976 | 26724
5215 | 420.1706 | 26724
5216 | 425.3673 | 26724
5217 | 428.3318 | 26724
5218 | 423.8346 | 26724
5219 | 414.3631 | 26724
5220 | 433.7553 | 26724
5221 | 420.043 | 26724
5222 | 408.8989 | 26724
5223 | 405.1462 | 26724
5224 | 418.9588 | 26724
5225 | 414.2684 | 26724
5226 | 397.8803 | 26724
5227 | 416.4938 | 26724
5228 | 410.7874 | 26724
5229 | 419.5889 | 26724
5230 | 414.5797 | 26724
5231 | 411.091 | 26724
5232 | 408.9294 | 26724
5233 | 413.5735 | 26724
5234 | 409.4899 | 26724
5235 | 406.0103 | 26724
5236 | 411.3563 | 26724
5237 | 410.3828 | 26724
5238 | 430.3528 | 26724
5239 | 417.2886 | 26724
5240 | 419.4392 | 26724
5241 | 418.6633 | 26724
5242 | 427.4065 | 26724
5243 | 421.4736 | 26724
5244 | 420.7422 | 26724
5245 | 420.8299 | 26724
5246 | 418.2008 | 26724
5247 | 420.4588 | 26724
5248 | 421.3033 | 26724
5249 | 418.5716 | 26724
5250 | 420.7038 | 26724
5251 | 434.8299 | 26724
5252 | 423.6092 | 26724
5253 | 418.2287 | 26724
5254 | 419.8462 | 26724
5255 | 427.265 | 26724
5256 | 422.3448 | 26724
5257 | 410.7958 | 26724
5258 | 411.4299 | 26724
5259 | 437.1397 | 26724
5260 | 403.2577 | 26724
5261 | 423.1173 | 26724
5262 | 419.8532 | 26724
5263 | 412.8932 | 26724
5264 | 404.8045 | 26724
5265 | 411.7949 | 26724
5266 | 424.0997 | 26724
5267 | 403.3184 | 26724
5268 | 418.7763 | 26724
5269 | 406.1729 | 26724
5270 | 411.6253 | 26724
5271 | 426.0643 | 26724
5272 | 424.9451 | 26724
5273 | 421.2737 | 26724
5274 | 410.8053 | 26724
5275 | 398.0294 | 26724
5276 | 410.711 | 26724
5277 | 407.8688 | 26724
5278 | 433.191 | 26724
5279 | 406.8108 | 26724
5280 | 427.0574 | 26724
5281 | 425.1239 | 26724
5282 | 411.8467 | 26724
5283 | 401.0918 | 26724
5284 | 405.6974 | 26724
5285 | 408.413 | 26724
5286 | 425.6789 | 26724
5287 | 424.5482 | 26724
5288 | 412.2358 | 26724
5289 | 414.6689 | 26724
5290 | 401.4911 | 26724
5291 | 405.896 | 26724
5292 | 413.2562 | 26724
5293 | 416.3672 | 26724
5294 | 413.3474 | 26724
5295 | 412.8599 | 26724
5296 | 409.6989 | 26724
5297 | 409.6002 | 26724
5298 | 416.9666 | 26724
5299 | 421.2919 | 26724
5300 | 431.3263 | 26724
5301 | 428.4899 | 26724
5302 | 414.6111 | 26724
5303 | 405.6413 | 26724
5304 | 423.0732 | 26724
5305 | 414.1716 | 26724
5306 | 401.6453 | 26724
5307 | 411.8947 | 26724
5308 | 424.9343 | 26724
5309 | 411.545 | 26724
5310 | 406.9878 | 26724
5311 | 414.9504 | 26724
5312 | 424.4674 | 26724
5313 | 433.4802 | 26724
5314 | 419.7715 | 26724
5315 | 423.8938 | 26724
5316 | 418.5909 | 26724
5317 | 413.9057 | 26724
5318 | 435.6032 | 26724
5319 | 407.4314 | 26724
5320 | 425.9977 | 26724
5321 | 400.867 | 26724
5322 | 415.1628 | 26724
5323 | 405.7398 | 26724
5324 | 424.6813 | 26724
5325 | 408.6879 | 26724
5326 | 430.1457 | 26724
5327 | 417.0129 | 26724
5328 | 408.8537 | 26724
5329 | 418.5731 | 26724
5330 | 420.6542 | 26724
5331 | 423.039 | 26724
5332 | 408.1413 | 26724
5333 | 414.9196 | 26724
5334 | 415.782 | 26724
5335 | 404.8157 | 26724
5336 | 419.6817 | 26724
5337 | 418.747 | 26724
5338 | 420.2972 | 26724
5339 | 409.283 | 26724
5340 | 410.9907 | 26724
5341 | 419.816 | 26724
5342 | 424.6764 | 26724
5343 | 412.267 | 26724
5344 | 402.699 | 26724
5345 | 415.4608 | 26724
5346 | 413.0807 | 26724
5347 | 409.6009 | 26724
5348 | 423.0189 | 26724
5349 | 415.7996 | 26724
5350 | 410.9565 | 26724
5351 | 407.2163 | 26724
5352 | 424.9397 | 26724
5353 | 409.4799 | 26724
5354 | 408.2048 | 26724
5355 | 407.6007 | 26724
5356 | 414.3461 | 26724
5357 | 433.2145 | 26724
5358 | 405.7975 | 26724
5359 | 403.5591 | 26724
5360 | 405.8857 | 26724
5361 | 430.6786 | 26724
5362 | 427.0431 | 26724
5363 | 416.0153 | 26724
5364 | 407.5198 | 26724
5365 | 418.4757 | 26724
5366 | 423.2583 | 26724
5367 | 419.4042 | 26724
5368 | 421.3539 | 26724
5369 | 416.8962 | 26724
5370 | 401.2365 | 26724
5371 | 415.0028 | 26724
5372 | 413.8137 | 26724
5373 | 425.7315 | 26724
5374 | 414.2654 | 26724
5375 | 422.4748 | 26724
5376 | 419.894 | 26724
5377 | 393.172 | 26724
5378 | 425.3956 | 26724
5379 | 419.986 | 26724
5380 | 414.938 | 26724
5381 | 420.0617 | 26724
5382 | 425.1986 | 26724
5383 | 406.3305 | 26724
5384 | 414.5562 | 26724
5385 | 417.505 | 26724
5386 | 408.484 | 26724
5387 | 424.4995 | 26724
5388 | 421.1293 | 26724
5389 | 420.7513 | 26724
5390 | 407.9947 | 26724
5391 | 418.7464 | 26724
5392 | 423.6797 | 26724
5393 | 405.5325 | 26724
5394 | 416.9922 | 26724
5395 | 401.0674 | 26724
5396 | 417.0201 | 26724
5397 | 406.6425 | 26724
5398 | 415.1338 | 26724
5399 | 409.8669 | 26724
5400 | 429.8741 | 26724
5401 | 418.7435 | 26724
5402 | 409.3872 | 26724
5403 | 421.9437 | 26724
5404 | 411.6464 | 26724
5405 | 413.9341 | 26724
5406 | 405.9519 | 26724
5407 | 420.9325 | 26724
5408 | 420.7736 | 26724
5409 | 432.5419 | 26724
5410 | 419.5317 | 26724
5411 | 423.4698 | 26724
5412 | 415.5346 | 26724
5413 | 407.3739 | 26724
5414 | 421.969 | 26724
5415 | 419.3462 | 26724
5416 | 424.7063 | 26724
5417 | 413.5819 | 26724
5418 | 410.6505 | 26724
5419 | 410.7078 | 26724
5420 | 412.22 | 26724
5421 | 420.4818 | 26724
5422 | 419.2179 | 26724
5423 | 414.0827 | 26724
5424 | 408.4314 | 26724
5425 | 420.1715 | 26724
5426 | 425.0339 | 26724
5427 | 425.299 | 26724
5428 | 415.0194 | 26724
5429 | 409.9626 | 26724
5430 | 415.8178 | 26724
5431 | 411.3096 | 26724
5432 | 420.2864 | 26724
5433 | 418.1444 | 26724
5434 | 413.5508 | 26724
5435 | 409.0479 | 26724
5436 | 412.4454 | 26724
5437 | 411.3083 | 26724
5438 | 421.0478 | 26724
5439 | 427.7426 | 26724
5440 | 413.2699 | 26724
5441 | 422.3486 | 26724
5442 | 415.7894 | 26724
5443 | 426.8186 | 26724
5444 | 417.8439 | 26724
5445 | 405.9225 | 26724
5446 | 415.0429 | 26724
5447 | 412.9851 | 26724
5448 | 424.3926 | 26724
5449 | 416.6683 | 26724
5450 | 422.6225 | 26724
5451 | 430.2653 | 26724
5452 | 421.3026 | 26724
5453 | 407.4244 | 26724
5454 | 414.0287 | 26724
5455 | 422.5533 | 26724
5456 | 398.7372 | 26724
5457 | 430.0523 | 26724
5458 | 407.0972 | 26724
5459 | 413.9972 | 26724
5460 | 417.9981 | 26724
5461 | 426.5033 | 26724
5462 | 431.7019 | 26724
5463 | 416.8017 | 26724
5464 | 415.7688 | 26724
5465 | 409.8743 | 26724
5466 | 411.7159 | 26724
5467 | 431.1474 | 26724
5468 | 404.198 | 26724
5469 | 426.7174 | 26724
5470 | 416.1046 | 26724
5471 | 414.5369 | 26724
5472 | 414.0766 | 26724
5473 | 411.0931 | 26724
5474 | 413.5091 | 26724
5475 | 410.6981 | 26724
5476 | 415.1999 | 26724
5477 | 423.8093 | 26724
5478 | 417.4351 | 26724
5479 | 426.818 | 26724
5480 | 421.0007 | 26724
5481 | 414.4916 | 26724
5482 | 423.3313 | 26724
5483 | 400.8098 | 26724
5484 | 404.221 | 26724
5485 | 421.0563 | 26724
5486 | 415.9249 | 26724
5487 | 405.592 | 26724
5488 | 420.4155 | 26724
5489 | 418.287 | 26724
5490 | 417.2801 | 26724
5491 | 415.9033 | 26724
5492 | 415.0918 | 26724
5493 | 405.2931 | 26724
5494 | 414.8947 | 26724
5495 | 422.3989 | 26724
5496 | 403.3418 | 26724
5497 | 419.3476 | 26724
5498 | 423.891 | 26724
5499 | 420.4455 | 26724
5500 | 424.7805 | 26724
5501 | 405.2713 | 26724
5502 | 431.2225 | 26724
5503 | 409.7361 | 26724
5504 | 420.0933 | 26724
5505 | 427.1033 | 26724
5506 | 412.2743 | 26724
5507 | 419.6864 | 26724
5508 | 422.2886 | 26724
5509 | 423.2267 | 26724
5510 | 421.0092 | 26724
5511 | 414.3871 | 26724
5512 | 428.7161 | 26724
5513 | 432.4977 | 26724
5514 | 437.3941 | 26724
5515 | 402.5784 | 26724
5516 | 418.8225 | 26724
5517 | 412.1217 | 26724
5518 | 410.3129 | 26724
5519 | 419.6927 | 26724
5520 | 412.4419 | 26724
5521 | 421.0422 | 26724
5522 | 415.0494 | 26724
5523 | 421.9028 | 26724
5524 | 407.9387 | 26724
5525 | 413.132 | 26724
5526 | 422.9174 | 26724
5527 | 416.9705 | 26724
5528 | 419.8171 | 26724
5529 | 405.9869 | 26724
5530 | 421.235 | 26724
5531 | 410.1338 | 26724
5532 | 419.2866 | 26724
5533 | 424.7002 | 26724
5534 | 416.2813 | 26724
5535 | 407.6072 | 26724
5536 | 429.7471 | 26724
5537 | 403.2095 | 26724
5538 | 411.2708 | 26724
5539 | 420.2316 | 26724
5540 | 428.3867 | 26724
5541 | 416.0331 | 26724
5542 | 413.9099 | 26724
5543 | 417.0491 | 26724
5544 | 427.8261 | 26724
5545 | 428.5769 | 26724
5546 | 417.2698 | 26724
5547 | 429.2923 | 26724
5548 | 418.3523 | 26724
5549 | 418.4107 | 26724
5550 | 401.7166 | 26724
5551 | 417.6735 | 26724
5552 | 415.4523 | 26724
5553 | 414.1904 | 26724
5554 | 411.6722 | 26724
5555 | 421.1889 | 26724
5556 | 418.865 | 26724
5557 | 404.9835 | 26724
5558 | 407.4982 | 26724
5559 | 416.5261 | 26724
5560 | 411.6833 | 26724
5561 | 421.6014 | 26724
5562 | 421.9112 | 26724
5563 | 410.8369 | 26724
5564 | 417.4841 | 26724
5565 | 410.3459 | 26724
5566 | 431.4577 | 26724
5567 | 419.9737 | 26724
5568 | 414.9505 | 26724
5569 | 423.22 | 26724
5570 | 423.4265 | 26724
5571 | 406.1685 | 26724
5572 | 412.4924 | 26724
5573 | 429.2254 | 26724
5574 | 408.8642 | 26724
5575 | 420.8792 | 26724
5576 | 411.4638 | 26724
5577 | 420.2636 | 26724
5578 | 426.68 | 26724
5579 | 424.6859 | 26724
5580 | 423.8644 | 26724
5581 | 396.4174 | 26724
5582 | 427.2853 | 26724
5583 | 414.9317 | 26724
5584 | 413.5767 | 26724
5585 | 416.2574 | 26724
5586 | 403.8506 | 26724
5587 | 411.6885 | 26724
5588 | 431.8076 | 26724
5589 | 416.8501 | 26724
5590 | 411.1079 | 26724
5591 | 424.7189 | 26724
5592 | 420.3936 | 26724
5593 | 413.5561 | 26724
5594 | 411.88 | 26724
5595 | 415.5217 | 26724
5596 | 405.3871 | 26724
5597 | 417.8152 | 26724
5598 | 405.9629 | 26724
5599 | 424.236 | 26724
5600 | 419.417 | 26724
5601 | 418.2322 | 26724
5602 | 411.6414 | 26724
5603 | 428.1091 | 26724
5604 | 421.7395 | 26724
5605 | 423.7677 | 26724
5606 | 408.4741 | 26724
5607 | 424.8755 | 26724
5608 | 410.3965 | 26724
5609 | 423.8345 | 26724
5610 | 423.092 | 26724
5611 | 412.8282 | 26724
5612 | 421.3207 | 26724
5613 | 428.0961 | 26724
5614 | 426.6235 | 26724
5615 | 413.5564 | 26724
5616 | 412.4599 | 26724
5617 | 407.2434 | 26724
5618 | 413.518 | 26724
5619 | 405.6985 | 26724
5620 | 405.4446 | 26724
5621 | 422.9205 | 26724
5622 | 416.6942 | 26724
5623 | 406.5723 | 26724
5624 | 419.6188 | 26724
5625 | 420.105 | 26724
5626 | 422.3786 | 26724
5627 | 402.7901 | 26724
5628 | 423.5519 | 26724
5629 | 432.1826 | 26724
5630 | 414.1547 | 26724
5631 | 416.6656 | 26724
5632 | 415.0066 | 26724
5633 | 421.2386 | 26724
5634 | 404.8003 | 26724
5635 | 402.9832 | 26724
5636 | 411.4765 | 26724
5637 | 416.6358 | 26724
5638 | 426.7526 | 26724
5639 | 409.6193 | 26724
5640 | 416.3296 | 26724
5641 | 430.6871 | 26724
5642 | 422.7884 | 26724
5643 | 426.4085 | 26724
5644 | 415.638 | 26724
5645 | 417.9513 | 26724
5646 | 399.7999 | 26724
5647 | 427.4251 | 26724
5648 | 412.8411 | 26724
5649 | 423.3085 | 26724
5650 | 407.3813 | 26724
5651 | 427.2629 | 26724
5652 | 407.8321 | 26724
5653 | 420.0272 | 26724
5654 | 421.3124 | 26724
5655 | 417.3647 | 26724
5656 | 426.6374 | 26724
5657 | 425.4186 | 26724
5658 | 405.5656 | 26724
5659 | 418.6456 | 26724
5660 | 418.919 | 26724
5661 | 417.9343 | 26724
5662 | 419.806 | 26724
5663 | 423.8671 | 26724
5664 | 414.462 | 26724
5665 | 413.4596 | 26724
5666 | 400.1072 | 26724
5667 | 424.6742 | 26724
5668 | 420.9665 | 26724
5669 | 413.5654 | 26724
5670 | 412.8636 | 26724
5671 | 416.563 | 26724
5672 | 411.3819 | 26724
5673 | 423.9586 | 26724
5674 | 417.0875 | 26724
5675 | 407.3185 | 26724
5676 | 419.5104 | 26724
5677 | 420.7011 | 26724
5678 | 407.8617 | 26724
5679 | 424.2894 | 26724
5680 | 411.7108 | 26724
5681 | 417.7733 | 26724
5682 | 418.0624 | 26724
5683 | 417.6452 | 26724
5684 | 411.6288 | 26724
5685 | 423.8406 | 26724
5686 | 426.0831 | 26724
5687 | 416.9461 | 26724
5688 | 418.6059 | 26724
5689 | 415.3403 | 26724
5690 | 421.5608 | 26724
5691 | 424.3019 | 26724
5692 | 417.859 | 26724
5693 | 413.7185 | 26724
5694 | 413.9851 | 26724
5695 | 424.8508 | 26724
5696 | 426.6844 | 26724
5697 | 434.925 | 26724
5698 | 412.343 | 26724
5699 | 426.1032 | 26724
5700 | 411.4868 | 26724
5701 | 423.8381 | 26724
5702 | 421.0199 | 26724
5703 | 421.5999 | 26724
5704 | 432.9226 | 26724
5705 | 420.0709 | 26724
5706 | 422.8337 | 26724
5707 | 425.1005 | 26724
5708 | 421.6925 | 26724
5709 | 417.2759 | 26724
5710 | 410.0657 | 26724
5711 | 417.5077 | 26724
5712 | 415.152 | 26724
5713 | 405.9883 | 26724
5714 | 416.6002 | 26724
5715 | 430.2115 | 26724
5716 | 406.6129 | 26724
5717 | 408.2118 | 26724
5718 | 423.607 | 26724
5719 | 408.9048 | 26724
5720 | 414.5714 | 26724
5721 | 413.36 | 26724
5722 | 415.8397 | 26724
5723 | 427.1946 | 26724
5724 | 412.5386 | 26724
5725 | 408.5172 | 26724
5726 | 422.4949 | 26724
5727 | 425.2027 | 26724
5728 | 422.306 | 26724
5729 | 431.4064 | 26724
5730 | 415.455 | 26724
5731 | 424.0679 | 26724
5732 | 417.417 | 26724
5733 | 423.2072 | 26724
5734 | 418.4531 | 26724
5735 | 414.3827 | 26724
5736 | 412.4864 | 26724
5737 | 417.7281 | 26724
5738 | 426.9166 | 26724
5739 | 412.2298 | 26724
5740 | 422.5614 | 26724
5741 | 420.3009 | 26724
5742 | 416.1827 | 26724
5743 | 426.9156 | 26724
5744 | 398.3058 | 26724
5745 | 411.4269 | 26724
5746 | 401.9026 | 26724
5747 | 418.0261 | 26724
5748 | 404.9252 | 26724
5749 | 411.8462 | 26724
5750 | 414.2871 | 26724
5751 | 418.7228 | 26724
5752 | 404.5325 | 26724
5753 | 416.0616 | 26724
5754 | 417.1592 | 26724
5755 | 416.1884 | 26724
5756 | 431.0026 | 26724
5757 | 407.5823 | 26724
5758 | 425.7473 | 26724
5759 | 411.3125 | 26724
5760 | 413.5573 | 26724
5761 | 420.0425 | 26724
5762 | 420.434 | 26724
5763 | 414.506 | 26724
5764 | 422.9245 | 26724
5765 | 411.6018 | 26724
5766 | 411.3365 | 26724
5767 | 409.6515 | 26724
5768 | 416.7212 | 26724
5769 | 423.0333 | 26724
5770 | 413.0747 | 26724
5771 | 413.5071 | 26724
5772 | 416.1316 | 26724
5773 | 420.9962 | 26724
5774 | 424.3676 | 26724
5775 | 418.5135 | 26724
5776 | 421.3382 | 26724
5777 | 414.7706 | 26724
5778 | 411.5555 | 26724
5779 | 414.083 | 26724
5780 | 403.6674 | 26724
5781 | 409.942 | 26724
5782 | 401.6553 | 26724
5783 | 419.1261 | 26724
5784 | 403.4915 | 26724
5785 | 415.5374 | 26724
5786 | 415.4183 | 26724
5787 | 411.8441 | 26724
5788 | 410.7533 | 26724
5789 | 420.0855 | 26724
5790 | 427.8382 | 26724
5791 | 408.8139 | 26724
5792 | 431.4187 | 26724
5793 | 396.8782 | 26724
5794 | 403.5852 | 26724
5795 | 414.592 | 26724
5796 | 412.7608 | 26724
5797 | 412.7025 | 26724
5798 | 421.3485 | 26724
5799 | 395.5449 | 26724
5800 | 412.755 | 26724
5801 | 415.4278 | 26724
5802 | 422.4098 | 26724
5803 | 430.6345 | 26724
5804 | 416.8412 | 26724
5805 | 405.9378 | 26724
5806 | 416.8147 | 26724
5807 | 404.2236 | 26724
5808 | 417.5 | 26724
5809 | 413.9723 | 26724
5810 | 413.8324 | 26724
5811 | 418.1556 | 26724
5812 | 423.7963 | 26724
5813 | 426.9794 | 26724
5814 | 408.8271 | 26724
5815 | 424.574 | 26724
5816 | 417.264 | 26724
5817 | 424.3974 | 26724
5818 | 407.7556 | 26724
5819 | 408.8023 | 26724
5820 | 412.181 | 26724
5821 | 413.7632 | 26724
5822 | 401.8844 | 26724
5823 | 417.2583 | 26724
5824 | 400.6813 | 26724
5825 | 424.224 | 26724
5826 | 419.0328 | 26724
5827 | 421.2604 | 26724
5828 | 423.3452 | 26724
5829 | 411.2181 | 26724
5830 | 411.576 | 26724
5831 | 412.6623 | 26724
5832 | 417.5258 | 26724
5833 | 428.3449 | 26724
5834 | 401.8821 | 26724
5835 | 422.8358 | 26724
5836 | 419.6571 | 26724
5837 | 417.796 | 26724
5838 | 409.1413 | 26724
5839 | 412.2279 | 26724
5840 | 404.7236 | 26724
5841 | 418.1753 | 26724
5842 | 429.4321 | 26724
5843 | 417.1881 | 26724
5844 | 417.0826 | 26724
5845 | 415.3979 | 26724
5846 | 422.3437 | 26724
5847 | 403.303 | 26724
5848 | 415.5714 | 26724
5849 | 425.6619 | 26724
5850 | 411.3032 | 26724
5851 | 411.1926 | 26724
5852 | 411.4264 | 26724
5853 | 408.8274 | 26724
5854 | 417.8263 | 26724
5855 | 412.9337 | 26724
5856 | 409.3141 | 26724
5857 | 420.0576 | 26724
5858 | 405.4725 | 26724
5859 | 414.7793 | 26724
5860 | 410.6002 | 26724
5861 | 396.3117 | 26724
5862 | 402.2536 | 26724
5863 | 417.1161 | 26724
5864 | 416.0358 | 26724
5865 | 428.9984 | 26724
5866 | 424.7497 | 26724
5867 | 414.176 | 26724
5868 | 400.7407 | 26724
5869 | 423.819 | 26724
5870 | 413.1194 | 26724
5871 | 418.0601 | 26724
5872 | 428.2333 | 26724
5873 | 414.8015 | 26724
5874 | 421.5908 | 26724
5875 | 429.702 | 26724
5876 | 408.7005 | 26724
5877 | 427.5834 | 26724
5878 | 424.26 | 26724
5879 | 400.8734 | 26724
5880 | 413.1999 | 26724
5881 | 422.3154 | 26724
5882 | 419.5787 | 26724
5883 | 412.2249 | 26724
5884 | 422.5342 | 26724
5885 | 426.8994 | 26724
5886 | 411.4907 | 26724
5887 | 413.2542 | 26724
5888 | 434.8905 | 26724
5889 | 418.9008 | 26724
5890 | 422.8487 | 26724
5891 | 406.8525 | 26724
5892 | 400.7252 | 26724
5893 | 423.9594 | 26724
5894 | 426.1604 | 26724
5895 | 425.9965 | 26724
5896 | 405.6271 | 26724
5897 | 411.018 | 26724
5898 | 415.5384 | 26724
5899 | 418.6442 | 26724
5900 | 413.8861 | 26724
5901 | 426.3973 | 26724
5902 | 413.2206 | 26724
5903 | 434.8526 | 26724
5904 | 422.0179 | 26724
5905 | 424.3573 | 26724
5906 | 422.4897 | 26724
5907 | 426.6547 | 26724
5908 | 408.8279 | 26724
5909 | 418.4663 | 26724
5910 | 415.6489 | 26724
5911 | 411.43 | 26724
5912 | 409.1314 | 26724
5913 | 426.2971 | 26724
5914 | 430.3911 | 26724
5915 | 402.627 | 26724
5916 | 417.5155 | 26724
5917 | 427.8681 | 26724
5918 | 417.3386 | 26724
5919 | 427.5362 | 26724
5920 | 410.8284 | 26724
5921 | 402.6077 | 26724
5922 | 411.3764 | 26724
5923 | 420.7613 | 26724
5924 | 422.0521 | 26724
5925 | 406.3202 | 26724
5926 | 421.6254 | 26724
5927 | 411.6629 | 26724
5928 | 401.6763 | 26724
5929 | 403.3799 | 26724
5930 | 411.4599 | 26724
5931 | 408.8069 | 26724
5932 | 415.3323 | 26724
5933 | 427.6589 | 26724
5934 | 397.8581 | 26724
5935 | 427.2547 | 26724
5936 | 427.6871 | 26724
5937 | 420.9851 | 26724
5938 | 412.7076 | 26724
5939 | 430.3752 | 26724
5940 | 417.4006 | 26724
5941 | 415.5106 | 26724
5942 | 405.2047 | 26724
5943 | 413.3181 | 26724
5944 | 418.1844 | 26724
5945 | 416.8489 | 26724
5946 | 410.0888 | 26724
5947 | 415.2588 | 26724
5948 | 424.0543 | 26724
5949 | 401.8281 | 26724
5950 | 416.9738 | 26724
5951 | 430.2078 | 26724
5952 | 403.9957 | 26724
5953 | 406.8586 | 26724
5954 | 411.3457 | 26724
5955 | 414.8442 | 26724
5956 | 429.7649 | 26724
5957 | 410.0528 | 26724
5958 | 408.99 | 26724
5959 | 405.5666 | 26724
5960 | 407.6585 | 26724
5961 | 405.3646 | 26724
5962 | 412.7179 | 26724
5963 | 422.8941 | 26724
5964 | 411.6769 | 26724
5965 | 407.978 | 26724
5966 | 406.6896 | 26724
5967 | 410.1732 | 26724
5968 | 413.3635 | 26724
5969 | 401.6112 | 26724
5970 | 418.5391 | 26724
5971 | 418.4801 | 26724
5972 | 430.1404 | 26724
5973 | 413.4467 | 26724
5974 | 431.0163 | 26724
5975 | 419.8311 | 26724
5976 | 419.1719 | 26724
5977 | 411.852 | 26724
5978 | 424.0454 | 26724
5979 | 418.0727 | 26724
5980 | 420.9683 | 26724
5981 | 418.8545 | 26724
5982 | 423.9374 | 26724
5983 | 421.4299 | 26724
5984 | 406.42 | 26724
5985 | 410.8968 | 26724
5986 | 428.4284 | 26724
5987 | 411.1001 | 26724
5988 | 406.633 | 26724
5989 | 426.5656 | 26724
5990 | 420.3709 | 26724
5991 | 416.6494 | 26724
5992 | 403.0338 | 26724
5993 | 411.7798 | 26724
5994 | 416.9884 | 26724
5995 | 420.328 | 26724
5996 | 412.3716 | 26724
5997 | 423.9732 | 26724
5998 | 410.5056 | 26724
5999 | 427.136 | 26724
6000 | 412.5595 | 26724
6001 | 391.0227 | 26724
6002 | 412.0607 | 26724
6003 | 428.2882 | 26724
6004 | 403.8767 | 26724
6005 | 412.9183 | 26724
6006 | 419.0056 | 26724
6007 | 418.3494 | 26724
6008 | 422.404 | 26724
6009 | 413.2038 | 26724
6010 | 417.8937 | 26724
6011 | 401.53 | 26724
6012 | 428.2757 | 26724
6013 | 409.2521 | 26724
6014 | 398.6097 | 26724
6015 | 416.6753 | 26724
6016 | 410.4021 | 26724
6017 | 413.4877 | 26724
6018 | 405.3489 | 26724
6019 | 425.8972 | 26724
6020 | 422.6679 | 26724
6021 | 429.7486 | 26724
6022 | 413.0889 | 26724
6023 | 418.3051 | 26724
6024 | 411.2317 | 26724
6025 | 416.3431 | 26724
6026 | 409.3202 | 26724
6027 | 420.9947 | 26724
6028 | 410.2925 | 26724
6029 | 413.729 | 26724
6030 | 415.5846 | 26724
6031 | 422.1524 | 26724
6032 | 418.8415 | 26724
6033 | 407.8857 | 26724
6034 | 419.2916 | 26724
6035 | 424.8246 | 26724
6036 | 406.3797 | 26724
6037 | 413.0886 | 26724
6038 | 420.1265 | 26724
6039 | 420.0071 | 26724
6040 | 407.1039 | 26724
6041 | 412.9249 | 26724
6042 | 406.8322 | 26724
6043 | 408.6611 | 26724
6044 | 420.8445 | 26724
6045 | 403.2875 | 26724
6046 | 426.171 | 26724
6047 | 411.5843 | 26724
6048 | 405.9944 | 26724
6049 | 399.1175 | 26724
6050 | 399.2452 | 26724
6051 | 425.0734 | 26724
6052 | 424.2709 | 26724
6053 | 409.4962 | 26724
6054 | 421.0103 | 26724
6055 | 427.0109 | 26724
6056 | 422.1949 | 26724
6057 | 409.3522 | 26724
6058 | 402.2522 | 26724
6059 | 425.8851 | 26724
6060 | 428.7656 | 26724
6061 | 408.4211 | 26724
6062 | 430.6814 | 26724
6063 | 419.362 | 26724
6064 | 427.9251 | 26724
6065 | 409.5102 | 26724
6066 | 429.0709 | 26724
6067 | 415.4973 | 26724
6068 | 408.965 | 26724
6069 | 413.4589 | 26724
6070 | 403.9391 | 26724
6071 | 421.4206 | 26724
6072 | 410.0812 | 26724
6073 | 419.6505 | 26724
6074 | 420.7481 | 26724
6075 | 411.5389 | 26724
6076 | 403.81 | 26724
6077 | 408.7845 | 26724
6078 | 413.3987 | 26724
6079 | 408.6452 | 26724
6080 | 420.7881 | 26724
6081 | 402.4263 | 26724
6082 | 409.2552 | 26724
6083 | 407.2367 | 26724
6084 | 416.1071 | 26724
6085 | 410.8082 | 26724
6086 | 410.2918 | 26724
6087 | 426.0356 | 26724
6088 | 419.8087 | 26724
6089 | 420.3688 | 26724
6090 | 429.5669 | 26724
6091 | 415.7219 | 26724
6092 | 415.0481 | 26724
6093 | 413.4206 | 26724
6094 | 421.8815 | 26724
6095 | 411.8518 | 26724
6096 | 411.9631 | 26724
6097 | 418.7353 | 26724
6098 | 422.8361 | 26724
6099 | 408.4047 | 26724
6100 | 431.1622 | 26724
6101 | 422.3828 | 26724
6102 | 415.5537 | 26724
6103 | 413.5952 | 26724
6104 | 420.902 | 26724
6105 | 398.4957 | 26724
6106 | 402.4955 | 26724
6107 | 410.6734 | 26724
6108 | 420.3054 | 26724
6109 | 414.9157 | 26724
6110 | 401.7551 | 26724
6111 | 416.2425 | 26724
6112 | 418.2113 | 26724
6113 | 418.8292 | 26724
6114 | 407.7292 | 26724
6115 | 411.5686 | 26724
6116 | 423.7729 | 26724
6117 | 425.568 | 26724
6118 | 410.202 | 26724
6119 | 418.927 | 26724
6120 | 413.2268 | 26724
6121 | 420.5591 | 26724
6122 | 430.5581 | 26724
6123 | 402.0077 | 26724
6124 | 413.5733 | 26724
6125 | 412.6921 | 26724
6126 | 410.7617 | 26724
6127 | 405.2191 | 26724
6128 | 428.1881 | 26724
6129 | 420.8544 | 26724
6130 | 425.3185 | 26724
6131 | 412.1025 | 26724
6132 | 413.6305 | 26724
6133 | 415.3129 | 26724
6134 | 426.988 | 26724
6135 | 421.6766 | 26724
6136 | 406.9327 | 26724
6137 | 427.3402 | 26724
6138 | 418.8801 | 26724
6139 | 402.3302 | 26724
6140 | 412.0389 | 26724
6141 | 426.3815 | 26724
6142 | 424.6034 | 26724
6143 | 409.3257 | 26724
6144 | 415.8804 | 26724
6145 | 401.3654 | 26724
6146 | 423.7479 | 26724
6147 | 405.9692 | 26724
6148 | 416.5345 | 26724
6149 | 422.7891 | 26724
6150 | 409.8101 | 26724
6151 | 402.1838 | 26724
6152 | 420.0026 | 26724
6153 | 414.037 | 26724
6154 | 399.368 | 26724
6155 | 429.8722 | 26724
6156 | 423.8498 | 26724
6157 | 420.5519 | 26724
6158 | 409.1062 | 26724
6159 | 422.2383 | 26724
6160 | 430.0911 | 26724
6161 | 404.4381 | 26724
6162 | 408.7075 | 26724
6163 | 400.3937 | 26724
6164 | 404.7483 | 26724
6165 | 418.2764 | 26724
6166 | 424.4272 | 26724
6167 | 407.4832 | 26724
6168 | 414.2435 | 26724
6169 | 407.8197 | 26724
6170 | 425.8411 | 26724
6171 | 408.2274 | 26724
6172 | 425.3312 | 26724
6173 | 405.2057 | 26724
6174 | 429.1179 | 26724
6175 | 398.7089 | 26724
6176 | 414.2452 | 26724
6177 | 422.7653 | 26724
6178 | 428.9361 | 26724
6179 | 405.0139 | 26724
6180 | 416.969 | 26724
6181 | 410.7715 | 26724
6182 | 419.2672 | 26724
6183 | 418.4314 | 26724
6184 | 418.8333 | 26724
6185 | 414.7438 | 26724
6186 | 407.3601 | 26724
6187 | 423.7756 | 26724
6188 | 428.2319 | 26724
6189 | 418.6548 | 26724
6190 | 411.8725 | 26724
6191 | 406.4751 | 26724
6192 | 418.0895 | 26724
6193 | 413.7911 | 26724
6194 | 405.3471 | 26724
6195 | 424.2118 | 26724
6196 | 419.7515 | 26724
6197 | 423.516 | 26724
6198 | 413.8001 | 26724
6199 | 414.5184 | 26724
6200 | 408.5524 | 26724
6201 | 428.1068 | 26724
6202 | 417.2802 | 26724
6203 | 416.0562 | 26724
6204 | 424.7719 | 26724
6205 | 418.0887 | 26724
6206 | 410.7683 | 26724
6207 | 419.58 | 26724
6208 | 408.9039 | 26724
6209 | 413.8164 | 26724
6210 | 421.2797 | 26724
6211 | 414.714 | 26724
6212 | 425.3477 | 26724
6213 | 409.4433 | 26724
6214 | 417.4584 | 26724
6215 | 411.7354 | 26724
6216 | 416.6816 | 26724
6217 | 419.5637 | 26724
6218 | 415.3282 | 26724
6219 | 420.308 | 26724
6220 | 419.3075 | 26724
6221 | 424.1553 | 26724
6222 | 418.4427 | 26724
6223 | 406.3284 | 26724
6224 | 417.9045 | 26724
6225 | 418.0166 | 26724
6226 | 425.9982 | 26724
6227 | 412.1478 | 26724
6228 | 401.677 | 26724
6229 | 409.9564 | 26724
6230 | 419.7897 | 26724
6231 | 410.498 | 26724
6232 | 432.8525 | 26724
6233 | 423.5093 | 26724
6234 | 411.3162 | 26724
6235 | 406.3302 | 26724
6236 | 408.7375 | 26724
6237 | 407.228 | 26724
6238 | 415.76 | 26724
6239 | 404.8278 | 26724
6240 | 409.3578 | 26724
6241 | 413.6659 | 26724
6242 | 420.4073 | 26724
6243 | 426.4455 | 26724
6244 | 406.6902 | 26724
6245 | 409.0262 | 26724
6246 | 413.2669 | 26724
6247 | 435.6818 | 26724
6248 | 430.3894 | 26724
6249 | 418.9184 | 26724
6250 | 411.272 | 26724
6251 | 428.7838 | 26724
6252 | 397.3169 | 26724
6253 | 420.8505 | 26724
6254 | 419.945 | 26724
6255 | 416.5173 | 26724
6256 | 420.5597 | 26724
6257 | 425.1642 | 26724
6258 | 432.6122 | 26724
6259 | 433.0017 | 26724
6260 | 403.5444 | 26724
6261 | 416.1082 | 26724
6262 | 418.5038 | 26724
6263 | 421.7439 | 26724
6264 | 411.2491 | 26724
6265 | 403.5924 | 26724
6266 | 420.3416 | 26724
6267 | 404.1959 | 26724
6268 | 415.8891 | 26724
6269 | 414.933 | 26724
6270 | 424.7471 | 26724
6271 | 422.0432 | 26724
6272 | 418.667 | 26724
6273 | 409.7748 | 26724
6274 | 421.7134 | 26724
6275 | 421.5262 | 26724
6276 | 416.3685 | 26724
6277 | 416.4011 | 26724
6278 | 419.9531 | 26724
6279 | 412.7586 | 26724
6280 | 414.8834 | 26724
6281 | 418.4427 | 26724
6282 | 420.2669 | 26724
6283 | 414.2947 | 26724
6284 | 419.5601 | 26724
6285 | 420.4369 | 26724
6286 | 416.4524 | 26724
6287 | 422.0922 | 26724
6288 | 413.6425 | 26724
6289 | 404.5802 | 26724
6290 | 409.9384 | 26724
6291 | 413.0152 | 26724
6292 | 410.3625 | 26724
6293 | 419.3465 | 26724
6294 | 404.8912 | 26724
6295 | 418.6671 | 26724
6296 | 418.1003 | 26724
6297 | 411.1275 | 26724
6298 | 406.8788 | 26724
6299 | 414.1526 | 26724
6300 | 415.9832 | 26724
6301 | 414.1779 | 26724
6302 | 421.9623 | 26724
6303 | 431.1943 | 26724
6304 | 403.9666 | 26724
6305 | 408.125 | 26724
6306 | 414.5105 | 26724
6307 | 425.8494 | 26724
6308 | 405.4786 | 26724
6309 | 416.6373 | 26724
6310 | 413.8162 | 26724
6311 | 410.1653 | 26724
6312 | 425.879 | 26724
6313 | 411.6493 | 26724
6314 | 407.7705 | 26724
6315 | 429.1908 | 26724
6316 | 416.2716 | 26724
6317 | 428.6528 | 26724
6318 | 418.4271 | 26724
6319 | 408.1467 | 26724
6320 | 418.2842 | 26724
6321 | 431.281 | 26724
6322 | 412.1215 | 26724
6323 | 433.0105 | 26724
6324 | 425.5733 | 26724
6325 | 415.9876 | 26724
6326 | 414.083 | 26724
6327 | 416.2376 | 26724
6328 | 426.7948 | 26724
6329 | 435.1253 | 26724
6330 | 420.4079 | 26724
6331 | 412.8894 | 26724
6332 | 423.5322 | 26724
6333 | 422.5311 | 26724
6334 | 428.7767 | 26724
6335 | 425.1142 | 26724
6336 | 415.5531 | 26724
6337 | 413.7884 | 26724
6338 | 420.5247 | 26724
6339 | 418.468 | 26724
6340 | 419.2146 | 26724
6341 | 405.8674 | 26724
6342 | 421.6086 | 26724
6343 | 400.2388 | 26724
6344 | 425.0778 | 26724
6345 | 426.5313 | 26724
6346 | 421.0494 | 26724
6347 | 403.6635 | 26724
6348 | 407.9128 | 26724
6349 | 393.8585 | 26724
6350 | 402.237 | 26724
6351 | 411.953 | 26724
6352 | 410.4867 | 26724
6353 | 415.2311 | 26724
6354 | 417.5602 | 26724
6355 | 399.9653 | 26724
6356 | 422.2917 | 26724
6357 | 428.0692 | 26724
6358 | 405.0587 | 26724
6359 | 417.1606 | 26724
6360 | 419.4828 | 26724
6361 | 421.4977 | 26724
6362 | 411.6991 | 26724
6363 | 413.5616 | 26724
6364 | 411.1084 | 26724
6365 | 410.5458 | 26724
6366 | 419.892 | 26724
6367 | 414.1178 | 26724
6368 | 414.3456 | 26724
6369 | 402.9298 | 26724
6370 | 403.9181 | 26724
6371 | 410.1509 | 26724
6372 | 400.8171 | 26724
6373 | 420.4092 | 26724
6374 | 431.4561 | 26724
6375 | 424.4421 | 26724
6376 | 419.8432 | 26724
6377 | 410.2586 | 26724
6378 | 420.6041 | 26724
6379 | 428.4064 | 26724
6380 | 429.0699 | 26724
6381 | 419.0572 | 26724
6382 | 403.7489 | 26724
6383 | 428.7189 | 26724
6384 | 401.7144 | 26724
6385 | 421.735 | 26724
6386 | 428.1402 | 26724
6387 | 410.6046 | 26724
6388 | 427.4904 | 26724
6389 | 417.2142 | 26724
6390 | 410.3653 | 26724
6391 | 421.9479 | 26724
6392 | 413.0876 | 26724
6393 | 416.703 | 26724
6394 | 408.8699 | 26724
6395 | 420.9542 | 26724
6396 | 410.4011 | 26724
6397 | 418.2527 | 26724
6398 | 409.7637 | 26724
6399 | 423.7959 | 26724
6400 | 403.8519 | 26724
6401 | 408.7566 | 26724
6402 | 407.543 | 26724
6403 | 422.9757 | 26724
6404 | 430.3961 | 26724
6405 | 421.986 | 26724
6406 | 398.8593 | 26724
6407 | 404.089 | 26724
6408 | 422.9415 | 26724
6409 | 429.8091 | 26724
6410 | 411.0708 | 26724
6411 | 406.6208 | 26724
6412 | 415.695 | 26724
6413 | 422.2486 | 26724
6414 | 410.2731 | 26724
6415 | 404.2974 | 26724
6416 | 416.6967 | 26724
6417 | 415.9426 | 26724
6418 | 400.5354 | 26724
6419 | 428.4206 | 26724
6420 | 414.3182 | 26724
6421 | 428.0461 | 26724
6422 | 406.1779 | 26724
6423 | 427.8424 | 26724
6424 | 421.7579 | 26724
6425 | 424.7519 | 26724
6426 | 408.5989 | 26724
6427 | 413.2029 | 26724
6428 | 423.1947 | 26724
6429 | 401.1401 | 26724
6430 | 410.4712 | 26724
6431 | 413.1583 | 26724
6432 | 411.0475 | 26724
6433 | 426.7121 | 26724
6434 | 399.4366 | 26724
6435 | 424.3595 | 26724
6436 | 415.521 | 26724
6437 | 420.7587 | 26724
6438 | 408.0139 | 26724
6439 | 412.1662 | 26724
6440 | 418.1669 | 26724
6441 | 402.0852 | 26724
6442 | 430.3758 | 26724
6443 | 422.2801 | 26724
6444 | 409.282 | 26724
6445 | 436.2291 | 26724
6446 | 412.681 | 26724
6447 | 418.3555 | 26724
6448 | 419.3588 | 26724
6449 | 407.2155 | 26724
6450 | 410.5908 | 26724
6451 | 417.9742 | 26724
6452 | 426.0046 | 26724
6453 | 414.5122 | 26724
6454 | 413.5718 | 26724
6455 | 411.2677 | 26724
6456 | 419.2726 | 26724
6457 | 418.77 | 26724
6458 | 431.8617 | 26724
6459 | 423.2323 | 26724
6460 | 405.2484 | 26724
6461 | 417.2866 | 26724
6462 | 429.1127 | 26724
6463 | 411.9652 | 26724
6464 | 426.0105 | 26724
6465 | 413.7792 | 26724
6466 | 413.8227 | 26724
6467 | 421.894 | 26724
6468 | 410.5875 | 26724
6469 | 435.4297 | 26724
6470 | 420.2048 | 26724
6471 | 409.7258 | 26724
6472 | 398.8378 | 26724
6473 | 410.4269 | 26724
6474 | 408.6004 | 26724
6475 | 401.6825 | 26724
6476 | 428.2168 | 26724
6477 | 415.9825 | 26724
6478 | 430.8201 | 26724
6479 | 405.0924 | 26724
6480 | 416.7092 | 26724
6481 | 418.0312 | 26724
6482 | 425.4811 | 26724
6483 | 403.9678 | 26724
6484 | 405.6931 | 26724
6485 | 432.9852 | 26724
6486 | 415.9526 | 26724
6487 | 403.4544 | 26724
6488 | 424.344 | 26724
6489 | 411.4726 | 26724
6490 | 408.6882 | 26724
6491 | 411.8213 | 26724
6492 | 421.9899 | 26724
6493 | 407.3769 | 26724
6494 | 411.1375 | 26724
6495 | 429.1153 | 26724
6496 | 403.2297 | 26724
6497 | 417.0528 | 26724
6498 | 410.3223 | 26724
6499 | 421.0065 | 26724
6500 | 404.8407 | 26724
6501 | 414.3662 | 26724
6502 | 411.4166 | 26724
6503 | 426.0861 | 26724
6504 | 423.0723 | 26724
6505 | 415.6015 | 26724
6506 | 412.9256 | 26724
6507 | 416.7208 | 26724
6508 | 437.9187 | 26724
6509 | 417.1986 | 26724
6510 | 412.9763 | 26724
6511 | 412.3513 | 26724
6512 | 406.6221 | 26724
6513 | 410.3117 | 26724
6514 | 413.7036 | 26724
6515 | 408.6406 | 26724
6516 | 407.3641 | 26724
6517 | 401.6389 | 26724
6518 | 423.1822 | 26724
6519 | 414.1842 | 26724
6520 | 423.5645 | 26724
6521 | 411.9965 | 26724
6522 | 416.2639 | 26724
6523 | 424.2674 | 26724
6524 | 399.8854 | 26724
6525 | 415.1737 | 26724
6526 | 419.9201 | 26724
6527 | 412.6047 | 26724
6528 | 414.5962 | 26724
6529 | 424.8574 | 26724
6530 | 417.2043 | 26724
6531 | 417.6982 | 26724
6532 | 412.7867 | 26724
6533 | 413.9595 | 26724
6534 | 417.9809 | 26724
6535 | 426.5698 | 26724
6536 | 428.8857 | 26724
6537 | 417.1175 | 26724
6538 | 406.0682 | 26724
6539 | 407.3327 | 26724
6540 | 426.3393 | 26724
6541 | 418.7146 | 26724
6542 | 408.3516 | 26724
6543 | 417.7213 | 26724
6544 | 427.0126 | 26724
6545 | 420.3423 | 26724
6546 | 402.553 | 26724
6547 | 422.9985 | 26724
6548 | 411.3699 | 26724
6549 | 413.4185 | 26724
6550 | 418.0742 | 26724
6551 | 417.5287 | 26724
6552 | 419.7768 | 26724
6553 | 408.2796 | 26724
6554 | 429.9958 | 26724
6555 | 423.3834 | 26724
6556 | 406.0472 | 26724
6557 | 425.0923 | 26724
6558 | 413.2999 | 26724
6559 | 401.2471 | 26724
6560 | 416.6257 | 26724
6561 | 420.4712 | 26724
6562 | 410.4504 | 26724
6563 | 399.7777 | 26724
6564 | 409.5881 | 26724
6565 | 419.2762 | 26724
6566 | 418.1212 | 26724
6567 | 423.4306 | 26724
6568 | 410.7667 | 26724
6569 | 404.8418 | 26724
6570 | 417.4457 | 26724
6571 | 424.471 | 26724
6572 | 407.0563 | 26724
6573 | 414.3593 | 26724
6574 | 416.2014 | 26724
6575 | 414.7778 | 26724
6576 | 428.8538 | 26724
6577 | 420.6947 | 26724
6578 | 402.9226 | 26724
6579 | 433.2101 | 26724
6580 | 411.3049 | 26724
6581 | 417.0085 | 26724
6582 | 424.731 | 26724
6583 | 416.1932 | 26724
6584 | 413.9916 | 26724
6585 | 421.4921 | 26724
6586 | 427.9191 | 26724
6587 | 401.7982 | 26724
6588 | 424.6115 | 26724
6589 | 400.9032 | 26724
6590 | 415.4104 | 26724
6591 | 413.3888 | 26724
6592 | 418.7736 | 26724
6593 | 413.552 | 26724
6594 | 420.2428 | 26724
6595 | 420.6257 | 26724
6596 | 426.7617 | 26724
6597 | 422.4043 | 26724
6598 | 426.1538 | 26724
6599 | 417.2452 | 26724
6600 | 416.28 | 26724
6601 | 416.3253 | 26724
6602 | 408.7197 | 26724
6603 | 410.8637 | 26724
6604 | 412.9569 | 26724
6605 | 414.0363 | 26724
6606 | 409.4313 | 26724
6607 | 406.865 | 26724
6608 | 433.6715 | 26724
6609 | 440.179 | 26724
6610 | 406.4777 | 26724
6611 | 418.8622 | 26724
6612 | 422.6647 | 26724
6613 | 415.1183 | 26724
6614 | 422.8962 | 26724
6615 | 419.3262 | 26724
6616 | 414.3539 | 26724
6617 | 415.3675 | 26724
6618 | 423.6952 | 26724
6619 | 422.5886 | 26724
6620 | 427.4251 | 26724
6621 | 409.1722 | 26724
6622 | 406.1548 | 26724
6623 | 408.0563 | 26724
6624 | 421.2768 | 26724
6625 | 426.1098 | 26724
6626 | 422.3482 | 26724
6627 | 415.6012 | 26724
6628 | 419.6051 | 26724
6629 | 438.689 | 26724
6630 | 410.4204 | 26724
6631 | 419.3906 | 26724
6632 | 400.0179 | 26724
6633 | 419.9698 | 26724
6634 | 409.3823 | 26724
6635 | 400.7538 | 26724
6636 | 432.1172 | 26724
6637 | 421.088 | 26724
6638 | 409.0316 | 26724
6639 | 422.5233 | 26724
6640 | 408.047 | 26724
6641 | 424.4736 | 26724
6642 | 424.2359 | 26724
6643 | 416.0491 | 26724
6644 | 411.4345 | 26724
6645 | 432.9149 | 26724
6646 | 414.3068 | 26724
6647 | 409.9519 | 26724
6648 | 411.9343 | 26724
6649 | 432.9281 | 26724
6650 | 426.3734 | 26724
6651 | 409.7017 | 26724
6652 | 423.0592 | 26724
6653 | 400.217 | 26724
6654 | 418.4217 | 26724
6655 | 419.1688 | 26724
6656 | 421.451 | 26724
6657 | 404.7009 | 26724
6658 | 410.686 | 26724
6659 | 406.2818 | 26724
6660 | 419.6945 | 26724
6661 | 418.1426 | 26724
6662 | 412.419 | 26724
6663 | 411.8882 | 26724
6664 | 412.0186 | 26724
6665 | 426.1064 | 26724
6666 | 405.8372 | 26724
6667 | 413.1514 | 26724
6668 | 424.2072 | 26724
6669 | 416.9508 | 26724
6670 | 425.3119 | 26724
6671 | 414.6393 | 26724
6672 | 427.2025 | 26724
6673 | 416.879 | 26724
6674 | 424.0786 | 26724
6675 | 420.8307 | 26724
6676 | 425.9009 | 26724
6677 | 413.3609 | 26724
6678 | 402.4516 | 26724
6679 | 424.3641 | 26724
6680 | 410.0943 | 26724
6681 | 414.6296 | 26724
6682 | 423.5633 | 26724
6683 | 412.0292 | 26724
6684 | 420.1348 | 26724
6685 | 413.5554 | 26724
6686 | 414.8315 | 26724
6687 | 410.6021 | 26724
6688 | 417.5872 | 26724
6689 | 416.1655 | 26724
6690 | 415.3914 | 26724
6691 | 406.6067 | 26724
6692 | 409.4769 | 26724
6693 | 423.616 | 26724
6694 | 431.4458 | 26724
6695 | 414.3776 | 26724
6696 | 425.6243 | 26724
6697 | 429.0593 | 26724
6698 | 416.6138 | 26724
6699 | 416.7282 | 26724
6700 | 421.6333 | 26724
6701 | 425.7405 | 26724
6702 | 409.5559 | 26724
6703 | 417.5327 | 26724
6704 | 410.5078 | 26724
6705 | 422.9866 | 26724
6706 | 414.4782 | 26724
6707 | 415.8235 | 26724
6708 | 420.1689 | 26724
6709 | 423.813 | 26724
6710 | 416.0696 | 26724
6711 | 408.5774 | 26724
6712 | 400.5231 | 26724
6713 | 409.7138 | 26724
6714 | 435.0933 | 26724
6715 | 421.0584 | 26724
6716 | 415.3119 | 26724
6717 | 405.5048 | 26724
6718 | 414.8143 | 26724
6719 | 425.3791 | 26724
6720 | 407.7214 | 26724
6721 | 415.367 | 26724
6722 | 420.1136 | 26724
6723 | 419.8725 | 26724
6724 | 415.9942 | 26724
6725 | 406.6668 | 26724
6726 | 417.4215 | 26724
6727 | 415.4095 | 26724
6728 | 420.8155 | 26724
6729 | 419.7503 | 26724
6730 | 420.1303 | 26724
6731 | 424.6572 | 26724
6732 | 415.8865 | 26724
6733 | 433.231 | 26724
6734 | 412.2238 | 26724
6735 | 423.2632 | 26724
6736 | 413.7524 | 26724
6737 | 415.9723 | 26724
6738 | 428.404 | 26724
6739 | 424.4474 | 26724
6740 | 398.7983 | 26724
6741 | 419.8492 | 26724
6742 | 423.6838 | 26724
6743 | 416.324 | 26724
6744 | 406.8166 | 26724
6745 | 423.1394 | 26724
6746 | 415.873 | 26724
6747 | 420.9918 | 26724
6748 | 415.3186 | 26724
6749 | 417.8007 | 26724
6750 | 407.2701 | 26724
6751 | 413.5615 | 26724
6752 | 426.9182 | 26724
6753 | 422.2631 | 26724
6754 | 411.4958 | 26724
6755 | 436.4275 | 26724
6756 | 431.925 | 26724
6757 | 416.1355 | 26724
6758 | 415.273 | 26724
6759 | 417.3574 | 26724
6760 | 415.0209 | 26724
6761 | 424.0981 | 26724
6762 | 416.7436 | 26724
6763 | 398.522 | 26724
6764 | 412.2823 | 26724
6765 | 418.1793 | 26724
6766 | 410.4286 | 26724
6767 | 407.46 | 26724
6768 | 415.9889 | 26724
6769 | 414.9463 | 26724
6770 | 428.1976 | 26724
6771 | 414.7533 | 26724
6772 | 409.2413 | 26724
6773 | 425.1976 | 26724
6774 | 409.5121 | 26724
6775 | 415.0125 | 26724
6776 | 418.4525 | 26724
6777 | 420.8353 | 26724
6778 | 400.2357 | 26724
6779 | 427.3976 | 26724
6780 | 426.4815 | 26724
6781 | 412.4061 | 26724
6782 | 407.2686 | 26724
6783 | 423.7335 | 26724
6784 | 426.3148 | 26724
6785 | 429.7493 | 26724
6786 | 414.5408 | 26724
6787 | 425.9002 | 26724
6788 | 398.3547 | 26724
6789 | 410.2012 | 26724
6790 | 411.7584 | 26724
6791 | 416.7765 | 26724
6792 | 413.5412 | 26724
6793 | 415.1716 | 26724
6794 | 422.8812 | 26724
6795 | 417.1291 | 26724
6796 | 414.4715 | 26724
6797 | 416.8325 | 26724
6798 | 405.686 | 26724
6799 | 420.1959 | 26724
6800 | 409.6858 | 26724
6801 | 407.1742 | 26724
6802 | 421.6299 | 26724
6803 | 417.5466 | 26724
6804 | 405.6186 | 26724
6805 | 426.8804 | 26724
6806 | 404.303 | 26724
6807 | 418.1334 | 26724
6808 | 416.7723 | 26724
6809 | 406.8887 | 26724
6810 | 415.1561 | 26724
6811 | 411.0781 | 26724
6812 | 425.8775 | 26724
6813 | 409.9192 | 26724
6814 | 425.7311 | 26724
6815 | 420.15 | 26724
6816 | 426.1711 | 26724
6817 | 417.907 | 26724
6818 | 431.4311 | 26724
6819 | 412.9555 | 26724
6820 | 412.2001 | 26724
6821 | 431.3859 | 26724
6822 | 411.8546 | 26724
6823 | 403.9434 | 26724
6824 | 418.6193 | 26724
6825 | 411.6735 | 26724
6826 | 410.0102 | 26724
6827 | 430.8796 | 26724
6828 | 422.5021 | 26724
6829 | 429.0804 | 26724
6830 | 428.2081 | 26724
6831 | 435.8665 | 26724
6832 | 424.9423 | 26724
6833 | 430.5211 | 26724
6834 | 408.8383 | 26724
6835 | 415.5148 | 26724
6836 | 421.9949 | 26724
6837 | 424.598 | 26724
6838 | 416.848 | 26724
6839 | 410.7728 | 26724
6840 | 414.001 | 26724
6841 | 421.4642 | 26724
6842 | 429.2721 | 26724
6843 | 420.9216 | 26724
6844 | 415.603 | 26724
6845 | 432.5162 | 26724
6846 | 426.506 | 26724
6847 | 409.0359 | 26724
6848 | 412.8863 | 26724
6849 | 406.0306 | 26724
6850 | 416.944 | 26724
6851 | 426.5033 | 26724
6852 | 420.8054 | 26724
6853 | 410.8207 | 26724
6854 | 406.4043 | 26724
6855 | 408.8671 | 26724
6856 | 403.0522 | 26724
6857 | 424.5046 | 26724
6858 | 418.9754 | 26724
6859 | 411.2307 | 26724
6860 | 422.9129 | 26724
6861 | 413.9347 | 26724
6862 | 417.3684 | 26724
6863 | 409.0633 | 26724
6864 | 413.6933 | 26724
6865 | 414.8174 | 26724
6866 | 421.6105 | 26724
6867 | 412.2774 | 26724
6868 | 433.7533 | 26724
6869 | 430.129 | 26724
6870 | 425.9523 | 26724
6871 | 438.4846 | 26724
6872 | 410.4988 | 26724
6873 | 420.5555 | 26724
6874 | 422.934 | 26724
6875 | 420.3473 | 26724
6876 | 423.4017 | 26724
6877 | 414.433 | 26724
6878 | 417.1043 | 26724
6879 | 405.6084 | 26724
6880 | 411.3212 | 26724
6881 | 404.9414 | 26724
6882 | 407.4208 | 26724
6883 | 403.3455 | 26724
6884 | 413.8825 | 26724
6885 | 423.0756 | 26724
6886 | 413.7852 | 26724
6887 | 411.0107 | 26724
6888 | 431.2862 | 26724
6889 | 415.1091 | 26724
6890 | 422.9464 | 26724
6891 | 416.689 | 26724
6892 | 412.759 | 26724
6893 | 417.4016 | 26724
6894 | 424.5063 | 26724
6895 | 408.6858 | 26724
6896 | 416.7804 | 26724
6897 | 421.3977 | 26724
6898 | 413.0987 | 26724
6899 | 428.4079 | 26724
6900 | 399.1959 | 26724
6901 | 420.9813 | 26724
6902 | 419.9505 | 26724
6903 | 411.0195 | 26724
6904 | 410.2839 | 26724
6905 | 418.722 | 26724
6906 | 422.901 | 26724
6907 | 421.5994 | 26724
6908 | 404.3242 | 26724
6909 | 416.7584 | 26724
6910 | 414.5665 | 26724
6911 | 410.5817 | 26724
6912 | 429.0418 | 26724
6913 | 421.2056 | 26724
6914 | 430.1621 | 26724
6915 | 410.764 | 26724
6916 | 427.4404 | 26724
6917 | 423.4313 | 26724
6918 | 410.1089 | 26724
6919 | 418.5103 | 26724
6920 | 412.9738 | 26724
6921 | 401.6962 | 26724
6922 | 419.0924 | 26724
6923 | 416.5675 | 26724
6924 | 417.7569 | 26724
6925 | 432.5829 | 26724
6926 | 400.4624 | 26724
6927 | 425.2351 | 26724
6928 | 406.5426 | 26724
6929 | 410.2477 | 26724
6930 | 399.7076 | 26724
6931 | 428.5567 | 26724
6932 | 431.2284 | 26724
6933 | 407.8945 | 26724
6934 | 407.024 | 26724
6935 | 402.5093 | 26724
6936 | 416.3218 | 26724
6937 | 423.6678 | 26724
6938 | 401.8718 | 26724
6939 | 412.8109 | 26724
6940 | 417.3441 | 26724
6941 | 423.4016 | 26724
6942 | 421.3455 | 26724
6943 | 416.4628 | 26724
6944 | 430.7735 | 26724
6945 | 409.3322 | 26724
6946 | 408.1494 | 26724
6947 | 423.306 | 26724
6948 | 413.0098 | 26724
6949 | 404.7693 | 26724
6950 | 418.07 | 26724
6951 | 429.4218 | 26724
6952 | 421.7002 | 26724
6953 | 414.8928 | 26724
6954 | 423.3668 | 26724
6955 | 416.075 | 26724
6956 | 421.9334 | 26724
6957 | 419.7695 | 26724
6958 | 409.9996 | 26724
6959 | 415.9636 | 26724
6960 | 417.4648 | 26724
6961 | 415.2742 | 26724
6962 | 421.1903 | 26724
6963 | 424.9311 | 26724
6964 | 423.1861 | 26724
6965 | 421.9221 | 26724
6966 | 418.9639 | 26724
6967 | 412.5531 | 26724
6968 | 404.8778 | 26724
6969 | 409.3797 | 26724
6970 | 414.6202 | 26724
6971 | 425.9518 | 26724
6972 | 418.1071 | 26724
6973 | 421.9796 | 26724
6974 | 429.5766 | 26724
6975 | 418.754 | 26724
6976 | 409.3231 | 26724
6977 | 416.6772 | 26724
6978 | 416.6995 | 26724
6979 | 410.0274 | 26724
6980 | 407.4476 | 26724
6981 | 406.955 | 26724
6982 | 409.6541 | 26724
6983 | 413.4329 | 26724
6984 | 421.081 | 26724
6985 | 421.1876 | 26724
6986 | 414.4127 | 26724
6987 | 401.9407 | 26724
6988 | 418.1866 | 26724
6989 | 412.4197 | 26724
6990 | 414.3963 | 26724
6991 | 421.4935 | 26724
6992 | 405.1705 | 26724
6993 | 418.1164 | 26724
6994 | 425.0089 | 26724
6995 | 415.4541 | 26724
6996 | 430.4354 | 26724
6997 | 411.5215 | 26724
6998 | 410.0042 | 26724
6999 | 417.2355 | 26724
7000 | 427.6215 | 26724
7001 | 412.5162 | 26724
7002 | 403.1573 | 26724
7003 | 428.7888 | 26724
7004 | 409.9943 | 26724
7005 | 415.8557 | 26724
7006 | 412.9735 | 26724
7007 | 417.023 | 26724
7008 | 411.6972 | 26724
7009 | 406.9126 | 26724
7010 | 411.0848 | 26724
7011 | 408.0064 | 26724
7012 | 408.716 | 26724
7013 | 419.1023 | 26724
7014 | 425.0909 | 26724
7015 | 425.9009 | 26724
7016 | 413.7723 | 26724
7017 | 412.3638 | 26724
7018 | 434.2288 | 26724
7019 | 407.6638 | 26724
7020 | 412.2701 | 26724
7021 | 425.5739 | 26724
7022 | 406.9188 | 26724
7023 | 413.8908 | 26724
7024 | 422.2137 | 26724
7025 | 412.3 | 26724
7026 | 415.077 | 26724
7027 | 411.8613 | 26724
7028 | 422.1549 | 26724
7029 | 409.975 | 26724
7030 | 410.0045 | 26724
7031 | 417.8501 | 26724
7032 | 404.2927 | 26724
7033 | 409.6992 | 26724
7034 | 412.4077 | 26724
7035 | 412.7065 | 26724
7036 | 410.718 | 26724
7037 | 410.1273 | 26724
7038 | 416.2989 | 26724
7039 | 417.7283 | 26724
7040 | 422.2569 | 26724
7041 | 431.5665 | 26724
7042 | 418.4929 | 26724
7043 | 420.7431 | 26724
7044 | 412.7721 | 26724
7045 | 395.5049 | 26724
7046 | 408.5255 | 26724
7047 | 409.3223 | 26724
7048 | 418.1349 | 26724
7049 | 411.1206 | 26724
7050 | 423.1971 | 26724
7051 | 417.7081 | 26724
7052 | 405.0135 | 26724
7053 | 434.3196 | 26724
7054 | 415.9927 | 26724
7055 | 417.7224 | 26724
7056 | 420.3543 | 26724
7057 | 415.8262 | 26724
7058 | 418.1717 | 26724
7059 | 404.6352 | 26724
7060 | 426.4043 | 26724
7061 | 413.3329 | 26724
7062 | 439.364 | 26724
7063 | 424.9656 | 26724
7064 | 415.9197 | 26724
7065 | 412.8635 | 26724
7066 | 421.5688 | 26724
7067 | 419.8237 | 26724
7068 | 425.966 | 26724
7069 | 420.4099 | 26724
7070 | 425.1114 | 26724
7071 | 416.3939 | 26724
7072 | 416.8843 | 26724
7073 | 415.791 | 26724
7074 | 419.7529 | 26724
7075 | 421.7779 | 26724
7076 | 420.8543 | 26724
7077 | 413.4483 | 26724
7078 | 404.2722 | 26724
7079 | 412.4557 | 26724
7080 | 417.0127 | 26724
7081 | 409.1436 | 26724
7082 | 413.8743 | 26724
7083 | 434.1069 | 26724
7084 | 429.0113 | 26724
7085 | 400.3944 | 26724
7086 | 402.384 | 26724
7087 | 440.5778 | 26724
7088 | 408.0793 | 26724
7089 | 416.1754 | 26724
7090 | 404.4656 | 26724
7091 | 422.7165 | 26724
7092 | 429.2621 | 26724
7093 | 424.199 | 26724
7094 | 419.5124 | 26724
7095 | 417.395 | 26724
7096 | 419.5205 | 26724
7097 | 416.4992 | 26724
7098 | 413.4405 | 26724
7099 | 420.1143 | 26724
7100 | 402.2658 | 26724
7101 | 425.9316 | 26724
7102 | 415.1677 | 26724
7103 | 411.8446 | 26724
7104 | 428.6445 | 26724
7105 | 409.7108 | 26724
7106 | 424.8436 | 26724
7107 | 433.3755 | 26724
7108 | 412.9191 | 26724
7109 | 428.042 | 26724
7110 | 399.8196 | 26724
7111 | 420.5797 | 26724
7112 | 399.584 | 26724
7113 | 408.4084 | 26724
7114 | 424.94 | 26724
7115 | 425.3988 | 26724
7116 | 409.7358 | 26724
7117 | 407.1215 | 26724
7118 | 407.1941 | 26724
7119 | 419.8354 | 26724
7120 | 414.1737 | 26724
7121 | 413.6566 | 26724
7122 | 429.8126 | 26724
7123 | 419.42 | 26724
7124 | 430.9033 | 26724
7125 | 416.5381 | 26724
7126 | 423.9985 | 26724
7127 | 418.7974 | 26724
7128 | 404.1536 | 26724
7129 | 434.4997 | 26724
7130 | 424.4399 | 26724
7131 | 418.4063 | 26724
7132 | 403.4953 | 26724
7133 | 409.8381 | 26724
7134 | 422.636 | 26724
7135 | 409.5729 | 26724
7136 | 419.5144 | 26724
7137 | 410.1933 | 26724
7138 | 417.7548 | 26724
7139 | 415.0812 | 26724
7140 | 420.4326 | 26724
7141 | 410.8852 | 26724
7142 | 415.1698 | 26724
7143 | 416.6562 | 26724
7144 | 418.3912 | 26724
7145 | 413.5688 | 26724
7146 | 427.3871 | 26724
7147 | 412.0774 | 26724
7148 | 420.6779 | 26724
7149 | 413.0289 | 26724
7150 | 408.8464 | 26724
7151 | 401.936 | 26724
7152 | 412.0247 | 26724
7153 | 410.8171 | 26724
7154 | 419.4531 | 26724
7155 | 416.5709 | 26724
7156 | 425.3367 | 26724
7157 | 431.4909 | 26724
7158 | 403.721 | 26724
7159 | 416.6402 | 26724
7160 | 421.183 | 26724
7161 | 414.6798 | 26724
7162 | 406.4027 | 26724
7163 | 420.0851 | 26724
7164 | 406.0549 | 26724
7165 | 422.7681 | 26724
7166 | 417.8274 | 26724
7167 | 421.7008 | 26724
7168 | 414.3265 | 26724
7169 | 420.4668 | 26724
7170 | 410.4613 | 26724
7171 | 407.1767 | 26724
7172 | 417.0981 | 26724
7173 | 426.6227 | 26724
7174 | 417.2816 | 26724
7175 | 428.2549 | 26724
7176 | 404.3545 | 26724
7177 | 416.131 | 26724
7178 | 418.3548 | 26724
7179 | 403.1628 | 26724
7180 | 419.7965 | 26724
7181 | 408.494 | 26724
7182 | 419.7307 | 26724
7183 | 417.045 | 26724
7184 | 424.9826 | 26724
7185 | 404.936 | 26724
7186 | 425.1561 | 26724
7187 | 424.8923 | 26724
7188 | 425.4156 | 26724
7189 | 409.1532 | 26724
7190 | 421.1646 | 26724
7191 | 405.0819 | 26724
7192 | 423.0896 | 26724
7193 | 418.7666 | 26724
7194 | 408.8774 | 26724
7195 | 406.2579 | 26724
7196 | 409.8491 | 26724
7197 | 433.6907 | 26724
7198 | 412.0851 | 26724
7199 | 417.6681 | 26724
7200 | 405.2571 | 26724
7201 | 422.4685 | 26724
7202 | 423.5068 | 26724
7203 | 414.528 | 26724
7204 | 412.9457 | 26724
7205 | 417.2414 | 26724
7206 | 404.254 | 26724
7207 | 420.7162 | 26724
7208 | 411.4363 | 26724
7209 | 426.6475 | 26724
7210 | 417.6075 | 26724
7211 | 413.2755 | 26724
7212 | 408.9031 | 26724
7213 | 414.0407 | 26724
7214 | 416.6889 | 26724
7215 | 424.403 | 26724
7216 | 409.8223 | 26724
7217 | 422.7408 | 26724
7218 | 420.239 | 26724
7219 | 419.802 | 26724
7220 | 410.1616 | 26724
7221 | 421.7561 | 26724
7222 | 419.4039 | 26724
7223 | 407.1357 | 26724
7224 | 409.9561 | 26724
7225 | 423.4099 | 26724
7226 | 423.7947 | 26724
7227 | 412.8369 | 26724
7228 | 416.0573 | 26724
7229 | 418.9249 | 26724
7230 | 424.501 | 26724
7231 | 416.1034 | 26724
7232 | 416.6107 | 26724
7233 | 413.9996 | 26724
7234 | 415.4639 | 26724
7235 | 414.824 | 26724
7236 | 412.3094 | 26724
7237 | 415.9695 | 26724
7238 | 427.8085 | 26724
7239 | 417.155 | 26724
7240 | 407.7308 | 26724
7241 | 418.375 | 26724
7242 | 423.0663 | 26724
7243 | 425.7644 | 26724
7244 | 431.726 | 26724
7245 | 422.027 | 26724
7246 | 409.4611 | 26724
7247 | 413.9612 | 26724
7248 | 428.5951 | 26724
7249 | 396.8809 | 26724
7250 | 416.5292 | 26724
7251 | 418.8639 | 26724
7252 | 425.9826 | 26724
7253 | 428.9657 | 26724
7254 | 427.876 | 26724
7255 | 422.6964 | 26724
7256 | 415.5956 | 26724
7257 | 423.2895 | 26724
7258 | 433.414 | 26724
7259 | 410.4869 | 26724
7260 | 409.2293 | 26724
7261 | 420.4928 | 26724
7262 | 418.4848 | 26724
7263 | 408.0765 | 26724
7264 | 402.0422 | 26724
7265 | 418.349 | 26724
7266 | 422.1566 | 26724
7267 | 407.2619 | 26724
7268 | 400.4561 | 26724
7269 | 414.4748 | 26724
7270 | 418.266 | 26724
7271 | 425.4689 | 26724
7272 | 425.7022 | 26724
7273 | 410.7283 | 26724
7274 | 438.7647 | 26724
7275 | 421.139 | 26724
7276 | 426.288 | 26724
7277 | 418.366 | 26724
7278 | 421.4578 | 26724
7279 | 421.5684 | 26724
7280 | 420.9158 | 26724
7281 | 423.1039 | 26724
7282 | 413.2462 | 26724
7283 | 407.6144 | 26724
7284 | 414.3196 | 26724
7285 | 416.2198 | 26724
7286 | 423.6329 | 26724
7287 | 408.8078 | 26724
7288 | 412.0971 | 26724
7289 | 418.4952 | 26724
7290 | 407.4322 | 26724
7291 | 401.3714 | 26724
7292 | 427.8476 | 26724
7293 | 411.3923 | 26724
7294 | 409.5513 | 26724
7295 | 428.2336 | 26724
7296 | 407.8778 | 26724
7297 | 409.3336 | 26724
7298 | 403.8674 | 26724
7299 | 414.9522 | 26724
7300 | 413.9309 | 26724
7301 | 415.707 | 26724
7302 | 419.1472 | 26724
7303 | 429.7137 | 26724
7304 | 418.5625 | 26724
7305 | 409.8814 | 26724
7306 | 427.2951 | 26724
7307 | 425.1066 | 26724
7308 | 416.8923 | 26724
7309 | 417.0542 | 26724
7310 | 401.4905 | 26724
7311 | 412.4959 | 26724
7312 | 417.1259 | 26724
7313 | 421.3884 | 26724
7314 | 431.6828 | 26724
7315 | 415.8968 | 26724
7316 | 405.8822 | 26724
7317 | 430.5408 | 26724
7318 | 399.7733 | 26724
7319 | 411.2687 | 26724
7320 | 417.1614 | 26724
7321 | 419.4788 | 26724
7322 | 421.071 | 26724
7323 | 422.1941 | 26724
7324 | 409.8152 | 26724
7325 | 426.4963 | 26724
7326 | 411.912 | 26724
7327 | 436.6654 | 26724
7328 | 403.6615 | 26724
7329 | 413.0738 | 26724
7330 | 426.2411 | 26724
7331 | 414.029 | 26724
7332 | 429.5122 | 26724
7333 | 433.2102 | 26724
7334 | 414.2933 | 26724
7335 | 433.0888 | 26724
7336 | 422.67 | 26724
7337 | 402.8946 | 26724
7338 | 423.0427 | 26724
7339 | 412.9633 | 26724
7340 | 422.8507 | 26724
7341 | 420.3014 | 26724
7342 | 409.3705 | 26724
7343 | 414.5665 | 26724
7344 | 434.6527 | 26724
7345 | 409.6414 | 26724
7346 | 406.5781 | 26724
7347 | 416.8697 | 26724
7348 | 413.3042 | 26724
7349 | 431.5023 | 26724
7350 | 407.6681 | 26724
7351 | 409.3153 | 26724
7352 | 410.7724 | 26724
7353 | 423.2048 | 26724
7354 | 410.8762 | 26724
7355 | 412.1726 | 26724
7356 | 414.7031 | 26724
7357 | 404.0012 | 26724
7358 | 424.1301 | 26724
7359 | 413.7258 | 26724
7360 | 413.9174 | 26724
7361 | 420.7147 | 26724
7362 | 417.7798 | 26724
7363 | 420.28 | 26724
7364 | 412.8887 | 26724
7365 | 416.202 | 26724
7366 | 420.8497 | 26724
7367 | 416.0649 | 26724
7368 | 419.5814 | 26724
7369 | 423.9592 | 26724
7370 | 413.7001 | 26724
7371 | 409.6668 | 26724
7372 | 420.2573 | 26724
7373 | 414.6855 | 26724
7374 | 405.4557 | 26724
7375 | 429.3883 | 26724
7376 | 408.0863 | 26724
7377 | 427.8397 | 26724
7378 | 418.7539 | 26724
7379 | 406.8384 | 26724
7380 | 418.415 | 26724
7381 | 423.1798 | 26724
7382 | 420.4562 | 26724
7383 | 399.4133 | 26724
7384 | 420.1112 | 26724
7385 | 419.0144 | 26724
7386 | 422.5914 | 26724
7387 | 424.5041 | 26724
7388 | 402.8802 | 26724
7389 | 424.9046 | 26724
7390 | 415.7982 | 26724
7391 | 418.9626 | 26724
7392 | 417.6262 | 26724
7393 | 405.7298 | 26724
7394 | 407.4993 | 26724
7395 | 420.3284 | 26724
7396 | 413.683 | 26724
7397 | 420.3711 | 26724
7398 | 414.0929 | 26724
7399 | 406.7259 | 26724
7400 | 416.2804 | 26724
7401 | 413.9147 | 26724
7402 | 403.6162 | 26724
7403 | 413.145 | 26724
7404 | 413.9066 | 26724
7405 | 408.4429 | 26724
7406 | 410.4837 | 26724
7407 | 416.0884 | 26724
7408 | 423.6963 | 26724
7409 | 400.7368 | 26724
7410 | 425.8284 | 26724
7411 | 398.3778 | 26724
7412 | 426.6379 | 26724
7413 | 415.9361 | 26724
7414 | 415.5842 | 26724
7415 | 413.8589 | 26724
7416 | 407.6571 | 26724
7417 | 425.157 | 26724
7418 | 417.8595 | 26724
7419 | 421.8269 | 26724
7420 | 413.9821 | 26724
7421 | 429.4436 | 26724
7422 | 404.818 | 26724
7423 | 413.1122 | 26724
7424 | 403.895 | 26724
7425 | 414.106 | 26724
7426 | 421.9726 | 26724
7427 | 419.0434 | 26724
7428 | 408.0933 | 26724
7429 | 418.569 | 26724
7430 | 430.5786 | 26724
7431 | 415.4506 | 26724
7432 | 421.2363 | 26724
7433 | 413.7849 | 26724
7434 | 420.8834 | 26724
7435 | 415.0367 | 26724
7436 | 418.7827 | 26724
7437 | 413.3049 | 26724
7438 | 408.1824 | 26724
7439 | 409.4307 | 26724
7440 | 424.849 | 26724
7441 | 422.3267 | 26724
7442 | 404.3157 | 26724
7443 | 404.1298 | 26724
7444 | 418.032 | 26724
7445 | 419.2267 | 26724
7446 | 416.203 | 26724
7447 | 427.6226 | 26724
7448 | 411.9323 | 26724
7449 | 414.1841 | 26724
7450 | 397.9781 | 26724
7451 | 417.7274 | 26724
7452 | 410.6867 | 26724
7453 | 421.5629 | 26724
7454 | 423.5026 | 26724
7455 | 421.1124 | 26724
7456 | 406.5024 | 26724
7457 | 407.2995 | 26724
7458 | 406.0657 | 26724
7459 | 407.504 | 26724
7460 | 421.7541 | 26724
7461 | 407.4269 | 26724
7462 | 409.7627 | 26724
7463 | 417.415 | 26724
7464 | 428.0137 | 26724
7465 | 420.3476 | 26724
7466 | 417.1621 | 26724
7467 | 405.5952 | 26724
7468 | 414.8809 | 26724
7469 | 433.7177 | 26724
7470 | 417.7042 | 26724
7471 | 404.6234 | 26724
7472 | 426.96 | 26724
7473 | 416.1333 | 26724
7474 | 420.6818 | 26724
7475 | 426.673 | 26724
7476 | 414.6895 | 26724
7477 | 421.1209 | 26724
7478 | 416.1659 | 26724
7479 | 409.5898 | 26724
7480 | 406.5658 | 26724
7481 | 412.8403 | 26724
7482 | 425.3471 | 26724
7483 | 416.4148 | 26724
7484 | 410.4051 | 26724
7485 | 420.2477 | 26724
7486 | 415.6698 | 26724
7487 | 411.0409 | 26724
7488 | 433.1743 | 26724
7489 | 422.5221 | 26724
7490 | 420.12 | 26724
7491 | 423.8412 | 26724
7492 | 418.9462 | 26724
7493 | 400.0631 | 26724
7494 | 416.6647 | 26724
7495 | 411.6615 | 26724
7496 | 440.2849 | 26724
7497 | 420.5737 | 26724
7498 | 404.7345 | 26724
7499 | 398.3802 | 26724
7500 | 412.3509 | 26724
7501 | 411.3261 | 26724
7502 | 412.9944 | 26724
7503 | 412.8289 | 26724
7504 | 430.2117 | 26724
7505 | 420.098 | 26724
7506 | 418.0263 | 26724
7507 | 415.7805 | 26724
7508 | 399.4931 | 26724
7509 | 412.5774 | 26724
7510 | 427.3994 | 26724
7511 | 403.0576 | 26724
7512 | 428.263 | 26724
7513 | 426.4131 | 26724
7514 | 404.7404 | 26724
7515 | 415.1506 | 26724
7516 | 409.9836 | 26724
7517 | 421.0508 | 26724
7518 | 412.7843 | 26724
7519 | 417.3628 | 26724
7520 | 412.2175 | 26724
7521 | 426.5338 | 26724
7522 | 409.7196 | 26724
7523 | 410.5368 | 26724
7524 | 410.8373 | 26724
7525 | 397.7663 | 26724
7526 | 424.6866 | 26724
7527 | 424.6051 | 26724
7528 | 401.1964 | 26724
7529 | 412.3388 | 26724
7530 | 420.6797 | 26724
7531 | 413.653 | 26724
7532 | 415.5751 | 26724
7533 | 420.6624 | 26724
7534 | 417.8279 | 26724
7535 | 423.3597 | 26724
7536 | 405.0554 | 26724
7537 | 421.5642 | 26724
7538 | 408.8696 | 26724
7539 | 400.9044 | 26724
7540 | 419.2223 | 26724
7541 | 417.4643 | 26724
7542 | 424.452 | 26724
7543 | 411.0901 | 26724
7544 | 404.051 | 26724
7545 | 415.3631 | 26724
7546 | 421.2859 | 26724
7547 | 400.4686 | 26724
7548 | 412.5535 | 26724
7549 | 429.5539 | 26724
7550 | 420.2604 | 26724
7551 | 403.472 | 26724
7552 | 423.2626 | 26724
7553 | 429.4214 | 26724
7554 | 407.723 | 26724
7555 | 406.0072 | 26724
7556 | 413.8695 | 26724
7557 | 416.8257 | 26724
7558 | 407.4387 | 26724
7559 | 422.426 | 26724
7560 | 420.073 | 26724
7561 | 427.8965 | 26724
7562 | 425.8612 | 26724
7563 | 406.2694 | 26724
7564 | 418.5738 | 26724
7565 | 404.9781 | 26724
7566 | 431.9782 | 26724
7567 | 408.5722 | 26724
7568 | 417.1452 | 26724
7569 | 407.7381 | 26724
7570 | 411.8896 | 26724
7571 | 411.7746 | 26724
7572 | 404.0778 | 26724
7573 | 422.5444 | 26724
7574 | 406.2264 | 26724
7575 | 407.5557 | 26724
7576 | 410.2142 | 26724
7577 | 414.3361 | 26724
7578 | 417.9376 | 26724
7579 | 405.225 | 26724
7580 | 408.0533 | 26724
7581 | 403.0791 | 26724
7582 | 426.4901 | 26724
7583 | 416.4018 | 26724
7584 | 429.0974 | 26724
7585 | 426.4355 | 26724
7586 | 412.9236 | 26724
7587 | 415.5068 | 26724
7588 | 424.9642 | 26724
7589 | 430.6023 | 26724
7590 | 410.3272 | 26724
7591 | 426.3657 | 26724
7592 | 419.1247 | 26724
7593 | 419.4782 | 26724
7594 | 425.2515 | 26724
7595 | 404.7501 | 26724
7596 | 420.733 | 26724
7597 | 413.0507 | 26724
7598 | 407.1846 | 26724
7599 | 416.6393 | 26724
7600 | 404.1736 | 26724
7601 | 421.0661 | 26724
7602 | 413.7982 | 26724
7603 | 413.3355 | 26724
7604 | 422.8289 | 26724
7605 | 427.5518 | 26724
7606 | 410.9098 | 26724
7607 | 431.8363 | 26724
7608 | 410.297 | 26724
7609 | 427.1935 | 26724
7610 | 426.7106 | 26724
7611 | 431.4086 | 26724
7612 | 422.7073 | 26724
7613 | 417.3364 | 26724
7614 | 415.522 | 26724
7615 | 419.837 | 26724
7616 | 404.8688 | 26724
7617 | 408.9933 | 26724
7618 | 406.0596 | 26724
7619 | 414.329 | 26724
7620 | 416.9301 | 26724
7621 | 419.4269 | 26724
7622 | 408.2177 | 26724
7623 | 403.6544 | 26724
7624 | 410.8447 | 26724
7625 | 419.8268 | 26724
7626 | 412.9302 | 26724
7627 | 425.3042 | 26724
7628 | 414.246 | 26724
7629 | 425.8312 | 26724
7630 | 414.9834 | 26724
7631 | 418.5009 | 26724
7632 | 418.2316 | 26724
7633 | 428.6266 | 26724
7634 | 419.3218 | 26724
7635 | 408.0348 | 26724
7636 | 419.2457 | 26724
7637 | 416.5092 | 26724
7638 | 411.7787 | 26724
7639 | 425.3207 | 26724
7640 | 431.4071 | 26724
7641 | 410.6476 | 26724
7642 | 418.219 | 26724
7643 | 411.0561 | 26724
7644 | 407.3418 | 26724
7645 | 406.3312 | 26724
7646 | 421.5484 | 26724
7647 | 420.3002 | 26724
7648 | 417.8315 | 26724
7649 | 410.6316 | 26724
7650 | 431.3609 | 26724
7651 | 421.3136 | 26724
7652 | 426.7995 | 26724
7653 | 430.2379 | 26724
7654 | 402.9556 | 26724
7655 | 429.5099 | 26724
7656 | 416.648 | 26724
7657 | 412.9918 | 26724
7658 | 421.3075 | 26724
7659 | 413.4928 | 26724
7660 | 425.2177 | 26724
7661 | 429.65 | 26724
7662 | 420.3142 | 26724
7663 | 417.1777 | 26724
7664 | 415.8147 | 26724
7665 | 399.5485 | 26724
7666 | 421.217 | 26724
7667 | 411.4859 | 26724
7668 | 420.4205 | 26724
7669 | 426.3866 | 26724
7670 | 425.6677 | 26724
7671 | 419.3439 | 26724
7672 | 403.6427 | 26724
7673 | 411.9833 | 26724
7674 | 418.4911 | 26724
7675 | 403.9734 | 26724
7676 | 423.8946 | 26724
7677 | 401.7179 | 26724
7678 | 422.0677 | 26724
7679 | 405.4875 | 26724
7680 | 417.1036 | 26724
7681 | 426.8082 | 26724
7682 | 414.5764 | 26724
7683 | 415.5827 | 26724
7684 | 417.2181 | 26724
7685 | 402.9513 | 26724
7686 | 421.6831 | 26724
7687 | 413.2453 | 26724
7688 | 415.1253 | 26724
7689 | 411.6352 | 26724
7690 | 439.2659 | 26724
7691 | 414.5952 | 26724
7692 | 411.6342 | 26724
7693 | 428.3421 | 26724
7694 | 419.6821 | 26724
7695 | 422.68 | 26724
7696 | 414.0424 | 26724
7697 | 412.482 | 26724
7698 | 431.4221 | 26724
7699 | 400.4832 | 26724
7700 | 412.5124 | 26724
7701 | 411.3377 | 26724
7702 | 414.1621 | 26724
7703 | 421.7675 | 26724
7704 | 417.758 | 26724
7705 | 417.3307 | 26724
7706 | 420.4128 | 26724
7707 | 414.5972 | 26724
7708 | 412.3911 | 26724
7709 | 422.1208 | 26724
7710 | 418.2695 | 26724
7711 | 415.8857 | 26724
7712 | 417.6405 | 26724
7713 | 420.7054 | 26724
7714 | 416.6796 | 26724
7715 | 415.927 | 26724
7716 | 431.1211 | 26724
7717 | 412.9211 | 26724
7718 | 420.8733 | 26724
7719 | 421.758 | 26724
7720 | 417.2406 | 26724
7721 | 408.2183 | 26724
7722 | 413.735 | 26724
7723 | 424.1346 | 26724
7724 | 404.4237 | 26724
7725 | 407.4843 | 26724
7726 | 416.1204 | 26724
7727 | 413.7537 | 26724
7728 | 414.4973 | 26724
7729 | 413.6109 | 26724
7730 | 410.5781 | 26724
7731 | 419.8548 | 26724
7732 | 423.9988 | 26724
7733 | 410.9617 | 26724
7734 | 415.1331 | 26724
7735 | 425.6912 | 26724
7736 | 415.8618 | 26724
7737 | 406.6436 | 26724
7738 | 405.7064 | 26724
7739 | 414.387 | 26724
7740 | 420.3021 | 26724
7741 | 414.122 | 26724
7742 | 417.4514 | 26724
7743 | 424.3339 | 26724
7744 | 423.1881 | 26724
7745 | 414.8351 | 26724
7746 | 402.3162 | 26724
7747 | 427.5853 | 26724
7748 | 408.026 | 26724
7749 | 404.6157 | 26724
7750 | 404.7152 | 26724
7751 | 418.2848 | 26724
7752 | 411.5708 | 26724
7753 | 434.6926 | 26724
7754 | 415.6162 | 26724
7755 | 395.1922 | 26724
7756 | 413.6681 | 26724
7757 | 416.7646 | 26724
7758 | 414.3641 | 26724
7759 | 402.5369 | 26724
7760 | 412.6376 | 26724
7761 | 428.8946 | 26724
7762 | 408.9041 | 26724
7763 | 432.3531 | 26724
7764 | 422.0401 | 26724
7765 | 420.1295 | 26724
7766 | 424.495 | 26724
7767 | 427.8759 | 26724
7768 | 406.2256 | 26724
7769 | 415.0817 | 26724
7770 | 420.0737 | 26724
7771 | 415.5901 | 26724
7772 | 413.369 | 26724
7773 | 424.4501 | 26724
7774 | 406.2856 | 26724
7775 | 403.252 | 26724
7776 | 419.7742 | 26724
7777 | 422.1291 | 26724
7778 | 429.9129 | 26724
7779 | 404.4711 | 26724
7780 | 427.2686 | 26724
7781 | 408.2951 | 26724
7782 | 402.6482 | 26724
7783 | 428.8407 | 26724
7784 | 408.2121 | 26724
7785 | 418.2609 | 26724
7786 | 415.5365 | 26724
7787 | 406.3212 | 26724
7788 | 429.1853 | 26724
7789 | 427.1822 | 26724
7790 | 407.7119 | 26724
7791 | 417.5551 | 26724
7792 | 421.7157 | 26724
7793 | 410.9585 | 26724
7794 | 411.5332 | 26724
7795 | 413.7263 | 26724
7796 | 415.9856 | 26724
7797 | 413.9031 | 26724
7798 | 408.59 | 26724
7799 | 412.0104 | 26724
7800 | 415.7799 | 26724
7801 | 417.3074 | 26724
7802 | 427.5706 | 26724
7803 | 423.1921 | 26724
7804 | 420.5701 | 26724
7805 | 416.1889 | 26724
7806 | 403.3168 | 26724
7807 | 418.9934 | 26724
7808 | 425.8782 | 26724
7809 | 424.2727 | 26724
7810 | 409.4251 | 26724
7811 | 436.1563 | 26724
7812 | 413.961 | 26724
7813 | 404.1408 | 26724
7814 | 419.0131 | 26724
7815 | 425.4344 | 26724
7816 | 412.0089 | 26724
7817 | 412.8198 | 26724
7818 | 422.7811 | 26724
7819 | 411.2657 | 26724
7820 | 419.1655 | 26724
7821 | 406.8326 | 26724
7822 | 427.3599 | 26724
7823 | 407.8891 | 26724
7824 | 425.4076 | 26724
7825 | 409.8948 | 26724
7826 | 420.8655 | 26724
7827 | 409.9387 | 26724
7828 | 399.7775 | 26724
7829 | 419.9944 | 26724
7830 | 419.8009 | 26724
7831 | 405.8653 | 26724
7832 | 411.3022 | 26724
7833 | 405.926 | 26724
7834 | 419.5403 | 26724
7835 | 416.7359 | 26724
7836 | 414.3105 | 26724
7837 | 404.8587 | 26724
7838 | 415.1966 | 26724
7839 | 403.6698 | 26724
7840 | 420.0432 | 26724
7841 | 410.5015 | 26724
7842 | 422.1718 | 26724
7843 | 425.1538 | 26724
7844 | 422.9269 | 26724
7845 | 423.5958 | 26724
7846 | 421.9308 | 26724
7847 | 412.0598 | 26724
7848 | 421.2355 | 26724
7849 | 403.6619 | 26724
7850 | 427.577 | 26724
7851 | 401.6851 | 26724
7852 | 432.0805 | 26724
7853 | 407.6377 | 26724
7854 | 415.4805 | 26724
7855 | 415.8656 | 26724
7856 | 410.0916 | 26724
7857 | 403.7942 | 26724
7858 | 420.8759 | 26724
7859 | 420.8482 | 26724
7860 | 420.1411 | 26724
7861 | 422.8282 | 26724
7862 | 415.8249 | 26724
7863 | 402.4152 | 26724
7864 | 406.1756 | 26724
7865 | 410.9988 | 26724
7866 | 406.1812 | 26724
7867 | 426.9163 | 26724
7868 | 405.9093 | 26724
7869 | 415.6759 | 26724
7870 | 407.6881 | 26724
7871 | 413.0636 | 26724
7872 | 417.8854 | 26724
7873 | 416.9288 | 26724
7874 | 425.5111 | 26724
7875 | 405.1005 | 26724
7876 | 414.7549 | 26724
7877 | 415.4133 | 26724
7878 | 421.1636 | 26724
7879 | 435.053 | 26724
7880 | 421.1796 | 26724
7881 | 401.7963 | 26724
7882 | 414.9652 | 26724
7883 | 409.1286 | 26724
7884 | 410.6837 | 26724
7885 | 409.0541 | 26724
7886 | 419.1189 | 26724
7887 | 408.7369 | 26724
7888 | 420.798 | 26724
7889 | 420.2615 | 26724
7890 | 407.995 | 26724
7891 | 419.5123 | 26724
7892 | 408.3188 | 26724
7893 | 412.1582 | 26724
7894 | 433.0722 | 26724
7895 | 414.0087 | 26724
7896 | 405.1527 | 26724
7897 | 414.9232 | 26724
7898 | 410.1048 | 26724
7899 | 400.8208 | 26724
7900 | 413.0145 | 26724
7901 | 405.3655 | 26724
7902 | 408.3467 | 26724
7903 | 421.6093 | 26724
7904 | 419.8615 | 26724
7905 | 421.4799 | 26724
7906 | 424.3016 | 26724
7907 | 421.4201 | 26724
7908 | 418.9297 | 26724
7909 | 401.8745 | 26724
7910 | 421.1924 | 26724
7911 | 413.2426 | 26724
7912 | 421.1484 | 26724
7913 | 427.348 | 26724
7914 | 408.8909 | 26724
7915 | 415.6689 | 26724
7916 | 423.5058 | 26724
7917 | 408.6177 | 26724
7918 | 417.6245 | 26724
7919 | 415.0328 | 26724
7920 | 423.0245 | 26724
7921 | 422.7277 | 26724
7922 | 416.5707 | 26724
7923 | 404.4093 | 26724
7924 | 411.5093 | 26724
7925 | 410.5139 | 26724
7926 | 417.4331 | 26724
7927 | 414.4211 | 26724
7928 | 411.213 | 26724
7929 | 405.6168 | 26724
7930 | 415.5185 | 26724
7931 | 424.8146 | 26724
7932 | 413.7817 | 26724
7933 | 419.7606 | 26724
7934 | 424.678 | 26724
7935 | 427.9132 | 26724
7936 | 415.5704 | 26724
7937 | 434.0529 | 26724
7938 | 414.9193 | 26724
7939 | 411.1125 | 26724
7940 | 411.0504 | 26724
7941 | 426.4717 | 26724
7942 | 416.9826 | 26724
7943 | 397.9634 | 26724
7944 | 410.3094 | 26724
7945 | 421.7524 | 26724
7946 | 415.1066 | 26724
7947 | 415.683 | 26724
7948 | 422.9138 | 26724
7949 | 407.6164 | 26724
7950 | 417.18 | 26724
7951 | 424.2518 | 26724
7952 | 427.7722 | 26724
7953 | 419.2596 | 26724
7954 | 419.9489 | 26724
7955 | 401.9255 | 26724
7956 | 408.4741 | 26724
7957 | 423.4607 | 26724
7958 | 417.7218 | 26724
7959 | 410.4868 | 26724
7960 | 405.2075 | 26724
7961 | 393.39 | 26724
7962 | 417.7957 | 26724
7963 | 421.7857 | 26724
7964 | 418.2163 | 26724
7965 | 407.2001 | 26724
7966 | 417.3309 | 26724
7967 | 416.468 | 26724
7968 | 413.8858 | 26724
7969 | 416.4206 | 26724
7970 | 416.7125 | 26724
7971 | 423.0763 | 26724
7972 | 408.6607 | 26724
7973 | 420.8938 | 26724
7974 | 423.211 | 26724
7975 | 406.9706 | 26724
7976 | 418.7477 | 26724
7977 | 410.7877 | 26724
7978 | 407.9576 | 26724
7979 | 415.9599 | 26724
7980 | 402.3789 | 26724
7981 | 415.8601 | 26724
7982 | 400.1768 | 26724
7983 | 416.9308 | 26724
7984 | 427.1102 | 26724
7985 | 420.8545 | 26724
7986 | 415.9913 | 26724
7987 | 430.2941 | 26724
7988 | 419.1762 | 26724
7989 | 419.9959 | 26724
7990 | 420.5492 | 26724
7991 | 397.9932 | 26724
7992 | 428.2488 | 26724
7993 | 414.9836 | 26724
7994 | 407.5787 | 26724
7995 | 410.0727 | 26724
7996 | 415.6659 | 26724
7997 | 420.1612 | 26724
7998 | 407.968 | 26724
7999 | 413.9667 | 26724
8000 | 411.1063 | 26724
8001 | 397.1115 | 26724
8002 | 410.1791 | 26724
8003 | 403.2654 | 26724
8004 | 414.6741 | 26724
8005 | 411.2671 | 26724
8006 | 411.186 | 26724
8007 | 411.0937 | 26724
8008 | 421.9605 | 26724
8009 | 433.4244 | 26724
8010 | 408.1169 | 26724
8011 | 419.3334 | 26724
8012 | 417.5101 | 26724
8013 | 417.7552 | 26724
8014 | 408.7474 | 26724
8015 | 426.4519 | 26724
8016 | 420.1778 | 26724
8017 | 412.4469 | 26724
8018 | 426.1916 | 26724
8019 | 422.6911 | 26724
8020 | 413.3295 | 26724
8021 | 402.8884 | 26724
8022 | 399.0513 | 26724
8023 | 422.7485 | 26724
8024 | 408.988 | 26724
8025 | 425.1576 | 26724
8026 | 419.7169 | 26724
8027 | 430.4705 | 26724
8028 | 399.7697 | 26724
8029 | 409.0962 | 26724
8030 | 410.8879 | 26724
8031 | 419.9441 | 26724
8032 | 403.0928 | 26724
8033 | 430.6189 | 26724
8034 | 415.4367 | 26724
8035 | 422.301 | 26724
8036 | 421.571 | 26724
8037 | 429.2655 | 26724
8038 | 419.1178 | 26724
8039 | 417.6589 | 26724
8040 | 425.2138 | 26724
8041 | 418.7668 | 26724
8042 | 414.7433 | 26724
8043 | 413.8756 | 26724
8044 | 422.3139 | 26724
8045 | 403.124 | 26724
8046 | 420.4846 | 26724
8047 | 415.7852 | 26724
8048 | 417.2935 | 26724
8049 | 422.1118 | 26724
8050 | 416.6665 | 26724
8051 | 422.0502 | 26724
8052 | 410.9 | 26724
8053 | 428.2444 | 26724
8054 | 416.042 | 26724
8055 | 416.336 | 26724
8056 | 417.1844 | 26724
8057 | 415.8714 | 26724
8058 | 424.1971 | 26724
8059 | 402.0625 | 26724
8060 | 417.8821 | 26724
8061 | 411.2118 | 26724
8062 | 420.8203 | 26724
8063 | 410.8592 | 26724
8064 | 422.2119 | 26724
8065 | 426.9777 | 26724
8066 | 410.6178 | 26724
8067 | 411.8881 | 26724
8068 | 409.8474 | 26724
8069 | 424.6408 | 26724
8070 | 418.9811 | 26724
8071 | 417.3013 | 26724
8072 | 407.3013 | 26724
8073 | 408.2572 | 26724
8074 | 396.9427 | 26724
8075 | 423.2024 | 26724
8076 | 428.4959 | 26724
8077 | 411.7715 | 26724
8078 | 406.9167 | 26724
8079 | 430.4948 | 26724
8080 | 429.5379 | 26724
8081 | 412.1106 | 26724
8082 | 413.7856 | 26724
8083 | 409.3898 | 26724
8084 | 414.3412 | 26724
8085 | 424.6136 | 26724
8086 | 419.4837 | 26724
8087 | 421.9116 | 26724
8088 | 410.6938 | 26724
8089 | 416.7191 | 26724
8090 | 410.0404 | 26724
8091 | 427.6886 | 26724
8092 | 406.5224 | 26724
8093 | 421.2874 | 26724
8094 | 429.2381 | 26724
8095 | 407.3662 | 26724
8096 | 413.8351 | 26724
8097 | 411.9818 | 26724
8098 | 423.4712 | 26724
8099 | 417.026 | 26724
8100 | 419.9835 | 26724
8101 | 417.1864 | 26724
8102 | 424.6512 | 26724
8103 | 427.3824 | 26724
8104 | 411.3695 | 26724
8105 | 403.6604 | 26724
8106 | 426.5806 | 26724
8107 | 419.2034 | 26724
8108 | 418.4952 | 26724
8109 | 416.4657 | 26724
8110 | 419.2494 | 26724
8111 | 406.9095 | 26724
8112 | 403.9435 | 26724
8113 | 417.8527 | 26724
8114 | 418.2201 | 26724
8115 | 417.2403 | 26724
8116 | 420.9118 | 26724
8117 | 418.8397 | 26724
8118 | 407.2754 | 26724
8119 | 408.3959 | 26724
8120 | 408.1861 | 26724
8121 | 412.8716 | 26724
8122 | 404.5963 | 26724
8123 | 417.5084 | 26724
8124 | 419.2612 | 26724
8125 | 414.7126 | 26724
8126 | 423.6737 | 26724
8127 | 430.6442 | 26724
8128 | 417.1028 | 26724
8129 | 417.2175 | 26724
8130 | 419.6725 | 26724
8131 | 413.4227 | 26724
8132 | 427.0007 | 26724
8133 | 405.8701 | 26724
8134 | 428.5373 | 26724
8135 | 421.4163 | 26724
8136 | 421.5178 | 26724
8137 | 419.9483 | 26724
8138 | 419.1452 | 26724
8139 | 403.8086 | 26724
8140 | 414.6711 | 26724
8141 | 418.4903 | 26724
8142 | 409.7352 | 26724
8143 | 411.8018 | 26724
8144 | 408.2928 | 26724
8145 | 410.2028 | 26724
8146 | 418.4461 | 26724
8147 | 429.6618 | 26724
8148 | 410.5962 | 26724
8149 | 418.0244 | 26724
8150 | 430.1194 | 26724
8151 | 411.4677 | 26724
8152 | 404.2352 | 26724
8153 | 415.7583 | 26724
8154 | 410.8097 | 26724
8155 | 411.3757 | 26724
8156 | 413.1846 | 26724
8157 | 420.7372 | 26724
8158 | 424.2582 | 26724
8159 | 426.9818 | 26724
8160 | 420.36 | 26724
8161 | 406.4923 | 26724
8162 | 415.9554 | 26724
8163 | 400.0539 | 26724
8164 | 418.7552 | 26724
8165 | 415.1439 | 26724
8166 | 427.6499 | 26724
8167 | 432.2319 | 26724
8168 | 419.2255 | 26724
8169 | 419.6715 | 26724
8170 | 405.9762 | 26724
8171 | 417.62 | 26724
8172 | 409.1669 | 26724
8173 | 417.7294 | 26724
8174 | 413.0541 | 26724
8175 | 421.6773 | 26724
8176 | 422.5077 | 26724
8177 | 422.7434 | 26724
8178 | 409.4283 | 26724
8179 | 408.8996 | 26724
8180 | 416.8276 | 26724
8181 | 436.7898 | 26724
8182 | 424.53 | 26724
8183 | 422.096 | 26724
8184 | 435.8273 | 26724
8185 | 410.7878 | 26724
8186 | 416.199 | 26724
8187 | 403.4528 | 26724
8188 | 414.467 | 26724
8189 | 407.5103 | 26724
8190 | 427.7193 | 26724
8191 | 410.355 | 26724
8192 | 417.1554 | 26724
8193 | 412.5488 | 26724
8194 | 416.1684 | 26724
8195 | 424.0373 | 26724
8196 | 422.6927 | 26724
8197 | 403.6062 | 26724
8198 | 415.0486 | 26724
8199 | 425.2568 | 26724
8200 | 415.8778 | 26724
8201 | 419.8272 | 26724
8202 | 418.436 | 26724
8203 | 419.5935 | 26724
8204 | 419.1757 | 26724
8205 | 414.1137 | 26724
8206 | 411.2272 | 26724
8207 | 413.3542 | 26724
8208 | 406.2436 | 26724
8209 | 410.9265 | 26724
8210 | 410.1875 | 26724
8211 | 412.0046 | 26724
8212 | 418.4497 | 26724
8213 | 423.004 | 26724
8214 | 414.749 | 26724
8215 | 422.2152 | 26724
8216 | 423.0925 | 26724
8217 | 422.8061 | 26724
8218 | 416.0606 | 26724
8219 | 403.4712 | 26724
8220 | 420.508 | 26724
8221 | 407.9822 | 26724
8222 | 412.6015 | 26724
8223 | 407.3207 | 26724
8224 | 409.1877 | 26724
8225 | 428.3236 | 26724
8226 | 422.9254 | 26724
8227 | 407.4358 | 26724
8228 | 406.7683 | 26724
8229 | 418.555 | 26724
8230 | 417.9309 | 26724
8231 | 420.7323 | 26724
8232 | 421.7688 | 26724
8233 | 418.9078 | 26724
8234 | 418.3186 | 26724
8235 | 409.513 | 26724
8236 | 403.366 | 26724
8237 | 406.2862 | 26724
8238 | 428.9431 | 26724
8239 | 408.2978 | 26724
8240 | 433.1889 | 26724
8241 | 419.2302 | 26724
8242 | 403.1074 | 26724
8243 | 408.6158 | 26724
8244 | 414.4233 | 26724
8245 | 404.0703 | 26724
8246 | 420.0322 | 26724
8247 | 415.6792 | 26724
8248 | 403.6089 | 26724
8249 | 414.9793 | 26724
8250 | 418.2784 | 26724
8251 | 419.6374 | 26724
8252 | 417.6519 | 26724
8253 | 421.6826 | 26724
8254 | 400.0217 | 26724
8255 | 416.7474 | 26724
8256 | 414.9837 | 26724
8257 | 408.8424 | 26724
8258 | 418.002 | 26724
8259 | 401.9955 | 26724
8260 | 423.3297 | 26724
8261 | 421.1703 | 26724
8262 | 425.0973 | 26724
8263 | 416.7066 | 26724
8264 | 426.8626 | 26724
8265 | 416.2863 | 26724
8266 | 423.2112 | 26724
8267 | 419.8072 | 26724
8268 | 416.9217 | 26724
8269 | 423.138 | 26724
8270 | 414.7828 | 26724
8271 | 420.2511 | 26724
8272 | 417.2752 | 26724
8273 | 423.2901 | 26724
8274 | 417.7867 | 26724
8275 | 418.6914 | 26724
8276 | 423.2071 | 26724
8277 | 415.8699 | 26724
8278 | 395.8694 | 26724
8279 | 429.6077 | 26724
8280 | 417.714 | 26724
8281 | 428.536 | 26724
8282 | 429.513 | 26724
8283 | 434.7823 | 26724
8284 | 418.4898 | 26724
8285 | 411.5751 | 26724
8286 | 409.5659 | 26724
8287 | 415.1687 | 26724
8288 | 403.4858 | 26724
8289 | 413.8294 | 26724
8290 | 420.892 | 26724
8291 | 422.6079 | 26724
8292 | 417.8731 | 26724
8293 | 412.8966 | 26724
8294 | 425.6111 | 26724
8295 | 419.5959 | 26724
8296 | 419.36 | 26724
8297 | 421.9697 | 26724
8298 | 418.2985 | 26724
8299 | 417.8943 | 26724
8300 | 424.2666 | 26724
8301 | 407.9118 | 26724
8302 | 409.9731 | 26724
8303 | 431.7478 | 26724
8304 | 408.9897 | 26724
8305 | 424.3841 | 26724
8306 | 418.4928 | 26724
8307 | 408.4393 | 26724
8308 | 404.1253 | 26724
8309 | 419.7427 | 26724
8310 | 408.4586 | 26724
8311 | 426.6321 | 26724
8312 | 414.3858 | 26724
8313 | 402.5125 | 26724
8314 | 417.6803 | 26724
8315 | 413.5035 | 26724
8316 | 407.0175 | 26724
8317 | 431.2772 | 26724
8318 | 419.7566 | 26724
8319 | 420.4117 | 26724
8320 | 414.7189 | 26724
8321 | 416.6083 | 26724
8322 | 406.4369 | 26724
8323 | 409.6495 | 26724
8324 | 419.9587 | 26724
8325 | 424.6511 | 26724
8326 | 407.8115 | 26724
8327 | 415.9109 | 26724
8328 | 404.8436 | 26724
8329 | 409.3222 | 26724
8330 | 435.7532 | 26724
8331 | 400.5107 | 26724
8332 | 416.2695 | 26724
8333 | 421.6285 | 26724
8334 | 414.2577 | 26724
8335 | 406.0499 | 26724
8336 | 408.0762 | 26724
8337 | 414.926 | 26724
8338 | 430.2749 | 26724
8339 | 414.6948 | 26724
8340 | 420.6564 | 26724
8341 | 406.812 | 26724
8342 | 427.3949 | 26724
8343 | 424.239 | 26724
8344 | 406.2759 | 26724
8345 | 426.127 | 26724
8346 | 406.3049 | 26724
8347 | 422.4791 | 26724
8348 | 427.416 | 26724
8349 | 415.2311 | 26724
8350 | 416.9236 | 26724
8351 | 393.8448 | 26724
8352 | 414.0213 | 26724
8353 | 415.7594 | 26724
8354 | 413.2251 | 26724
8355 | 415.5933 | 26724
8356 | 419.2928 | 26724
8357 | 428.3071 | 26724
8358 | 404.52 | 26724
8359 | 415.4453 | 26724
8360 | 411.8011 | 26724
8361 | 410.3762 | 26724
8362 | 404.8767 | 26724
8363 | 420.9036 | 26724
8364 | 425.4654 | 26724
8365 | 403.564 | 26724
8366 | 420.2517 | 26724
8367 | 420.8804 | 26724
8368 | 418.9429 | 26724
8369 | 404.8561 | 26724
8370 | 403.0477 | 26724
8371 | 418.9912 | 26724
8372 | 417.1476 | 26724
8373 | 408.6831 | 26724
8374 | 406.09 | 26724
8375 | 424.7617 | 26724
8376 | 407.693 | 26724
8377 | 406.8735 | 26724
8378 | 426.4779 | 26724
8379 | 405.5354 | 26724
8380 | 417.9836 | 26724
8381 | 417.2512 | 26724
8382 | 429.8437 | 26724
8383 | 430.3373 | 26724
8384 | 435.0992 | 26724
8385 | 410.7494 | 26724
8386 | 421.4787 | 26724
8387 | 404.9901 | 26724
8388 | 410.4986 | 26724
8389 | 421.1351 | 26724
8390 | 409.3417 | 26724
8391 | 426.6641 | 26724
8392 | 414.4906 | 26724
8393 | 420.57 | 26724
8394 | 422.9424 | 26724
8395 | 412.9563 | 26724
8396 | 397.6662 | 26724
8397 | 406.248 | 26724
8398 | 429.0877 | 26724
8399 | 411.9054 | 26724
8400 | 431.8198 | 26724
8401 | 402.5034 | 26724
8402 | 409.5003 | 26724
8403 | 424.98 | 26724
8404 | 420.2475 | 26724
8405 | 422.8476 | 26724
8406 | 434.2761 | 26724
8407 | 411.569 | 26724
8408 | 406.0771 | 26724
8409 | 423.5155 | 26724
8410 | 399.5066 | 26724
8411 | 436.301 | 26724
8412 | 416.5698 | 26724
8413 | 409.8178 | 26724
8414 | 417.2978 | 26724
8415 | 425.2589 | 26724
8416 | 407.4431 | 26724
8417 | 414.0237 | 26724
8418 | 421.9414 | 26724
8419 | 428.4459 | 26724
8420 | 422.9734 | 26724
8421 | 435.6252 | 26724
8422 | 399.1302 | 26724
8423 | 408.2461 | 26724
8424 | 416.9474 | 26724
8425 | 422.9947 | 26724
8426 | 429.102 | 26724
8427 | 424.3102 | 26724
8428 | 413.7995 | 26724
8429 | 425.1652 | 26724
8430 | 421.987 | 26724
8431 | 420.2341 | 26724
8432 | 403.9167 | 26724
8433 | 423.0519 | 26724
8434 | 431.2922 | 26724
8435 | 401.5414 | 26724
8436 | 425.6967 | 26724
8437 | 412.6986 | 26724
8438 | 422.4354 | 26724
8439 | 418.3513 | 26724
8440 | 409.1223 | 26724
8441 | 413.4855 | 26724
8442 | 408.9269 | 26724
8443 | 416.0171 | 26724
8444 | 422.9726 | 26724
8445 | 422.8882 | 26724
8446 | 411.3392 | 26724
8447 | 415.8589 | 26724
8448 | 427.4813 | 26724
8449 | 409.9422 | 26724
8450 | 421.214 | 26724
8451 | 432.6042 | 26724
8452 | 427.4395 | 26724
8453 | 413.5105 | 26724
8454 | 412.4832 | 26724
8455 | 411.3817 | 26724
8456 | 422.8735 | 26724
8457 | 419.0054 | 26724
8458 | 423.4924 | 26724
8459 | 416.7751 | 26724
8460 | 421.4701 | 26724
8461 | 404.1402 | 26724
8462 | 422.3327 | 26724
8463 | 413.2261 | 26724
8464 | 407.3729 | 26724
8465 | 405.2854 | 26724
8466 | 407.3614 | 26724
8467 | 419.22 | 26724
8468 | 428.8277 | 26724
8469 | 422.7096 | 26724
8470 | 400.6045 | 26724
8471 | 417.7696 | 26724
8472 | 404.286 | 26724
8473 | 406.9891 | 26724
8474 | 413.1376 | 26724
8475 | 413.7288 | 26724
8476 | 405.4948 | 26724
8477 | 427.0262 | 26724
8478 | 431.206 | 26724
8479 | 400.6492 | 26724
8480 | 415.0748 | 26724
8481 | 410.9878 | 26724
8482 | 428.2185 | 26724
8483 | 415.3752 | 26724
8484 | 424.9117 | 26724
8485 | 422.1732 | 26724
8486 | 411.1786 | 26724
8487 | 410.3991 | 26724
8488 | 415.3375 | 26724
8489 | 415.4274 | 26724
8490 | 406.9402 | 26724
8491 | 420.2623 | 26724
8492 | 429.0251 | 26724
8493 | 424.2993 | 26724
8494 | 410.8412 | 26724
8495 | 414.0154 | 26724
8496 | 416.327 | 26724
8497 | 408.6852 | 26724
8498 | 417.6612 | 26724
8499 | 428.1172 | 26724
8500 | 423.8281 | 26724
8501 | 419.773 | 26724
8502 | 406.4885 | 26724
8503 | 425.3411 | 26724
8504 | 405.2201 | 26724
8505 | 418.7772 | 26724
8506 | 418.3976 | 26724
8507 | 417.4762 | 26724
8508 | 436.424 | 26724
8509 | 432.8499 | 26724
8510 | 413.3107 | 26724
8511 | 406.4341 | 26724
8512 | 416.956 | 26724
8513 | 423.4968 | 26724
8514 | 406.3352 | 26724
8515 | 410.1583 | 26724
8516 | 422.2295 | 26724
8517 | 415.8837 | 26724
8518 | 424.3927 | 26724
8519 | 402.0903 | 26724
8520 | 436.5174 | 26724
8521 | 426.227 | 26724
8522 | 422.0015 | 26724
8523 | 428.7716 | 26724
8524 | 429.5186 | 26724
8525 | 416.0861 | 26724
8526 | 416.9593 | 26724
8527 | 409.9642 | 26724
8528 | 403.3199 | 26724
8529 | 415.9814 | 26724
8530 | 403.8967 | 26724
8531 | 412.7574 | 26724
8532 | 423.6305 | 26724
8533 | 414.4833 | 26724
8534 | 419.2131 | 26724
8535 | 418.4818 | 26724
8536 | 423.531 | 26724
8537 | 407.9057 | 26724
8538 | 421.1267 | 26724
8539 | 414.789 | 26724
8540 | 417.1659 | 26724
8541 | 426.0024 | 26724
8542 | 427.1385 | 26724
8543 | 414.4264 | 26724
8544 | 409.8415 | 26724
8545 | 423.9348 | 26724
8546 | 396.6591 | 26724
8547 | 425.4994 | 26724
8548 | 420.9594 | 26724
8549 | 407.4676 | 26724
8550 | 406.9835 | 26724
8551 | 420.171 | 26724
8552 | 415.7788 | 26724
8553 | 409.8098 | 26724
8554 | 406.4278 | 26724
8555 | 416.6349 | 26724
8556 | 414.4161 | 26724
8557 | 417.2981 | 26724
8558 | 422.2913 | 26724
8559 | 414.0626 | 26724
8560 | 420.8453 | 26724
8561 | 411.5301 | 26724
8562 | 412.2235 | 26724
8563 | 415.4335 | 26724
8564 | 419.1025 | 26724
8565 | 411.6249 | 26724
8566 | 411.3056 | 26724
8567 | 432.9382 | 26724
8568 | 413.3689 | 26724
8569 | 420.3065 | 26724
8570 | 420.9865 | 26724
8571 | 404.9851 | 26724
8572 | 427.5693 | 26724
8573 | 421.9084 | 26724
8574 | 420.5715 | 26724
8575 | 420.1259 | 26724
8576 | 406.1549 | 26724
8577 | 406.9175 | 26724
8578 | 416.8002 | 26724
8579 | 421.5394 | 26724
8580 | 427.0444 | 26724
8581 | 416.4518 | 26724
8582 | 421.6561 | 26724
8583 | 411.762 | 26724
8584 | 414.7221 | 26724
8585 | 432.6228 | 26724
8586 | 418.8621 | 26724
8587 | 418.4896 | 26724
8588 | 414.6735 | 26724
8589 | 408.5905 | 26724
8590 | 409.7308 | 26724
8591 | 401.6032 | 26724
8592 | 417.0466 | 26724
8593 | 422.4723 | 26724
8594 | 403.2128 | 26724
8595 | 412.8972 | 26724
8596 | 417.4048 | 26724
8597 | 411.6898 | 26724
8598 | 419.0707 | 26724
8599 | 422.8478 | 26724
8600 | 408.7645 | 26724
8601 | 411.2072 | 26724
8602 | 409.5459 | 26724
8603 | 412.9607 | 26724
8604 | 409.2806 | 26724
8605 | 422.979 | 26724
8606 | 413.189 | 26724
8607 | 404.4087 | 26724
8608 | 425.986 | 26724
8609 | 421.3197 | 26724
8610 | 408.9268 | 26724
8611 | 412.9636 | 26724
8612 | 404.7345 | 26724
8613 | 419.4988 | 26724
8614 | 416.1054 | 26724
8615 | 425.7331 | 26724
8616 | 413.8119 | 26724
8617 | 418.6132 | 26724
8618 | 404.2109 | 26724
8619 | 422.0812 | 26724
8620 | 424.7365 | 26724
8621 | 410.933 | 26724
8622 | 414.7922 | 26724
8623 | 418.4347 | 26724
8624 | 401.0254 | 26724
8625 | 416.6258 | 26724
8626 | 433.378 | 26724
8627 | 414.339 | 26724
8628 | 431.4326 | 26724
8629 | 421.7578 | 26724
8630 | 412.2878 | 26724
8631 | 415.7301 | 26724
8632 | 426.2857 | 26724
8633 | 422.4863 | 26724
8634 | 410.4284 | 26724
8635 | 405.9664 | 26724
8636 | 434.0721 | 26724
8637 | 433.4909 | 26724
8638 | 416.0756 | 26724
8639 | 419.7818 | 26724
8640 | 425.1863 | 26724
8641 | 406.4582 | 26724
8642 | 420.1984 | 26724
8643 | 427.5049 | 26724
8644 | 411.1081 | 26724
8645 | 426.1641 | 26724
8646 | 424.4082 | 26724
8647 | 415.7644 | 26724
8648 | 415.175 | 26724
8649 | 400.1126 | 26724
8650 | 422.7967 | 26724
8651 | 423.0328 | 26724
8652 | 410.7458 | 26724
8653 | 422.8888 | 26724
8654 | 412.6306 | 26724
8655 | 417.9189 | 26724
8656 | 417.7166 | 26724
8657 | 419.0268 | 26724
8658 | 426.5553 | 26724
8659 | 407.7885 | 26724
8660 | 414.0202 | 26724
8661 | 417.3642 | 26724
8662 | 398.731 | 26724
8663 | 428.6882 | 26724
8664 | 410.515 | 26724
8665 | 410.8639 | 26724
8666 | 395.7461 | 26724
8667 | 409.5999 | 26724
8668 | 421.1506 | 26724
8669 | 412.1009 | 26724
8670 | 416.5714 | 26724
8671 | 399.5016 | 26724
8672 | 407.2597 | 26724
8673 | 416.5292 | 26724
8674 | 401.5079 | 26724
8675 | 423.4428 | 26724
8676 | 405.6094 | 26724
8677 | 408.739 | 26724
8678 | 404.6659 | 26724
8679 | 427.3909 | 26724
8680 | 420.9065 | 26724
8681 | 410.5648 | 26724
8682 | 426.227 | 26724
8683 | 403.7595 | 26724
8684 | 432.6101 | 26724
8685 | 411.6106 | 26724
8686 | 420.4179 | 26724
8687 | 422.2222 | 26724
8688 | 419.4307 | 26724
8689 | 409.6263 | 26724
8690 | 423.0522 | 26724
8691 | 427.1482 | 26724
8692 | 424.9653 | 26724
8693 | 424.7251 | 26724
8694 | 419.0904 | 26724
8695 | 407.9138 | 26724
8696 | 410.8186 | 26724
8697 | 429.6341 | 26724
8698 | 402.9174 | 26724
8699 | 421.1906 | 26724
8700 | 403.3533 | 26724
8701 | 423.0598 | 26724
8702 | 418.5274 | 26724
8703 | 416.6682 | 26724
8704 | 409.3348 | 26724
8705 | 406.842 | 26724
8706 | 406.8155 | 26724
8707 | 408.8135 | 26724
8708 | 411.83 | 26724
8709 | 415.7678 | 26724
8710 | 417.1814 | 26724
8711 | 406.9895 | 26724
8712 | 424.1286 | 26724
8713 | 424.616 | 26724
8714 | 422.0641 | 26724
8715 | 409.7837 | 26724
8716 | 414.1964 | 26724
8717 | 414.9235 | 26724
8718 | 420.4103 | 26724
8719 | 409.9468 | 26724
8720 | 406.1299 | 26724
8721 | 430.5369 | 26724
8722 | 406.7442 | 26724
8723 | 412.8362 | 26724
8724 | 424.4395 | 26724
8725 | 415.8366 | 26724
8726 | 414.5073 | 26724
8727 | 428.5699 | 26724
8728 | 405.2815 | 26724
8729 | 425.0146 | 26724
8730 | 408.5357 | 26724
8731 | 397.4309 | 26724
8732 | 409.6761 | 26724
8733 | 421.9758 | 26724
8734 | 403.8341 | 26724
8735 | 414.1584 | 26724
8736 | 429.6545 | 26724
8737 | 426.0474 | 26724
8738 | 423.9424 | 26724
8739 | 404.4385 | 26724
8740 | 417.6687 | 26724
8741 | 397.4904 | 26724
8742 | 434.0489 | 26724
8743 | 429.5679 | 26724
8744 | 409.7286 | 26724
8745 | 423.5558 | 26724
8746 | 418.2845 | 26724
8747 | 408.1623 | 26724
8748 | 413.4093 | 26724
8749 | 419.5003 | 26724
8750 | 423.1244 | 26724
8751 | 423.979 | 26724
8752 | 410.0436 | 26724
8753 | 414.2768 | 26724
8754 | 422.0296 | 26724
8755 | 416.1438 | 26724
8756 | 421.5665 | 26724
8757 | 420.7501 | 26724
8758 | 432.6357 | 26724
8759 | 426.8062 | 26724
8760 | 414.5873 | 26724
8761 | 409.5217 | 26724
8762 | 420.6162 | 26724
8763 | 428.015 | 26724
8764 | 415.0073 | 26724
8765 | 417.2882 | 26724
8766 | 424.2957 | 26724
8767 | 404.338 | 26724
8768 | 429.7405 | 26724
8769 | 432.5991 | 26724
8770 | 429.7559 | 26724
8771 | 433.9763 | 26724
8772 | 408.6251 | 26724
8773 | 427.6491 | 26724
8774 | 406.0311 | 26724
8775 | 417.5514 | 26724
8776 | 417.147 | 26724
8777 | 416.2353 | 26724
8778 | 418.2269 | 26724
8779 | 404.1208 | 26724
8780 | 420.9451 | 26724
8781 | 410.4958 | 26724
8782 | 430.8455 | 26724
8783 | 409.9662 | 26724
8784 | 414.3623 | 26724
8785 | 418.3991 | 26724
8786 | 417.9048 | 26724
8787 | 417.0003 | 26724
8788 | 398.1603 | 26724
8789 | 408.8882 | 26724
8790 | 407.2238 | 26724
8791 | 399.637 | 26724
8792 | 399.3037 | 26724
8793 | 411.3077 | 26724
8794 | 400.9068 | 26724
8795 | 425.8168 | 26724
8796 | 417.083 | 26724
8797 | 414.6476 | 26724
8798 | 411.8591 | 26724
8799 | 416.8318 | 26724
8800 | 417.7882 | 26724
8801 | 416.1814 | 26724
8802 | 419.5205 | 26724
8803 | 415.2878 | 26724
8804 | 422.3908 | 26724
8805 | 425.3903 | 26724
8806 | 407.0132 | 26724
8807 | 421.044 | 26724
8808 | 417.9249 | 26724
8809 | 419.9354 | 26724
8810 | 422.7904 | 26724
8811 | 419.0845 | 26724
8812 | 427.8143 | 26724
8813 | 410.3085 | 26724
8814 | 417.8283 | 26724
8815 | 420.1517 | 26724
8816 | 422.7608 | 26724
8817 | 399.1631 | 26724
8818 | 428.1775 | 26724
8819 | 402.4548 | 26724
8820 | 413.8484 | 26724
8821 | 409.9152 | 26724
8822 | 403.4427 | 26724
8823 | 417.2632 | 26724
8824 | 410.6327 | 26724
8825 | 405.7343 | 26724
8826 | 417.0241 | 26724
8827 | 422.9107 | 26724
8828 | 416.216 | 26724
8829 | 422.2017 | 26724
8830 | 412.3344 | 26724
8831 | 400.5097 | 26724
8832 | 414.503 | 26724
8833 | 418.668 | 26724
8834 | 422.8976 | 26724
8835 | 412.6291 | 26724
8836 | 409.5837 | 26724
8837 | 424.2317 | 26724
8838 | 408.5975 | 26724
8839 | 413.2901 | 26724
8840 | 434.12 | 26724
8841 | 421.0943 | 26724
8842 | 417.8825 | 26724
8843 | 406.3662 | 26724
8844 | 405.1908 | 26724
8845 | 416.7211 | 26724
8846 | 415.5057 | 26724
8847 | 425.4958 | 26724
8848 | 418.4576 | 26724
8849 | 417.97 | 26724
8850 | 410.3251 | 26724
8851 | 420.2893 | 26724
8852 | 420.1623 | 26724
8853 | 404.3094 | 26724
8854 | 409.6076 | 26724
8855 | 415.354 | 26724
8856 | 405.3563 | 26724
8857 | 421.1179 | 26724
8858 | 406.3274 | 26724
8859 | 418.2965 | 26724
8860 | 407.6913 | 26724
8861 | 408.2471 | 26724
8862 | 427.4847 | 26724
8863 | 410.5109 | 26724
8864 | 420.9324 | 26724
8865 | 412.8522 | 26724
8866 | 416.222 | 26724
8867 | 404.1598 | 26724
8868 | 421.0982 | 26724
8869 | 415.7001 | 26724
8870 | 425.1271 | 26724
8871 | 417.9526 | 26724
8872 | 416.4761 | 26724
8873 | 425.4815 | 26724
8874 | 414.4464 | 26724
8875 | 425.8786 | 26724
8876 | 411.2109 | 26724
8877 | 419.2751 | 26724
8878 | 409.3445 | 26724
8879 | 423.0954 | 26724
8880 | 404.3849 | 26724
8881 | 408.9236 | 26724
8882 | 414.6583 | 26724
8883 | 425.2308 | 26724
8884 | 418.3454 | 26724
8885 | 428.3077 | 26724
8886 | 409.277 | 26724
8887 | 404.9231 | 26724
8888 | 416.3178 | 26724
8889 | 411.8967 | 26724
8890 | 407.1457 | 26724
8891 | 411.1551 | 26724
8892 | 416.5639 | 26724
8893 | 418.6132 | 26724
8894 | 417.4963 | 26724
8895 | 414.2105 | 26724
8896 | 413.599 | 26724
8897 | 424.7612 | 26724
8898 | 415.4618 | 26724
8899 | 406.2352 | 26724
8900 | 416.0524 | 26724
8901 | 410.8866 | 26724
8902 | 410.624 | 26724
8903 | 411.1023 | 26724
8904 | 416.9419 | 26724
8905 | 432.6884 | 26724
8906 | 427.878 | 26724
8907 | 429.272 | 26724
8908 | 420.5068 | 26724
8909 | 407.4703 | 26724
8910 | 411.9131 | 26724
8911 | 405.3519 | 26724
8912 | 434.3916 | 26724
8913 | 410.3643 | 26724
8914 | 422.8094 | 26724
8915 | 420.7031 | 26724
8916 | 410.0465 | 26724
8917 | 406.1418 | 26724
8918 | 420.2365 | 26724
8919 | 401.0341 | 26724
8920 | 414.0524 | 26724
8921 | 412.3771 | 26724
8922 | 419.6732 | 26724
8923 | 426.0404 | 26724
8924 | 421.3008 | 26724
8925 | 424.7843 | 26724
8926 | 418.631 | 26724
8927 | 415.4632 | 26724
8928 | 429.2055 | 26724
8929 | 417.696 | 26724
8930 | 429.2307 | 26724
8931 | 401.9274 | 26724
8932 | 412.1059 | 26724
8933 | 416.6626 | 26724
8934 | 417.1825 | 26724
8935 | 418.4312 | 26724
8936 | 416.5578 | 26724
8937 | 424.1148 | 26724
8938 | 419.6486 | 26724
8939 | 406.9261 | 26724
8940 | 408.837 | 26724
8941 | 409.8337 | 26724
8942 | 421.3302 | 26724
8943 | 420.7335 | 26724
8944 | 430.5303 | 26724
8945 | 420.5087 | 26724
8946 | 421.7237 | 26724
8947 | 428.5234 | 26724
8948 | 420.9915 | 26724
8949 | 417.9914 | 26724
8950 | 422.3717 | 26724
8951 | 419.97 | 26724
8952 | 419.4862 | 26724
8953 | 424.6325 | 26724
8954 | 416.4723 | 26724
8955 | 398.8553 | 26724
8956 | 405.8346 | 26724
8957 | 410.4833 | 26724
8958 | 422.7619 | 26724
8959 | 429.3151 | 26724
8960 | 423.6156 | 26724
8961 | 422.8793 | 26724
8962 | 425.6805 | 26724
8963 | 421.2625 | 26724
8964 | 413.8876 | 26724
8965 | 429.2858 | 26724
8966 | 414.2985 | 26724
8967 | 411.6782 | 26724
8968 | 400.3122 | 26724
8969 | 417.7172 | 26724
8970 | 427.1147 | 26724
8971 | 409.8638 | 26724
8972 | 421.1869 | 26724
8973 | 410.4298 | 26724
8974 | 415.9796 | 26724
8975 | 425.2076 | 26724
8976 | 404.9199 | 26724
8977 | 430.9498 | 26724
8978 | 410.2029 | 26724
8979 | 415.9181 | 26724
8980 | 408.1422 | 26724
8981 | 413.28 | 26724
8982 | 412.1436 | 26724
8983 | 407.6814 | 26724
8984 | 416.2393 | 26724
8985 | 432.5098 | 26724
8986 | 432.2112 | 26724
8987 | 426.6815 | 26724
8988 | 416.8269 | 26724
8989 | 429.3402 | 26724
8990 | 413.8563 | 26724
8991 | 415.9027 | 26724
8992 | 426.7061 | 26724
8993 | 411.4893 | 26724
8994 | 433.9481 | 26724
8995 | 414.9785 | 26724
8996 | 417.4352 | 26724
8997 | 418.8027 | 26724
8998 | 408.4235 | 26724
8999 | 414.9725 | 26724
9000 | 397.4473 | 26724
9001 | 407.175 | 26724
9002 | 422.4729 | 26724
9003 | 425.2754 | 26724
9004 | 424.4627 | 26724
9005 | 405.8251 | 26724
9006 | 416.8673 | 26724
9007 | 404.6293 | 26724
9008 | 408.9898 | 26724
9009 | 423.2985 | 26724
9010 | 415.9381 | 26724
9011 | 435.561 | 26724
9012 | 413.7095 | 26724
9013 | 407.5403 | 26724
9014 | 415.7008 | 26724
9015 | 429.2465 | 26724
9016 | 417.3046 | 26724
9017 | 413.0428 | 26724
9018 | 421.7262 | 26724
9019 | 429.2769 | 26724
9020 | 395.3841 | 26724
9021 | 432.0499 | 26724
9022 | 427.231 | 26724
9023 | 400.7744 | 26724
9024 | 424.8676 | 26724
9025 | 412.7105 | 26724
9026 | 408.3546 | 26724
9027 | 407.7447 | 26724
9028 | 413.2507 | 26724
9029 | 412.0369 | 26724
9030 | 413.5301 | 26724
9031 | 407.9273 | 26724
9032 | 419.4863 | 26724
9033 | 415.8736 | 26724
9034 | 421.9887 | 26724
9035 | 422.9391 | 26724
9036 | 420.8655 | 26724
9037 | 401.2681 | 26724
9038 | 424.5868 | 26724
9039 | 409.4114 | 26724
9040 | 419.6162 | 26724
9041 | 412.1232 | 26724
9042 | 419.6154 | 26724
9043 | 414.6591 | 26724
9044 | 411.2185 | 26724
9045 | 410.6328 | 26724
9046 | 394.3449 | 26724
9047 | 413.2247 | 26724
9048 | 418.6745 | 26724
9049 | 426.9528 | 26724
9050 | 415.0136 | 26724
9051 | 427.5395 | 26724
9052 | 409.7331 | 26724
9053 | 425.597 | 26724
9054 | 417.2506 | 26724
9055 | 417.7834 | 26724
9056 | 413.1636 | 26724
9057 | 410.0155 | 26724
9058 | 422.1336 | 26724
9059 | 403.3473 | 26724
9060 | 418.1838 | 26724
9061 | 411.37 | 26724
9062 | 419.7147 | 26724
9063 | 403.6715 | 26724
9064 | 425.5616 | 26724
9065 | 408.4484 | 26724
9066 | 419.1436 | 26724
9067 | 415.0324 | 26724
9068 | 419.8288 | 26724
9069 | 427.9019 | 26724
9070 | 426.2152 | 26724
9071 | 406.4484 | 26724
9072 | 418.6371 | 26724
9073 | 419.9118 | 26724
9074 | 418.4476 | 26724
9075 | 409.0498 | 26724
9076 | 420.9035 | 26724
9077 | 398.387 | 26724
9078 | 419.9033 | 26724
9079 | 423.9835 | 26724
9080 | 408.6717 | 26724
9081 | 422.6441 | 26724
9082 | 423.493 | 26724
9083 | 420.9568 | 26724
9084 | 413.9573 | 26724
9085 | 419.9467 | 26724
9086 | 400.7115 | 26724
9087 | 413.6247 | 26724
9088 | 421.7964 | 26724
9089 | 407.3579 | 26724
9090 | 419.6317 | 26724
9091 | 423.5204 | 26724
9092 | 429.2778 | 26724
9093 | 404.0445 | 26724
9094 | 406.0717 | 26724
9095 | 419.7848 | 26724
9096 | 425.7884 | 26724
9097 | 405.4849 | 26724
9098 | 421.762 | 26724
9099 | 416.923 | 26724
9100 | 412.2667 | 26724
9101 | 422.5409 | 26724
9102 | 414.2993 | 26724
9103 | 430.9933 | 26724
9104 | 403.7205 | 26724
9105 | 421.1147 | 26724
9106 | 424.1503 | 26724
9107 | 400.9698 | 26724
9108 | 419.0836 | 26724
9109 | 415.9744 | 26724
9110 | 415.174 | 26724
9111 | 416.1038 | 26724
9112 | 400.2496 | 26724
9113 | 407.3568 | 26724
9114 | 411.7742 | 26724
9115 | 410.2774 | 26724
9116 | 421.3405 | 26724
9117 | 411.5657 | 26724
9118 | 403.0422 | 26724
9119 | 422.7118 | 26724
9120 | 415.875 | 26724
9121 | 423.6289 | 26724
9122 | 423.7868 | 26724
9123 | 424.929 | 26724
9124 | 416.0048 | 26724
9125 | 421.5177 | 26724
9126 | 428.0556 | 26724
9127 | 432.1587 | 26724
9128 | 422.0337 | 26724
9129 | 423.7475 | 26724
9130 | 409.4808 | 26724
9131 | 416.2133 | 26724
9132 | 423.7973 | 26724
9133 | 413.239 | 26724
9134 | 425.1877 | 26724
9135 | 418.8959 | 26724
9136 | 417.5951 | 26724
9137 | 416.7748 | 26724
9138 | 429.2688 | 26724
9139 | 412.3224 | 26724
9140 | 439.1491 | 26724
9141 | 400.0386 | 26724
9142 | 412.4171 | 26724
9143 | 429.1259 | 26724
9144 | 421.5557 | 26724
9145 | 418.084 | 26724
9146 | 416.5095 | 26724
9147 | 411.5201 | 26724
9148 | 410.7609 | 26724
9149 | 417.8942 | 26724
9150 | 420.1427 | 26724
9151 | 415.7016 | 26724
9152 | 424.4136 | 26724
9153 | 419.4472 | 26724
9154 | 408.8586 | 26724
9155 | 408.2156 | 26724
9156 | 411.7003 | 26724
9157 | 416.9403 | 26724
9158 | 413.0689 | 26724
9159 | 430.0951 | 26724
9160 | 405.5026 | 26724
9161 | 423.6677 | 26724
9162 | 419.7809 | 26724
9163 | 426.7562 | 26724
9164 | 408.7562 | 26724
9165 | 432.182 | 26724
9166 | 414.9297 | 26724
9167 | 410.6144 | 26724
9168 | 425.6929 | 26724
9169 | 412.9595 | 26724
9170 | 425.81 | 26724
9171 | 404.4013 | 26724
9172 | 403.383 | 26724
9173 | 411.6699 | 26724
9174 | 418.3752 | 26724
9175 | 413.5839 | 26724
9176 | 414.7819 | 26724
9177 | 419.896 | 26724
9178 | 408.4512 | 26724
9179 | 425.8432 | 26724
9180 | 420.6256 | 26724
9181 | 412.9775 | 26724
9182 | 423.3236 | 26724
9183 | 421.4054 | 26724
9184 | 429.6762 | 26724
9185 | 420.2114 | 26724
9186 | 403.7952 | 26724
9187 | 398.7283 | 26724
9188 | 415.6011 | 26724
9189 | 412.3584 | 26724
9190 | 413.8891 | 26724
9191 | 421.1707 | 26724
9192 | 415.7737 | 26724
9193 | 406.5553 | 26724
9194 | 426.3928 | 26724
9195 | 415.0637 | 26724
9196 | 425.6411 | 26724
9197 | 422.1581 | 26724
9198 | 418.6376 | 26724
9199 | 413.2983 | 26724
9200 | 412.9892 | 26724
9201 | 421.8248 | 26724
9202 | 413.9076 | 26724
9203 | 416.4634 | 26724
9204 | 406.2135 | 26724
9205 | 419.2178 | 26724
9206 | 417.5337 | 26724
9207 | 427.7436 | 26724
9208 | 408.7636 | 26724
9209 | 423.1828 | 26724
9210 | 419.7994 | 26724
9211 | 425.9573 | 26724
9212 | 417.1345 | 26724
9213 | 421.134 | 26724
9214 | 416.5833 | 26724
9215 | 411.9504 | 26724
9216 | 412.2155 | 26724
9217 | 412.3081 | 26724
9218 | 419.618 | 26724
9219 | 400.1962 | 26724
9220 | 413.6064 | 26724
9221 | 424.5526 | 26724
9222 | 426.5225 | 26724
9223 | 405.4099 | 26724
9224 | 415.5465 | 26724
9225 | 409.8117 | 26724
9226 | 429.6535 | 26724
9227 | 419.0093 | 26724
9228 | 415.7883 | 26724
9229 | 421.1647 | 26724
9230 | 417.5538 | 26724
9231 | 403.4283 | 26724
9232 | 416.9258 | 26724
9233 | 420.1087 | 26724
9234 | 414.0578 | 26724
9235 | 408.5744 | 26724
9236 | 412.6658 | 26724
9237 | 415.5937 | 26724
9238 | 409.7244 | 26724
9239 | 408.3417 | 26724
9240 | 420.8282 | 26724
9241 | 420.6217 | 26724
9242 | 411.5938 | 26724
9243 | 410.4562 | 26724
9244 | 415.9631 | 26724
9245 | 411.9842 | 26724
9246 | 420.2336 | 26724
9247 | 414.7914 | 26724
9248 | 410.5648 | 26724
9249 | 416.4935 | 26724
9250 | 411.5438 | 26724
9251 | 413.1693 | 26724
9252 | 417.0233 | 26724
9253 | 413.6044 | 26724
9254 | 409.3568 | 26724
9255 | 411.035 | 26724
9256 | 415.7058 | 26724
9257 | 427.2448 | 26724
9258 | 430.6895 | 26724
9259 | 423.1031 | 26724
9260 | 399.4978 | 26724
9261 | 405.8754 | 26724
9262 | 431.1352 | 26724
9263 | 419.4087 | 26724
9264 | 411.7086 | 26724
9265 | 410.5455 | 26724
9266 | 407.2503 | 26724
9267 | 425.5471 | 26724
9268 | 403.7948 | 26724
9269 | 413.7365 | 26724
9270 | 405.765 | 26724
9271 | 438.399 | 26724
9272 | 409.3165 | 26724
9273 | 404.3801 | 26724
9274 | 395.1697 | 26724
9275 | 412.9004 | 26724
9276 | 414.5808 | 26724
9277 | 405.9176 | 26724
9278 | 407.7948 | 26724
9279 | 417.5996 | 26724
9280 | 406.726 | 26724
9281 | 411.4954 | 26724
9282 | 416.0578 | 26724
9283 | 417.8529 | 26724
9284 | 424.273 | 26724
9285 | 409.9549 | 26724
9286 | 412.0077 | 26724
9287 | 412.4451 | 26724
9288 | 423.7644 | 26724
9289 | 412.3746 | 26724
9290 | 411.6791 | 26724
9291 | 398.0898 | 26724
9292 | 416.5906 | 26724
9293 | 427.0793 | 26724
9294 | 421.8835 | 26724
9295 | 424.9947 | 26724
9296 | 417.4893 | 26724
9297 | 429.5619 | 26724
9298 | 407.7203 | 26724
9299 | 419.4185 | 26724
9300 | 428.0475 | 26724
9301 | 415.0331 | 26724
9302 | 413.3788 | 26724
9303 | 413.0402 | 26724
9304 | 415.1528 | 26724
9305 | 417.4398 | 26724
9306 | 420.4751 | 26724
9307 | 414.2406 | 26724
9308 | 416.5767 | 26724
9309 | 420.2355 | 26724
9310 | 412.0837 | 26724
9311 | 411.577 | 26724
9312 | 405.1034 | 26724
9313 | 421.8009 | 26724
9314 | 420.9805 | 26724
9315 | 421.6992 | 26724
9316 | 411.6457 | 26724
9317 | 406.2432 | 26724
9318 | 427.6267 | 26724
9319 | 421.6995 | 26724
9320 | 416.195 | 26724
9321 | 410.8402 | 26724
9322 | 425.2726 | 26724
9323 | 414.4479 | 26724
9324 | 426.126 | 26724
9325 | 405.906 | 26724
9326 | 414.7129 | 26724
9327 | 405.3124 | 26724
9328 | 413.6531 | 26724
9329 | 416.093 | 26724
9330 | 406.6926 | 26724
9331 | 404.3414 | 26724
9332 | 400.5747 | 26724
9333 | 425.4174 | 26724
9334 | 422.8208 | 26724
9335 | 408.0649 | 26724
9336 | 414.7877 | 26724
9337 | 403.0058 | 26724
9338 | 408.8749 | 26724
9339 | 409.8119 | 26724
9340 | 410.0513 | 26724
9341 | 410.4286 | 26724
9342 | 430.3719 | 26724
9343 | 413.5762 | 26724
9344 | 413.5861 | 26724
9345 | 424.5486 | 26724
9346 | 411.9697 | 26724
9347 | 422.9633 | 26724
9348 | 414.3924 | 26724
9349 | 412.842 | 26724
9350 | 397.8132 | 26724
9351 | 413.9361 | 26724
9352 | 419.6801 | 26724
9353 | 418.0526 | 26724
9354 | 410.5952 | 26724
9355 | 414.43 | 26724
9356 | 432.4321 | 26724
9357 | 412.171 | 26724
9358 | 420.6651 | 26724
9359 | 418.1913 | 26724
9360 | 412.9476 | 26724
9361 | 411.1262 | 26724
9362 | 412.67 | 26724
9363 | 416.6003 | 26724
9364 | 412.8819 | 26724
9365 | 410.4777 | 26724
9366 | 400.2367 | 26724
9367 | 419.1784 | 26724
9368 | 425.4412 | 26724
9369 | 416.5261 | 26724
9370 | 415.9496 | 26724
9371 | 421.1165 | 26724
9372 | 403.4879 | 26724
9373 | 411.0695 | 26724
9374 | 425.7645 | 26724
9375 | 393.9093 | 26724
9376 | 434.1153 | 26724
9377 | 413.5258 | 26724
9378 | 411.5354 | 26724
9379 | 408.672 | 26724
9380 | 413.3411 | 26724
9381 | 415.894 | 26724
9382 | 424.3676 | 26724
9383 | 414.1814 | 26724
9384 | 416.4878 | 26724
9385 | 415.5941 | 26724
9386 | 419.7266 | 26724
9387 | 420.5484 | 26724
9388 | 420.4516 | 26724
9389 | 422.7431 | 26724
9390 | 424.744 | 26724
9391 | 407.3189 | 26724
9392 | 419.5699 | 26724
9393 | 402.8872 | 26724
9394 | 409.8262 | 26724
9395 | 414.8449 | 26724
9396 | 421.4205 | 26724
9397 | 412.1502 | 26724
9398 | 417.7478 | 26724
9399 | 430.6807 | 26724
9400 | 410.9833 | 26724
9401 | 412.6444 | 26724
9402 | 412.9378 | 26724
9403 | 416.949 | 26724
9404 | 421.0681 | 26724
9405 | 424.51 | 26724
9406 | 398.2268 | 26724
9407 | 429.362 | 26724
9408 | 422.2917 | 26724
9409 | 412.3179 | 26724
9410 | 418.9362 | 26724
9411 | 419.0212 | 26724
9412 | 431.8779 | 26724
9413 | 428.554 | 26724
9414 | 407.2928 | 26724
9415 | 410.0222 | 26724
9416 | 420.4488 | 26724
9417 | 404.9385 | 26724
9418 | 403.2334 | 26724
9419 | 412.541 | 26724
9420 | 407.3841 | 26724
9421 | 430.1479 | 26724
9422 | 424.2349 | 26724
9423 | 417.1433 | 26724
9424 | 410.2263 | 26724
9425 | 417.3066 | 26724
9426 | 421.0841 | 26724
9427 | 429.8048 | 26724
9428 | 397.4744 | 26724
9429 | 436.8428 | 26724
9430 | 406.3445 | 26724
9431 | 415.6223 | 26724
9432 | 409.4176 | 26724
9433 | 428.9916 | 26724
9434 | 418.3786 | 26724
9435 | 419.4952 | 26724
9436 | 409.724 | 26724
9437 | 427.3871 | 26724
9438 | 411.3757 | 26724
9439 | 421.7477 | 26724
9440 | 415.2206 | 26724
9441 | 408.2685 | 26724
9442 | 422.0984 | 26724
9443 | 409.934 | 26724
9444 | 412.1678 | 26724
9445 | 427.2032 | 26724
9446 | 427.7265 | 26724
9447 | 405.499 | 26724
9448 | 399.8262 | 26724
9449 | 425.4656 | 26724
9450 | 419.3515 | 26724
9451 | 425.7224 | 26724
9452 | 408.6201 | 26724
9453 | 423.4143 | 26724
9454 | 432.0123 | 26724
9455 | 409.0293 | 26724
9456 | 416.4404 | 26724
9457 | 415.6864 | 26724
9458 | 416.2018 | 26724
9459 | 405.4763 | 26724
9460 | 425.1171 | 26724
9461 | 424.1883 | 26724
9462 | 412.6571 | 26724
9463 | 410.9675 | 26724
9464 | 418.1707 | 26724
9465 | 419.0938 | 26724
9466 | 433.2675 | 26724
9467 | 415.7881 | 26724
9468 | 418.1969 | 26724
9469 | 420.9301 | 26724
9470 | 402.806 | 26724
9471 | 424.3958 | 26724
9472 | 411.6245 | 26724
9473 | 426.2241 | 26724
9474 | 403.9735 | 26724
9475 | 419.4043 | 26724
9476 | 424.0856 | 26724
9477 | 415.7605 | 26724
9478 | 407.8979 | 26724
9479 | 410.3357 | 26724
9480 | 407.128 | 26724
9481 | 433.4815 | 26724
9482 | 420.2404 | 26724
9483 | 415.1335 | 26724
9484 | 408.2902 | 26724
9485 | 417.3374 | 26724
9486 | 408.0622 | 26724
9487 | 422.3118 | 26724
9488 | 418.0629 | 26724
9489 | 415.3561 | 26724
9490 | 421.8273 | 26724
9491 | 424.482 | 26724
9492 | 404.3083 | 26724
9493 | 406.7056 | 26724
9494 | 408.747 | 26724
9495 | 428.7274 | 26724
9496 | 417.1747 | 26724
9497 | 414.6156 | 26724
9498 | 424.1472 | 26724
9499 | 409.7051 | 26724
9500 | 399.33 | 26724
9501 | 418.3895 | 26724
9502 | 439.044 | 26724
9503 | 410.7339 | 26724
9504 | 411.6975 | 26724
9505 | 427.4101 | 26724
9506 | 399.8646 | 26724
9507 | 395.2563 | 26724
9508 | 406.4465 | 26724
9509 | 409.5139 | 26724
9510 | 430.433 | 26724
9511 | 427.909 | 26724
9512 | 426.5681 | 26724
9513 | 426.3029 | 26724
9514 | 407.3328 | 26724
9515 | 426.6524 | 26724
9516 | 412.4258 | 26724
9517 | 410.3855 | 26724
9518 | 417.9947 | 26724
9519 | 408.1763 | 26724
9520 | 404.4823 | 26724
9521 | 430.3486 | 26724
9522 | 403.9858 | 26724
9523 | 418.7614 | 26724
9524 | 421.2265 | 26724
9525 | 411.934 | 26724
9526 | 416.3664 | 26724
9527 | 407.9619 | 26724
9528 | 426.5951 | 26724
9529 | 420.8669 | 26724
9530 | 406.1869 | 26724
9531 | 419.3685 | 26724
9532 | 409.0237 | 26724
9533 | 424.5542 | 26724
9534 | 426.8503 | 26724
9535 | 422.7128 | 26724
9536 | 417.0384 | 26724
9537 | 437.5433 | 26724
9538 | 407.1779 | 26724
9539 | 411.2487 | 26724
9540 | 428.4 | 26724
9541 | 414.8738 | 26724
9542 | 411.5798 | 26724
9543 | 417.167 | 26724
9544 | 418.1584 | 26724
9545 | 398.5953 | 26724
9546 | 431.6524 | 26724
9547 | 402.9971 | 26724
9548 | 409.0585 | 26724
9549 | 419.3186 | 26724
9550 | 415.4485 | 26724
9551 | 421.5887 | 26724
9552 | 417.2834 | 26724
9553 | 419.4073 | 26724
9554 | 413.6615 | 26724
9555 | 432.1398 | 26724
9556 | 407.621 | 26724
9557 | 419.5041 | 26724
9558 | 413.5258 | 26724
9559 | 424.5728 | 26724
9560 | 420.421 | 26724
9561 | 423.1957 | 26724
9562 | 408.2098 | 26724
9563 | 430.8415 | 26724
9564 | 413.1181 | 26724
9565 | 423.4961 | 26724
9566 | 429.9116 | 26724
9567 | 410.1817 | 26724
9568 | 416.5802 | 26724
9569 | 405.2028 | 26724
9570 | 413.8945 | 26724
9571 | 422.9309 | 26724
9572 | 419.5007 | 26724
9573 | 429.7051 | 26724
9574 | 425.9441 | 26724
9575 | 413.7356 | 26724
9576 | 436.2042 | 26724
9577 | 399.5169 | 26724
9578 | 412.0917 | 26724
9579 | 415.3106 | 26724
9580 | 424.1747 | 26724
9581 | 414.9093 | 26724
9582 | 419.1129 | 26724
9583 | 411.2307 | 26724
9584 | 427.9856 | 26724
9585 | 420.0466 | 26724
9586 | 418.8982 | 26724
9587 | 408.1008 | 26724
9588 | 422.0325 | 26724
9589 | 417.0622 | 26724
9590 | 413.0388 | 26724
9591 | 422.177 | 26724
9592 | 410.637 | 26724
9593 | 413.2508 | 26724
9594 | 412.8299 | 26724
9595 | 406.9169 | 26724
9596 | 415.3273 | 26724
9597 | 410.0276 | 26724
9598 | 418.5562 | 26724
9599 | 404.8125 | 26724
9600 | 411.3113 | 26724
9601 | 418.1735 | 26724
9602 | 422.4148 | 26724
9603 | 422.0772 | 26724
9604 | 407.1149 | 26724
9605 | 402.6388 | 26724
9606 | 419.8448 | 26724
9607 | 418.8482 | 26724
9608 | 413.9027 | 26724
9609 | 426.3324 | 26724
9610 | 398.1317 | 26724
9611 | 410.6374 | 26724
9612 | 415.9094 | 26724
9613 | 413.5882 | 26724
9614 | 432.3923 | 26724
9615 | 405.2974 | 26724
9616 | 415.9088 | 26724
9617 | 411.3424 | 26724
9618 | 412.2557 | 26724
9619 | 426.6265 | 26724
9620 | 408.8516 | 26724
9621 | 419.9507 | 26724
9622 | 420.5442 | 26724
9623 | 420.3093 | 26724
9624 | 416.1251 | 26724
9625 | 416.0591 | 26724
9626 | 405.3696 | 26724
9627 | 422.3899 | 26724
9628 | 410.5723 | 26724
9629 | 412.2465 | 26724
9630 | 428.6558 | 26724
9631 | 403.0699 | 26724
9632 | 420.7048 | 26724
9633 | 401.6787 | 26724
9634 | 415.0483 | 26724
9635 | 416.8419 | 26724
9636 | 417.2743 | 26724
9637 | 410.0074 | 26724
9638 | 424.0707 | 26724
9639 | 417.9037 | 26724
9640 | 408.2434 | 26724
9641 | 419.8319 | 26724
9642 | 418.8474 | 26724
9643 | 412.105 | 26724
9644 | 425.5856 | 26724
9645 | 421.5535 | 26724
9646 | 428.9755 | 26724
9647 | 425.6361 | 26724
9648 | 398.5392 | 26724
9649 | 420.7094 | 26724
9650 | 425.2175 | 26724
9651 | 400.1537 | 26724
9652 | 415.6504 | 26724
9653 | 412.0334 | 26724
9654 | 413.0766 | 26724
9655 | 420.9631 | 26724
9656 | 417.4734 | 26724
9657 | 413.0695 | 26724
9658 | 418.7294 | 26724
9659 | 411.5914 | 26724
9660 | 424.5113 | 26724
9661 | 423.7166 | 26724
9662 | 432.1223 | 26724
9663 | 420.7872 | 26724
9664 | 418.3368 | 26724
9665 | 423.8202 | 26724
9666 | 409.0736 | 26724
9667 | 405.9034 | 26724
9668 | 408.7184 | 26724
9669 | 422.725 | 26724
9670 | 409.5627 | 26724
9671 | 400.4708 | 26724
9672 | 419.9659 | 26724
9673 | 419.0377 | 26724
9674 | 401.7526 | 26724
9675 | 405.3995 | 26724
9676 | 427.7431 | 26724
9677 | 431.2734 | 26724
9678 | 408.1902 | 26724
9679 | 417.9473 | 26724
9680 | 411.4848 | 26724
9681 | 416.2554 | 26724
9682 | 410.8886 | 26724
9683 | 415.3235 | 26724
9684 | 409.8217 | 26724
9685 | 426.3218 | 26724
9686 | 410.2485 | 26724
9687 | 417.345 | 26724
9688 | 408.8272 | 26724
9689 | 419.2382 | 26724
9690 | 427.7544 | 26724
9691 | 423.5628 | 26724
9692 | 420.8049 | 26724
9693 | 427.0923 | 26724
9694 | 426.2618 | 26724
9695 | 401.2224 | 26724
9696 | 416.5041 | 26724
9697 | 409.4234 | 26724
9698 | 401.5583 | 26724
9699 | 432.088 | 26724
9700 | 406.2082 | 26724
9701 | 424.0469 | 26724
9702 | 423.4523 | 26724
9703 | 407.7413 | 26724
9704 | 414.0188 | 26724
9705 | 421.1703 | 26724
9706 | 407.1655 | 26724
9707 | 410.2176 | 26724
9708 | 417.7435 | 26724
9709 | 426.0359 | 26724
9710 | 419.1769 | 26724
9711 | 412.7339 | 26724
9712 | 417.6667 | 26724
9713 | 403.6743 | 26724
9714 | 417.8012 | 26724
9715 | 412.5307 | 26724
9716 | 424.1075 | 26724
9717 | 411.7561 | 26724
9718 | 426.4361 | 26724
9719 | 407.6278 | 26724
9720 | 423.0085 | 26724
9721 | 423.3778 | 26724
9722 | 419.7292 | 26724
9723 | 414.1566 | 26724
9724 | 425.5095 | 26724
9725 | 421.048 | 26724
9726 | 408.2372 | 26724
9727 | 409.5843 | 26724
9728 | 422.9634 | 26724
9729 | 415.7028 | 26724
9730 | 406.0838 | 26724
9731 | 419.3606 | 26724
9732 | 416.7146 | 26724
9733 | 422.3034 | 26724
9734 | 408.2549 | 26724
9735 | 406.9409 | 26724
9736 | 414.7296 | 26724
9737 | 411.1457 | 26724
9738 | 422.9746 | 26724
9739 | 421.9148 | 26724
9740 | 415.704 | 26724
9741 | 400.2221 | 26724
9742 | 411.8639 | 26724
9743 | 412.8406 | 26724
9744 | 415.2291 | 26724
9745 | 421.1436 | 26724
9746 | 422.3455 | 26724
9747 | 424.5246 | 26724
9748 | 413.5466 | 26724
9749 | 413.7281 | 26724
9750 | 407.5531 | 26724
9751 | 422.1707 | 26724
9752 | 417.197 | 26724
9753 | 413.9469 | 26724
9754 | 408.6655 | 26724
9755 | 421.7992 | 26724
9756 | 412.5781 | 26724
9757 | 414.7386 | 26724
9758 | 409.6717 | 26724
9759 | 426.4039 | 26724
9760 | 415.9171 | 26724
9761 | 410.9042 | 26724
9762 | 409.9906 | 26724
9763 | 423.9053 | 26724
9764 | 406.2032 | 26724
9765 | 414.2989 | 26724
9766 | 402.501 | 26724
9767 | 412.4701 | 26724
9768 | 423.9576 | 26724
9769 | 420.9068 | 26724
9770 | 422.9571 | 26724
9771 | 425.5609 | 26724
9772 | 417.0204 | 26724
9773 | 417.9862 | 26724
9774 | 417.9842 | 26724
9775 | 425.6021 | 26724
9776 | 409.0493 | 26724
9777 | 405.6198 | 26724
9778 | 423.1737 | 26724
9779 | 421.049 | 26724
9780 | 428.1994 | 26724
9781 | 403.4008 | 26724
9782 | 407.2001 | 26724
9783 | 404.0616 | 26724
9784 | 414.2177 | 26724
9785 | 404.765 | 26724
9786 | 417.918 | 26724
9787 | 425.7167 | 26724
9788 | 413.7469 | 26724
9789 | 417.3707 | 26724
9790 | 407.4898 | 26724
9791 | 411.9959 | 26724
9792 | 414.9478 | 26724
9793 | 421.7369 | 26724
9794 | 402.5441 | 26724
9795 | 423.5069 | 26724
9796 | 428.9968 | 26724
9797 | 416.8735 | 26724
9798 | 418.5202 | 26724
9799 | 406.0201 | 26724
9800 | 418.1342 | 26724
9801 | 408.1718 | 26724
9802 | 418.7 | 26724
9803 | 427.4914 | 26724
9804 | 424.733 | 26724
9805 | 424.1451 | 26724
9806 | 406.5283 | 26724
9807 | 421.4912 | 26724
9808 | 412.5872 | 26724
9809 | 412.1447 | 26724
9810 | 409.8015 | 26724
9811 | 419.0146 | 26724
9812 | 402.3353 | 26724
9813 | 419.4948 | 26724
9814 | 433.8446 | 26724
9815 | 416.8478 | 26724
9816 | 417.7383 | 26724
9817 | 420.1953 | 26724
9818 | 424.0059 | 26724
9819 | 409.6753 | 26724
9820 | 419.2067 | 26724
9821 | 424.4185 | 26724
9822 | 413.7215 | 26724
9823 | 423.4148 | 26724
9824 | 419.942 | 26724
9825 | 410.1183 | 26724
9826 | 409.5121 | 26724
9827 | 412.4658 | 26724
9828 | 404.7563 | 26724
9829 | 412.6764 | 26724
9830 | 406.3052 | 26724
9831 | 424.0916 | 26724
9832 | 418.3311 | 26724
9833 | 412.9824 | 26724
9834 | 407.2242 | 26724
9835 | 424.1293 | 26724
9836 | 421.5932 | 26724
9837 | 412.8723 | 26724
9838 | 400.0321 | 26724
9839 | 420.3759 | 26724
9840 | 426.6998 | 26724
9841 | 422.8122 | 26724
9842 | 416.0432 | 26724
9843 | 401.8128 | 26724
9844 | 403.3504 | 26724
9845 | 420.7809 | 26724
9846 | 414.3243 | 26724
9847 | 398.4734 | 26724
9848 | 412.6177 | 26724
9849 | 406.0157 | 26724
9850 | 407.8001 | 26724
9851 | 413.3943 | 26724
9852 | 418.1512 | 26724
9853 | 407.0916 | 26724
9854 | 412.6358 | 26724
9855 | 407.8608 | 26724
9856 | 405.7687 | 26724
9857 | 412.0459 | 26724
9858 | 429.9227 | 26724
9859 | 425.0653 | 26724
9860 | 415.3719 | 26724
9861 | 416.1663 | 26724
9862 | 406.0382 | 26724
9863 | 415.0515 | 26724
9864 | 423.2832 | 26724
9865 | 409.0348 | 26724
9866 | 412.3592 | 26724
9867 | 419.4248 | 26724
9868 | 423.8862 | 26724
9869 | 418.6541 | 26724
9870 | 417.1333 | 26724
9871 | 416.5195 | 26724
9872 | 417.6757 | 26724
9873 | 421.9027 | 26724
9874 | 414.4831 | 26724
9875 | 416.1479 | 26724
9876 | 420.9143 | 26724
9877 | 410.0791 | 26724
9878 | 406.9777 | 26724
9879 | 427.6869 | 26724
9880 | 423.5912 | 26724
9881 | 414.4774 | 26724
9882 | 418.437 | 26724
9883 | 412.5783 | 26724
9884 | 423.2965 | 26724
9885 | 415.2665 | 26724
9886 | 424.7106 | 26724
9887 | 415.8917 | 26724
9888 | 413.0565 | 26724
9889 | 402.5141 | 26724
9890 | 403.9935 | 26724
9891 | 427.7145 | 26724
9892 | 421.4786 | 26724
9893 | 426.4755 | 26724
9894 | 416.8026 | 26724
9895 | 402.5067 | 26724
9896 | 414.4523 | 26724
9897 | 429.4237 | 26724
9898 | 425.5558 | 26724
9899 | 412.0965 | 26724
9900 | 395.843 | 26724
9901 | 431.1056 | 26724
9902 | 424.8662 | 26724
9903 | 410.4528 | 26724
9904 | 401.886 | 26724
9905 | 418.2667 | 26724
9906 | 432.3877 | 26724
9907 | 413.9036 | 26724
9908 | 414.5492 | 26724
9909 | 424.7479 | 26724
9910 | 405.0464 | 26724
9911 | 413.0519 | 26724
9912 | 401.6597 | 26724
9913 | 427.1518 | 26724
9914 | 434.8081 | 26724
9915 | 410.6497 | 26724
9916 | 422.7667 | 26724
9917 | 427.1921 | 26724
9918 | 413.3299 | 26724
9919 | 403.5103 | 26724
9920 | 418.6979 | 26724
9921 | 423.829 | 26724
9922 | 409.378 | 26724
9923 | 416.8004 | 26724
9924 | 412.2429 | 26724
9925 | 427.0953 | 26724
9926 | 409.0826 | 26724
9927 | 405.4039 | 26724
9928 | 397.1477 | 26724
9929 | 411.2518 | 26724
9930 | 428.1823 | 26724
9931 | 432.8754 | 26724
9932 | 414.5998 | 26724
9933 | 425.4561 | 26724
9934 | 411.7363 | 26724
9935 | 407.3761 | 26724
9936 | 421.6333 | 26724
9937 | 411.5222 | 26724
9938 | 400.703 | 26724
9939 | 411.836 | 26724
9940 | 420.0255 | 26724
9941 | 423.0064 | 26724
9942 | 413.8442 | 26724
9943 | 419.0338 | 26724
9944 | 411.3052 | 26724
9945 | 429.0287 | 26724
9946 | 414.1178 | 26724
9947 | 424.8645 | 26724
9948 | 409.735 | 26724
9949 | 412.8679 | 26724
9950 | 412.7453 | 26724
9951 | 410.5054 | 26724
9952 | 422.6317 | 26724
9953 | 410.2607 | 26724
9954 | 430.3597 | 26724
9955 | 416.9659 | 26724
9956 | 415.7094 | 26724
9957 | 409.1005 | 26724
9958 | 418.3931 | 26724
9959 | 420.1042 | 26724
9960 | 413.0419 | 26724
9961 | 409.3062 | 26724
9962 | 414.5961 | 26724
9963 | 411.5757 | 26724
9964 | 397.8176 | 26724
9965 | 418.4675 | 26724
9966 | 424.0132 | 26724
9967 | 417.9531 | 26724
9968 | 418.2937 | 26724
9969 | 404.4023 | 26724
9970 | 397.2029 | 26724
9971 | 409.9115 | 26724
9972 | 420.3852 | 26724
9973 | 412.3448 | 26724
9974 | 417.6743 | 26724
9975 | 408.1084 | 26724
9976 | 413.9891 | 26724
9977 | 427.7118 | 26724
9978 | 412.5434 | 26724
9979 | 411.0327 | 26724
9980 | 415.2144 | 26724
9981 | 402.862 | 26724
9982 | 418.2911 | 26724
9983 | 399.8452 | 26724
9984 | 416.1932 | 26724
9985 | 406.4115 | 26724
9986 | 418.9648 | 26724
9987 | 414.1698 | 26724
9988 | 403.0932 | 26724
9989 | 428.7663 | 26724
9990 | 412.6403 | 26724
9991 | 408.487 | 26724
9992 | 417.1293 | 26724
9993 | 413.8244 | 26724
9994 | 415.6491 | 26724
9995 | 410.6289 | 26724
9996 | 414.4247 | 26724
9997 | 416.8614 | 26724
9998 | 409.2403 | 26724
9999 | 403.228 | 26724
10000 | 428.9815 | 26724
10001 | 418.0271 | 26724
10002 | 414.2811 | 26724
10003 | 401.4824 | 26724
10004 | 404.7494 | 26724
10005 | 415.4508 | 26724
10006 | 417.9102 | 26724
10007 | 409.6575 | 26724
10008 | 406.1621 | 26724
10009 | 430.0172 | 26724
10010 | 412.6652 | 26724
10011 | 409.976 | 26724
10012 | 423.2547 | 26724
10013 | 422.6699 | 26724
10014 | 411.458 | 26724
10015 | 415.5634 | 26724
10016 | 406.8774 | 26724
10017 | 408.0903 | 26724
10018 | 412.453 | 26724
10019 | 410.1178 | 26724
10020 | 413.025 | 26724
10021 | 409.1466 | 26724
10022 | 413.3519 | 26724
10023 | 420.5139 | 26724
10024 | 425.231 | 26724
10025 | 425.3903 | 26724
10026 | 431.3665 | 26724
10027 | 420.5204 | 26724
10028 | 430.2244 | 26724
10029 | 420.2893 | 26724
10030 | 423.9585 | 26724
10031 | 406.5758 | 26724
10032 | 426.6794 | 26724
10033 | 422.7316 | 26724
10034 | 416.5448 | 26724
10035 | 410.7745 | 26724
10036 | 436.2409 | 26724
10037 | 429.4147 | 26724
10038 | 421.7687 | 26724
10039 | 412.3082 | 26724
10040 | 421.5112 | 26724
10041 | 429.197 | 26724
10042 | 432.2777 | 26724
10043 | 409.9992 | 26724
10044 | 410.5544 | 26724
10045 | 426.5525 | 26724
10046 | 400.8706 | 26724
10047 | 423.6477 | 26724
10048 | 418.5964 | 26724
10049 | 421.9385 | 26724
10050 | 418.2799 | 26724
10051 | 424.4295 | 26724
10052 | 409.2006 | 26724
10053 | 403.1043 | 26724
10054 | 419.3449 | 26724
10055 | 426.5637 | 26724
10056 | 413.993 | 26724
10057 | 435.802 | 26724
10058 | 406.8169 | 26724
10059 | 417.3348 | 26724
10060 | 421.53 | 26724
10061 | 423.3353 | 26724
10062 | 405.468 | 26724
10063 | 416.1848 | 26724
10064 | 416.3282 | 26724
10065 | 410.1541 | 26724
10066 | 425.1092 | 26724
10067 | 412.797 | 26724
10068 | 415.0455 | 26724
10069 | 418.3945 | 26724
10070 | 416.9692 | 26724
10071 | 406.4718 | 26724
10072 | 408.9067 | 26724
10073 | 397.3232 | 26724
10074 | 403.9907 | 26724
10075 | 416.6945 | 26724
10076 | 421.7782 | 26724
10077 | 406.8427 | 26724
10078 | 413.0193 | 26724
10079 | 426.1932 | 26724
10080 | 428.0351 | 26724
10081 | 411.2261 | 26724
10082 | 416.2709 | 26724
10083 | 412.3309 | 26724
10084 | 427.2261 | 26724
10085 | 403.9768 | 26724
10086 | 410.7431 | 26724
10087 | 421.2798 | 26724
10088 | 405.9139 | 26724
10089 | 417.301 | 26724
10090 | 430.3348 | 26724
10091 | 416.2095 | 26724
10092 | 425.6105 | 26724
10093 | 422.2942 | 26724
10094 | 406.0964 | 26724
10095 | 411.805 | 26724
10096 | 435.2762 | 26724
10097 | 427.3425 | 26724
10098 | 429.2583 | 26724
10099 | 420.6296 | 26724
10100 | 411.604 | 26724
10101 | 400.2574 | 26724
10102 | 421.48 | 26724
10103 | 414.0952 | 26724
10104 | 418.1192 | 26724
10105 | 426.4191 | 26724
10106 | 406.8346 | 26724
10107 | 426.0134 | 26724
10108 | 426.291 | 26724
10109 | 415.7641 | 26724
10110 | 412.2211 | 26724
10111 | 421.8821 | 26724
10112 | 436.2856 | 26724
10113 | 423.7634 | 26724
10114 | 419.2792 | 26724
10115 | 413.4283 | 26724
10116 | 418.5907 | 26724
10117 | 427.5037 | 26724
10118 | 416.623 | 26724
10119 | 407.2926 | 26724
10120 | 402.477 | 26724
10121 | 434.6712 | 26724
10122 | 417.1729 | 26724
10123 | 415.7522 | 26724
10124 | 407.9435 | 26724
10125 | 411.6572 | 26724
10126 | 413.1921 | 26724
10127 | 433.7455 | 26724
10128 | 425.592 | 26724
10129 | 405.0427 | 26724
10130 | 411.9217 | 26724
10131 | 410.9101 | 26724
10132 | 426.7742 | 26724
10133 | 404.0207 | 26724
10134 | 408.5982 | 26724
10135 | 423.8365 | 26724
10136 | 409.8746 | 26724
10137 | 418.6903 | 26724
10138 | 420.6628 | 26724
10139 | 418.7321 | 26724
10140 | 404.8551 | 26724
10141 | 424.5689 | 26724
10142 | 421.5644 | 26724
10143 | 414.519 | 26724
10144 | 416.6931 | 26724
10145 | 413.1836 | 26724
10146 | 418.6355 | 26724
10147 | 420.8927 | 26724
10148 | 412.7161 | 26724
10149 | 431.096 | 26724
10150 | 411.5163 | 26724
10151 | 408.6274 | 26724
10152 | 402.8626 | 26724
10153 | 423.1438 | 26724
10154 | 417.35 | 26724
10155 | 428.4563 | 26724
10156 | 427.4443 | 26724
10157 | 421.7715 | 26724
10158 | 406.6376 | 26724
10159 | 428.0092 | 26724
10160 | 417.3604 | 26724
10161 | 423.2562 | 26724
10162 | 420.5965 | 26724
10163 | 417.999 | 26724
10164 | 417.6462 | 26724
10165 | 410.09 | 26724
10166 | 407.0985 | 26724
10167 | 408.9235 | 26724
10168 | 408.4249 | 26724
10169 | 404.449 | 26724
10170 | 417.2471 | 26724
10171 | 416.1319 | 26724
10172 | 431.1773 | 26724
10173 | 416.2946 | 26724
10174 | 410.5923 | 26724
10175 | 415.8987 | 26724
10176 | 427.3926 | 26724
10177 | 413.8468 | 26724
10178 | 415.9646 | 26724
10179 | 399.7811 | 26724
10180 | 424.7086 | 26724
10181 | 399.4713 | 26724
10182 | 425.3893 | 26724
10183 | 402.1242 | 26724
10184 | 419.2985 | 26724
10185 | 404.976 | 26724
10186 | 406.9901 | 26724
10187 | 412.2231 | 26724
10188 | 416.8928 | 26724
10189 | 423.3396 | 26724
10190 | 409.708 | 26724
10191 | 413.9932 | 26724
10192 | 409.4848 | 26724
10193 | 408.0317 | 26724
10194 | 415.3806 | 26724
10195 | 416.9957 | 26724
10196 | 397.4974 | 26724
10197 | 412.8888 | 26724
10198 | 424.6423 | 26724
10199 | 422.0645 | 26724
10200 | 405.1957 | 26724
10201 | 403.2288 | 26724
10202 | 414.5079 | 26724
10203 | 416.1737 | 26724
10204 | 428.5157 | 26724
10205 | 399.641 | 26724
10206 | 411.9742 | 26724
10207 | 423.8368 | 26724
10208 | 410.535 | 26724
10209 | 413.837 | 26724
10210 | 404.6598 | 26724
10211 | 423.711 | 26724
10212 | 416.3396 | 26724
10213 | 411.6515 | 26724
10214 | 411.575 | 26724
10215 | 422.3555 | 26724
10216 | 411.8505 | 26724
10217 | 406.2894 | 26724
10218 | 417.4963 | 26724
10219 | 419.4194 | 26724
10220 | 420.249 | 26724
10221 | 414.1427 | 26724
10222 | 420.6966 | 26724
10223 | 417.7645 | 26724
10224 | 426.7397 | 26724
10225 | 419.9045 | 26724
10226 | 425.318 | 26724
10227 | 424.2093 | 26724
10228 | 408.3116 | 26724
10229 | 408.8315 | 26724
10230 | 420.5883 | 26724
10231 | 422.0953 | 26724
10232 | 406.6899 | 26724
10233 | 422.8006 | 26724
10234 | 412.9254 | 26724
10235 | 414.6256 | 26724
10236 | 406.2588 | 26724
10237 | 426.1894 | 26724
10238 | 427.2804 | 26724
10239 | 425.7287 | 26724
10240 | 430.8093 | 26724
10241 | 422.5326 | 26724
10242 | 418.2619 | 26724
10243 | 421.7334 | 26724
10244 | 418.1461 | 26724
10245 | 425.2451 | 26724
10246 | 407.6247 | 26724
10247 | 409.0055 | 26724
10248 | 407.9791 | 26724
10249 | 414.6147 | 26724
10250 | 436.672 | 26724
10251 | 412.9075 | 26724
10252 | 422.0619 | 26724
10253 | 414.0216 | 26724
10254 | 424.0426 | 26724
10255 | 415.1917 | 26724
10256 | 412.0188 | 26724
10257 | 421.1836 | 26724
10258 | 426.5786 | 26724
10259 | 416.0847 | 26724
10260 | 423.4676 | 26724
10261 | 425.2697 | 26724
10262 | 411.0455 | 26724
10263 | 428.5636 | 26724
10264 | 417.2282 | 26724
10265 | 409.8369 | 26724
10266 | 408.8407 | 26724
10267 | 416.1206 | 26724
10268 | 424.4243 | 26724
10269 | 423.175 | 26724
10270 | 410.2792 | 26724
10271 | 413.323 | 26724
10272 | 424.6563 | 26724
10273 | 401.3833 | 26724
10274 | 427.1116 | 26724
10275 | 423.5849 | 26724
10276 | 414.7493 | 26724
10277 | 427.7327 | 26724
10278 | 391.2988 | 26724
10279 | 409.7313 | 26724
10280 | 425.9863 | 26724
10281 | 427.7411 | 26724
10282 | 415.1622 | 26724
10283 | 430.2032 | 26724
10284 | 424.5045 | 26724
10285 | 411.4199 | 26724
10286 | 427.153 | 26724
10287 | 415.1755 | 26724
10288 | 412.1232 | 26724
10289 | 416.3082 | 26724
10290 | 437.4691 | 26724
10291 | 416.8236 | 26724
10292 | 414.7692 | 26724
10293 | 420.6664 | 26724
10294 | 405.4352 | 26724
10295 | 418.2875 | 26724
10296 | 423.3056 | 26724
10297 | 423.5617 | 26724
10298 | 430.6211 | 26724
10299 | 400.5204 | 26724
10300 | 416.9567 | 26724
10301 | 428.4838 | 26724
10302 | 419.5995 | 26724
10303 | 419.2153 | 26724
10304 | 408.7554 | 26724
10305 | 416.2765 | 26724
10306 | 421.4055 | 26724
10307 | 414.6323 | 26724
10308 | 418.5734 | 26724
10309 | 406.2009 | 26724
10310 | 415.286 | 26724
10311 | 431.356 | 26724
10312 | 418.627 | 26724
10313 | 419.5871 | 26724
10314 | 422.7547 | 26724
10315 | 428.6775 | 26724
10316 | 427.3126 | 26724
10317 | 409.1907 | 26724
10318 | 426.6748 | 26724
10319 | 426.3568 | 26724
10320 | 411.1692 | 26724
10321 | 426.0516 | 26724
10322 | 412.6935 | 26724
10323 | 413.4159 | 26724
10324 | 401.3342 | 26724
10325 | 408.7681 | 26724
10326 | 415.7128 | 26724
10327 | 414.4917 | 26724
10328 | 426.2878 | 26724
10329 | 407.7417 | 26724
10330 | 415.8646 | 26724
10331 | 403.7077 | 26724
10332 | 411.8908 | 26724
10333 | 425.0303 | 26724
10334 | 406.2452 | 26724
10335 | 418.0783 | 26724
10336 | 406.2443 | 26724
10337 | 423.4882 | 26724
10338 | 415.4491 | 26724
10339 | 421.5823 | 26724
10340 | 414.2858 | 26724
10341 | 409.6724 | 26724
10342 | 410.3095 | 26724
10343 | 420.1354 | 26724
10344 | 420.1449 | 26724
10345 | 417.5772 | 26724
10346 | 401.8566 | 26724
10347 | 425.2657 | 26724
10348 | 423.9773 | 26724
10349 | 423.2347 | 26724
10350 | 404.5537 | 26724
10351 | 417.8311 | 26724
10352 | 420.8475 | 26724
10353 | 419.2911 | 26724
10354 | 423.3644 | 26724
10355 | 420.3185 | 26724
10356 | 421.8065 | 26724
10357 | 431.2492 | 26724
10358 | 417.9757 | 26724
10359 | 412.8804 | 26724
10360 | 416.7036 | 26724
10361 | 422.5219 | 26724
10362 | 410.9176 | 26724
10363 | 417.8455 | 26724
10364 | 404.277 | 26724
10365 | 406.1353 | 26724
10366 | 414.8762 | 26724
10367 | 421.2258 | 26724
10368 | 424.3997 | 26724
10369 | 427.7028 | 26724
10370 | 405.8087 | 26724
10371 | 417.3975 | 26724
10372 | 410.7131 | 26724
10373 | 410.7927 | 26724
10374 | 417.0957 | 26724
10375 | 422.4917 | 26724
10376 | 416.6534 | 26724
10377 | 400.2604 | 26724
10378 | 435.9774 | 26724
10379 | 433.6162 | 26724
10380 | 419.6282 | 26724
10381 | 421.7927 | 26724
10382 | 423.9482 | 26724
10383 | 408.2434 | 26724
10384 | 424.1756 | 26724
10385 | 411.882 | 26724
10386 | 418.4323 | 26724
10387 | 403.259 | 26724
10388 | 424.269 | 26724
10389 | 416.4843 | 26724
10390 | 420.897 | 26724
10391 | 412.5317 | 26724
10392 | 413.5272 | 26724
10393 | 415.1517 | 26724
10394 | 423.3398 | 26724
10395 | 414.768 | 26724
10396 | 411.1935 | 26724
10397 | 427.0852 | 26724
10398 | 412.5 | 26724
10399 | 410.5765 | 26724
10400 | 418.3139 | 26724
10401 | 412.4149 | 26724
10402 | 417.2308 | 26724
10403 | 425.2883 | 26724
10404 | 407.7297 | 26724
10405 | 434.1454 | 26724
10406 | 408.7173 | 26724
10407 | 402.9476 | 26724
10408 | 409.9826 | 26724
10409 | 420.6651 | 26724
10410 | 432.1753 | 26724
10411 | 406.6468 | 26724
10412 | 409.6974 | 26724
10413 | 422.3017 | 26724
10414 | 414.6733 | 26724
10415 | 410.8721 | 26724
10416 | 419.0074 | 26724
10417 | 414.1331 | 26724
10418 | 413.6304 | 26724
10419 | 410.9361 | 26724
10420 | 418.0168 | 26724
10421 | 413.7631 | 26724
10422 | 427.422 | 26724
10423 | 419.8622 | 26724
10424 | 416.8498 | 26724
10425 | 410.9618 | 26724
10426 | 420.963 | 26724
10427 | 413.3644 | 26724
10428 | 412.1327 | 26724
10429 | 411.8484 | 26724
10430 | 413.0406 | 26724
10431 | 419.7883 | 26724
10432 | 400.9652 | 26724
10433 | 431.3588 | 26724
10434 | 421.374 | 26724
10435 | 420.5763 | 26724
10436 | 417.681 | 26724
10437 | 415.9438 | 26724
10438 | 418.2062 | 26724
10439 | 416.2394 | 26724
10440 | 423.8913 | 26724
10441 | 419.9716 | 26724
10442 | 410.9857 | 26724
10443 | 420.0255 | 26724
10444 | 425.9394 | 26724
10445 | 407.1133 | 26724
10446 | 422.0457 | 26724
10447 | 416.7173 | 26724
10448 | 427.4445 | 26724
10449 | 421.7464 | 26724
10450 | 407.608 | 26724
10451 | 404.8063 | 26724
10452 | 417.0498 | 26724
10453 | 413.6772 | 26724
10454 | 426.9447 | 26724
10455 | 411.9718 | 26724
10456 | 404.0814 | 26724
10457 | 430.4462 | 26724
10458 | 414.977 | 26724
10459 | 423.0663 | 26724
10460 | 421.0309 | 26724
10461 | 416.7193 | 26724
10462 | 414.4255 | 26724
10463 | 414.2543 | 26724
10464 | 422.8686 | 26724
10465 | 433.2713 | 26724
10466 | 413.9908 | 26724
10467 | 419.5786 | 26724
10468 | 414.7792 | 26724
10469 | 420.1995 | 26724
10470 | 416.908 | 26724
10471 | 410.2931 | 26724
10472 | 415.3998 | 26724
10473 | 406.8555 | 26724
10474 | 418.3506 | 26724
10475 | 416.4866 | 26724
10476 | 426.8092 | 26724
10477 | 410.6829 | 26724
10478 | 425.4178 | 26724
10479 | 406.5384 | 26724
10480 | 419.1875 | 26724
10481 | 420.8384 | 26724
10482 | 411.6908 | 26724
10483 | 425.4805 | 26724
10484 | 424.0231 | 26724
10485 | 410.7802 | 26724
10486 | 414.4517 | 26724
10487 | 428.4725 | 26724
10488 | 421.2414 | 26724
10489 | 421.3047 | 26724
10490 | 419.204 | 26724
10491 | 416.2148 | 26724
10492 | 411.3127 | 26724
10493 | 421.4658 | 26724
10494 | 421.9079 | 26724
10495 | 423.4461 | 26724
10496 | 419.1814 | 26724
10497 | 417.5427 | 26724
10498 | 404.2811 | 26724
10499 | 411.1832 | 26724
10500 | 419.7911 | 26724
10501 | 415.9683 | 26724
10502 | 411.661 | 26724
10503 | 423.558 | 26724
10504 | 414.875 | 26724
10505 | 414.2407 | 26724
10506 | 400.0594 | 26724
10507 | 409.9074 | 26724
10508 | 415.0668 | 26724
10509 | 413.7805 | 26724
10510 | 408.9061 | 26724
10511 | 417.9943 | 26724
10512 | 416.8152 | 26724
10513 | 414.6027 | 26724
10514 | 425.1226 | 26724
10515 | 434.0864 | 26724
10516 | 418.7136 | 26724
10517 | 424.8517 | 26724
10518 | 415.0139 | 26724
10519 | 411.1482 | 26724
10520 | 417.6535 | 26724
10521 | 411.5012 | 26724
10522 | 424.9809 | 26724
10523 | 405.0855 | 26724
10524 | 404.219 | 26724
10525 | 418.9021 | 26724
10526 | 408.4141 | 26724
10527 | 422.7922 | 26724
10528 | 423.3598 | 26724
10529 | 414.1462 | 26724
10530 | 413.3693 | 26724
10531 | 409.8868 | 26724
10532 | 427.6657 | 26724
10533 | 427.2373 | 26724
10534 | 428.8076 | 26724
10535 | 409.1119 | 26724
10536 | 412.0921 | 26724
10537 | 424.6644 | 26724
10538 | 412.5312 | 26724
10539 | 407.847 | 26724
10540 | 414.7922 | 26724
10541 | 402.2181 | 26724
10542 | 421.6437 | 26724
10543 | 419.4381 | 26724
10544 | 408.954 | 26724
10545 | 405.4587 | 26724
10546 | 419.4711 | 26724
10547 | 410.226 | 26724
10548 | 432.2834 | 26724
10549 | 440.035 | 26724
10550 | 410.5592 | 26724
10551 | 414.6318 | 26724
10552 | 418.4998 | 26724
10553 | 424.5851 | 26724
10554 | 415.3137 | 26724
10555 | 415.5163 | 26724
10556 | 406.7476 | 26724
10557 | 413.967 | 26724
10558 | 413.6752 | 26724
10559 | 418.6881 | 26724
10560 | 421.7066 | 26724
10561 | 408.1425 | 26724
10562 | 436.2906 | 26724
10563 | 406.4653 | 26724
10564 | 415.8574 | 26724
10565 | 425.9847 | 26724
10566 | 411.6715 | 26724
10567 | 408.8673 | 26724
10568 | 416.4631 | 26724
10569 | 407.418 | 26724
10570 | 411.4319 | 26724
10571 | 423.3473 | 26724
10572 | 424.2717 | 26724
10573 | 423.9728 | 26724
10574 | 424.1229 | 26724
10575 | 413.3668 | 26724
10576 | 410.9782 | 26724
10577 | 431.1079 | 26724
10578 | 417.7091 | 26724
10579 | 418.8183 | 26724
10580 | 427.1055 | 26724
10581 | 415.7496 | 26724
10582 | 429.9013 | 26724
10583 | 425.1132 | 26724
10584 | 413.0544 | 26724
10585 | 407.2142 | 26724
10586 | 404.8572 | 26724
10587 | 418.164 | 26724
10588 | 413.7524 | 26724
10589 | 405.0703 | 26724
10590 | 401.7104 | 26724
10591 | 429.9629 | 26724
10592 | 412.1005 | 26724
10593 | 414.6949 | 26724
10594 | 407.3405 | 26724
10595 | 411.8264 | 26724
10596 | 426.1234 | 26724
10597 | 427.9292 | 26724
10598 | 410.6553 | 26724
10599 | 408.1586 | 26724
10600 | 410.5307 | 26724
10601 | 405.0331 | 26724
10602 | 407.1847 | 26724
10603 | 428.0841 | 26724
10604 | 429.3133 | 26724
10605 | 409.8886 | 26724
10606 | 411.1225 | 26724
10607 | 423.9137 | 26724
10608 | 432.4614 | 26724
10609 | 404.1841 | 26724
10610 | 406.8765 | 26724
10611 | 410.1958 | 26724
10612 | 433.063 | 26724
10613 | 403.0614 | 26724
10614 | 405.7682 | 26724
10615 | 415.2058 | 26724
10616 | 416.9898 | 26724
10617 | 424.0359 | 26724
10618 | 417.8866 | 26724
10619 | 408.061 | 26724
10620 | 417.5373 | 26724
10621 | 411.7318 | 26724
10622 | 412.9456 | 26724
10623 | 418.7397 | 26724
10624 | 418.2485 | 26724
10625 | 431.0704 | 26724
10626 | 425.133 | 26724
10627 | 404.4846 | 26724
10628 | 412.1278 | 26724
10629 | 422.7684 | 26724
10630 | 415.6121 | 26724
10631 | 403.4757 | 26724
10632 | 412.5716 | 26724
10633 | 430.154 | 26724
10634 | 419.6004 | 26724
10635 | 404.0488 | 26724
10636 | 435.2803 | 26724
10637 | 428.5576 | 26724
10638 | 438.3081 | 26724
10639 | 427.0289 | 26724
10640 | 424.6192 | 26724
10641 | 429.7972 | 26724
10642 | 425.6472 | 26724
10643 | 409.0793 | 26724
10644 | 415.6349 | 26724
10645 | 423.8295 | 26724
10646 | 416.8354 | 26724
10647 | 406.7931 | 26724
10648 | 411.7353 | 26724
10649 | 424.8841 | 26724
10650 | 419.6935 | 26724
10651 | 422.4044 | 26724
10652 | 425.3268 | 26724
10653 | 407.7981 | 26724
10654 | 400.5279 | 26724
10655 | 414.7799 | 26724
10656 | 432.5722 | 26724
10657 | 405.3032 | 26724
10658 | 415.158 | 26724
10659 | 431.7949 | 26724
10660 | 418.459 | 26724
10661 | 424.5246 | 26724
10662 | 419.7777 | 26724
10663 | 426.2726 | 26724
10664 | 428.49 | 26724
10665 | 422.3009 | 26724
10666 | 418.9464 | 26724
10667 | 410.21 | 26724
10668 | 427.4925 | 26724
10669 | 405.8364 | 26724
10670 | 426.4036 | 26724
10671 | 407.7998 | 26724
10672 | 414.1009 | 26724
10673 | 424.3285 | 26724
10674 | 414.8075 | 26724
10675 | 411.9091 | 26724
10676 | 423.1778 | 26724
10677 | 416.8317 | 26724
10678 | 420.4428 | 26724
10679 | 422.6391 | 26724
10680 | 420.9971 | 26724
10681 | 410.3818 | 26724
10682 | 420.5907 | 26724
10683 | 430.3739 | 26724
10684 | 416.6186 | 26724
10685 | 417.551 | 26724
10686 | 414.5685 | 26724
10687 | 413.4513 | 26724
10688 | 431.5092 | 26724
10689 | 426.3052 | 26724
10690 | 422.5542 | 26724
10691 | 411.6326 | 26724
10692 | 413.776 | 26724
10693 | 410.6352 | 26724
10694 | 406.4207 | 26724
10695 | 416.5862 | 26724
10696 | 429.7573 | 26724
10697 | 418.4297 | 26724
10698 | 417.9808 | 26724
10699 | 409.8869 | 26724
10700 | 417.021 | 26724
10701 | 418.4182 | 26724
10702 | 415.2572 | 26724
10703 | 401.5963 | 26724
10704 | 425.2313 | 26724
10705 | 426.9603 | 26724
10706 | 412.4925 | 26724
10707 | 407.9601 | 26724
10708 | 411.7329 | 26724
10709 | 417.5757 | 26724
10710 | 402.9769 | 26724
10711 | 430.8624 | 26724
10712 | 431.9724 | 26724
10713 | 417.6582 | 26724
10714 | 420.8187 | 26724
10715 | 423.8448 | 26724
10716 | 402.2006 | 26724
10717 | 421.0761 | 26724
10718 | 400.5643 | 26724
10719 | 407.4167 | 26724
10720 | 414.6549 | 26724
10721 | 421.881 | 26724
10722 | 418.7055 | 26724
10723 | 409.2001 | 26724
10724 | 410.1894 | 26724
10725 | 412.8878 | 26724
10726 | 412.7093 | 26724
10727 | 421.6211 | 26724
10728 | 421.2848 | 26724
10729 | 424.6619 | 26724
10730 | 430.6729 | 26724
10731 | 414.0943 | 26724
10732 | 412.1146 | 26724
10733 | 414.921 | 26724
10734 | 413.0776 | 26724
10735 | 415.3079 | 26724
10736 | 408.6247 | 26724
10737 | 417.2046 | 26724
10738 | 427.2618 | 26724
10739 | 417.3168 | 26724
10740 | 407.543 | 26724
10741 | 404.8747 | 26724
10742 | 413.8252 | 26724
10743 | 419.288 | 26724
10744 | 430.9818 | 26724
10745 | 407.2729 | 26724
10746 | 406.09 | 26724
10747 | 426.1804 | 26724
10748 | 427.8188 | 26724
10749 | 421.251 | 26724
10750 | 423.5228 | 26724
10751 | 426.6621 | 26724
10752 | 411.9608 | 26724
10753 | 407.4305 | 26724
10754 | 412.5277 | 26724
10755 | 409.1032 | 26724
10756 | 426.4183 | 26724
10757 | 415.5437 | 26724
10758 | 420.4522 | 26724
10759 | 416.0533 | 26724
10760 | 415.3153 | 26724
10761 | 410.6511 | 26724
10762 | 418.5389 | 26724
10763 | 416.7735 | 26724
10764 | 413.2962 | 26724
10765 | 417.8573 | 26724
10766 | 408.2317 | 26724
10767 | 424.5255 | 26724
10768 | 432.2954 | 26724
10769 | 419.2515 | 26724
10770 | 427.251 | 26724
10771 | 424.1194 | 26724
10772 | 421.4822 | 26724
10773 | 434.0861 | 26724
10774 | 417.1416 | 26724
10775 | 409.5235 | 26724
10776 | 413.8904 | 26724
10777 | 414.8498 | 26724
10778 | 419.6162 | 26724
10779 | 404.3293 | 26724
10780 | 418.9573 | 26724
10781 | 415.457 | 26724
10782 | 413.9144 | 26724
10783 | 420.7981 | 26724
10784 | 426.0687 | 26724
10785 | 431.8926 | 26724
10786 | 408.1056 | 26724
10787 | 420.1204 | 26724
10788 | 414.6831 | 26724
10789 | 423.2967 | 26724
10790 | 416.5131 | 26724
10791 | 432.1481 | 26724
10792 | 418.9483 | 26724
10793 | 415.7335 | 26724
10794 | 425.5861 | 26724
10795 | 421.8509 | 26724
10796 | 411.3245 | 26724
10797 | 423.9419 | 26724
10798 | 423.162 | 26724
10799 | 411.8788 | 26724
10800 | 419.1948 | 26724
10801 | 406.7065 | 26724
10802 | 408.2795 | 26724
10803 | 422.0486 | 26724
10804 | 427.3154 | 26724
10805 | 410.9437 | 26724
10806 | 404.7953 | 26724
10807 | 421.1049 | 26724
10808 | 409.2935 | 26724
10809 | 427.3732 | 26724
10810 | 427.0667 | 26724
10811 | 412.0371 | 26724
10812 | 410.9245 | 26724
10813 | 422.2854 | 26724
10814 | 418.2289 | 26724
10815 | 426.8652 | 26724
10816 | 431.781 | 26724
10817 | 421.3656 | 26724
10818 | 421.3815 | 26724
10819 | 411.084 | 26724
10820 | 411.8629 | 26724
10821 | 412.9084 | 26724
10822 | 418.0508 | 26724
10823 | 412.6714 | 26724
10824 | 418.1157 | 26724
10825 | 419.7658 | 26724
10826 | 415.8589 | 26724
10827 | 413.6011 | 26724
10828 | 416.3036 | 26724
10829 | 417.1045 | 26724
10830 | 414.4547 | 26724
10831 | 420.2448 | 26724
10832 | 402.046 | 26724
10833 | 398.2181 | 26724
10834 | 409.1128 | 26724
10835 | 425.1502 | 26724
10836 | 416.7025 | 26724
10837 | 409.5028 | 26724
10838 | 429.4603 | 26724
10839 | 418.293 | 26724
10840 | 420.9812 | 26724
10841 | 421.6943 | 26724
10842 | 413.9048 | 26724
10843 | 418.0566 | 26724
10844 | 418.7366 | 26724
10845 | 416.5441 | 26724
10846 | 404.7119 | 26724
10847 | 408.7888 | 26724
10848 | 410.2253 | 26724
10849 | 418.758 | 26724
10850 | 411.3484 | 26724
10851 | 416.9512 | 26724
10852 | 418.911 | 26724
10853 | 419.8506 | 26724
10854 | 417.1605 | 26724
10855 | 426.3771 | 26724
10856 | 419.5866 | 26724
10857 | 424.662 | 26724
10858 | 424.4123 | 26724
10859 | 415.0741 | 26724
10860 | 417.77 | 26724
10861 | 416.8565 | 26724
10862 | 405.1791 | 26724
10863 | 420.6553 | 26724
10864 | 420.7963 | 26724
10865 | 410.7773 | 26724
10866 | 414.2085 | 26724
10867 | 413.1072 | 26724
10868 | 401.7896 | 26724
10869 | 406.8721 | 26724
10870 | 416.2045 | 26724
10871 | 417.2218 | 26724
10872 | 403.7636 | 26724
10873 | 415.0222 | 26724
10874 | 404.0871 | 26724
10875 | 420.4541 | 26724
10876 | 418.7305 | 26724
10877 | 410.9801 | 26724
10878 | 417.7976 | 26724
10879 | 403.1966 | 26724
10880 | 429.0258 | 26724
10881 | 416.8122 | 26724
10882 | 425 | 26724
10883 | 427.6071 | 26724
10884 | 419.766 | 26724
10885 | 406.0326 | 26724
10886 | 430.2682 | 26724
10887 | 424.344 | 26724
10888 | 421.69 | 26724
10889 | 414.1601 | 26724
10890 | 416.8847 | 26724
10891 | 421.5191 | 26724
10892 | 410.5826 | 26724
10893 | 423.6011 | 26724
10894 | 418.9424 | 26724
10895 | 424.7808 | 26724
10896 | 415.8188 | 26724
10897 | 431.812 | 26724
10898 | 408.4986 | 26724
10899 | 417.7532 | 26724
10900 | 415.9139 | 26724
10901 | 398.4999 | 26724
10902 | 400.1844 | 26724
10903 | 431.7846 | 26724
10904 | 418.7919 | 26724
10905 | 421.8508 | 26724
10906 | 409.4869 | 26724
10907 | 414.8505 | 26724
10908 | 412.6381 | 26724
10909 | 397.0994 | 26724
10910 | 417.186 | 26724
10911 | 421.2879 | 26724
10912 | 416.4547 | 26724
10913 | 417.8025 | 26724
10914 | 405.4686 | 26724
10915 | 419.204 | 26724
10916 | 417.7626 | 26724
10917 | 410.601 | 26724
10918 | 407.7204 | 26724
10919 | 405.6429 | 26724
10920 | 430.8078 | 26724
10921 | 427.542 | 26724
10922 | 401.2824 | 26724
10923 | 403.844 | 26724
10924 | 413.7925 | 26724
10925 | 427.4425 | 26724
10926 | 417.1821 | 26724
10927 | 415.2927 | 26724
10928 | 413.4123 | 26724
10929 | 419.9152 | 26724
10930 | 434.7892 | 26724
10931 | 421.2276 | 26724
10932 | 420.361 | 26724
10933 | 421.2034 | 26724
10934 | 432.9683 | 26724
10935 | 420.6404 | 26724
10936 | 417.3391 | 26724
10937 | 425.1235 | 26724
10938 | 414.0249 | 26724
10939 | 421.5572 | 26724
10940 | 404.4459 | 26724
10941 | 408.5014 | 26724
10942 | 419.0622 | 26724
10943 | 403.6564 | 26724
10944 | 414.7807 | 26724
10945 | 400.4986 | 26724
10946 | 403.5987 | 26724
10947 | 400.9166 | 26724
10948 | 407.6519 | 26724
10949 | 427.2216 | 26724
10950 | 417.0384 | 26724
10951 | 415.231 | 26724
10952 | 417.5175 | 26724
10953 | 417.5913 | 26724
10954 | 423.6194 | 26724
10955 | 417.028 | 26724
10956 | 427.3128 | 26724
10957 | 422.4763 | 26724
10958 | 423.1143 | 26724
10959 | 412.6587 | 26724
10960 | 406.8648 | 26724
10961 | 412.4274 | 26724
10962 | 411.7954 | 26724
10963 | 404.103 | 26724
10964 | 414.0997 | 26724
10965 | 426.4617 | 26724
10966 | 406.8651 | 26724
10967 | 404.388 | 26724
10968 | 398.0186 | 26724
10969 | 429.4794 | 26724
10970 | 429.5844 | 26724
10971 | 422.1314 | 26724
10972 | 411.8595 | 26724
10973 | 421.7546 | 26724
10974 | 402.7281 | 26724
10975 | 412.6468 | 26724
10976 | 407.036 | 26724
10977 | 416.034 | 26724
10978 | 411.3514 | 26724
10979 | 414.5508 | 26724
10980 | 417.7845 | 26724
10981 | 409.6206 | 26724
10982 | 422.8762 | 26724
10983 | 416.9252 | 26724
10984 | 413.8494 | 26724
10985 | 409.1989 | 26724
10986 | 402.2667 | 26724
10987 | 411.5546 | 26724
10988 | 416.6881 | 26724
10989 | 399.1931 | 26724
10990 | 413.7546 | 26724
10991 | 407.3413 | 26724
10992 | 419.0209 | 26724
10993 | 411.7194 | 26724
10994 | 408.0035 | 26724
10995 | 408.2352 | 26724
10996 | 412.4805 | 26724
10997 | 421.3461 | 26724
10998 | 409.6784 | 26724
10999 | 408.326 | 26724
11000 | 415.3834 | 26724
11001 | 416.0392 | 26724
11002 | 421.4141 | 26724
11003 | 413.5247 | 26724
11004 | 410.7731 | 26724
11005 | 415.8406 | 26724
11006 | 419.2586 | 26724
11007 | 413.8378 | 26724
11008 | 415.3741 | 26724
11009 | 430.7411 | 26724
11010 | 422.567 | 26724
11011 | 410.1632 | 26724
11012 | 418.3536 | 26724
11013 | 418.1141 | 26724
11014 | 410.297 | 26724
11015 | 410.2413 | 26724
11016 | 411.2487 | 26724
11017 | 405.0339 | 26724
11018 | 414.9803 | 26724
11019 | 403.2506 | 26724
11020 | 412.1839 | 26724
11021 | 431.6965 | 26724
11022 | 425.4267 | 26724
11023 | 416.5429 | 26724
11024 | 411.6234 | 26724
11025 | 420.6288 | 26724
11026 | 410.5558 | 26724
11027 | 421.5147 | 26724
11028 | 419.9654 | 26724
11029 | 410.2512 | 26724
11030 | 431.406 | 26724
11031 | 410.3737 | 26724
11032 | 408.9062 | 26724
11033 | 415.2009 | 26724
11034 | 423.6245 | 26724
11035 | 421.6647 | 26724
11036 | 413.1771 | 26724
11037 | 413.462 | 26724
11038 | 413.2367 | 26724
11039 | 413.3434 | 26724
11040 | 406.009 | 26724
11041 | 410.2408 | 26724
11042 | 416.5384 | 26724
11043 | 404.6204 | 26724
11044 | 419.0312 | 26724
11045 | 401.0861 | 26724
11046 | 424.4257 | 26724
11047 | 409.719 | 26724
11048 | 419.0737 | 26724
11049 | 421.6353 | 26724
11050 | 420.8495 | 26724
11051 | 409.7255 | 26724
11052 | 417.3609 | 26724
11053 | 418.1493 | 26724
11054 | 412.6261 | 26724
11055 | 419.5695 | 26724
11056 | 414.8374 | 26724
11057 | 424.2858 | 26724
11058 | 416.8265 | 26724
11059 | 424.1355 | 26724
11060 | 415.091 | 26724
11061 | 411.8695 | 26724
11062 | 404.4451 | 26724
11063 | 405.8548 | 26724
11064 | 423.3959 | 26724
11065 | 405.3516 | 26724
11066 | 415.9144 | 26724
11067 | 414.2183 | 26724
11068 | 425.4375 | 26724
11069 | 409.7062 | 26724
11070 | 403.588 | 26724
11071 | 402.2721 | 26724
11072 | 409.0888 | 26724
11073 | 427.9508 | 26724
11074 | 415.3589 | 26724
11075 | 414.2528 | 26724
11076 | 408.1198 | 26724
11077 | 402.7772 | 26724
11078 | 419.0253 | 26724
11079 | 418.7347 | 26724
11080 | 404.4878 | 26724
11081 | 418.5755 | 26724
11082 | 425.6945 | 26724
11083 | 415.325 | 26724
11084 | 421.9384 | 26724
11085 | 419.9164 | 26724
11086 | 394.0558 | 26724
11087 | 410.8353 | 26724
11088 | 407.5327 | 26724
11089 | 429.8451 | 26724
11090 | 407.4547 | 26724
11091 | 416.8085 | 26724
11092 | 409.6103 | 26724
11093 | 406.8039 | 26724
11094 | 408.1045 | 26724
11095 | 408.848 | 26724
11096 | 425.0327 | 26724
11097 | 420.308 | 26724
11098 | 421.9116 | 26724
11099 | 413.6411 | 26724
11100 | 431.9032 | 26724
11101 | 416.5608 | 26724
11102 | 410.6399 | 26724
11103 | 424.8524 | 26724
11104 | 417.6128 | 26724
11105 | 407.7008 | 26724
11106 | 420.2458 | 26724
11107 | 409.879 | 26724
11108 | 417.6717 | 26724
11109 | 409.9528 | 26724
11110 | 426.8311 | 26724
11111 | 426.1531 | 26724
11112 | 415.53 | 26724
11113 | 414.5541 | 26724
11114 | 415.0271 | 26724
11115 | 405.8977 | 26724
11116 | 414.3065 | 26724
11117 | 423.5588 | 26724
11118 | 425.7519 | 26724
11119 | 406.3121 | 26724
11120 | 431.844 | 26724
11121 | 425.9315 | 26724
11122 | 424.4951 | 26724
11123 | 410.8799 | 26724
11124 | 409.4551 | 26724
11125 | 416.9244 | 26724
11126 | 415.5625 | 26724
11127 | 431.1627 | 26724
11128 | 426.9605 | 26724
11129 | 433.2352 | 26724
11130 | 423.4477 | 26724
11131 | 414.0374 | 26724
11132 | 412.9869 | 26724
11133 | 411.6918 | 26724
11134 | 407.0284 | 26724
11135 | 426.6636 | 26724
11136 | 400.5348 | 26724
11137 | 411.9962 | 26724
11138 | 420.0926 | 26724
11139 | 412.1095 | 26724
11140 | 415.883 | 26724
11141 | 407.0194 | 26724
11142 | 414.2054 | 26724
11143 | 430.4616 | 26724
11144 | 410.9845 | 26724
11145 | 418.6701 | 26724
11146 | 422.7529 | 26724
11147 | 412.0089 | 26724
11148 | 417.3348 | 26724
11149 | 416.2408 | 26724
11150 | 414.53 | 26724
11151 | 412.6671 | 26724
11152 | 420.455 | 26724
11153 | 412.8836 | 26724
11154 | 420.2939 | 26724
11155 | 426.5303 | 26724
11156 | 425.943 | 26724
11157 | 412.2969 | 26724
11158 | 428.461 | 26724
11159 | 425.41 | 26724
11160 | 408.9593 | 26724
11161 | 418.8626 | 26724
11162 | 413.24 | 26724
11163 | 428.0606 | 26724
11164 | 408.1164 | 26724
11165 | 420.2789 | 26724
11166 | 419.8665 | 26724
11167 | 401.0618 | 26724
11168 | 411.0442 | 26724
11169 | 416.285 | 26724
11170 | 423.5594 | 26724
11171 | 401.3627 | 26724
11172 | 432.9957 | 26724
11173 | 415.0145 | 26724
11174 | 413.7425 | 26724
11175 | 413.6521 | 26724
11176 | 413.2993 | 26724
11177 | 425.5801 | 26724
11178 | 414.155 | 26724
11179 | 412.1417 | 26724
11180 | 411.1893 | 26724
11181 | 429.2461 | 26724
11182 | 421.7609 | 26724
11183 | 421.6763 | 26724
11184 | 432.0499 | 26724
11185 | 410.334 | 26724
11186 | 412.6534 | 26724
11187 | 405.4281 | 26724
11188 | 410.8419 | 26724
11189 | 404.1903 | 26724
11190 | 422.0103 | 26724
11191 | 418.2007 | 26724
11192 | 407.228 | 26724
11193 | 422.6155 | 26724
11194 | 413.9466 | 26724
11195 | 416.6952 | 26724
11196 | 405.8711 | 26724
11197 | 426.0119 | 26724
11198 | 413.0446 | 26724
11199 | 414.0307 | 26724
11200 | 424.0562 | 26724
11201 | 408.6964 | 26724
11202 | 414.7694 | 26724
11203 | 416.9221 | 26724
11204 | 429.4542 | 26724
11205 | 407.6896 | 26724
11206 | 417.5698 | 26724
11207 | 417.8666 | 26724
11208 | 418.4938 | 26724
11209 | 421.7844 | 26724
11210 | 409.7412 | 26724
11211 | 417.6317 | 26724
11212 | 412.3024 | 26724
11213 | 424.6926 | 26724
11214 | 417.4297 | 26724
11215 | 406.9336 | 26724
11216 | 425.8367 | 26724
11217 | 423.1035 | 26724
11218 | 427.8711 | 26724
11219 | 415.6473 | 26724
11220 | 422.7499 | 26724
11221 | 425.3437 | 26724
11222 | 412.0307 | 26724
11223 | 412.0566 | 26724
11224 | 413.6078 | 26724
11225 | 405.6003 | 26724
11226 | 414.4041 | 26724
11227 | 436.5734 | 26724
11228 | 420.1706 | 26724
11229 | 403.1242 | 26724
11230 | 423.6124 | 26724
11231 | 426.4904 | 26724
11232 | 422.8019 | 26724
11233 | 415.4103 | 26724
11234 | 423.1752 | 26724
11235 | 427.6581 | 26724
11236 | 407.5234 | 26724
11237 | 424.3809 | 26724
11238 | 419.2729 | 26724
11239 | 422.8782 | 26724
11240 | 413.2238 | 26724
11241 | 435.7299 | 26724
11242 | 408.8864 | 26724
11243 | 409.5164 | 26724
11244 | 396.6145 | 26724
11245 | 418.2046 | 26724
11246 | 408.3652 | 26724
11247 | 420.1102 | 26724
11248 | 421.9626 | 26724
11249 | 404.343 | 26724
11250 | 405.7453 | 26724
11251 | 422.6206 | 26724
11252 | 417.78 | 26724
11253 | 412.8385 | 26724
11254 | 419.789 | 26724
11255 | 408.6288 | 26724
11256 | 434.4732 | 26724
11257 | 417.1713 | 26724
11258 | 425.2423 | 26724
11259 | 416.8558 | 26724
11260 | 425.4762 | 26724
11261 | 404.1983 | 26724
11262 | 405.2505 | 26724
11263 | 414.6955 | 26724
11264 | 408.309 | 26724
11265 | 408.6348 | 26724
11266 | 425.9375 | 26724
11267 | 420.7495 | 26724
11268 | 427.4562 | 26724
11269 | 420.0895 | 26724
11270 | 421.844 | 26724
11271 | 423.3093 | 26724
11272 | 408.9163 | 26724
11273 | 405.7472 | 26724
11274 | 422.0161 | 26724
11275 | 413.0823 | 26724
11276 | 420.6806 | 26724
11277 | 414.8083 | 26724
11278 | 417.6629 | 26724
11279 | 403.4473 | 26724
11280 | 429.7441 | 26724
11281 | 428.4853 | 26724
11282 | 422.3915 | 26724
11283 | 427.004 | 26724
11284 | 410.4646 | 26724
11285 | 404.1008 | 26724
11286 | 416.4243 | 26724
11287 | 414.5016 | 26724
11288 | 408.9381 | 26724
11289 | 415.7375 | 26724
11290 | 411.1273 | 26724
11291 | 430.194 | 26724
11292 | 409.626 | 26724
11293 | 418.0451 | 26724
11294 | 407.2421 | 26724
11295 | 409.0218 | 26724
11296 | 416.7274 | 26724
11297 | 411.3628 | 26724
11298 | 408.9461 | 26724
11299 | 416.1146 | 26724
11300 | 414.9331 | 26724
11301 | 425.999 | 26724
11302 | 403.9747 | 26724
11303 | 408.4188 | 26724
11304 | 408.362 | 26724
11305 | 401.5005 | 26724
11306 | 419.259 | 26724
11307 | 412.6005 | 26724
11308 | 416.4945 | 26724
11309 | 426.8365 | 26724
11310 | 421.0107 | 26724
11311 | 406.7326 | 26724
11312 | 412.7975 | 26724
11313 | 414.6392 | 26724
11314 | 423.264 | 26724
11315 | 413.973 | 26724
11316 | 419.7813 | 26724
11317 | 415.5179 | 26724
11318 | 419.5613 | 26724
11319 | 418.4841 | 26724
11320 | 419.0524 | 26724
11321 | 419.3516 | 26724
11322 | 411.8989 | 26724
11323 | 419.721 | 26724
11324 | 404.0606 | 26724
11325 | 422.7747 | 26724
11326 | 421.3938 | 26724
11327 | 411.2371 | 26724
11328 | 417.0981 | 26724
11329 | 424.0951 | 26724
11330 | 422.8656 | 26724
11331 | 421.5249 | 26724
11332 | 412.9289 | 26724
11333 | 415.3964 | 26724
11334 | 406.492 | 26724
11335 | 407.0418 | 26724
11336 | 422.7393 | 26724
11337 | 420.0538 | 26724
11338 | 413.9382 | 26724
11339 | 416.8428 | 26724
11340 | 406.0468 | 26724
11341 | 420.0681 | 26724
11342 | 401.3815 | 26724
11343 | 425.817 | 26724
11344 | 417.2332 | 26724
11345 | 424.2574 | 26724
11346 | 413.2516 | 26724
11347 | 417.9442 | 26724
11348 | 421.1373 | 26724
11349 | 421.0061 | 26724
11350 | 415.4615 | 26724
11351 | 414.2447 | 26724
11352 | 409.5304 | 26724
11353 | 423.9943 | 26724
11354 | 400.5792 | 26724
11355 | 418.6944 | 26724
11356 | 412.1778 | 26724
11357 | 413.0578 | 26724
11358 | 416.3521 | 26724
11359 | 419.6597 | 26724
11360 | 422.5682 | 26724
11361 | 405.6316 | 26724
11362 | 427.3369 | 26724
11363 | 407.5082 | 26724
11364 | 422.9036 | 26724
11365 | 412.93 | 26724
11366 | 414.1273 | 26724
11367 | 413.1731 | 26724
11368 | 411.5774 | 26724
11369 | 420.9805 | 26724
11370 | 420.4095 | 26724
11371 | 406.8386 | 26724
11372 | 418.3585 | 26724
11373 | 411.4722 | 26724
11374 | 422.1847 | 26724
11375 | 419.2349 | 26724
11376 | 413.119 | 26724
11377 | 421.3424 | 26724
11378 | 425.3077 | 26724
11379 | 425.4457 | 26724
11380 | 418.9167 | 26724
11381 | 405.1483 | 26724
11382 | 422.1287 | 26724
11383 | 426.3255 | 26724
11384 | 415.6034 | 26724
11385 | 413.756 | 26724
11386 | 429.1613 | 26724
11387 | 426.4173 | 26724
11388 | 409.1025 | 26724
11389 | 411.8687 | 26724
11390 | 414.5787 | 26724
11391 | 424.806 | 26724
11392 | 422.3996 | 26724
11393 | 416.1012 | 26724
11394 | 412.3459 | 26724
11395 | 420.9447 | 26724
11396 | 422.3449 | 26724
11397 | 418.0492 | 26724
11398 | 429.0847 | 26724
11399 | 422.1239 | 26724
11400 | 415.2282 | 26724
11401 | 413.0909 | 26724
11402 | 416.0956 | 26724
11403 | 412.6305 | 26724
11404 | 416.2038 | 26724
11405 | 408.7998 | 26724
11406 | 439.5214 | 26724
11407 | 413.1406 | 26724
11408 | 403.4945 | 26724
11409 | 409.1885 | 26724
11410 | 413.2545 | 26724
11411 | 425.8506 | 26724
11412 | 427.3473 | 26724
11413 | 418.9183 | 26724
11414 | 407.7724 | 26724
11415 | 408.4972 | 26724
11416 | 413.4051 | 26724
11417 | 410.3208 | 26724
11418 | 428.6141 | 26724
11419 | 421.4437 | 26724
11420 | 400.7167 | 26724
11421 | 426.4463 | 26724
11422 | 422.2381 | 26724
11423 | 429.6871 | 26724
11424 | 414.3245 | 26724
11425 | 434.1637 | 26724
11426 | 430.5387 | 26724
11427 | 407.4293 | 26724
11428 | 402.5095 | 26724
11429 | 433.0718 | 26724
11430 | 423.6015 | 26724
11431 | 421.7007 | 26724
11432 | 419.0951 | 26724
11433 | 404.4205 | 26724
11434 | 428.3711 | 26724
11435 | 425.1584 | 26724
11436 | 416.4114 | 26724
11437 | 420.0739 | 26724
11438 | 422.371 | 26724
11439 | 419.5419 | 26724
11440 | 413.141 | 26724
11441 | 419.0728 | 26724
11442 | 414.2878 | 26724
11443 | 430.5076 | 26724
11444 | 408.9407 | 26724
11445 | 409.3621 | 26724
11446 | 404.5017 | 26724
11447 | 412.4385 | 26724
11448 | 414.7478 | 26724
11449 | 414.5353 | 26724
11450 | 426.4177 | 26724
11451 | 411.5408 | 26724
11452 | 399.762 | 26724
11453 | 422.6485 | 26724
11454 | 434.2953 | 26724
11455 | 408.845 | 26724
11456 | 418.2634 | 26724
11457 | 422.3973 | 26724
11458 | 441.4732 | 26724
11459 | 416.39 | 26724
11460 | 395.6487 | 26724
11461 | 419.1461 | 26724
11462 | 404.8516 | 26724
11463 | 409.1898 | 26724
11464 | 403.8279 | 26724
11465 | 409.9538 | 26724
11466 | 414.7571 | 26724
11467 | 404.1847 | 26724
11468 | 412.9065 | 26724
11469 | 414.5865 | 26724
11470 | 410.7895 | 26724
11471 | 414.4554 | 26724
11472 | 418.4045 | 26724
11473 | 408.7182 | 26724
11474 | 413.1559 | 26724
11475 | 424.1019 | 26724
11476 | 409.4251 | 26724
11477 | 417.942 | 26724
11478 | 412.7469 | 26724
11479 | 412.1372 | 26724
11480 | 407.3835 | 26724
11481 | 413.681 | 26724
11482 | 390.8856 | 26724
11483 | 425.8345 | 26724
11484 | 414.55 | 26724
11485 | 418.8771 | 26724
11486 | 425.5374 | 26724
11487 | 398.3111 | 26724
11488 | 413.9369 | 26724
11489 | 406.8558 | 26724
11490 | 413.504 | 26724
11491 | 426.2107 | 26724
11492 | 417.3202 | 26724
11493 | 415.2855 | 26724
11494 | 428.8971 | 26724
11495 | 420.2088 | 26724
11496 | 413.4449 | 26724
11497 | 416.4879 | 26724
11498 | 420.0023 | 26724
11499 | 406.7011 | 26724
11500 | 419.6061 | 26724
11501 | 412.5235 | 26724
11502 | 423.7629 | 26724
11503 | 414.251 | 26724
11504 | 428.1127 | 26724
11505 | 420.7117 | 26724
11506 | 413.6991 | 26724
11507 | 423.7266 | 26724
11508 | 416.282 | 26724
11509 | 431.9416 | 26724
11510 | 410.8816 | 26724
11511 | 412.5235 | 26724
11512 | 411.748 | 26724
11513 | 432.5716 | 26724
11514 | 427.8378 | 26724
11515 | 420.2793 | 26724
11516 | 414.7161 | 26724
11517 | 405.7787 | 26724
11518 | 411.9555 | 26724
11519 | 424.287 | 26724
11520 | 425.7778 | 26724
11521 | 424.2302 | 26724
11522 | 410.0209 | 26724
11523 | 430.5228 | 26724
11524 | 409.3456 | 26724
11525 | 430.4178 | 26724
11526 | 418.3713 | 26724
11527 | 432.2616 | 26724
11528 | 421.885 | 26724
11529 | 425.6034 | 26724
11530 | 407.1233 | 26724
11531 | 417.6648 | 26724
11532 | 409.9945 | 26724
11533 | 418.8628 | 26724
11534 | 433.196 | 26724
11535 | 429.891 | 26724
11536 | 422.01 | 26724
11537 | 401.9439 | 26724
11538 | 411.9241 | 26724
11539 | 404.8233 | 26724
11540 | 402.3339 | 26724
11541 | 403.0281 | 26724
11542 | 404.4295 | 26724
11543 | 425.1166 | 26724
11544 | 421.9922 | 26724
11545 | 406.5119 | 26724
11546 | 418.2807 | 26724
11547 | 408.842 | 26724
11548 | 406.7683 | 26724
11549 | 421.9959 | 26724
11550 | 418.8121 | 26724
11551 | 413.2927 | 26724
11552 | 429.5134 | 26724
11553 | 419.1365 | 26724
11554 | 414.8156 | 26724
11555 | 399.9209 | 26724
11556 | 421.3255 | 26724
11557 | 416.6744 | 26724
11558 | 410.9684 | 26724
11559 | 416.4777 | 26724
11560 | 414.4352 | 26724
11561 | 413.5697 | 26724
11562 | 411.0156 | 26724
11563 | 412.0845 | 26724
11564 | 427.7452 | 26724
11565 | 409.4061 | 26724
11566 | 416.3345 | 26724
11567 | 415.2955 | 26724
11568 | 417.6162 | 26724
11569 | 423.9669 | 26724
11570 | 418.151 | 26724
11571 | 406.5034 | 26724
11572 | 428.7496 | 26724
11573 | 416.0105 | 26724
11574 | 402.2699 | 26724
11575 | 404.1004 | 26724
11576 | 417.2542 | 26724
11577 | 422.5132 | 26724
11578 | 419.9913 | 26724
11579 | 411.2533 | 26724
11580 | 414.6084 | 26724
11581 | 420.4555 | 26724
11582 | 413.8091 | 26724
11583 | 413.4205 | 26724
11584 | 402.501 | 26724
11585 | 429.6226 | 26724
11586 | 408.7212 | 26724
11587 | 411.3246 | 26724
11588 | 416.1316 | 26724
11589 | 409.5256 | 26724
11590 | 425.0752 | 26724
11591 | 426.4935 | 26724
11592 | 410.8039 | 26724
11593 | 417.1684 | 26724
11594 | 421.6363 | 26724
11595 | 417.7065 | 26724
11596 | 419.7479 | 26724
11597 | 413.3669 | 26724
11598 | 422.0089 | 26724
11599 | 409.0128 | 26724
11600 | 422.3121 | 26724
11601 | 411.7704 | 26724
11602 | 411.6918 | 26724
11603 | 409.4351 | 26724
11604 | 404.4121 | 26724
11605 | 432.039 | 26724
11606 | 408.2981 | 26724
11607 | 416.1167 | 26724
11608 | 412.6146 | 26724
11609 | 419.318 | 26724
11610 | 414.8838 | 26724
11611 | 421.9233 | 26724
11612 | 413.5415 | 26724
11613 | 428.1705 | 26724
11614 | 421.6892 | 26724
11615 | 408.1303 | 26724
11616 | 418.0814 | 26724
11617 | 425.034 | 26724
11618 | 421.321 | 26724
11619 | 417.7432 | 26724
11620 | 423.1004 | 26724
11621 | 418.8122 | 26724
11622 | 425.2648 | 26724
11623 | 428.1281 | 26724
11624 | 423.6675 | 26724
11625 | 429.1349 | 26724
11626 | 413.0137 | 26724
11627 | 418.0597 | 26724
11628 | 424.309 | 26724
11629 | 410.0375 | 26724
11630 | 422.4953 | 26724
11631 | 405.3384 | 26724
11632 | 414.8229 | 26724
11633 | 404.4902 | 26724
11634 | 427.615 | 26724
11635 | 402.8132 | 26724
11636 | 419.9163 | 26724
11637 | 431.3724 | 26724
11638 | 424.0015 | 26724
11639 | 413.5927 | 26724
11640 | 410.8224 | 26724
11641 | 421.5386 | 26724
11642 | 422.1724 | 26724
11643 | 423.4024 | 26724
11644 | 427.2804 | 26724
11645 | 431.9047 | 26724
11646 | 419.1337 | 26724
11647 | 420.3574 | 26724
11648 | 409.4609 | 26724
11649 | 410.0568 | 26724
11650 | 425.4818 | 26724
11651 | 414.4697 | 26724
11652 | 422.6778 | 26724
11653 | 420.6086 | 26724
11654 | 429.3061 | 26724
11655 | 414.4922 | 26724
11656 | 415.4658 | 26724
11657 | 404.2884 | 26724
11658 | 410.4018 | 26724
11659 | 408.2494 | 26724
11660 | 412.0354 | 26724
11661 | 432.5989 | 26724
11662 | 419.8452 | 26724
11663 | 423.0945 | 26724
11664 | 406.2498 | 26724
11665 | 402.4486 | 26724
11666 | 406.6891 | 26724
11667 | 412.3436 | 26724
11668 | 417.8931 | 26724
11669 | 407.9567 | 26724
11670 | 414.0868 | 26724
11671 | 415.228 | 26724
11672 | 425.7954 | 26724
11673 | 423.2692 | 26724
11674 | 408.6581 | 26724
11675 | 419.7329 | 26724
11676 | 422.5951 | 26724
11677 | 414.9527 | 26724
11678 | 413.2294 | 26724
11679 | 413.0699 | 26724
11680 | 411.8977 | 26724
11681 | 415.9295 | 26724
11682 | 404.635 | 26724
11683 | 417.6097 | 26724
11684 | 424.4145 | 26724
11685 | 423.0492 | 26724
11686 | 403.8838 | 26724
11687 | 406.8271 | 26724
11688 | 416.1599 | 26724
11689 | 413.1473 | 26724
11690 | 407.4419 | 26724
11691 | 422.8929 | 26724
11692 | 407.0705 | 26724
11693 | 423.9306 | 26724
11694 | 410.8847 | 26724
11695 | 420.3337 | 26724
11696 | 418.9329 | 26724
11697 | 427.4744 | 26724
11698 | 417.4524 | 26724
11699 | 416.6303 | 26724
11700 | 404.4005 | 26724
11701 | 415.7816 | 26724
11702 | 417.9615 | 26724
11703 | 420.9258 | 26724
11704 | 411.98 | 26724
11705 | 401.3301 | 26724
11706 | 412.8101 | 26724
11707 | 426.1327 | 26724
11708 | 409.3725 | 26724
11709 | 407.3188 | 26724
11710 | 423.6138 | 26724
11711 | 427.582 | 26724
11712 | 426.6701 | 26724
11713 | 423.1744 | 26724
11714 | 418.3063 | 26724
11715 | 423.4936 | 26724
11716 | 417.3327 | 26724
11717 | 426.1696 | 26724
11718 | 417.8704 | 26724
11719 | 436.2786 | 26724
11720 | 414.8707 | 26724
11721 | 412.2747 | 26724
11722 | 404.8152 | 26724
11723 | 407.6801 | 26724
11724 | 407.1554 | 26724
11725 | 415.5232 | 26724
11726 | 410.6812 | 26724
11727 | 404.4499 | 26724
11728 | 413.3479 | 26724
11729 | 406.2373 | 26724
11730 | 418.3318 | 26724
11731 | 402.9254 | 26724
11732 | 419.3256 | 26724
11733 | 416.9063 | 26724
11734 | 413.955 | 26724
11735 | 408.2245 | 26724
11736 | 398.6543 | 26724
11737 | 406.7401 | 26724
11738 | 414.3064 | 26724
11739 | 409.1196 | 26724
11740 | 406.8072 | 26724
11741 | 414.1929 | 26724
11742 | 424.1393 | 26724
11743 | 433.8468 | 26724
11744 | 423.3076 | 26724
11745 | 404.1955 | 26724
11746 | 407.7638 | 26724
11747 | 419.6183 | 26724
11748 | 415.5909 | 26724
11749 | 425.9253 | 26724
11750 | 421.0143 | 26724
11751 | 433.5906 | 26724
11752 | 421.7322 | 26724
11753 | 399.9973 | 26724
11754 | 416.41 | 26724
11755 | 422.8537 | 26724
11756 | 406.9225 | 26724
11757 | 425.6136 | 26724
11758 | 421.2837 | 26724
11759 | 426.3924 | 26724
11760 | 428.691 | 26724
11761 | 411.7667 | 26724
11762 | 406.1311 | 26724
11763 | 420.9284 | 26724
11764 | 408.7694 | 26724
11765 | 429.8333 | 26724
11766 | 417.0111 | 26724
11767 | 425.9613 | 26724
11768 | 402.5286 | 26724
11769 | 405.6091 | 26724
11770 | 410.5869 | 26724
11771 | 420.1697 | 26724
11772 | 402.2942 | 26724
11773 | 419.5194 | 26724
11774 | 419.9966 | 26724
11775 | 426.5257 | 26724
11776 | 412.7866 | 26724
11777 | 415.3676 | 26724
11778 | 421.5719 | 26724
11779 | 426.2746 | 26724
11780 | 416.1387 | 26724
11781 | 410.3646 | 26724
11782 | 404.2631 | 26724
11783 | 420.8611 | 26724
11784 | 396.917 | 26724
11785 | 426.1383 | 26724
11786 | 418.0847 | 26724
11787 | 412.9196 | 26724
11788 | 431.3176 | 26724
11789 | 402.5068 | 26724
11790 | 407.7498 | 26724
11791 | 421.9057 | 26724
11792 | 422.5107 | 26724
11793 | 421.9001 | 26724
11794 | 418.8854 | 26724
11795 | 428.4656 | 26724
11796 | 409.5509 | 26724
11797 | 420.5771 | 26724
11798 | 416.1358 | 26724
11799 | 415.4397 | 26724
11800 | 426.223 | 26724
11801 | 401.1356 | 26724
11802 | 408.9313 | 26724
11803 | 403.5186 | 26724
11804 | 429.6542 | 26724
11805 | 421.1151 | 26724
11806 | 418.2935 | 26724
11807 | 405.9518 | 26724
11808 | 414.2136 | 26724
11809 | 427.0156 | 26724
11810 | 420.3609 | 26724
11811 | 416.2524 | 26724
11812 | 412.2118 | 26724
11813 | 420.4576 | 26724
11814 | 409.3027 | 26724
11815 | 426.8356 | 26724
11816 | 423.6223 | 26724
11817 | 423.7339 | 26724
11818 | 398.7276 | 26724
11819 | 406.3675 | 26724
11820 | 432.2858 | 26724
11821 | 410.8312 | 26724
11822 | 401.6225 | 26724
11823 | 418.2294 | 26724
11824 | 408.8531 | 26724
11825 | 408.7057 | 26724
11826 | 417.8646 | 26724
11827 | 417.6256 | 26724
11828 | 418.743 | 26724
11829 | 409.246 | 26724
11830 | 414.9402 | 26724
11831 | 426.9942 | 26724
11832 | 427.9526 | 26724
11833 | 434.6712 | 26724
11834 | 414.9634 | 26724
11835 | 419.1841 | 26724
11836 | 414.8728 | 26724
11837 | 412.0197 | 26724
11838 | 411.384 | 26724
11839 | 422.6445 | 26724
11840 | 426.5259 | 26724
11841 | 416.2913 | 26724
11842 | 412.1473 | 26724
11843 | 421.8177 | 26724
11844 | 416.3938 | 26724
11845 | 413.9881 | 26724
11846 | 408.8046 | 26724
11847 | 410.7464 | 26724
11848 | 424.0292 | 26724
11849 | 421.1575 | 26724
11850 | 415.7297 | 26724
11851 | 415.4224 | 26724
11852 | 421.3114 | 26724
11853 | 413.6498 | 26724
11854 | 421.2471 | 26724
11855 | 434.8652 | 26724
11856 | 414.5307 | 26724
11857 | 420.8826 | 26724
11858 | 414.1506 | 26724
11859 | 431.1051 | 26724
11860 | 425.247 | 26724
11861 | 415.0759 | 26724
11862 | 406.5544 | 26724
11863 | 414.9206 | 26724
11864 | 424.5495 | 26724
11865 | 410.4497 | 26724
11866 | 427.7074 | 26724
11867 | 410.192 | 26724
11868 | 416.7867 | 26724
11869 | 408.035 | 26724
11870 | 408.8265 | 26724
11871 | 413.2772 | 26724
11872 | 402.2122 | 26724
11873 | 413.899 | 26724
11874 | 420.6832 | 26724
11875 | 421.8454 | 26724
11876 | 408.3311 | 26724
11877 | 414.4388 | 26724
11878 | 404.1637 | 26724
11879 | 425.6488 | 26724
11880 | 418.8099 | 26724
11881 | 413.4194 | 26724
11882 | 421.1299 | 26724
11883 | 420.9807 | 26724
11884 | 424.5376 | 26724
11885 | 411.4891 | 26724
11886 | 414.1467 | 26724
11887 | 399.0232 | 26724
11888 | 419.6102 | 26724
11889 | 412.816 | 26724
11890 | 430.7419 | 26724
11891 | 419.3125 | 26724
11892 | 422.3576 | 26724
11893 | 421.8151 | 26724
11894 | 416.5135 | 26724
11895 | 423.0977 | 26724
11896 | 408.6374 | 26724
11897 | 418.5774 | 26724
11898 | 426.2426 | 26724
11899 | 426.7198 | 26724
11900 | 412.6983 | 26724
11901 | 409.3404 | 26724
11902 | 416.9517 | 26724
11903 | 414.3832 | 26724
11904 | 416.7373 | 26724
11905 | 415.2236 | 26724
11906 | 419.3455 | 26724
11907 | 433.7308 | 26724
11908 | 428.5595 | 26724
11909 | 406.1106 | 26724
11910 | 403.2799 | 26724
11911 | 410.0932 | 26724
11912 | 408.9412 | 26724
11913 | 418.1 | 26724
11914 | 430.1354 | 26724
11915 | 417.6419 | 26724
11916 | 418.2719 | 26724
11917 | 422.1495 | 26724
11918 | 425.2742 | 26724
11919 | 423.9993 | 26724
11920 | 404.0607 | 26724
11921 | 435.4664 | 26724
11922 | 406.2065 | 26724
11923 | 416.6591 | 26724
11924 | 424.9047 | 26724
11925 | 415.3959 | 26724
11926 | 410.7861 | 26724
11927 | 418.183 | 26724
11928 | 422.8668 | 26724
11929 | 413.1629 | 26724
11930 | 421.7527 | 26724
11931 | 419.6868 | 26724
11932 | 419.8778 | 26724
11933 | 412.3046 | 26724
11934 | 398.6585 | 26724
11935 | 411.835 | 26724
11936 | 419.7726 | 26724
11937 | 406.4687 | 26724
11938 | 415.063 | 26724
11939 | 410.478 | 26724
11940 | 428.5412 | 26724
11941 | 415.4443 | 26724
11942 | 397.9871 | 26724
11943 | 417.0735 | 26724
11944 | 417.741 | 26724
11945 | 419.59 | 26724
11946 | 420.4372 | 26724
11947 | 425.6038 | 26724
11948 | 428.1456 | 26724
11949 | 418.3692 | 26724
11950 | 414.1493 | 26724
11951 | 417.1634 | 26724
11952 | 420.9136 | 26724
11953 | 419.2921 | 26724
11954 | 418.3014 | 26724
11955 | 421.057 | 26724
11956 | 405.5465 | 26724
11957 | 409.6721 | 26724
11958 | 417.4725 | 26724
11959 | 406.0649 | 26724
11960 | 424.7931 | 26724
11961 | 424.4516 | 26724
11962 | 412.586 | 26724
11963 | 413.1482 | 26724
11964 | 406.817 | 26724
11965 | 422.6811 | 26724
11966 | 425.7831 | 26724
11967 | 419.916 | 26724
11968 | 416.2447 | 26724
11969 | 409.7309 | 26724
11970 | 400.8406 | 26724
11971 | 407.2334 | 26724
11972 | 418.2141 | 26724
11973 | 416.4006 | 26724
11974 | 422.6688 | 26724
11975 | 418.8686 | 26724
11976 | 413.419 | 26724
11977 | 419.8019 | 26724
11978 | 406.3058 | 26724
11979 | 412.7517 | 26724
11980 | 411.6506 | 26724
11981 | 420.7349 | 26724
11982 | 421.6593 | 26724
11983 | 429.54 | 26724
11984 | 409.6477 | 26724
11985 | 411.88 | 26724
11986 | 422.9946 | 26724
11987 | 415.9451 | 26724
11988 | 418.0358 | 26724
11989 | 415.2596 | 26724
11990 | 429.3738 | 26724
11991 | 417.1163 | 26724
11992 | 412.625 | 26724
11993 | 428.9779 | 26724
11994 | 403.2015 | 26724
11995 | 416.3766 | 26724
11996 | 417.5782 | 26724
11997 | 416.7499 | 26724
11998 | 414.2314 | 26724
11999 | 419.3215 | 26724
12000 | 416.0739 | 26724
12001 | 413.2031 | 26724
12002 | 406.1967 | 26724
12003 | 419.806 | 26724
12004 | 419.751 | 26724
12005 | 409.9456 | 26724
12006 | 426.1055 | 26724
12007 | 428.3771 | 26724
12008 | 415.7719 | 26724
12009 | 405.2435 | 26724
12010 | 422.3379 | 26724
12011 | 423.7855 | 26724
12012 | 410.1604 | 26724
12013 | 420.4658 | 26724
12014 | 414.8224 | 26724
12015 | 419.6952 | 26724
12016 | 417.6686 | 26724
12017 | 415.4629 | 26724
12018 | 425.5609 | 26724
12019 | 418.0813 | 26724
12020 | 423.609 | 26724
12021 | 426.2589 | 26724
12022 | 413.7629 | 26724
12023 | 413.9505 | 26724
12024 | 408.4566 | 26724
12025 | 420.0947 | 26724
12026 | 419.0052 | 26724
12027 | 427.3478 | 26724
12028 | 412.0638 | 26724
12029 | 424.7284 | 26724
12030 | 422.2752 | 26724
12031 | 424.1357 | 26724
12032 | 423.1224 | 26724
12033 | 416.5313 | 26724
12034 | 408.7306 | 26724
12035 | 414.8375 | 26724
12036 | 419.9233 | 26724
12037 | 422.1658 | 26724
12038 | 410.8167 | 26724
12039 | 408.1878 | 26724
12040 | 426.7229 | 26724
12041 | 421.8483 | 26724
12042 | 419.2706 | 26724
12043 | 421.2974 | 26724
12044 | 397.7098 | 26724
12045 | 410.2324 | 26724
12046 | 420.5403 | 26724
12047 | 421.9544 | 26724
12048 | 423.9268 | 26724
12049 | 408.957 | 26724
12050 | 430.0406 | 26724
12051 | 410.1793 | 26724
12052 | 414.131 | 26724
12053 | 429.645 | 26724
12054 | 412.7347 | 26724
12055 | 407.0573 | 26724
12056 | 408.8457 | 26724
12057 | 408.6517 | 26724
12058 | 407.6236 | 26724
12059 | 421.8015 | 26724
12060 | 416.589 | 26724
12061 | 421.4784 | 26724
12062 | 413.3803 | 26724
12063 | 414.9846 | 26724
12064 | 418.8178 | 26724
12065 | 418.9271 | 26724
12066 | 430.2787 | 26724
12067 | 410.7768 | 26724
12068 | 415.0122 | 26724
12069 | 427.7474 | 26724
12070 | 406.1365 | 26724
12071 | 425.7155 | 26724
12072 | 420.5557 | 26724
12073 | 425.2106 | 26724
12074 | 421.0645 | 26724
12075 | 433.9468 | 26724
12076 | 407.8785 | 26724
12077 | 423.4331 | 26724
12078 | 412.4079 | 26724
12079 | 427.9256 | 26724
12080 | 414.6091 | 26724
12081 | 408.0586 | 26724
12082 | 426.9532 | 26724
12083 | 420.3024 | 26724
12084 | 412.8853 | 26724
12085 | 410.2882 | 26724
12086 | 408.9346 | 26724
12087 | 418.4643 | 26724
12088 | 428.1369 | 26724
12089 | 403.5817 | 26724
12090 | 424.5519 | 26724
12091 | 428.575 | 26724
12092 | 428.8607 | 26724
12093 | 416.1638 | 26724
12094 | 409.1542 | 26724
12095 | 412.942 | 26724
12096 | 403.1567 | 26724
12097 | 410.715 | 26724
12098 | 425.5742 | 26724
12099 | 408.7621 | 26724
12100 | 424.3683 | 26724
12101 | 425.1721 | 26724
12102 | 425.9676 | 26724
12103 | 407.8573 | 26724
12104 | 419.4922 | 26724
12105 | 418.5687 | 26724
12106 | 424.2879 | 26724
12107 | 426.3444 | 26724
12108 | 438.4458 | 26724
12109 | 412.3329 | 26724
12110 | 406.4816 | 26724
12111 | 415.5911 | 26724
12112 | 419.3139 | 26724
12113 | 436.2012 | 26724
12114 | 412.156 | 26724
12115 | 426.0181 | 26724
12116 | 413.8595 | 26724
12117 | 397.7031 | 26724
12118 | 427.1052 | 26724
12119 | 423.9328 | 26724
12120 | 405.6214 | 26724
12121 | 421.6607 | 26724
12122 | 416.8207 | 26724
12123 | 425.5711 | 26724
12124 | 414.2896 | 26724
12125 | 406.5299 | 26724
12126 | 414.4309 | 26724
12127 | 409.5118 | 26724
12128 | 415.6407 | 26724
12129 | 423.1831 | 26724
12130 | 418.8476 | 26724
12131 | 421.2736 | 26724
12132 | 429.8681 | 26724
12133 | 422.2988 | 26724
12134 | 420.5058 | 26724
12135 | 421.3851 | 26724
12136 | 421.6096 | 26724
12137 | 422.6888 | 26724
12138 | 427.7531 | 26724
12139 | 413.7061 | 26724
12140 | 404.3822 | 26724
12141 | 423.9251 | 26724
12142 | 410.1676 | 26724
12143 | 419.5987 | 26724
12144 | 427.285 | 26724
12145 | 415.8301 | 26724
12146 | 405.0696 | 26724
12147 | 408.6182 | 26724
12148 | 419.3405 | 26724
12149 | 411.822 | 26724
12150 | 430.939 | 26724
12151 | 423.9445 | 26724
12152 | 405.91 | 26724
12153 | 422.6882 | 26724
12154 | 400.3054 | 26724
12155 | 405.8142 | 26724
12156 | 426.2452 | 26724
12157 | 414.7266 | 26724
12158 | 427.4536 | 26724
12159 | 418.1507 | 26724
12160 | 424.2082 | 26724
12161 | 406.0104 | 26724
12162 | 425.616 | 26724
12163 | 419.8778 | 26724
12164 | 415.91 | 26724
12165 | 407.6645 | 26724
12166 | 403.3109 | 26724
12167 | 422.365 | 26724
12168 | 410.9675 | 26724
12169 | 425.4117 | 26724
12170 | 426.1438 | 26724
12171 | 408.3244 | 26724
12172 | 410.3058 | 26724
12173 | 406.9505 | 26724
12174 | 416.5939 | 26724
12175 | 430.9222 | 26724
12176 | 411.2919 | 26724
12177 | 431.3413 | 26724
12178 | 419.8409 | 26724
12179 | 412.2742 | 26724
12180 | 419.8626 | 26724
12181 | 408.6073 | 26724
12182 | 414.3749 | 26724
12183 | 410.5242 | 26724
12184 | 406.1065 | 26724
12185 | 422.5012 | 26724
12186 | 408.2984 | 26724
12187 | 413.2798 | 26724
12188 | 428.6581 | 26724
12189 | 405.3949 | 26724
12190 | 406.1403 | 26724
12191 | 410.6718 | 26724
12192 | 419.7826 | 26724
12193 | 415.59 | 26724
12194 | 412.3287 | 26724
12195 | 422.0283 | 26724
12196 | 414.6408 | 26724
12197 | 422.648 | 26724
12198 | 410.0821 | 26724
12199 | 437.7172 | 26724
12200 | 406.6889 | 26724
12201 | 420.4434 | 26724
12202 | 424.7903 | 26724
12203 | 429.1028 | 26724
12204 | 419.8892 | 26724
12205 | 418.0249 | 26724
12206 | 413.9917 | 26724
12207 | 407.5816 | 26724
12208 | 418.5659 | 26724
12209 | 413.2359 | 26724
12210 | 419.5699 | 26724
12211 | 398.3483 | 26724
12212 | 402.701 | 26724
12213 | 401.6147 | 26724
12214 | 418.0867 | 26724
12215 | 429.1845 | 26724
12216 | 420.759 | 26724
12217 | 416.2413 | 26724
12218 | 401.2941 | 26724
12219 | 411.8648 | 26724
12220 | 412.2093 | 26724
12221 | 409.2599 | 26724
12222 | 419.9942 | 26724
12223 | 421.1516 | 26724
12224 | 410.7799 | 26724
12225 | 414.1889 | 26724
12226 | 403.0568 | 26724
12227 | 419.8575 | 26724
12228 | 425.1466 | 26724
12229 | 421.7015 | 26724
12230 | 415.0451 | 26724
12231 | 412.2923 | 26724
12232 | 420.1214 | 26724
12233 | 415.3256 | 26724
12234 | 420.1902 | 26724
12235 | 425.5287 | 26724
12236 | 428.8461 | 26724
12237 | 428.8911 | 26724
12238 | 413.3357 | 26724
12239 | 405.5906 | 26724
12240 | 408.863 | 26724
12241 | 409.0895 | 26724
12242 | 434.7205 | 26724
12243 | 422.4841 | 26724
12244 | 412.1571 | 26724
12245 | 420.7625 | 26724
12246 | 413.8373 | 26724
12247 | 401.9425 | 26724
12248 | 427.1538 | 26724
12249 | 429.5439 | 26724
12250 | 416.0854 | 26724
12251 | 404.1975 | 26724
12252 | 432.1668 | 26724
12253 | 420.0405 | 26724
12254 | 412.8375 | 26724
12255 | 415.9969 | 26724
12256 | 407.1225 | 26724
12257 | 410.5937 | 26724
12258 | 409.5015 | 26724
12259 | 421.2709 | 26724
12260 | 424.7222 | 26724
12261 | 414.0664 | 26724
12262 | 428.7492 | 26724
12263 | 422.2428 | 26724
12264 | 421.7764 | 26724
12265 | 414.193 | 26724
12266 | 415.3008 | 26724
12267 | 420.361 | 26724
12268 | 415.75 | 26724
12269 | 427.0413 | 26724
12270 | 416.3714 | 26724
12271 | 428.0465 | 26724
12272 | 410.1311 | 26724
12273 | 419.6455 | 26724
12274 | 417.5123 | 26724
12275 | 412.0585 | 26724
12276 | 420.6936 | 26724
12277 | 413.9887 | 26724
12278 | 419.9241 | 26724
12279 | 402.7537 | 26724
12280 | 427.6539 | 26724
12281 | 409.9798 | 26724
12282 | 408.3098 | 26724
12283 | 431.5829 | 26724
12284 | 404.9378 | 26724
12285 | 422.6833 | 26724
12286 | 422.8205 | 26724
12287 | 422.7868 | 26724
12288 | 412.7622 | 26724
12289 | 407.8011 | 26724
12290 | 423.4779 | 26724
12291 | 415.163 | 26724
12292 | 421.3702 | 26724
12293 | 407.543 | 26724
12294 | 395.9145 | 26724
12295 | 427.4595 | 26724
12296 | 422.3853 | 26724
12297 | 405.066 | 26724
12298 | 424.1363 | 26724
12299 | 421.6863 | 26724
12300 | 424.7714 | 26724
12301 | 418.2196 | 26724
12302 | 416.6873 | 26724
12303 | 423.0436 | 26724
12304 | 405.9728 | 26724
12305 | 416.0859 | 26724
12306 | 407.0189 | 26724
12307 | 415.2699 | 26724
12308 | 419.2181 | 26724
12309 | 413.3636 | 26724
12310 | 404.9955 | 26724
12311 | 414.8798 | 26724
12312 | 399.2031 | 26724
12313 | 410.7077 | 26724
12314 | 408.2245 | 26724
12315 | 430.7738 | 26724
12316 | 418.4309 | 26724
12317 | 428.9607 | 26724
12318 | 414.1308 | 26724
12319 | 400.5761 | 26724
12320 | 412.4629 | 26724
12321 | 416.5652 | 26724
12322 | 407.5699 | 26724
12323 | 415.0658 | 26724
12324 | 400.8832 | 26724
12325 | 411.6546 | 26724
12326 | 431.3185 | 26724
12327 | 414.4949 | 26724
12328 | 409.2477 | 26724
12329 | 418.8545 | 26724
12330 | 411.4318 | 26724
12331 | 412.9776 | 26724
12332 | 414.3065 | 26724
12333 | 412.5732 | 26724
12334 | 415.1212 | 26724
12335 | 423.8624 | 26724
12336 | 421.4701 | 26724
12337 | 432.663 | 26724
12338 | 414.2547 | 26724
12339 | 412.0769 | 26724
12340 | 430.1336 | 26724
12341 | 432.6813 | 26724
12342 | 403.5632 | 26724
12343 | 414.3364 | 26724
12344 | 417.4137 | 26724
12345 | 420.3779 | 26724
12346 | 415.7972 | 26724
12347 | 423.0385 | 26724
12348 | 391.9838 | 26724
12349 | 421.3882 | 26724
12350 | 413.6066 | 26724
12351 | 419.5155 | 26724
12352 | 412.792 | 26724
12353 | 411.2225 | 26724
12354 | 406.2131 | 26724
12355 | 401.1619 | 26724
12356 | 417.5913 | 26724
12357 | 424.78 | 26724
12358 | 424.3247 | 26724
12359 | 429.4779 | 26724
12360 | 426.5278 | 26724
12361 | 416.9947 | 26724
12362 | 413.2523 | 26724
12363 | 422.9338 | 26724
12364 | 418.3194 | 26724
12365 | 411.7523 | 26724
12366 | 426.6147 | 26724
12367 | 405.4544 | 26724
12368 | 421.8656 | 26724
12369 | 414.2255 | 26724
12370 | 420.3717 | 26724
12371 | 411.2617 | 26724
12372 | 418.5765 | 26724
12373 | 397.8542 | 26724
12374 | 399.0776 | 26724
12375 | 409.4408 | 26724
12376 | 422.4985 | 26724
12377 | 415.7546 | 26724
12378 | 409.9194 | 26724
12379 | 401.1798 | 26724
12380 | 417.8714 | 26724
12381 | 422.453 | 26724
12382 | 416.4266 | 26724
12383 | 401.7191 | 26724
12384 | 411.3098 | 26724
12385 | 412.9092 | 26724
12386 | 420.1473 | 26724
12387 | 419.7972 | 26724
12388 | 415.967 | 26724
12389 | 404.0982 | 26724
12390 | 421.2639 | 26724
12391 | 402.8356 | 26724
12392 | 421.7554 | 26724
12393 | 411.0884 | 26724
12394 | 411.3164 | 26724
12395 | 426.901 | 26724
12396 | 427.1926 | 26724
12397 | 421.8783 | 26724
12398 | 416.5949 | 26724
12399 | 418.2865 | 26724
12400 | 408.0643 | 26724
12401 | 404.7061 | 26724
12402 | 424.4919 | 26724
12403 | 417.411 | 26724
12404 | 419.0984 | 26724
12405 | 416.2614 | 26724
12406 | 403.1643 | 26724
12407 | 421.1721 | 26724
12408 | 410.6307 | 26724
12409 | 406.4465 | 26724
12410 | 407.276 | 26724
12411 | 406.0447 | 26724
12412 | 414.8476 | 26724
12413 | 420.2606 | 26724
12414 | 416.1246 | 26724
12415 | 415.656 | 26724
12416 | 426.677 | 26724
12417 | 412.4351 | 26724
12418 | 407.1373 | 26724
12419 | 423.5126 | 26724
12420 | 422.185 | 26724
12421 | 411.3041 | 26724
12422 | 413.9479 | 26724
12423 | 419.171 | 26724
12424 | 426.2642 | 26724
12425 | 409.9197 | 26724
12426 | 408.6075 | 26724
12427 | 409.714 | 26724
12428 | 413.606 | 26724
12429 | 416.547 | 26724
12430 | 403.2029 | 26724
12431 | 427.4877 | 26724
12432 | 409.4407 | 26724
12433 | 424.5845 | 26724
12434 | 402.796 | 26724
12435 | 414.8227 | 26724
12436 | 425.268 | 26724
12437 | 396.8909 | 26724
12438 | 422.7355 | 26724
12439 | 408.8604 | 26724
12440 | 414.3971 | 26724
12441 | 412.9251 | 26724
12442 | 417.6619 | 26724
12443 | 429.5532 | 26724
12444 | 407.2753 | 26724
12445 | 410.5094 | 26724
12446 | 424.632 | 26724
12447 | 426.1555 | 26724
12448 | 406.9133 | 26724
12449 | 418.6001 | 26724
12450 | 401.9911 | 26724
12451 | 416.7643 | 26724
12452 | 418.0965 | 26724
12453 | 421.0236 | 26724
12454 | 407.2815 | 26724
12455 | 418.0758 | 26724
12456 | 416.8306 | 26724
12457 | 412.2692 | 26724
12458 | 418.8225 | 26724
12459 | 399.7524 | 26724
12460 | 419.2278 | 26724
12461 | 405.9444 | 26724
12462 | 415.2557 | 26724
12463 | 422.9244 | 26724
12464 | 424.9491 | 26724
12465 | 406.9899 | 26724
12466 | 417.1434 | 26724
12467 | 408.1585 | 26724
12468 | 410.7723 | 26724
12469 | 404.762 | 26724
12470 | 419.3014 | 26724
12471 | 410.0839 | 26724
12472 | 423.6151 | 26724
12473 | 432.1086 | 26724
12474 | 424.7457 | 26724
12475 | 411.7 | 26724
12476 | 421.2003 | 26724
12477 | 418.1767 | 26724
12478 | 423.2998 | 26724
12479 | 402.1552 | 26724
12480 | 410.3012 | 26724
12481 | 404.5172 | 26724
12482 | 417.1447 | 26724
12483 | 421.1689 | 26724
12484 | 430.9344 | 26724
12485 | 419.5577 | 26724
12486 | 415.2131 | 26724
12487 | 408.1456 | 26724
12488 | 408.4427 | 26724
12489 | 413.0795 | 26724
12490 | 427.2386 | 26724
12491 | 403.7009 | 26724
12492 | 429.0402 | 26724
12493 | 432.4846 | 26724
12494 | 413.4225 | 26724
12495 | 414.6122 | 26724
12496 | 433.9464 | 26724
12497 | 415.2934 | 26724
12498 | 414.68 | 26724
12499 | 407.481 | 26724
12500 | 432.2411 | 26724
12501 | 405.9886 | 26724
12502 | 410.735 | 26724
12503 | 412.7037 | 26724
12504 | 435.9326 | 26724
12505 | 407.2482 | 26724
12506 | 399.4502 | 26724
12507 | 408.4119 | 26724
12508 | 425.5752 | 26724
12509 | 415.6232 | 26724
12510 | 425.8852 | 26724
12511 | 420.8072 | 26724
12512 | 401.2931 | 26724
12513 | 420.4626 | 26724
12514 | 411.6758 | 26724
12515 | 418.082 | 26724
12516 | 422.8634 | 26724
12517 | 416.512 | 26724
12518 | 409.2074 | 26724
12519 | 426.6045 | 26724
12520 | 412.1542 | 26724
12521 | 421.2806 | 26724
12522 | 415.6841 | 26724
12523 | 419.1356 | 26724
12524 | 416.7881 | 26724
12525 | 409.3724 | 26724
12526 | 416.8663 | 26724
12527 | 405.3351 | 26724
12528 | 418.088 | 26724
12529 | 434.2782 | 26724
12530 | 409.4635 | 26724
12531 | 428.215 | 26724
12532 | 408.2468 | 26724
12533 | 415.8248 | 26724
12534 | 413.6303 | 26724
12535 | 412.1154 | 26724
12536 | 415.7698 | 26724
12537 | 414.5946 | 26724
12538 | 407.8542 | 26724
12539 | 419.8991 | 26724
12540 | 411.6711 | 26724
12541 | 404.3872 | 26724
12542 | 424.1881 | 26724
12543 | 416.4996 | 26724
12544 | 423.5615 | 26724
12545 | 422.453 | 26724
12546 | 416.629 | 26724
12547 | 408.8581 | 26724
12548 | 433.7561 | 26724
12549 | 405.105 | 26724
12550 | 414.9117 | 26724
12551 | 416.5709 | 26724
12552 | 412.259 | 26724
12553 | 416.6937 | 26724
12554 | 424.6611 | 26724
12555 | 416.1259 | 26724
12556 | 414.7575 | 26724
12557 | 417.2625 | 26724
12558 | 404.0272 | 26724
12559 | 413.2866 | 26724
12560 | 419.8723 | 26724
12561 | 395.2625 | 26724
12562 | 425.3505 | 26724
12563 | 414.1535 | 26724
12564 | 425.1846 | 26724
12565 | 418.182 | 26724
12566 | 418.7898 | 26724
12567 | 408.4777 | 26724
12568 | 415.9895 | 26724
12569 | 427.3033 | 26724
12570 | 404.6778 | 26724
12571 | 422.2506 | 26724
12572 | 412.7852 | 26724
12573 | 406.0178 | 26724
12574 | 410.5145 | 26724
12575 | 409.452 | 26724
12576 | 419.5681 | 26724
12577 | 412.5406 | 26724
12578 | 402.9246 | 26724
12579 | 412.7638 | 26724
12580 | 412.5916 | 26724
12581 | 407.4106 | 26724
12582 | 400.7649 | 26724
12583 | 412.6046 | 26724
12584 | 411.632 | 26724
12585 | 416.3551 | 26724
12586 | 409.8457 | 26724
12587 | 428.9148 | 26724
12588 | 407.9395 | 26724
12589 | 404.4663 | 26724
12590 | 407.4887 | 26724
12591 | 412.4439 | 26724
12592 | 405.1717 | 26724
12593 | 412.7247 | 26724
12594 | 393.3055 | 26724
12595 | 406.6549 | 26724
12596 | 427.6737 | 26724
12597 | 406.3932 | 26724
12598 | 416.6371 | 26724
12599 | 421.1097 | 26724
12600 | 412.429 | 26724
12601 | 414.664 | 26724
12602 | 421.8809 | 26724
12603 | 413.9573 | 26724
12604 | 411.395 | 26724
12605 | 431.6336 | 26724
12606 | 423.8105 | 26724
12607 | 420.6744 | 26724
12608 | 420.1676 | 26724
12609 | 412.6043 | 26724
12610 | 425.3727 | 26724
12611 | 421.2048 | 26724
12612 | 417.5158 | 26724
12613 | 413.9531 | 26724
12614 | 406.1016 | 26724
12615 | 431.0624 | 26724
12616 | 436.025 | 26724
12617 | 424.3227 | 26724
12618 | 430.9835 | 26724
12619 | 413.0341 | 26724
12620 | 427.9374 | 26724
12621 | 422.4902 | 26724
12622 | 408.455 | 26724
12623 | 407.5658 | 26724
12624 | 433.2665 | 26724
12625 | 420.3927 | 26724
12626 | 410.2989 | 26724
12627 | 423.8036 | 26724
12628 | 404.1728 | 26724
12629 | 416.5019 | 26724
12630 | 431.8716 | 26724
12631 | 417.8285 | 26724
12632 | 414.7774 | 26724
12633 | 425.5863 | 26724
12634 | 403.7148 | 26724
12635 | 414.4938 | 26724
12636 | 415.5013 | 26724
12637 | 418.694 | 26724
12638 | 417.4034 | 26724
12639 | 423.9622 | 26724
12640 | 427.4568 | 26724
12641 | 413.503 | 26724
12642 | 415.7606 | 26724
12643 | 413.2337 | 26724
12644 | 406.8698 | 26724
12645 | 426.1215 | 26724
12646 | 414.0366 | 26724
12647 | 417.727 | 26724
12648 | 411.5593 | 26724
12649 | 420.3864 | 26724
12650 | 430.6458 | 26724
12651 | 397.003 | 26724
12652 | 402.2945 | 26724
12653 | 408.7396 | 26724
12654 | 421.2424 | 26724
12655 | 427.5647 | 26724
12656 | 401.556 | 26724
12657 | 433.0931 | 26724
12658 | 408.2017 | 26724
12659 | 429.0089 | 26724
12660 | 424.5834 | 26724
12661 | 408.1281 | 26724
12662 | 405.4602 | 26724
12663 | 408.1914 | 26724
12664 | 419.3823 | 26724
12665 | 411.031 | 26724
12666 | 405.2577 | 26724
12667 | 424.845 | 26724
12668 | 419.794 | 26724
12669 | 428.093 | 26724
12670 | 408.806 | 26724
12671 | 427.9614 | 26724
12672 | 428.7489 | 26724
12673 | 406.4351 | 26724
12674 | 411.3026 | 26724
12675 | 416.7066 | 26724
12676 | 415.6789 | 26724
12677 | 412.228 | 26724
12678 | 414.5952 | 26724
12679 | 417.0256 | 26724
12680 | 405.182 | 26724
12681 | 425.2502 | 26724
12682 | 415.3587 | 26724
12683 | 417.382 | 26724
12684 | 418.9587 | 26724
12685 | 418.3887 | 26724
12686 | 410.5513 | 26724
12687 | 413.2399 | 26724
12688 | 427.1123 | 26724
12689 | 417.352 | 26724
12690 | 429.0818 | 26724
12691 | 434.4802 | 26724
12692 | 411.207 | 26724
12693 | 422.4097 | 26724
12694 | 430.4637 | 26724
12695 | 428.6426 | 26724
12696 | 416.884 | 26724
12697 | 423.5438 | 26724
12698 | 416.5584 | 26724
12699 | 417.1295 | 26724
12700 | 420.7104 | 26724
12701 | 415.4322 | 26724
12702 | 409.8882 | 26724
12703 | 425.8451 | 26724
12704 | 421.9028 | 26724
12705 | 396.0789 | 26724
12706 | 404.5251 | 26724
12707 | 423.574 | 26724
12708 | 423.4133 | 26724
12709 | 416.5063 | 26724
12710 | 408.4421 | 26724
12711 | 409.7392 | 26724
12712 | 416.1739 | 26724
12713 | 408.2012 | 26724
12714 | 414.354 | 26724
12715 | 425.7617 | 26724
12716 | 409.5461 | 26724
12717 | 424.1731 | 26724
12718 | 424.8533 | 26724
12719 | 415.5463 | 26724
12720 | 408.1674 | 26724
12721 | 427.2191 | 26724
12722 | 412.9598 | 26724
12723 | 419.094 | 26724
12724 | 413.5108 | 26724
12725 | 428.4662 | 26724
12726 | 426.0696 | 26724
12727 | 423.0545 | 26724
12728 | 425.2758 | 26724
12729 | 425.5709 | 26724
12730 | 409.8283 | 26724
12731 | 405.5528 | 26724
12732 | 419.753 | 26724
12733 | 419.925 | 26724
12734 | 414.4748 | 26724
12735 | 422.2465 | 26724
12736 | 409.5904 | 26724
12737 | 419.9857 | 26724
12738 | 405.4085 | 26724
12739 | 416.9379 | 26724
12740 | 418.2248 | 26724
12741 | 423.6825 | 26724
12742 | 438.5875 | 26724
12743 | 414.9099 | 26724
12744 | 414.6002 | 26724
12745 | 422.3066 | 26724
12746 | 392.566 | 26724
12747 | 417.2089 | 26724
12748 | 408.374 | 26724
12749 | 426.1582 | 26724
12750 | 420.6784 | 26724
12751 | 415.5349 | 26724
12752 | 418.7818 | 26724
12753 | 410.3765 | 26724
12754 | 430.6376 | 26724
12755 | 424.2081 | 26724
12756 | 400.4034 | 26724
12757 | 426.2055 | 26724
12758 | 413.9253 | 26724
12759 | 415.9246 | 26724
12760 | 416.2085 | 26724
12761 | 413.9415 | 26724
12762 | 406.4505 | 26724
12763 | 404.013 | 26724
12764 | 429.0457 | 26724
12765 | 411.3716 | 26724
12766 | 410.7478 | 26724
12767 | 421.0376 | 26724
12768 | 422.7061 | 26724
12769 | 409.9108 | 26724
12770 | 410.1956 | 26724
12771 | 407.162 | 26724
12772 | 421.3334 | 26724
12773 | 419.3504 | 26724
12774 | 427.3956 | 26724
12775 | 424.9788 | 26724
12776 | 418.3297 | 26724
12777 | 414.0424 | 26724
12778 | 413.2087 | 26724
12779 | 415.1087 | 26724
12780 | 419.5976 | 26724
12781 | 418.6352 | 26724
12782 | 402.5572 | 26724
12783 | 428.9319 | 26724
12784 | 415.9594 | 26724
12785 | 420.29 | 26724
12786 | 398.4797 | 26724
12787 | 422.6424 | 26724
12788 | 400.2156 | 26724
12789 | 408.5064 | 26724
12790 | 422.2309 | 26724
12791 | 410.8539 | 26724
12792 | 421.7256 | 26724
12793 | 408.3931 | 26724
12794 | 412.8324 | 26724
12795 | 424.6374 | 26724
12796 | 420.8663 | 26724
12797 | 409.192 | 26724
12798 | 418.537 | 26724
12799 | 433.8006 | 26724
12800 | 412.3126 | 26724
12801 | 402.1943 | 26724
12802 | 404.9083 | 26724
12803 | 435.0397 | 26724
12804 | 411.5013 | 26724
12805 | 416.5384 | 26724
12806 | 417.5107 | 26724
12807 | 410.9681 | 26724
12808 | 413.324 | 26724
12809 | 425.8167 | 26724
12810 | 419.8905 | 26724
12811 | 409.9181 | 26724
12812 | 414.0309 | 26724
12813 | 419.7804 | 26724
12814 | 425.8934 | 26724
12815 | 424.813 | 26724
12816 | 415.2016 | 26724
12817 | 412.3805 | 26724
12818 | 412.3911 | 26724
12819 | 420.5888 | 26724
12820 | 412.3519 | 26724
12821 | 428.0836 | 26724
12822 | 414.8639 | 26724
12823 | 424.9299 | 26724
12824 | 422.0096 | 26724
12825 | 401.5506 | 26724
12826 | 415.8848 | 26724
12827 | 418.3719 | 26724
12828 | 423.2462 | 26724
12829 | 418.938 | 26724
12830 | 402.7108 | 26724
12831 | 408.9554 | 26724
12832 | 413.1042 | 26724
12833 | 408.2151 | 26724
12834 | 430.4652 | 26724
12835 | 421.2424 | 26724
12836 | 412.946 | 26724
12837 | 422.0676 | 26724
12838 | 402.3392 | 26724
12839 | 425.1409 | 26724
12840 | 429.4855 | 26724
12841 | 413.9411 | 26724
12842 | 408.7149 | 26724
12843 | 414.93 | 26724
12844 | 413.3723 | 26724
12845 | 416.8301 | 26724
12846 | 408.8356 | 26724
12847 | 403.7114 | 26724
12848 | 405.1553 | 26724
12849 | 396.1971 | 26724
12850 | 419.5732 | 26724
12851 | 417.1842 | 26724
12852 | 411.6092 | 26724
12853 | 418.1612 | 26724
12854 | 403.5998 | 26724
12855 | 405.8618 | 26724
12856 | 413.0752 | 26724
12857 | 407.03 | 26724
12858 | 406.2821 | 26724
12859 | 413.3513 | 26724
12860 | 416.9942 | 26724
12861 | 407.5621 | 26724
12862 | 407.983 | 26724
12863 | 423.9498 | 26724
12864 | 411.5575 | 26724
12865 | 424.8662 | 26724
12866 | 416.4702 | 26724
12867 | 413.6843 | 26724
12868 | 410.841 | 26724
12869 | 425.6653 | 26724
12870 | 414.2683 | 26724
12871 | 407.5343 | 26724
12872 | 407.6913 | 26724
12873 | 418.9229 | 26724
12874 | 427.5244 | 26724
12875 | 414.0072 | 26724
12876 | 409.3604 | 26724
12877 | 402.8854 | 26724
12878 | 426.8797 | 26724
12879 | 410.3114 | 26724
12880 | 409.8586 | 26724
12881 | 427.5412 | 26724
12882 | 407.6787 | 26724
12883 | 424.5345 | 26724
12884 | 416.5597 | 26724
12885 | 426.2156 | 26724
12886 | 413.6207 | 26724
12887 | 414.4326 | 26724
12888 | 420.4684 | 26724
12889 | 396.4792 | 26724
12890 | 412.9644 | 26724
12891 | 405.0164 | 26724
12892 | 420.953 | 26724
12893 | 414.9453 | 26724
12894 | 408.9696 | 26724
12895 | 411.4952 | 26724
12896 | 411.3789 | 26724
12897 | 419.1221 | 26724
12898 | 416.3763 | 26724
12899 | 414.5838 | 26724
12900 | 409.7309 | 26724
12901 | 419.0244 | 26724
12902 | 403.4759 | 26724
12903 | 401.6324 | 26724
12904 | 403.174 | 26724
12905 | 406.4086 | 26724
12906 | 418.6689 | 26724
12907 | 405.9311 | 26724
12908 | 414.9954 | 26724
12909 | 427.2963 | 26724
12910 | 417.4314 | 26724
12911 | 423.8303 | 26724
12912 | 422.7978 | 26724
12913 | 410.6114 | 26724
12914 | 412.5337 | 26724
12915 | 428.6647 | 26724
12916 | 413.7431 | 26724
12917 | 429.2204 | 26724
12918 | 417.0585 | 26724
12919 | 412.8609 | 26724
12920 | 418.2951 | 26724
12921 | 429.987 | 26724
12922 | 420.58 | 26724
12923 | 407.8787 | 26724
12924 | 405.8315 | 26724
12925 | 412.0406 | 26724
12926 | 412.0752 | 26724
12927 | 427.2664 | 26724
12928 | 408.2274 | 26724
12929 | 416.7186 | 26724
12930 | 415.268 | 26724
12931 | 418.352 | 26724
12932 | 407.4967 | 26724
12933 | 419.2279 | 26724
12934 | 400.4619 | 26724
12935 | 428.5054 | 26724
12936 | 414.3908 | 26724
12937 | 404.3466 | 26724
12938 | 411.4709 | 26724
12939 | 414.1969 | 26724
12940 | 405.1568 | 26724
12941 | 423.0294 | 26724
12942 | 417.915 | 26724
12943 | 407.982 | 26724
12944 | 405.3471 | 26724
12945 | 411.7138 | 26724
12946 | 428.0408 | 26724
12947 | 411.3654 | 26724
12948 | 426.4509 | 26724
12949 | 414.7575 | 26724
12950 | 409.6841 | 26724
12951 | 415.4582 | 26724
12952 | 426.8111 | 26724
12953 | 411.5147 | 26724
12954 | 413.3468 | 26724
12955 | 420.2165 | 26724
12956 | 415.4448 | 26724
12957 | 410.97 | 26724
12958 | 420.6208 | 26724
12959 | 412.6528 | 26724
12960 | 431.1701 | 26724
12961 | 426.9053 | 26724
12962 | 424.9476 | 26724
12963 | 412.4586 | 26724
12964 | 420.0528 | 26724
12965 | 418.6755 | 26724
12966 | 419.2491 | 26724
12967 | 428.8611 | 26724
12968 | 421.2318 | 26724
12969 | 403.3379 | 26724
12970 | 424.492 | 26724
12971 | 421.2788 | 26724
12972 | 404.4516 | 26724
12973 | 400.2182 | 26724
12974 | 401.9479 | 26724
12975 | 403.7916 | 26724
12976 | 417.6623 | 26724
12977 | 421.0488 | 26724
12978 | 411.3827 | 26724
12979 | 411.2021 | 26724
12980 | 408.4992 | 26724
12981 | 430.1452 | 26724
12982 | 413.2351 | 26724
12983 | 409.3108 | 26724
12984 | 418.6253 | 26724
12985 | 411.9187 | 26724
12986 | 423.3591 | 26724
12987 | 399.1305 | 26724
12988 | 406.7842 | 26724
12989 | 414.0385 | 26724
12990 | 427.002 | 26724
12991 | 416.8638 | 26724
12992 | 401.1726 | 26724
12993 | 414.2837 | 26724
12994 | 404.2019 | 26724
12995 | 427.0729 | 26724
12996 | 414.9253 | 26724
12997 | 408.6544 | 26724
12998 | 422.8159 | 26724
12999 | 407.3092 | 26724
13000 | 411.0756 | 26724
13001 | 425.203 | 26724
13002 | 417.0075 | 26724
13003 | 417.1226 | 26724
13004 | 407.3461 | 26724
13005 | 426.5437 | 26724
13006 | 407.0843 | 26724
13007 | 410.362 | 26724
13008 | 401.7178 | 26724
13009 | 414.73 | 26724
13010 | 414.5102 | 26724
13011 | 413.4735 | 26724
13012 | 421.1977 | 26724
13013 | 413.5433 | 26724
13014 | 407.6064 | 26724
13015 | 412.2562 | 26724
13016 | 402.1763 | 26724
13017 | 407.3145 | 26724
13018 | 418.3055 | 26724
13019 | 422.2596 | 26724
13020 | 418.145 | 26724
13021 | 401.3749 | 26724
13022 | 425.9155 | 26724
13023 | 414.5808 | 26724
13024 | 418.4707 | 26724
13025 | 411.4918 | 26724
13026 | 423.6371 | 26724
13027 | 413.0781 | 26724
13028 | 411.4719 | 26724
13029 | 399.6002 | 26724
13030 | 412.1688 | 26724
13031 | 426.7848 | 26724
13032 | 425.109 | 26724
13033 | 407.5689 | 26724
13034 | 417.1133 | 26724
13035 | 408.8587 | 26724
13036 | 393.0394 | 26724
13037 | 425.7678 | 26724
13038 | 412.1668 | 26724
13039 | 414.3382 | 26724
13040 | 414.0845 | 26724
13041 | 407.9078 | 26724
13042 | 411.9546 | 26724
13043 | 416.4596 | 26724
13044 | 416.0115 | 26724
13045 | 431.9088 | 26724
13046 | 419.2063 | 26724
13047 | 415.9708 | 26724
13048 | 415.7261 | 26724
13049 | 407.8742 | 26724
13050 | 419.2609 | 26724
13051 | 416.5113 | 26724
13052 | 400.0186 | 26724
13053 | 400.0846 | 26724
13054 | 410.6845 | 26724
13055 | 408.9905 | 26724
13056 | 421.8918 | 26724
13057 | 410.5556 | 26724
13058 | 412.328 | 26724
13059 | 413.116 | 26724
13060 | 423.0279 | 26724
13061 | 422.631 | 26724
13062 | 410.7674 | 26724
13063 | 401.9288 | 26724
13064 | 425.193 | 26724
13065 | 420.1708 | 26724
13066 | 414.5204 | 26724
13067 | 416.0253 | 26724
13068 | 415.6337 | 26724
13069 | 417.7932 | 26724
13070 | 421.7473 | 26724
13071 | 413.0874 | 26724
13072 | 420.4103 | 26724
13073 | 420.1855 | 26724
13074 | 417.2514 | 26724
13075 | 405.2243 | 26724
13076 | 419.4573 | 26724
13077 | 416.065 | 26724
13078 | 424.0088 | 26724
13079 | 412.1935 | 26724
13080 | 422.5079 | 26724
13081 | 407.7336 | 26724
13082 | 422.7389 | 26724
13083 | 403.7931 | 26724
13084 | 405.923 | 26724
13085 | 420.6601 | 26724
13086 | 430.4649 | 26724
13087 | 416.9388 | 26724
13088 | 428.7613 | 26724
13089 | 411.8338 | 26724
13090 | 395.0698 | 26724
13091 | 419.105 | 26724
13092 | 400.211 | 26724
13093 | 426.1997 | 26724
13094 | 407.0081 | 26724
13095 | 420.281 | 26724
13096 | 403.9953 | 26724
13097 | 419.1978 | 26724
13098 | 420.6821 | 26724
13099 | 412.9798 | 26724
13100 | 415.1811 | 26724
13101 | 421.5406 | 26724
13102 | 418.4991 | 26724
13103 | 411.9288 | 26724
13104 | 419.667 | 26724
13105 | 400.6122 | 26724
13106 | 412.6519 | 26724
13107 | 410.1887 | 26724
13108 | 415.2661 | 26724
13109 | 418.0817 | 26724
13110 | 402.6755 | 26724
13111 | 427.5632 | 26724
13112 | 417.5909 | 26724
13113 | 412.0721 | 26724
13114 | 436.0047 | 26724
13115 | 420.2693 | 26724
13116 | 429.4728 | 26724
13117 | 411.7844 | 26724
13118 | 415.7283 | 26724
13119 | 414.0635 | 26724
13120 | 410.0407 | 26724
13121 | 412.4684 | 26724
13122 | 416.8262 | 26724
13123 | 413.0577 | 26724
13124 | 416.091 | 26724
13125 | 416.5043 | 26724
13126 | 410.3243 | 26724
13127 | 429.6987 | 26724
13128 | 414.7539 | 26724
13129 | 407.9343 | 26724
13130 | 429.4002 | 26724
13131 | 412.7971 | 26724
13132 | 410.5058 | 26724
13133 | 395.332 | 26724
13134 | 421.321 | 26724
13135 | 416.2445 | 26724
13136 | 419.6337 | 26724
13137 | 420.1053 | 26724
13138 | 413.363 | 26724
13139 | 421.4291 | 26724
13140 | 422.5587 | 26724
13141 | 401.3322 | 26724
13142 | 416.3382 | 26724
13143 | 408.919 | 26724
13144 | 412.237 | 26724
13145 | 416.2976 | 26724
13146 | 419.8381 | 26724
13147 | 410.8285 | 26724
13148 | 398.7188 | 26724
13149 | 429.6488 | 26724
13150 | 418.4109 | 26724
13151 | 406.2312 | 26724
13152 | 427.9611 | 26724
13153 | 422.1224 | 26724
13154 | 410.2858 | 26724
13155 | 422.0084 | 26724
13156 | 414.1099 | 26724
13157 | 412.0089 | 26724
13158 | 408.2686 | 26724
13159 | 396.9158 | 26724
13160 | 419.4834 | 26724
13161 | 420.1979 | 26724
13162 | 408.5567 | 26724
13163 | 420.7351 | 26724
13164 | 412.0979 | 26724
13165 | 419.9398 | 26724
13166 | 425.4036 | 26724
13167 | 407.6511 | 26724
13168 | 416.0578 | 26724
13169 | 415.5108 | 26724
13170 | 412.9695 | 26724
13171 | 424.3591 | 26724
13172 | 427.9896 | 26724
13173 | 409.387 | 26724
13174 | 409.1562 | 26724
13175 | 407.0766 | 26724
13176 | 409.7331 | 26724
13177 | 408.1514 | 26724
13178 | 420.1207 | 26724
13179 | 426.5255 | 26724
13180 | 419.6303 | 26724
13181 | 418.7403 | 26724
13182 | 414.4138 | 26724
13183 | 413.4102 | 26724
13184 | 427.1393 | 26724
13185 | 436.0534 | 26724
13186 | 427.7697 | 26724
13187 | 410.3595 | 26724
13188 | 420.8661 | 26724
13189 | 427.4811 | 26724
13190 | 406.7893 | 26724
13191 | 405.0551 | 26724
13192 | 406.3662 | 26724
13193 | 419.7517 | 26724
13194 | 421.3148 | 26724
13195 | 413.9124 | 26724
13196 | 425.3424 | 26724
13197 | 414.3158 | 26724
13198 | 404.555 | 26724
13199 | 415.0009 | 26724
13200 | 415.3048 | 26724
13201 | 413.8198 | 26724
13202 | 425.0748 | 26724
13203 | 425.8906 | 26724
13204 | 427.4172 | 26724
13205 | 399.6106 | 26724
13206 | 407.6527 | 26724
13207 | 413.3794 | 26724
13208 | 419.9301 | 26724
13209 | 406.0621 | 26724
13210 | 400.4829 | 26724
13211 | 403.0554 | 26724
13212 | 424.4925 | 26724
13213 | 413.7381 | 26724
13214 | 411.4792 | 26724
13215 | 420.4992 | 26724
13216 | 410.3299 | 26724
13217 | 418.3896 | 26724
13218 | 413.4034 | 26724
13219 | 423.4346 | 26724
13220 | 427.8367 | 26724
13221 | 407.4564 | 26724
13222 | 420.6019 | 26724
13223 | 412.8868 | 26724
13224 | 428.9199 | 26724
13225 | 401.1468 | 26724
13226 | 414.0178 | 26724
13227 | 408.5286 | 26724
13228 | 405.9305 | 26724
13229 | 424.1322 | 26724
13230 | 398.2997 | 26724
13231 | 418.5363 | 26724
13232 | 422.1027 | 26724
13233 | 410.9673 | 26724
13234 | 410.819 | 26724
13235 | 403.9396 | 26724
13236 | 412.0742 | 26724
13237 | 414.1284 | 26724
13238 | 404.8159 | 26724
13239 | 421.6545 | 26724
13240 | 423.7124 | 26724
13241 | 401.2794 | 26724
13242 | 407.5181 | 26724
13243 | 408.7099 | 26724
13244 | 416.0312 | 26724
13245 | 427.1777 | 26724
13246 | 419.9417 | 26724
13247 | 415.3648 | 26724
13248 | 418.7778 | 26724
13249 | 397.216 | 26724
13250 | 422.9323 | 26724
13251 | 421.2649 | 26724
13252 | 399.8246 | 26724
13253 | 414.1673 | 26724
13254 | 409.1025 | 26724
13255 | 424.27 | 26724
13256 | 424.8674 | 26724
13257 | 411.233 | 26724
13258 | 420.8433 | 26724
13259 | 419.2428 | 26724
13260 | 436.8023 | 26724
13261 | 410.1215 | 26724
13262 | 414.4015 | 26724
13263 | 405.9045 | 26724
13264 | 402.9748 | 26724
13265 | 423.072 | 26724
13266 | 418.2688 | 26724
13267 | 420.9367 | 26724
13268 | 414.7297 | 26724
13269 | 412.018 | 26724
13270 | 411.8239 | 26724
13271 | 399.9674 | 26724
13272 | 419.1344 | 26724
13273 | 421.6222 | 26724
13274 | 398.5534 | 26724
13275 | 421.389 | 26724
13276 | 421.1851 | 26724
13277 | 429.7502 | 26724
13278 | 405.5211 | 26724
13279 | 415.6315 | 26724
13280 | 421.8723 | 26724
13281 | 415.2509 | 26724
13282 | 425.0966 | 26724
13283 | 423.2292 | 26724
13284 | 411.6327 | 26724
13285 | 411.9744 | 26724
13286 | 405.3915 | 26724
13287 | 414.3881 | 26724
13288 | 412.3882 | 26724
13289 | 423.3849 | 26724
13290 | 421.8203 | 26724
13291 | 416.0822 | 26724
13292 | 416.9093 | 26724
13293 | 407.4 | 26724
13294 | 413.7612 | 26724
13295 | 414.9903 | 26724
13296 | 408.2874 | 26724
13297 | 421.3141 | 26724
13298 | 420.1934 | 26724
13299 | 415.7906 | 26724
13300 | 419.7024 | 26724
13301 | 418.052 | 26724
13302 | 404.8372 | 26724
13303 | 408.8321 | 26724
13304 | 404.9121 | 26724
13305 | 411.697 | 26724
13306 | 427.8479 | 26724
13307 | 400.6152 | 26724
13308 | 414.4539 | 26724
13309 | 408.8835 | 26724
13310 | 419.4944 | 26724
13311 | 410.8366 | 26724
13312 | 413.2729 | 26724
13313 | 426.7763 | 26724
13314 | 430.7161 | 26724
13315 | 415.3541 | 26724
13316 | 422.6258 | 26724
13317 | 411.3664 | 26724
13318 | 409.172 | 26724
13319 | 404.8174 | 26724
13320 | 402.6061 | 26724
13321 | 412.9145 | 26724
13322 | 428.6462 | 26724
13323 | 419.7765 | 26724
13324 | 435.0715 | 26724
13325 | 428.2147 | 26724
13326 | 416.7188 | 26724
13327 | 418.4963 | 26724
13328 | 422.5139 | 26724
13329 | 414.68 | 26724
13330 | 417.8017 | 26724
13331 | 410.7666 | 26724
13332 | 432.4238 | 26724
13333 | 405.1108 | 26724
13334 | 403.244 | 26724
13335 | 412.317 | 26724
13336 | 412.4178 | 26724
13337 | 412.5968 | 26724
13338 | 426.6135 | 26724
13339 | 413.7846 | 26724
13340 | 408.1217 | 26724
13341 | 415.8471 | 26724
13342 | 422.2647 | 26724
13343 | 409.9291 | 26724
13344 | 417.1394 | 26724
13345 | 409.8297 | 26724
13346 | 435.3464 | 26724
13347 | 427.9398 | 26724
13348 | 411.0319 | 26724
13349 | 412.7286 | 26724
13350 | 403.186 | 26724
13351 | 423.7876 | 26724
13352 | 414.4108 | 26724
13353 | 415.2732 | 26724
13354 | 398.4723 | 26724
13355 | 404.2883 | 26724
13356 | 422.0865 | 26724
13357 | 419.4149 | 26724
13358 | 412.409 | 26724
13359 | 425.6457 | 26724
13360 | 415.2887 | 26724
13361 | 414.9582 | 26724
13362 | 419.822 | 26724
13363 | 401.1368 | 26724
13364 | 415.2156 | 26724
13365 | 421.0228 | 26724
13366 | 424.9077 | 26724
13367 | 408.1714 | 26724
13368 | 420.9237 | 26724
13369 | 399.9034 | 26724
13370 | 414.573 | 26724
13371 | 423.0199 | 26724
13372 | 417.7586 | 26724
13373 | 411.2133 | 26724
13374 | 406.0995 | 26724
13375 | 413.6926 | 26724
13376 | 411.3214 | 26724
13377 | 414.4354 | 26724
13378 | 416.6893 | 26724
13379 | 401.2042 | 26724
13380 | 407.7629 | 26724
13381 | 422.3005 | 26724
13382 | 415.071 | 26724
13383 | 414.6723 | 26724
13384 | 411.8168 | 26724
13385 | 412.4579 | 26724
13386 | 432.9611 | 26724
13387 | 416.8148 | 26724
13388 | 412.1893 | 26724
13389 | 421.567 | 26724
13390 | 413.9169 | 26724
13391 | 412.4042 | 26724
13392 | 410.9405 | 26724
13393 | 415.7785 | 26724
13394 | 427.9407 | 26724
13395 | 408.6865 | 26724
13396 | 417.3638 | 26724
13397 | 417.1382 | 26724
13398 | 422.5341 | 26724
13399 | 410.237 | 26724
13400 | 404.9463 | 26724
13401 | 414.6785 | 26724
13402 | 415.8168 | 26724
13403 | 423.7622 | 26724
13404 | 423.5405 | 26724
13405 | 405.824 | 26724
13406 | 418.5162 | 26724
13407 | 417.6733 | 26724
13408 | 423.3352 | 26724
13409 | 416.8549 | 26724
13410 | 412.7682 | 26724
13411 | 412.0407 | 26724
13412 | 420.0933 | 26724
13413 | 421.5835 | 26724
13414 | 413.1223 | 26724
13415 | 411.6767 | 26724
13416 | 415.8442 | 26724
13417 | 410.486 | 26724
13418 | 419.5123 | 26724
13419 | 426.6405 | 26724
13420 | 417.9961 | 26724
13421 | 416.9738 | 26724
13422 | 410.4123 | 26724
13423 | 414.1346 | 26724
13424 | 412.3766 | 26724
13425 | 429.5754 | 26724
13426 | 425.3085 | 26724
13427 | 417.7566 | 26724
13428 | 434.6236 | 26724
13429 | 404.0729 | 26724
13430 | 413.8453 | 26724
13431 | 405.9176 | 26724
13432 | 422.7237 | 26724
13433 | 421.096 | 26724
13434 | 418.0913 | 26724
13435 | 422.6614 | 26724
13436 | 424.8872 | 26724
13437 | 416.3975 | 26724
13438 | 418.7766 | 26724
13439 | 424.1541 | 26724
13440 | 395.2981 | 26724
13441 | 415.0337 | 26724
13442 | 428.1343 | 26724
13443 | 415.3757 | 26724
13444 | 419.0034 | 26724
13445 | 413.0884 | 26724
13446 | 425.341 | 26724
13447 | 423.0581 | 26724
13448 | 405.6035 | 26724
13449 | 414.5686 | 26724
13450 | 411.536 | 26724
13451 | 420.6994 | 26724
13452 | 429.2824 | 26724
13453 | 406.2602 | 26724
13454 | 399.3287 | 26724
13455 | 416.1933 | 26724
13456 | 420.1055 | 26724
13457 | 428.2654 | 26724
13458 | 407.5679 | 26724
13459 | 405.0888 | 26724
13460 | 418.8198 | 26724
13461 | 413.1274 | 26724
13462 | 418.3991 | 26724
13463 | 407.5975 | 26724
13464 | 413.0407 | 26724
13465 | 420.911 | 26724
13466 | 420.8649 | 26724
13467 | 409.9929 | 26724
13468 | 415.596 | 26724
13469 | 428.1156 | 26724
13470 | 420.3749 | 26724
13471 | 406.3809 | 26724
13472 | 406.5741 | 26724
13473 | 410.124 | 26724
13474 | 410.3013 | 26724
13475 | 415.3125 | 26724
13476 | 428.0991 | 26724
13477 | 415.2979 | 26724
13478 | 423.8419 | 26724
13479 | 425.9373 | 26724
13480 | 425.7668 | 26724
13481 | 432.4778 | 26724
13482 | 422.6205 | 26724
13483 | 420.2106 | 26724
13484 | 414.0862 | 26724
13485 | 414.5926 | 26724
13486 | 407.543 | 26724
13487 | 418.6436 | 26724
13488 | 412.2206 | 26724
13489 | 423.105 | 26724
13490 | 416.5762 | 26724
13491 | 416.0313 | 26724
13492 | 408.5998 | 26724
13493 | 402.8029 | 26724
13494 | 427.8759 | 26724
13495 | 419.985 | 26724
13496 | 415.8721 | 26724
13497 | 433.8615 | 26724
13498 | 418.5305 | 26724
13499 | 414.8409 | 26724
13500 | 413.9004 | 26724
13501 | 425.8294 | 26724
13502 | 410.2303 | 26724
13503 | 411.3645 | 26724
13504 | 426.0972 | 26724
13505 | 412.5734 | 26724
13506 | 418.7846 | 26724
13507 | 401.9783 | 26724
13508 | 407.0996 | 26724
13509 | 412.6043 | 26724
13510 | 411.7028 | 26724
13511 | 409.1867 | 26724
13512 | 413.1075 | 26724
13513 | 413.4528 | 26724
13514 | 419.9768 | 26724
13515 | 393.7217 | 26724
13516 | 423.2417 | 26724
13517 | 411.7012 | 26724
13518 | 419.4752 | 26724
13519 | 423.984 | 26724
13520 | 407.6392 | 26724
13521 | 414.3799 | 26724
13522 | 425.8723 | 26724
13523 | 425.0746 | 26724
13524 | 426.955 | 26724
13525 | 412.5528 | 26724
13526 | 430.5543 | 26724
13527 | 415.6822 | 26724
13528 | 410.4036 | 26724
13529 | 414.3965 | 26724
13530 | 413.4147 | 26724
13531 | 420.5349 | 26724
13532 | 425.2802 | 26724
13533 | 420.7406 | 26724
13534 | 434.1478 | 26724
13535 | 418.4267 | 26724
13536 | 424.5231 | 26724
13537 | 415.8189 | 26724
13538 | 415.1725 | 26724
13539 | 411.1204 | 26724
13540 | 431.285 | 26724
13541 | 418.3931 | 26724
13542 | 413.825 | 26724
13543 | 398.3161 | 26724
13544 | 417.1035 | 26724
13545 | 424.5897 | 26724
13546 | 408.1597 | 26724
13547 | 424.3609 | 26724
13548 | 404.3455 | 26724
13549 | 419.5616 | 26724
13550 | 411.1122 | 26724
13551 | 425.3253 | 26724
13552 | 418.0061 | 26724
13553 | 416.2123 | 26724
13554 | 427.6366 | 26724
13555 | 412.5616 | 26724
13556 | 403.8277 | 26724
13557 | 418.6795 | 26724
13558 | 408.5169 | 26724
13559 | 421.1389 | 26724
13560 | 420.2434 | 26724
13561 | 417.4058 | 26724
13562 | 416.335 | 26724
13563 | 408.9713 | 26724
13564 | 412.0981 | 26724
13565 | 409.3154 | 26724
13566 | 416.3894 | 26724
13567 | 426.9974 | 26724
13568 | 409.1816 | 26724
13569 | 423.4184 | 26724
13570 | 414.017 | 26724
13571 | 404.8151 | 26724
13572 | 418.5232 | 26724
13573 | 408.6436 | 26724
13574 | 413.55 | 26724
13575 | 415.4224 | 26724
13576 | 411.2268 | 26724
13577 | 427.3703 | 26724
13578 | 416.4801 | 26724
13579 | 422.2176 | 26724
13580 | 402.3902 | 26724
13581 | 423.2675 | 26724
13582 | 413.6046 | 26724
13583 | 422.666 | 26724
13584 | 420.0561 | 26724
13585 | 418.4668 | 26724
13586 | 415.232 | 26724
13587 | 421.7332 | 26724
13588 | 404.7484 | 26724
13589 | 425.2006 | 26724
13590 | 406.0582 | 26724
13591 | 407.5613 | 26724
13592 | 415.9881 | 26724
13593 | 428.8242 | 26724
13594 | 399.7023 | 26724
13595 | 417.3445 | 26724
13596 | 423.5624 | 26724
13597 | 409.0394 | 26724
13598 | 427.1777 | 26724
13599 | 426.8629 | 26724
13600 | 414.0119 | 26724
13601 | 399.513 | 26724
13602 | 418.5645 | 26724
13603 | 409.8877 | 26724
13604 | 424.7482 | 26724
13605 | 411.6439 | 26724
13606 | 423.3752 | 26724
13607 | 415.554 | 26724
13608 | 429.9373 | 26724
13609 | 427.2104 | 26724
13610 | 430.2846 | 26724
13611 | 420.0877 | 26724
13612 | 417.7567 | 26724
13613 | 418.6495 | 26724
13614 | 411.5768 | 26724
13615 | 402.3853 | 26724
13616 | 422.0799 | 26724
13617 | 418.7843 | 26724
13618 | 431.2848 | 26724
13619 | 418.3213 | 26724
13620 | 416.4222 | 26724
13621 | 411.4161 | 26724
13622 | 430.6634 | 26724
13623 | 411.0767 | 26724
13624 | 416.7173 | 26724
13625 | 408.1962 | 26724
13626 | 434.2827 | 26724
13627 | 412.8008 | 26724
13628 | 415.2117 | 26724
13629 | 413.2018 | 26724
13630 | 410.547 | 26724
13631 | 425.247 | 26724
13632 | 410.0436 | 26724
13633 | 398.769 | 26724
13634 | 412.6607 | 26724
13635 | 425.3829 | 26724
13636 | 422.7362 | 26724
13637 | 415.0989 | 26724
13638 | 419.7554 | 26724
13639 | 420.2494 | 26724
13640 | 414.1296 | 26724
13641 | 414.1683 | 26724
13642 | 437.8682 | 26724
13643 | 424.6284 | 26724
13644 | 406.3593 | 26724
13645 | 420.5856 | 26724
13646 | 423.3718 | 26724
13647 | 407.2122 | 26724
13648 | 430.9211 | 26724
13649 | 415.2127 | 26724
13650 | 413.5452 | 26724
13651 | 414.5477 | 26724
13652 | 405.9233 | 26724
13653 | 401.1499 | 26724
13654 | 422.0985 | 26724
13655 | 408.7526 | 26724
13656 | 411.2103 | 26724
13657 | 420.5496 | 26724
13658 | 408.127 | 26724
13659 | 415.678 | 26724
13660 | 420.9926 | 26724
13661 | 416.9074 | 26724
13662 | 421.6806 | 26724
13663 | 417.6683 | 26724
13664 | 421.2674 | 26724
13665 | 405.7546 | 26724
13666 | 417.9177 | 26724
13667 | 421.8693 | 26724
13668 | 413.796 | 26724
13669 | 423.8922 | 26724
13670 | 425.7008 | 26724
13671 | 415.6537 | 26724
13672 | 419.7165 | 26724
13673 | 413.2221 | 26724
13674 | 425.6219 | 26724
13675 | 414.7299 | 26724
13676 | 421.2378 | 26724
13677 | 425.8009 | 26724
13678 | 409.7506 | 26724
13679 | 414.876 | 26724
13680 | 416.1763 | 26724
13681 | 406.1624 | 26724
13682 | 430.0421 | 26724
13683 | 416.8768 | 26724
13684 | 428.0182 | 26724
13685 | 419.9862 | 26724
13686 | 415.8344 | 26724
13687 | 414.6333 | 26724
13688 | 406.3346 | 26724
13689 | 399.9455 | 26724
13690 | 431.5556 | 26724
13691 | 412.6682 | 26724
13692 | 411.316 | 26724
13693 | 411.5525 | 26724
13694 | 418.7342 | 26724
13695 | 405.8839 | 26724
13696 | 415.5093 | 26724
13697 | 422.2036 | 26724
13698 | 409.2518 | 26724
13699 | 430.4385 | 26724
13700 | 419.2783 | 26724
13701 | 421.2724 | 26724
13702 | 415.4753 | 26724
13703 | 412.9899 | 26724
13704 | 413.3013 | 26724
13705 | 422.7104 | 26724
13706 | 411.9693 | 26724
13707 | 411.2135 | 26724
13708 | 413.4432 | 26724
13709 | 417.3798 | 26724
13710 | 409.551 | 26724
13711 | 412.5932 | 26724
13712 | 423.7973 | 26724
13713 | 407.4051 | 26724
13714 | 422.3552 | 26724
13715 | 412.9137 | 26724
13716 | 412.0741 | 26724
13717 | 411.8992 | 26724
13718 | 425.324 | 26724
13719 | 414.4447 | 26724
13720 | 411.5144 | 26724
13721 | 406.3726 | 26724
13722 | 399.2077 | 26724
13723 | 415.3902 | 26724
13724 | 429.517 | 26724
13725 | 419.5816 | 26724
13726 | 422.5962 | 26724
13727 | 411.4559 | 26724
13728 | 420.934 | 26724
13729 | 424.5538 | 26724
13730 | 425.2876 | 26724
13731 | 407.575 | 26724
13732 | 412.9123 | 26724
13733 | 414.0711 | 26724
13734 | 406.1331 | 26724
13735 | 421.3197 | 26724
13736 | 421.2836 | 26724
13737 | 413.0043 | 26724
13738 | 422.888 | 26724
13739 | 415.1039 | 26724
13740 | 406.9124 | 26724
13741 | 410.3135 | 26724
13742 | 401.2221 | 26724
13743 | 421.2967 | 26724
13744 | 405.5227 | 26724
13745 | 402.8606 | 26724
13746 | 415.8226 | 26724
13747 | 406.4907 | 26724
13748 | 413.5685 | 26724
13749 | 430.4287 | 26724
13750 | 424.6257 | 26724
13751 | 422.7506 | 26724
13752 | 414.0129 | 26724
13753 | 413.9082 | 26724
13754 | 405.148 | 26724
13755 | 431.8196 | 26724
13756 | 415.7415 | 26724
13757 | 418.8617 | 26724
13758 | 413.7977 | 26724
13759 | 417.1757 | 26724
13760 | 416.3701 | 26724
13761 | 414.767 | 26724
13762 | 411.1651 | 26724
13763 | 412.9942 | 26724
13764 | 423.3103 | 26724
13765 | 401.0117 | 26724
13766 | 425.1379 | 26724
13767 | 415.0161 | 26724
13768 | 412.0305 | 26724
13769 | 432.1581 | 26724
13770 | 419.1212 | 26724
13771 | 416.9082 | 26724
13772 | 432.0623 | 26724
13773 | 411.6325 | 26724
13774 | 406.8103 | 26724
13775 | 414.0217 | 26724
13776 | 411.1724 | 26724
13777 | 423.871 | 26724
13778 | 405.9509 | 26724
13779 | 426.38 | 26724
13780 | 416.1702 | 26724
13781 | 407.8229 | 26724
13782 | 430.4385 | 26724
13783 | 418.4506 | 26724
13784 | 404.6571 | 26724
13785 | 418.9735 | 26724
13786 | 424.1965 | 26724
13787 | 410.6259 | 26724
13788 | 416.7937 | 26724
13789 | 416.3336 | 26724
13790 | 425.3105 | 26724
13791 | 426.1132 | 26724
13792 | 418.5847 | 26724
13793 | 421.5599 | 26724
13794 | 407.5893 | 26724
13795 | 411.6948 | 26724
13796 | 434.8229 | 26724
13797 | 395.4725 | 26724
13798 | 426.8524 | 26724
13799 | 433.3112 | 26724
13800 | 411.4172 | 26724
13801 | 419.8825 | 26724
13802 | 404.5698 | 26724
13803 | 413.5206 | 26724
13804 | 424.1853 | 26724
13805 | 426.5928 | 26724
13806 | 410.6426 | 26724
13807 | 419.847 | 26724
13808 | 413.5088 | 26724
13809 | 430.4324 | 26724
13810 | 421.8386 | 26724
13811 | 426.6808 | 26724
13812 | 394.968 | 26724
13813 | 416.175 | 26724
13814 | 422.2725 | 26724
13815 | 399.8617 | 26724
13816 | 423.7633 | 26724
13817 | 429.1696 | 26724
13818 | 403.8042 | 26724
13819 | 423.576 | 26724
13820 | 410.1877 | 26724
13821 | 417.1735 | 26724
13822 | 406.1635 | 26724
13823 | 416.2946 | 26724
13824 | 418.6676 | 26724
13825 | 417.8834 | 26724
13826 | 414.3402 | 26724
13827 | 412.9063 | 26724
13828 | 419.35 | 26724
13829 | 404.9696 | 26724
13830 | 407.6195 | 26724
13831 | 418.1625 | 26724
13832 | 406.1748 | 26724
13833 | 416.1148 | 26724
13834 | 424.0523 | 26724
13835 | 417.1662 | 26724
13836 | 401.0733 | 26724
13837 | 412.5115 | 26724
13838 | 413.7763 | 26724
13839 | 420.2979 | 26724
13840 | 404.5817 | 26724
13841 | 421.2535 | 26724
13842 | 413.294 | 26724
13843 | 411.7145 | 26724
13844 | 421.253 | 26724
13845 | 418.1302 | 26724
13846 | 410.8123 | 26724
13847 | 407.219 | 26724
13848 | 416.8636 | 26724
13849 | 415.8384 | 26724
13850 | 423.6882 | 26724
13851 | 409.8601 | 26724
13852 | 406.3322 | 26724
13853 | 422.7421 | 26724
13854 | 416.2486 | 26724
13855 | 415.0582 | 26724
13856 | 404.218 | 26724
13857 | 408.8291 | 26724
13858 | 408.0824 | 26724
13859 | 402.9265 | 26724
13860 | 419.3083 | 26724
13861 | 429.9547 | 26724
13862 | 415.3796 | 26724
13863 | 435.6726 | 26724
13864 | 429.2262 | 26724
13865 | 409.9091 | 26724
13866 | 431.0801 | 26724
13867 | 415.1619 | 26724
13868 | 423.065 | 26724
13869 | 428.4177 | 26724
13870 | 415.7497 | 26724
13871 | 414.0601 | 26724
13872 | 420.3459 | 26724
13873 | 418.3609 | 26724
13874 | 419.8546 | 26724
13875 | 423.3145 | 26724
13876 | 429.8619 | 26724
13877 | 424.3822 | 26724
13878 | 429.8558 | 26724
13879 | 415.7133 | 26724
13880 | 413.0396 | 26724
13881 | 426.468 | 26724
13882 | 420.9694 | 26724
13883 | 428.527 | 26724
13884 | 399.2296 | 26724
13885 | 405.7344 | 26724
13886 | 415.7924 | 26724
13887 | 419.263 | 26724
13888 | 426.9716 | 26724
13889 | 417.9716 | 26724
13890 | 417.858 | 26724
13891 | 418.2969 | 26724
13892 | 397.3 | 26724
13893 | 411.2137 | 26724
13894 | 403.1514 | 26724
13895 | 422.7937 | 26724
13896 | 407.5288 | 26724
13897 | 406.5368 | 26724
13898 | 417.307 | 26724
13899 | 425.8079 | 26724
13900 | 410.7994 | 26724
13901 | 407.9325 | 26724
13902 | 417.5802 | 26724
13903 | 411.3309 | 26724
13904 | 423.5938 | 26724
13905 | 408.5753 | 26724
13906 | 421.2934 | 26724
13907 | 418.8063 | 26724
13908 | 405.634 | 26724
13909 | 422.6059 | 26724
13910 | 402.221 | 26724
13911 | 408.6434 | 26724
13912 | 421.0371 | 26724
13913 | 410.2088 | 26724
13914 | 416.8542 | 26724
13915 | 419.4191 | 26724
13916 | 422.3002 | 26724
13917 | 408.0596 | 26724
13918 | 416.7053 | 26724
13919 | 422.7663 | 26724
13920 | 421.695 | 26724
13921 | 414.3037 | 26724
13922 | 404.5011 | 26724
13923 | 421.6652 | 26724
13924 | 423.9576 | 26724
13925 | 427.1534 | 26724
13926 | 428.4483 | 26724
13927 | 415.2971 | 26724
13928 | 427.4484 | 26724
13929 | 413.5032 | 26724
13930 | 425.2316 | 26724
13931 | 412.2916 | 26724
13932 | 422.2224 | 26724
13933 | 426.1675 | 26724
13934 | 424.0071 | 26724
13935 | 415.1932 | 26724
13936 | 414.2025 | 26724
13937 | 396.5803 | 26724
13938 | 416.4245 | 26724
13939 | 403.137 | 26724
13940 | 428.8716 | 26724
13941 | 413.9042 | 26724
13942 | 419.9904 | 26724
13943 | 410.1588 | 26724
13944 | 414.4002 | 26724
13945 | 423.7717 | 26724
13946 | 427.8624 | 26724
13947 | 426.2827 | 26724
13948 | 403.397 | 26724
13949 | 420.6349 | 26724
13950 | 409.3507 | 26724
13951 | 397.1734 | 26724
13952 | 424.2625 | 26724
13953 | 424.9435 | 26724
13954 | 411.667 | 26724
13955 | 416.3509 | 26724
13956 | 413.8824 | 26724
13957 | 430.1958 | 26724
13958 | 410.4367 | 26724
13959 | 415.3733 | 26724
13960 | 427.5793 | 26724
13961 | 422.5928 | 26724
13962 | 416.2989 | 26724
13963 | 411.7937 | 26724
13964 | 434.9223 | 26724
13965 | 419.5368 | 26724
13966 | 413.0126 | 26724
13967 | 417.8455 | 26724
13968 | 418.4218 | 26724
13969 | 417.6109 | 26724
13970 | 429.207 | 26724
13971 | 414.3254 | 26724
13972 | 423.9281 | 26724
13973 | 417.8782 | 26724
13974 | 418.0989 | 26724
13975 | 416.3865 | 26724
13976 | 423.5156 | 26724
13977 | 423.2242 | 26724
13978 | 407.7611 | 26724
13979 | 418.8753 | 26724
13980 | 417.3091 | 26724
13981 | 408.1629 | 26724
13982 | 399.7651 | 26724
13983 | 423.6202 | 26724
13984 | 412.2482 | 26724
13985 | 413.6423 | 26724
13986 | 421.0012 | 26724
13987 | 420.9248 | 26724
13988 | 417.6388 | 26724
13989 | 417.1981 | 26724
13990 | 416.4388 | 26724
13991 | 407.7525 | 26724
13992 | 420.3859 | 26724
13993 | 413.605 | 26724
13994 | 424.0937 | 26724
13995 | 413.1147 | 26724
13996 | 424.6306 | 26724
13997 | 409.8018 | 26724
13998 | 415.8236 | 26724
13999 | 426.9784 | 26724
14000 | 420.5713 | 26724
14001 | 394.5179 | 26724
14002 | 407.5925 | 26724
14003 | 418.0654 | 26724
14004 | 411.1095 | 26724
14005 | 426.684 | 26724
14006 | 426.0844 | 26724
14007 | 414.4939 | 26724
14008 | 417.8109 | 26724
14009 | 420.7215 | 26724
14010 | 420.6597 | 26724
14011 | 416.4386 | 26724
14012 | 406.8794 | 26724
14013 | 436.8606 | 26724
14014 | 406.671 | 26724
14015 | 416.2775 | 26724
14016 | 429.3466 | 26724
14017 | 419.5131 | 26724
14018 | 397.4425 | 26724
14019 | 416.5557 | 26724
14020 | 420.5258 | 26724
14021 | 411.8855 | 26724
14022 | 424.8363 | 26724
14023 | 433.8383 | 26724
14024 | 412.4071 | 26724
14025 | 418.5568 | 26724
14026 | 408.0571 | 26724
14027 | 403.2599 | 26724
14028 | 402.4788 | 26724
14029 | 423.987 | 26724
14030 | 430.5902 | 26724
14031 | 419.7221 | 26724
14032 | 423.0627 | 26724
14033 | 413.8662 | 26724
14034 | 417.47 | 26724
14035 | 419.6792 | 26724
14036 | 414.3717 | 26724
14037 | 410.0777 | 26724
14038 | 411.8924 | 26724
14039 | 412.7079 | 26724
14040 | 425.9604 | 26724
14041 | 427.5538 | 26724
14042 | 422.3849 | 26724
14043 | 398.554 | 26724
14044 | 400.2267 | 26724
14045 | 425.9164 | 26724
14046 | 406.0173 | 26724
14047 | 405.5674 | 26724
14048 | 431.4296 | 26724
14049 | 401.6861 | 26724
14050 | 429.4205 | 26724
14051 | 402.9283 | 26724
14052 | 413.8268 | 26724
14053 | 421.94 | 26724
14054 | 416.0681 | 26724
14055 | 430.5648 | 26724
14056 | 434.19 | 26724
14057 | 414.1041 | 26724
14058 | 409.7298 | 26724
14059 | 417.786 | 26724
14060 | 421.6852 | 26724
14061 | 421.2384 | 26724
14062 | 426.4994 | 26724
14063 | 406.8511 | 26724
14064 | 413.7757 | 26724
14065 | 424.2695 | 26724
14066 | 418.7475 | 26724
14067 | 425.2944 | 26724
14068 | 423.2851 | 26724
14069 | 435.1535 | 26724
14070 | 418.8479 | 26724
14071 | 406.5754 | 26724
14072 | 413.8862 | 26724
14073 | 400.405 | 26724
14074 | 413.4462 | 26724
14075 | 422.1711 | 26724
14076 | 415.9258 | 26724
14077 | 404.4292 | 26724
14078 | 417.8918 | 26724
14079 | 408.1919 | 26724
14080 | 426.3989 | 26724
14081 | 426.7751 | 26724
14082 | 425.7895 | 26724
14083 | 415.4988 | 26724
14084 | 412.3079 | 26724
14085 | 412.2409 | 26724
14086 | 407.7583 | 26724
14087 | 415.6866 | 26724
14088 | 417.5142 | 26724
14089 | 427.7759 | 26724
14090 | 410.5924 | 26724
14091 | 426.7236 | 26724
14092 | 419.4176 | 26724
14093 | 419.0079 | 26724
14094 | 421.7582 | 26724
14095 | 423.6008 | 26724
14096 | 419.687 | 26724
14097 | 413.0292 | 26724
14098 | 420.6029 | 26724
14099 | 416.3339 | 26724
14100 | 404.7523 | 26724
14101 | 404.8957 | 26724
14102 | 410.445 | 26724
14103 | 418.6897 | 26724
14104 | 405.461 | 26724
14105 | 418.1172 | 26724
14106 | 424.3648 | 26724
14107 | 421.5853 | 26724
14108 | 414.6014 | 26724
14109 | 421.2105 | 26724
14110 | 411.2774 | 26724
14111 | 417.6742 | 26724
14112 | 424.704 | 26724
14113 | 423.4616 | 26724
14114 | 419.5498 | 26724
14115 | 415.6286 | 26724
14116 | 414.4737 | 26724
14117 | 409.1717 | 26724
14118 | 411.0464 | 26724
14119 | 411.2537 | 26724
14120 | 411.3015 | 26724
14121 | 415.6825 | 26724
14122 | 411.1939 | 26724
14123 | 424.1401 | 26724
14124 | 419.5375 | 26724
14125 | 427.9765 | 26724
14126 | 420.3317 | 26724
14127 | 409.7745 | 26724
14128 | 421.0628 | 26724
14129 | 406.5369 | 26724
14130 | 421.1122 | 26724
14131 | 410.9829 | 26724
14132 | 410.9613 | 26724
14133 | 419.1456 | 26724
14134 | 405.6204 | 26724
14135 | 407.3209 | 26724
14136 | 398.7438 | 26724
14137 | 411.2429 | 26724
14138 | 400.7026 | 26724
14139 | 407.9461 | 26724
14140 | 422.8926 | 26724
14141 | 419.6722 | 26724
14142 | 406.8044 | 26724
14143 | 414.3482 | 26724
14144 | 397.3188 | 26724
14145 | 418.5928 | 26724
14146 | 413.6186 | 26724
14147 | 416.6431 | 26724
14148 | 419.1131 | 26724
14149 | 427.0969 | 26724
14150 | 416.7321 | 26724
14151 | 423.5609 | 26724
14152 | 424.0443 | 26724
14153 | 415.4024 | 26724
14154 | 405.1296 | 26724
14155 | 422.6425 | 26724
14156 | 407.223 | 26724
14157 | 424.0353 | 26724
14158 | 411.9334 | 26724
14159 | 426.1333 | 26724
14160 | 413.2978 | 26724
14161 | 417.9279 | 26724
14162 | 406.7037 | 26724
14163 | 428.2134 | 26724
14164 | 413.7241 | 26724
14165 | 410.7959 | 26724
14166 | 415.0462 | 26724
14167 | 405.2673 | 26724
14168 | 415.6821 | 26724
14169 | 426.6664 | 26724
14170 | 415.2367 | 26724
14171 | 412.7834 | 26724
14172 | 424.0579 | 26724
14173 | 418.5219 | 26724
14174 | 419.195 | 26724
14175 | 432.813 | 26724
14176 | 419.1976 | 26724
14177 | 415.8375 | 26724
14178 | 424.601 | 26724
14179 | 412.1171 | 26724
14180 | 410.7089 | 26724
14181 | 415.6681 | 26724
14182 | 435.0221 | 26724
14183 | 418.4295 | 26724
14184 | 412.1368 | 26724
14185 | 415.6199 | 26724
14186 | 418.922 | 26724
14187 | 423.8624 | 26724
14188 | 415.8071 | 26724
14189 | 407.2929 | 26724
14190 | 413.5108 | 26724
14191 | 414.4961 | 26724
14192 | 409.4993 | 26724
14193 | 417.7167 | 26724
14194 | 421.3394 | 26724
14195 | 412.0229 | 26724
14196 | 418.0365 | 26724
14197 | 409.4414 | 26724
14198 | 409.2787 | 26724
14199 | 421.3773 | 26724
14200 | 407.891 | 26724
14201 | 419.8728 | 26724
14202 | 411.9432 | 26724
14203 | 431.4589 | 26724
14204 | 423.0339 | 26724
14205 | 416.0709 | 26724
14206 | 418.6829 | 26724
14207 | 431.8042 | 26724
14208 | 406.1206 | 26724
14209 | 428.4799 | 26724
14210 | 411.1767 | 26724
14211 | 404.8988 | 26724
14212 | 419.4129 | 26724
14213 | 411.6012 | 26724
14214 | 423.6726 | 26724
14215 | 412.1912 | 26724
14216 | 415.2779 | 26724
14217 | 417.279 | 26724
14218 | 422.6773 | 26724
14219 | 425.2353 | 26724
14220 | 409.51 | 26724
14221 | 402.8102 | 26724
14222 | 407.6203 | 26724
14223 | 422.1658 | 26724
14224 | 424.6025 | 26724
14225 | 420.9922 | 26724
14226 | 407.026 | 26724
14227 | 419.9513 | 26724
14228 | 411.8233 | 26724
14229 | 419.5951 | 26724
14230 | 413.4234 | 26724
14231 | 426.9338 | 26724
14232 | 415.386 | 26724
14233 | 415.0662 | 26724
14234 | 431.2617 | 26724
14235 | 410.6564 | 26724
14236 | 407.4631 | 26724
14237 | 399.9739 | 26724
14238 | 427.0702 | 26724
14239 | 414.6823 | 26724
14240 | 416.493 | 26724
14241 | 407.529 | 26724
14242 | 422.0991 | 26724
14243 | 415.1843 | 26724
14244 | 402.9387 | 26724
14245 | 417.9053 | 26724
14246 | 437.0303 | 26724
14247 | 424.2862 | 26724
14248 | 405.8084 | 26724
14249 | 410.7549 | 26724
14250 | 414.8809 | 26724
14251 | 415.3912 | 26724
14252 | 426.1864 | 26724
14253 | 414.9254 | 26724
14254 | 423.4726 | 26724
14255 | 424.4147 | 26724
14256 | 418.2118 | 26724
14257 | 412.9715 | 26724
14258 | 407.1126 | 26724
14259 | 421.6025 | 26724
14260 | 430.9495 | 26724
14261 | 428.37 | 26724
14262 | 413.3311 | 26724
14263 | 422.9857 | 26724
14264 | 406.5698 | 26724
14265 | 417.6763 | 26724
14266 | 425.1064 | 26724
14267 | 428.3959 | 26724
14268 | 425.5358 | 26724
14269 | 424.4566 | 26724
14270 | 398.0682 | 26724
14271 | 418.0424 | 26724
14272 | 423.5915 | 26724
14273 | 415.4746 | 26724
14274 | 403.2843 | 26724
14275 | 415.9132 | 26724
14276 | 414.6379 | 26724
14277 | 416.312 | 26724
14278 | 424.0234 | 26724
14279 | 422.3853 | 26724
14280 | 410.0765 | 26724
14281 | 411.3693 | 26724
14282 | 426.8006 | 26724
14283 | 421.2678 | 26724
14284 | 427.3622 | 26724
14285 | 418.5359 | 26724
14286 | 422.2877 | 26724
14287 | 426.3106 | 26724
14288 | 412.7235 | 26724
14289 | 430.9 | 26724
14290 | 416.106 | 26724
14291 | 419.3573 | 26724
14292 | 410.1353 | 26724
14293 | 421.0056 | 26724
14294 | 414.6134 | 26724
14295 | 418.8203 | 26724
14296 | 417.3392 | 26724
14297 | 418.4697 | 26724
14298 | 413.789 | 26724
14299 | 419.8968 | 26724
14300 | 418.1788 | 26724
14301 | 427.3395 | 26724
14302 | 412.7847 | 26724
14303 | 427.9261 | 26724
14304 | 426.8144 | 26724
14305 | 424.6122 | 26724
14306 | 428.8984 | 26724
14307 | 420.4515 | 26724
14308 | 435.0816 | 26724
14309 | 417.9834 | 26724
14310 | 423.2763 | 26724
14311 | 418.0737 | 26724
14312 | 419.8338 | 26724
14313 | 421.2642 | 26724
14314 | 412.0231 | 26724
14315 | 414.0351 | 26724
14316 | 426.0865 | 26724
14317 | 424.9288 | 26724
14318 | 406.8149 | 26724
14319 | 411.1808 | 26724
14320 | 404.7444 | 26724
14321 | 421.9985 | 26724
14322 | 416.0276 | 26724
14323 | 425.7887 | 26724
14324 | 407.6989 | 26724
14325 | 420.8364 | 26724
14326 | 421.449 | 26724
14327 | 415.0699 | 26724
14328 | 436.2797 | 26724
14329 | 414.3823 | 26724
14330 | 428.4132 | 26724
14331 | 425.1506 | 26724
14332 | 408.0637 | 26724
14333 | 405.1541 | 26724
14334 | 417.3383 | 26724
14335 | 424.3238 | 26724
14336 | 418.7077 | 26724
14337 | 404.8807 | 26724
14338 | 418.1516 | 26724
14339 | 419.697 | 26724
14340 | 409.1884 | 26724
14341 | 413.609 | 26724
14342 | 416.0163 | 26724
14343 | 421.2472 | 26724
14344 | 405.3573 | 26724
14345 | 414.7761 | 26724
14346 | 416.1456 | 26724
14347 | 413.6683 | 26724
14348 | 412.8964 | 26724
14349 | 406.524 | 26724
14350 | 410.8935 | 26724
14351 | 410.491 | 26724
14352 | 413.925 | 26724
14353 | 406.2763 | 26724
14354 | 426.1368 | 26724
14355 | 416.2358 | 26724
14356 | 422.3896 | 26724
14357 | 413.7392 | 26724
14358 | 421.0932 | 26724
14359 | 430.119 | 26724
14360 | 396.4664 | 26724
14361 | 409.8156 | 26724
14362 | 422.6196 | 26724
14363 | 404.5227 | 26724
14364 | 427.7902 | 26724
14365 | 432.2096 | 26724
14366 | 417.1155 | 26724
14367 | 416.8832 | 26724
14368 | 412.7768 | 26724
14369 | 416.6419 | 26724
14370 | 424.4578 | 26724
14371 | 417.2877 | 26724
14372 | 425.1956 | 26724
14373 | 414.4372 | 26724
14374 | 405.0751 | 26724
14375 | 430.5378 | 26724
14376 | 411.5312 | 26724
14377 | 417.0213 | 26724
14378 | 428.3738 | 26724
14379 | 425.1212 | 26724
14380 | 421.3557 | 26724
14381 | 418.4693 | 26724
14382 | 427.7667 | 26724
14383 | 410.6558 | 26724
14384 | 422.8116 | 26724
14385 | 432.318 | 26724
14386 | 403.6409 | 26724
14387 | 395.4838 | 26724
14388 | 403.147 | 26724
14389 | 402.3395 | 26724
14390 | 409.1626 | 26724
14391 | 424.5947 | 26724
14392 | 409.6399 | 26724
14393 | 414.8493 | 26724
14394 | 424.2086 | 26724
14395 | 402.5148 | 26724
14396 | 402.0458 | 26724
14397 | 416.8254 | 26724
14398 | 412.4205 | 26724
14399 | 405.0217 | 26724
14400 | 413.8754 | 26724
14401 | 421.2837 | 26724
14402 | 418.6599 | 26724
14403 | 417.0568 | 26724
14404 | 420.9069 | 26724
14405 | 424.2097 | 26724
14406 | 412.953 | 26724
14407 | 418.6921 | 26724
14408 | 421.9448 | 26724
14409 | 417.8797 | 26724
14410 | 412.054 | 26724
14411 | 411.3475 | 26724
14412 | 415.1652 | 26724
14413 | 410.8189 | 26724
14414 | 421.4259 | 26724
14415 | 426.1097 | 26724
14416 | 429.7911 | 26724
14417 | 413.9729 | 26724
14418 | 419.2151 | 26724
14419 | 419.1951 | 26724
14420 | 405.1191 | 26724
14421 | 411.4483 | 26724
14422 | 399.5308 | 26724
14423 | 416.066 | 26724
14424 | 418.0306 | 26724
14425 | 406.5943 | 26724
14426 | 413.5392 | 26724
14427 | 424.0916 | 26724
14428 | 412.805 | 26724
14429 | 429.1516 | 26724
14430 | 422.9285 | 26724
14431 | 416.6432 | 26724
14432 | 412.0433 | 26724
14433 | 411.6001 | 26724
14434 | 417.9894 | 26724
14435 | 419.0934 | 26724
14436 | 417.4988 | 26724
14437 | 424.0428 | 26724
14438 | 413.8493 | 26724
14439 | 414.1243 | 26724
14440 | 419.1891 | 26724
14441 | 425.107 | 26724
14442 | 427.4155 | 26724
14443 | 412.2402 | 26724
14444 | 427.2857 | 26724
14445 | 417.2684 | 26724
14446 | 429.0994 | 26724
14447 | 419.5575 | 26724
14448 | 412.1298 | 26724
14449 | 413.6035 | 26724
14450 | 426.4959 | 26724
14451 | 409.5961 | 26724
14452 | 412.9952 | 26724
14453 | 408.6987 | 26724
14454 | 410.1847 | 26724
14455 | 415.0524 | 26724
14456 | 414.1403 | 26724
14457 | 409.3426 | 26724
14458 | 418.2439 | 26724
14459 | 416.8949 | 26724
14460 | 420.8808 | 26724
14461 | 402.0328 | 26724
14462 | 423.4172 | 26724
14463 | 420.3454 | 26724
14464 | 430.142 | 26724
14465 | 415.089 | 26724
14466 | 415.9244 | 26724
14467 | 413.9655 | 26724
14468 | 417.492 | 26724
14469 | 419.4929 | 26724
14470 | 424.4129 | 26724
14471 | 423.5077 | 26724
14472 | 404.3161 | 26724
14473 | 411.756 | 26724
14474 | 420.6285 | 26724
14475 | 418.7019 | 26724
14476 | 402.7854 | 26724
14477 | 411.5665 | 26724
14478 | 427.6237 | 26724
14479 | 404.4722 | 26724
14480 | 409.6524 | 26724
14481 | 422.8852 | 26724
14482 | 407.061 | 26724
14483 | 426.024 | 26724
14484 | 420.0401 | 26724
14485 | 405.8977 | 26724
14486 | 426.7786 | 26724
14487 | 408.884 | 26724
14488 | 427.4747 | 26724
14489 | 409.6238 | 26724
14490 | 415.1383 | 26724
14491 | 428.1878 | 26724
14492 | 416.7066 | 26724
14493 | 407.3499 | 26724
14494 | 414.7036 | 26724
14495 | 419.2649 | 26724
14496 | 414.6469 | 26724
14497 | 413.8529 | 26724
14498 | 423.4063 | 26724
14499 | 422.938 | 26724
14500 | 414.2722 | 26724
14501 | 426.3975 | 26724
14502 | 415.5366 | 26724
14503 | 417.5012 | 26724
14504 | 422.0401 | 26724
14505 | 406.2334 | 26724
14506 | 416.4877 | 26724
14507 | 402.7848 | 26724
14508 | 424.5102 | 26724
14509 | 424.0272 | 26724
14510 | 426.1916 | 26724
14511 | 403.5998 | 26724
14512 | 415.6608 | 26724
14513 | 428.2761 | 26724
14514 | 412.3536 | 26724
14515 | 402.2877 | 26724
14516 | 404.3026 | 26724
14517 | 412.0219 | 26724
14518 | 418.341 | 26724
14519 | 407.362 | 26724
14520 | 416.174 | 26724
14521 | 427.5378 | 26724
14522 | 410.6332 | 26724
14523 | 403.8535 | 26724
14524 | 422.9491 | 26724
14525 | 411.1295 | 26724
14526 | 417.1196 | 26724
14527 | 410.8187 | 26724
14528 | 402.9681 | 26724
14529 | 416.7945 | 26724
14530 | 400.0208 | 26724
14531 | 428.1795 | 26724
14532 | 402.5556 | 26724
14533 | 413.3098 | 26724
14534 | 401.5464 | 26724
14535 | 414.3341 | 26724
14536 | 429.0232 | 26724
14537 | 415.7429 | 26724
14538 | 413.0312 | 26724
14539 | 415.6832 | 26724
14540 | 420.4566 | 26724
14541 | 406.7132 | 26724
14542 | 427.6217 | 26724
14543 | 414.199 | 26724
14544 | 408.9931 | 26724
14545 | 418.7317 | 26724
14546 | 411.4799 | 26724
14547 | 417.281 | 26724
14548 | 429.0891 | 26724
14549 | 431.4705 | 26724
14550 | 430.1963 | 26724
14551 | 414.8254 | 26724
14552 | 410.6793 | 26724
14553 | 407.9755 | 26724
14554 | 404.2262 | 26724
14555 | 421.2373 | 26724
14556 | 406.0065 | 26724
14557 | 419.7537 | 26724
14558 | 407.1165 | 26724
14559 | 427.8397 | 26724
14560 | 415.8535 | 26724
14561 | 413.3019 | 26724
14562 | 418.3329 | 26724
14563 | 408.8182 | 26724
14564 | 400.0493 | 26724
14565 | 422.6375 | 26724
14566 | 430.8825 | 26724
14567 | 431.9352 | 26724
14568 | 413.7745 | 26724
14569 | 409.6705 | 26724
14570 | 421.3392 | 26724
14571 | 403.5151 | 26724
14572 | 415.3122 | 26724
14573 | 420.1951 | 26724
14574 | 427.0156 | 26724
14575 | 420.3784 | 26724
14576 | 420.1754 | 26724
14577 | 429.6946 | 26724
14578 | 406.0201 | 26724
14579 | 423.8333 | 26724
14580 | 415.6987 | 26724
14581 | 419.0506 | 26724
14582 | 398.366 | 26724
14583 | 402.4382 | 26724
14584 | 419.2788 | 26724
14585 | 420.671 | 26724
14586 | 427.3156 | 26724
14587 | 411.7402 | 26724
14588 | 427.7631 | 26724
14589 | 415.0075 | 26724
14590 | 415.3663 | 26724
14591 | 421.7904 | 26724
14592 | 423.8828 | 26724
14593 | 432.35 | 26724
14594 | 408.8156 | 26724
14595 | 411.5537 | 26724
14596 | 423.6409 | 26724
14597 | 419.0728 | 26724
14598 | 417.5314 | 26724
14599 | 425.9538 | 26724
14600 | 430.3792 | 26724
14601 | 431.0569 | 26724
14602 | 423.2863 | 26724
14603 | 415.3958 | 26724
14604 | 431.3684 | 26724
14605 | 427.7852 | 26724
14606 | 413.207 | 26724
14607 | 415.8303 | 26724
14608 | 405.6821 | 26724
14609 | 428.068 | 26724
14610 | 423.8907 | 26724
14611 | 423.5586 | 26724
14612 | 419.553 | 26724
14613 | 415.713 | 26724
14614 | 415.5775 | 26724
14615 | 429.8374 | 26724
14616 | 403.993 | 26724
14617 | 406.7743 | 26724
14618 | 424.5091 | 26724
14619 | 425.7984 | 26724
14620 | 410.6532 | 26724
14621 | 410.1768 | 26724
14622 | 422.176 | 26724
14623 | 412.4017 | 26724
14624 | 412.1933 | 26724
14625 | 414.8282 | 26724
14626 | 432.9788 | 26724
14627 | 419.7739 | 26724
14628 | 414.8909 | 26724
14629 | 421.1774 | 26724
14630 | 402.7523 | 26724
14631 | 425.5732 | 26724
14632 | 405.1361 | 26724
14633 | 425.6611 | 26724
14634 | 415.46 | 26724
14635 | 415.7843 | 26724
14636 | 400.4791 | 26724
14637 | 414.1424 | 26724
14638 | 417.4439 | 26724
14639 | 415.3791 | 26724
14640 | 419.0173 | 26724
14641 | 416.7554 | 26724
14642 | 406.8148 | 26724
14643 | 428.8603 | 26724
14644 | 424.1283 | 26724
14645 | 411.4059 | 26724
14646 | 415.7518 | 26724
14647 | 423.7991 | 26724
14648 | 419.98 | 26724
14649 | 408.7754 | 26724
14650 | 416.1267 | 26724
14651 | 429.5693 | 26724
14652 | 418.7682 | 26724
14653 | 414.8208 | 26724
14654 | 422.5588 | 26724
14655 | 395.1419 | 26724
14656 | 411.7167 | 26724
14657 | 426.8531 | 26724
14658 | 413.727 | 26724
14659 | 419.1093 | 26724
14660 | 407.9491 | 26724
14661 | 426.1623 | 26724
14662 | 391.3626 | 26724
14663 | 421.512 | 26724
14664 | 411.991 | 26724
14665 | 423.9932 | 26724
14666 | 418.409 | 26724
14667 | 420.885 | 26724
14668 | 414.6367 | 26724
14669 | 419.8439 | 26724
14670 | 402.9601 | 26724
14671 | 425.6114 | 26724
14672 | 419.1363 | 26724
14673 | 410.3589 | 26724
14674 | 414.9744 | 26724
14675 | 413.5967 | 26724
14676 | 418.8182 | 26724
14677 | 427.729 | 26724
14678 | 406.6175 | 26724
14679 | 418.4171 | 26724
14680 | 414.1064 | 26724
14681 | 408.0205 | 26724
14682 | 414.6985 | 26724
14683 | 408.7359 | 26724
14684 | 424.643 | 26724
14685 | 414.4908 | 26724
14686 | 420.5277 | 26724
14687 | 416.6628 | 26724
14688 | 412.3274 | 26724
14689 | 419.9801 | 26724
14690 | 428.6472 | 26724
14691 | 415.5216 | 26724
14692 | 408.013 | 26724
14693 | 415.105 | 26724
14694 | 417.7494 | 26724
14695 | 415.7566 | 26724
14696 | 412.0059 | 26724
14697 | 425.5444 | 26724
14698 | 423.5334 | 26724
14699 | 403.939 | 26724
14700 | 409.3169 | 26724
14701 | 419.6527 | 26724
14702 | 410.4611 | 26724
14703 | 424.7463 | 26724
14704 | 412.972 | 26724
14705 | 415.7185 | 26724
14706 | 416.4503 | 26724
14707 | 421.3927 | 26724
14708 | 405.5907 | 26724
14709 | 400.9935 | 26724
14710 | 422.302 | 26724
14711 | 431.7883 | 26724
14712 | 423.0135 | 26724
14713 | 411.0338 | 26724
14714 | 410.6388 | 26724
14715 | 409.2616 | 26724
14716 | 412.3226 | 26724
14717 | 418.4339 | 26724
14718 | 409.5803 | 26724
14719 | 429.5345 | 26724
14720 | 426.7103 | 26724
14721 | 430.6378 | 26724
14722 | 403.8332 | 26724
14723 | 416.373 | 26724
14724 | 405.7529 | 26724
14725 | 418.2844 | 26724
14726 | 402.4955 | 26724
14727 | 415.3669 | 26724
14728 | 418.0234 | 26724
14729 | 421.2407 | 26724
14730 | 426.2655 | 26724
14731 | 418.0459 | 26724
14732 | 412.5785 | 26724
14733 | 428.6003 | 26724
14734 | 411.1274 | 26724
14735 | 428.8845 | 26724
14736 | 418.1145 | 26724
14737 | 416.2589 | 26724
14738 | 400.8308 | 26724
14739 | 418.1675 | 26724
14740 | 426.0404 | 26724
14741 | 420.7102 | 26724
14742 | 423.1673 | 26724
14743 | 403.6361 | 26724
14744 | 414.9301 | 26724
14745 | 425.0653 | 26724
14746 | 427.071 | 26724
14747 | 421.6812 | 26724
14748 | 417.4131 | 26724
14749 | 417.9007 | 26724
14750 | 419.8661 | 26724
14751 | 417.1759 | 26724
14752 | 428.6921 | 26724
14753 | 408.296 | 26724
14754 | 403.0848 | 26724
14755 | 418.2782 | 26724
14756 | 409.6338 | 26724
14757 | 423.3742 | 26724
14758 | 403.8524 | 26724
14759 | 423.1775 | 26724
14760 | 414.1079 | 26724
14761 | 412.1263 | 26724
14762 | 428.9955 | 26724
14763 | 406.0552 | 26724
14764 | 409.179 | 26724
14765 | 424.5063 | 26724
14766 | 420.3285 | 26724
14767 | 413.3281 | 26724
14768 | 409.0619 | 26724
14769 | 412.8717 | 26724
14770 | 413.7009 | 26724
14771 | 426.5451 | 26724
14772 | 420.1932 | 26724
14773 | 419.0376 | 26724
14774 | 417.7576 | 26724
14775 | 418.2419 | 26724
14776 | 418.3167 | 26724
14777 | 409.1974 | 26724
14778 | 421.5534 | 26724
14779 | 421.7666 | 26724
14780 | 418.2013 | 26724
14781 | 409.3868 | 26724
14782 | 420.9144 | 26724
14783 | 424.3511 | 26724
14784 | 419.1538 | 26724
14785 | 424.2335 | 26724
14786 | 412.8962 | 26724
14787 | 427.3077 | 26724
14788 | 420.2872 | 26724
14789 | 416.6363 | 26724
14790 | 410.7586 | 26724
14791 | 417.4653 | 26724
14792 | 401.7133 | 26724
14793 | 410.4803 | 26724
14794 | 413.8756 | 26724
14795 | 410.0242 | 26724
14796 | 427.9018 | 26724
14797 | 410.9173 | 26724
14798 | 404.9686 | 26724
14799 | 409.0758 | 26724
14800 | 430.5699 | 26724
14801 | 418.0252 | 26724
14802 | 414.4939 | 26724
14803 | 423.1939 | 26724
14804 | 420.9917 | 26724
14805 | 409.876 | 26724
14806 | 403.1135 | 26724
14807 | 423.0102 | 26724
14808 | 412.5995 | 26724
14809 | 412.2042 | 26724
14810 | 420.6126 | 26724
14811 | 424.0329 | 26724
14812 | 410.3924 | 26724
14813 | 406.639 | 26724
14814 | 407.939 | 26724
14815 | 406.6913 | 26724
14816 | 437.2347 | 26724
14817 | 421.3459 | 26724
14818 | 412.8375 | 26724
14819 | 408.9202 | 26724
14820 | 409.2498 | 26724
14821 | 416.3933 | 26724
14822 | 422.2039 | 26724
14823 | 424.5116 | 26724
14824 | 427.2571 | 26724
14825 | 414.3353 | 26724
14826 | 410.8973 | 26724
14827 | 403.7121 | 26724
14828 | 405.611 | 26724
14829 | 415.8231 | 26724
14830 | 416.6232 | 26724
14831 | 425.5284 | 26724
14832 | 421.3248 | 26724
14833 | 411.1821 | 26724
14834 | 419.2268 | 26724
14835 | 406.0097 | 26724
14836 | 420.3921 | 26724
14837 | 404.1486 | 26724
14838 | 401.986 | 26724
14839 | 408.1351 | 26724
14840 | 416.8559 | 26724
14841 | 414.9984 | 26724
14842 | 421.0451 | 26724
14843 | 402.9925 | 26724
14844 | 402.2252 | 26724
14845 | 408.9493 | 26724
14846 | 416.6539 | 26724
14847 | 430.6939 | 26724
14848 | 399.7856 | 26724
14849 | 419.6779 | 26724
14850 | 412.5488 | 26724
14851 | 409.5007 | 26724
14852 | 419.341 | 26724
14853 | 410.1919 | 26724
14854 | 404.6678 | 26724
14855 | 415.5421 | 26724
14856 | 437.364 | 26724
14857 | 424.5704 | 26724
14858 | 405.4633 | 26724
14859 | 414.5929 | 26724
14860 | 415.8956 | 26724
14861 | 403.1375 | 26724
14862 | 425.2005 | 26724
14863 | 410.0779 | 26724
14864 | 406.6312 | 26724
14865 | 427.7347 | 26724
14866 | 417.5529 | 26724
14867 | 431.129 | 26724
14868 | 412.2753 | 26724
14869 | 416.5411 | 26724
14870 | 429.2582 | 26724
14871 | 413.6451 | 26724
14872 | 421.7338 | 26724
14873 | 427.7434 | 26724
14874 | 426.684 | 26724
14875 | 420.4009 | 26724
14876 | 415.2535 | 26724
14877 | 417.4936 | 26724
14878 | 409.3675 | 26724
14879 | 411.178 | 26724
14880 | 425.0898 | 26724
14881 | 403.0238 | 26724
14882 | 411.188 | 26724
14883 | 409.1368 | 26724
14884 | 414.345 | 26724
14885 | 420.157 | 26724
14886 | 418.6015 | 26724
14887 | 416.269 | 26724
14888 | 419.7539 | 26724
14889 | 416.7423 | 26724
14890 | 402.8866 | 26724
14891 | 423.5936 | 26724
14892 | 419.3789 | 26724
14893 | 429.7609 | 26724
14894 | 411.7014 | 26724
14895 | 412.3121 | 26724
14896 | 430.8648 | 26724
14897 | 410.866 | 26724
14898 | 424.4366 | 26724
14899 | 416.1776 | 26724
14900 | 427.1616 | 26724
14901 | 416.1189 | 26724
14902 | 411.1096 | 26724
14903 | 412.5483 | 26724
14904 | 422.1247 | 26724
14905 | 422.8092 | 26724
14906 | 405.1689 | 26724
14907 | 411.7463 | 26724
14908 | 431.4761 | 26724
14909 | 420.2325 | 26724
14910 | 420.2817 | 26724
14911 | 402.36 | 26724
14912 | 424.8797 | 26724
14913 | 416.1252 | 26724
14914 | 412.3441 | 26724
14915 | 418.1974 | 26724
14916 | 411.3551 | 26724
14917 | 408.4002 | 26724
14918 | 399.2297 | 26724
14919 | 424.8881 | 26724
14920 | 421.5929 | 26724
14921 | 420.9913 | 26724
14922 | 421.0455 | 26724
14923 | 409.3757 | 26724
14924 | 415.3976 | 26724
14925 | 408.6865 | 26724
14926 | 413.0617 | 26724
14927 | 409.3617 | 26724
14928 | 418.0557 | 26724
14929 | 410.7004 | 26724
14930 | 410.1619 | 26724
14931 | 408.6038 | 26724
14932 | 404.3842 | 26724
14933 | 433.4502 | 26724
14934 | 413.1895 | 26724
14935 | 409.502 | 26724
14936 | 416.5034 | 26724
14937 | 418.2994 | 26724
14938 | 414.4797 | 26724
14939 | 424.9796 | 26724
14940 | 407.197 | 26724
14941 | 423.1959 | 26724
14942 | 415.9608 | 26724
14943 | 417.2508 | 26724
14944 | 407.4145 | 26724
14945 | 404.6647 | 26724
14946 | 403.8394 | 26724
14947 | 419.0775 | 26724
14948 | 414.4143 | 26724
14949 | 425.7342 | 26724
14950 | 421.9148 | 26724
14951 | 421.2538 | 26724
14952 | 400.4201 | 26724
14953 | 405.1948 | 26724
14954 | 416.812 | 26724
14955 | 414.5337 | 26724
14956 | 419.7409 | 26724
14957 | 399.8199 | 26724
14958 | 402.1625 | 26724
14959 | 425.4845 | 26724
14960 | 417.1538 | 26724
14961 | 420.5643 | 26724
14962 | 403.483 | 26724
14963 | 418.4789 | 26724
14964 | 420.4619 | 26724
14965 | 424.4189 | 26724
14966 | 406.4535 | 26724
14967 | 430.4298 | 26724
14968 | 402.185 | 26724
14969 | 426.4646 | 26724
14970 | 423.1696 | 26724
14971 | 433.2172 | 26724
14972 | 428.1905 | 26724
14973 | 416.5751 | 26724
14974 | 405.3204 | 26724
14975 | 412.1686 | 26724
14976 | 422.5727 | 26724
14977 | 425.095 | 26724
14978 | 415.6526 | 26724
14979 | 418.972 | 26724
14980 | 416.5275 | 26724
14981 | 402.1609 | 26724
14982 | 402.3757 | 26724
14983 | 419.8188 | 26724
14984 | 419.3804 | 26724
14985 | 413.0792 | 26724
14986 | 426.0546 | 26724
14987 | 415.0599 | 26724
14988 | 422.8309 | 26724
14989 | 419.5211 | 26724
14990 | 418.6417 | 26724
14991 | 420.6653 | 26724
14992 | 396.034 | 26724
14993 | 421.1592 | 26724
14994 | 411.3095 | 26724
14995 | 421.679 | 26724
14996 | 407.8843 | 26724
14997 | 411.4007 | 26724
14998 | 405.1773 | 26724
14999 | 419.7481 | 26724
15000 | 410.335 | 26724
15001 | 412.0586 | 26724
15002 | 421.5865 | 26724
15003 | 410.7007 | 26724
15004 | 418.9861 | 26724
15005 | 415.4502 | 26724
15006 | 411.9085 | 26724
15007 | 413.0323 | 26724
15008 | 407.6142 | 26724
15009 | 417.3905 | 26724
15010 | 424.8017 | 26724
15011 | 407.0538 | 26724
15012 | 425.1257 | 26724
15013 | 413.8044 | 26724
15014 | 409.3799 | 26724
15015 | 420.2881 | 26724
15016 | 412.9786 | 26724
15017 | 426.0835 | 26724
15018 | 424.4658 | 26724
15019 | 401.7046 | 26724
15020 | 420.6224 | 26724
15021 | 400.3337 | 26724
15022 | 421.798 | 26724
15023 | 429.6361 | 26724
15024 | 422.9677 | 26724
15025 | 413.733 | 26724
15026 | 414.0067 | 26724
15027 | 418.3345 | 26724
15028 | 402.2864 | 26724
15029 | 424.3659 | 26724
15030 | 412.5635 | 26724
15031 | 412.4684 | 26724
15032 | 425.7142 | 26724
15033 | 412.09 | 26724
15034 | 414.606 | 26724
15035 | 422.4366 | 26724
15036 | 421.539 | 26724
15037 | 423.9328 | 26724
15038 | 415.7778 | 26724
15039 | 407.5733 | 26724
15040 | 416.0207 | 26724
15041 | 424.7964 | 26724
15042 | 415.9611 | 26724
15043 | 409.4547 | 26724
15044 | 410.0004 | 26724
15045 | 422.089 | 26724
15046 | 429.7198 | 26724
15047 | 406.531 | 26724
15048 | 427.452 | 26724
15049 | 424.0857 | 26724
15050 | 421.7244 | 26724
15051 | 426.8426 | 26724
15052 | 423.9424 | 26724
15053 | 419.5878 | 26724
15054 | 416.4046 | 26724
15055 | 418.0332 | 26724
15056 | 418.9625 | 26724
15057 | 409.7546 | 26724
15058 | 408.0267 | 26724
15059 | 414.4837 | 26724
15060 | 410.8986 | 26724
15061 | 419.6112 | 26724
15062 | 400.2214 | 26724
15063 | 419.149 | 26724
15064 | 413.8371 | 26724
15065 | 417.9438 | 26724
15066 | 419.8591 | 26724
15067 | 415.1348 | 26724
15068 | 414.6214 | 26724
15069 | 418.525 | 26724
15070 | 416.9006 | 26724
15071 | 410.7815 | 26724
15072 | 423.5847 | 26724
15073 | 415.2975 | 26724
15074 | 410.6024 | 26724
15075 | 411.6782 | 26724
15076 | 413.5664 | 26724
15077 | 401.1774 | 26724
15078 | 420.3064 | 26724
15079 | 422.277 | 26724
15080 | 419.1098 | 26724
15081 | 422.6674 | 26724
15082 | 426.2926 | 26724
15083 | 409.0724 | 26724
15084 | 421.3464 | 26724
15085 | 419.5206 | 26724
15086 | 413.461 | 26724
15087 | 417.7629 | 26724
15088 | 419.1503 | 26724
15089 | 411.3202 | 26724
15090 | 421.7556 | 26724
15091 | 409.2591 | 26724
15092 | 410.0283 | 26724
15093 | 414.7289 | 26724
15094 | 407.9439 | 26724
15095 | 403.1772 | 26724
15096 | 420.6949 | 26724
15097 | 410.4182 | 26724
15098 | 418.661 | 26724
15099 | 428.7492 | 26724
15100 | 429.3268 | 26724
15101 | 430.8224 | 26724
15102 | 416.1595 | 26724
15103 | 411.6046 | 26724
15104 | 411.3368 | 26724
15105 | 407.3686 | 26724
15106 | 408.0481 | 26724
15107 | 427.4797 | 26724
15108 | 419.5757 | 26724
15109 | 415.9499 | 26724
15110 | 399.0915 | 26724
15111 | 422.8382 | 26724
15112 | 420.6489 | 26724
15113 | 428.3276 | 26724
15114 | 409.5861 | 26724
15115 | 418.382 | 26724
15116 | 429.8641 | 26724
15117 | 430.699 | 26724
15118 | 419.9418 | 26724
15119 | 425.8436 | 26724
15120 | 428.7264 | 26724
15121 | 427.4116 | 26724
15122 | 410.2185 | 26724
15123 | 422.1624 | 26724
15124 | 404.0518 | 26724
15125 | 419.723 | 26724
15126 | 414.4763 | 26724
15127 | 420.5226 | 26724
15128 | 419.6607 | 26724
15129 | 409.8935 | 26724
15130 | 411.6645 | 26724
15131 | 415.1727 | 26724
15132 | 399.2696 | 26724
15133 | 406.8842 | 26724
15134 | 414.1724 | 26724
15135 | 403.3784 | 26724
15136 | 403.7825 | 26724
15137 | 410.7236 | 26724
15138 | 423.1608 | 26724
15139 | 419.2011 | 26724
15140 | 420.6807 | 26724
15141 | 414.6696 | 26724
15142 | 422.2292 | 26724
15143 | 431.735 | 26724
15144 | 414.9223 | 26724
15145 | 409.4393 | 26724
15146 | 425.6737 | 26724
15147 | 419.2175 | 26724
15148 | 410.5307 | 26724
15149 | 418.7282 | 26724
15150 | 409.6883 | 26724
15151 | 418.2268 | 26724
15152 | 423.8304 | 26724
15153 | 408.206 | 26724
15154 | 413.5599 | 26724
15155 | 411.6827 | 26724
15156 | 407.1196 | 26724
15157 | 402.4408 | 26724
15158 | 418.3109 | 26724
15159 | 411.0978 | 26724
15160 | 420.4698 | 26724
15161 | 398.6814 | 26724
15162 | 428.2032 | 26724
15163 | 406.5452 | 26724
15164 | 424.3716 | 26724
15165 | 417.8991 | 26724
15166 | 420.008 | 26724
15167 | 414.1723 | 26724
15168 | 404.0369 | 26724
15169 | 429.5867 | 26724
15170 | 409.9172 | 26724
15171 | 431.4076 | 26724
15172 | 418.9422 | 26724
15173 | 408.0973 | 26724
15174 | 406.5559 | 26724
15175 | 415.5427 | 26724
15176 | 416.8883 | 26724
15177 | 424.6188 | 26724
15178 | 400.6221 | 26724
15179 | 401.7013 | 26724
15180 | 422.1237 | 26724
15181 | 402.7915 | 26724
15182 | 411.2678 | 26724
15183 | 419.151 | 26724
15184 | 405.8766 | 26724
15185 | 422.037 | 26724
15186 | 409.4358 | 26724
15187 | 429.8365 | 26724
15188 | 416.3465 | 26724
15189 | 400.2868 | 26724
15190 | 411.576 | 26724
15191 | 418.5238 | 26724
15192 | 429.3576 | 26724
15193 | 413.4971 | 26724
15194 | 406.6649 | 26724
15195 | 423.2964 | 26724
15196 | 422.9729 | 26724
15197 | 402.8818 | 26724
15198 | 416.9313 | 26724
15199 | 413.5489 | 26724
15200 | 406.9421 | 26724
15201 | 409.2883 | 26724
15202 | 418.0374 | 26724
15203 | 424.0598 | 26724
15204 | 420.5419 | 26724
15205 | 428.7296 | 26724
15206 | 420.4764 | 26724
15207 | 417.0199 | 26724
15208 | 426.7183 | 26724
15209 | 413.8607 | 26724
15210 | 433.2953 | 26724
15211 | 424.6556 | 26724
15212 | 414.2256 | 26724
15213 | 404.7812 | 26724
15214 | 421.0401 | 26724
15215 | 414.4481 | 26724
15216 | 409.3716 | 26724
15217 | 402.7876 | 26724
15218 | 411.5676 | 26724
15219 | 420.0398 | 26724
15220 | 412.5446 | 26724
15221 | 410.3496 | 26724
15222 | 412.6286 | 26724
15223 | 414.1447 | 26724
15224 | 408.7624 | 26724
15225 | 419.4057 | 26724
15226 | 410.4016 | 26724
15227 | 400.5155 | 26724
15228 | 406.4698 | 26724
15229 | 435.2634 | 26724
15230 | 416.5834 | 26724
15231 | 422.4105 | 26724
15232 | 419.3427 | 26724
15233 | 427.2506 | 26724
15234 | 411.5991 | 26724
15235 | 421.283 | 26724
15236 | 415.1634 | 26724
15237 | 424.3693 | 26724
15238 | 432.6758 | 26724
15239 | 436.3857 | 26724
15240 | 427.2432 | 26724
15241 | 417.2503 | 26724
15242 | 410.5878 | 26724
15243 | 407.8949 | 26724
15244 | 424.2729 | 26724
15245 | 415.2335 | 26724
15246 | 412.0593 | 26724
15247 | 432.3137 | 26724
15248 | 404.6981 | 26724
15249 | 399.7072 | 26724
15250 | 419.6565 | 26724
15251 | 427.5534 | 26724
15252 | 412.5033 | 26724
15253 | 427.302 | 26724
15254 | 412.8028 | 26724
15255 | 429.7692 | 26724
15256 | 430.6465 | 26724
15257 | 421.1273 | 26724
15258 | 419.6594 | 26724
15259 | 413.7296 | 26724
15260 | 430.1846 | 26724
15261 | 423.5468 | 26724
15262 | 409.6809 | 26724
15263 | 414.7268 | 26724
15264 | 420.9416 | 26724
15265 | 414.5788 | 26724
15266 | 406.0817 | 26724
15267 | 417.9677 | 26724
15268 | 419.4366 | 26724
15269 | 421.1661 | 26724
15270 | 429.6898 | 26724
15271 | 427.6266 | 26724
15272 | 419.7732 | 26724
15273 | 418.7509 | 26724
15274 | 419.5067 | 26724
15275 | 422.709 | 26724
15276 | 424.985 | 26724
15277 | 409.1162 | 26724
15278 | 402.4875 | 26724
15279 | 429.1378 | 26724
15280 | 421.761 | 26724
15281 | 428.546 | 26724
15282 | 432.8152 | 26724
15283 | 413.296 | 26724
15284 | 421.3274 | 26724
15285 | 412.9166 | 26724
15286 | 416.1166 | 26724
15287 | 405.3528 | 26724
15288 | 417.3941 | 26724
15289 | 419.1737 | 26724
15290 | 420.245 | 26724
15291 | 418.4066 | 26724
15292 | 411.8207 | 26724
15293 | 412.0793 | 26724
15294 | 410.7577 | 26724
15295 | 429.0366 | 26724
15296 | 411.7278 | 26724
15297 | 416.9746 | 26724
15298 | 421.7833 | 26724
15299 | 410.4707 | 26724
15300 | 408.39 | 26724
15301 | 410.9446 | 26724
15302 | 408.4131 | 26724
15303 | 425.8222 | 26724
15304 | 419.1171 | 26724
15305 | 399.1298 | 26724
15306 | 409.1992 | 26724
15307 | 417.2401 | 26724
15308 | 419.6644 | 26724
15309 | 421.0693 | 26724
15310 | 409.0046 | 26724
15311 | 424.8724 | 26724
15312 | 426.5089 | 26724
15313 | 413.987 | 26724
15314 | 425.8272 | 26724
15315 | 425.3324 | 26724
15316 | 421.9027 | 26724
15317 | 410.4208 | 26724
15318 | 414.5555 | 26724
15319 | 411.099 | 26724
15320 | 415.6349 | 26724
15321 | 418.9595 | 26724
15322 | 415.4893 | 26724
15323 | 414.3384 | 26724
15324 | 422.2253 | 26724
15325 | 403.6428 | 26724
15326 | 426.2769 | 26724
15327 | 420.2079 | 26724
15328 | 418.3318 | 26724
15329 | 418.219 | 26724
15330 | 409.2168 | 26724
15331 | 427.6464 | 26724
15332 | 422.7802 | 26724
15333 | 410.4446 | 26724
15334 | 412.3537 | 26724
15335 | 411.9882 | 26724
15336 | 406.4894 | 26724
15337 | 407.648 | 26724
15338 | 417.9173 | 26724
15339 | 414.1789 | 26724
15340 | 412.0291 | 26724
15341 | 433.4793 | 26724
15342 | 411.3526 | 26724
15343 | 413.1693 | 26724
15344 | 402.9433 | 26724
15345 | 408.2166 | 26724
15346 | 407.115 | 26724
15347 | 408.3853 | 26724
15348 | 425.2379 | 26724
15349 | 413.7803 | 26724
15350 | 425.0583 | 26724
15351 | 413.2942 | 26724
15352 | 419.7665 | 26724
15353 | 421.2918 | 26724
15354 | 408.853 | 26724
15355 | 413.4492 | 26724
15356 | 422.2542 | 26724
15357 | 413.006 | 26724
15358 | 419.6035 | 26724
15359 | 406.3147 | 26724
15360 | 423.1023 | 26724
15361 | 404.4164 | 26724
15362 | 407.0202 | 26724
15363 | 415.4063 | 26724
15364 | 414.3517 | 26724
15365 | 419.6003 | 26724
15366 | 412.4233 | 26724
15367 | 426.4989 | 26724
15368 | 424.0749 | 26724
15369 | 425.6042 | 26724
15370 | 415.6441 | 26724
15371 | 424.6974 | 26724
15372 | 406.8628 | 26724
15373 | 421.1579 | 26724
15374 | 431.9172 | 26724
15375 | 430.3542 | 26724
15376 | 410.5857 | 26724
15377 | 416.4313 | 26724
15378 | 406.7187 | 26724
15379 | 422.2984 | 26724
15380 | 424.969 | 26724
15381 | 403.2184 | 26724
15382 | 429.8911 | 26724
15383 | 425.2911 | 26724
15384 | 421.6431 | 26724
15385 | 422.2597 | 26724
15386 | 411.7186 | 26724
15387 | 416.6527 | 26724
15388 | 408.8181 | 26724
15389 | 407.632 | 26724
15390 | 424.934 | 26724
15391 | 418.3305 | 26724
15392 | 413.9731 | 26724
15393 | 410.357 | 26724
15394 | 411.9923 | 26724
15395 | 412.8002 | 26724
15396 | 415.3879 | 26724
15397 | 415.3407 | 26724
15398 | 420.21 | 26724
15399 | 408.4019 | 26724
15400 | 420.3123 | 26724
15401 | 415.6329 | 26724
15402 | 410.5949 | 26724
15403 | 402.5148 | 26724
15404 | 410.6259 | 26724
15405 | 413.7566 | 26724
15406 | 414.5236 | 26724
15407 | 421.3758 | 26724
15408 | 418.4968 | 26724
15409 | 418.3643 | 26724
15410 | 416.4763 | 26724
15411 | 414.6389 | 26724
15412 | 421.0348 | 26724
15413 | 424.8994 | 26724
15414 | 401.7461 | 26724
15415 | 407.5913 | 26724
15416 | 414.2606 | 26724
15417 | 408.7115 | 26724
15418 | 414.2317 | 26724
15419 | 426.8994 | 26724
15420 | 420.3483 | 26724
15421 | 396.658 | 26724
15422 | 413.7562 | 26724
15423 | 417.5162 | 26724
15424 | 419.4059 | 26724
15425 | 428.935 | 26724
15426 | 411.1814 | 26724
15427 | 422.827 | 26724
15428 | 401.6115 | 26724
15429 | 407.817 | 26724
15430 | 424.6017 | 26724
15431 | 424.9881 | 26724
15432 | 419.9492 | 26724
15433 | 429.7206 | 26724
15434 | 421.7008 | 26724
15435 | 416.7156 | 26724
15436 | 404.7964 | 26724
15437 | 415.7902 | 26724
15438 | 426.5365 | 26724
15439 | 425.3986 | 26724
15440 | 414.7729 | 26724
15441 | 420.777 | 26724
15442 | 417.7398 | 26724
15443 | 415.4532 | 26724
15444 | 412.7503 | 26724
15445 | 404.8581 | 26724
15446 | 416.064 | 26724
15447 | 420.5637 | 26724
15448 | 418.4676 | 26724
15449 | 404.3882 | 26724
15450 | 418.792 | 26724
15451 | 403.1307 | 26724
15452 | 413.8337 | 26724
15453 | 431.7169 | 26724
15454 | 404.0864 | 26724
15455 | 431.6662 | 26724
15456 | 416.8962 | 26724
15457 | 417.2783 | 26724
15458 | 414.6353 | 26724
15459 | 412.5191 | 26724
15460 | 423.213 | 26724
15461 | 425.9836 | 26724
15462 | 409.4242 | 26724
15463 | 410.0901 | 26724
15464 | 419.4743 | 26724
15465 | 410.3886 | 26724
15466 | 409.4037 | 26724
15467 | 424.2174 | 26724
15468 | 415.7977 | 26724
15469 | 400.8485 | 26724
15470 | 423.8226 | 26724
15471 | 419.2786 | 26724
15472 | 408.9729 | 26724
15473 | 416.0439 | 26724
15474 | 422.8603 | 26724
15475 | 417.6115 | 26724
15476 | 398.1304 | 26724
15477 | 415.8133 | 26724
15478 | 407.628 | 26724
15479 | 434.2403 | 26724
15480 | 414.0912 | 26724
15481 | 407.5106 | 26724
15482 | 407.8462 | 26724
15483 | 407.6907 | 26724
15484 | 412.1578 | 26724
15485 | 419.0374 | 26724
15486 | 418.1693 | 26724
15487 | 412.2168 | 26724
15488 | 419.9255 | 26724
15489 | 416.8026 | 26724
15490 | 430.7529 | 26724
15491 | 435.1773 | 26724
15492 | 397.5685 | 26724
15493 | 412.1984 | 26724
15494 | 409.7683 | 26724
15495 | 409.6281 | 26724
15496 | 410.6404 | 26724
15497 | 411.0112 | 26724
15498 | 407.052 | 26724
15499 | 412.2637 | 26724
15500 | 418.9974 | 26724
15501 | 421.9038 | 26724
15502 | 412.7249 | 26724
15503 | 414.8233 | 26724
15504 | 418.3328 | 26724
15505 | 415.2931 | 26724
15506 | 403.5002 | 26724
15507 | 414.8668 | 26724
15508 | 414.2055 | 26724
15509 | 410.1184 | 26724
15510 | 400.5837 | 26724
15511 | 417.5141 | 26724
15512 | 418.0092 | 26724
15513 | 426.5998 | 26724
15514 | 420.2823 | 26724
15515 | 418.6462 | 26724
15516 | 402.4791 | 26724
15517 | 419.7774 | 26724
15518 | 416.5752 | 26724
15519 | 417.7479 | 26724
15520 | 407.9091 | 26724
15521 | 412.6239 | 26724
15522 | 403.4276 | 26724
15523 | 409.0245 | 26724
15524 | 413.456 | 26724
15525 | 409.6075 | 26724
15526 | 408.0311 | 26724
15527 | 411.1935 | 26724
15528 | 411.6264 | 26724
15529 | 413.3381 | 26724
15530 | 430.9498 | 26724
15531 | 417.1111 | 26724
15532 | 414.0548 | 26724
15533 | 415.4878 | 26724
15534 | 413.9441 | 26724
15535 | 420.6515 | 26724
15536 | 426.8668 | 26724
15537 | 407.5859 | 26724
15538 | 410.1744 | 26724
15539 | 400.7156 | 26724
15540 | 412.3663 | 26724
15541 | 427.4127 | 26724
15542 | 408.4877 | 26724
15543 | 430.9413 | 26724
15544 | 404.8609 | 26724
15545 | 417.4878 | 26724
15546 | 422.653 | 26724
15547 | 425.5784 | 26724
15548 | 412.3005 | 26724
15549 | 424.1156 | 26724
15550 | 411.9695 | 26724
15551 | 403.3916 | 26724
15552 | 419.697 | 26724
15553 | 430.2895 | 26724
15554 | 411.2495 | 26724
15555 | 417.2917 | 26724
15556 | 419.5244 | 26724
15557 | 423.1687 | 26724
15558 | 416.5449 | 26724
15559 | 420.5506 | 26724
15560 | 411.4775 | 26724
15561 | 417.3961 | 26724
15562 | 410.0814 | 26724
15563 | 433.7759 | 26724
15564 | 404.3126 | 26724
15565 | 410.6198 | 26724
15566 | 414.0446 | 26724
15567 | 399.7974 | 26724
15568 | 429.9952 | 26724
15569 | 402.9792 | 26724
15570 | 418.4445 | 26724
15571 | 424.5881 | 26724
15572 | 397.5998 | 26724
15573 | 410.6254 | 26724
15574 | 421.8379 | 26724
15575 | 434.4546 | 26724
15576 | 407.3143 | 26724
15577 | 422.1459 | 26724
15578 | 413.9217 | 26724
15579 | 404.8991 | 26724
15580 | 400.1062 | 26724
15581 | 414.0119 | 26724
15582 | 411.5973 | 26724
15583 | 415.8892 | 26724
15584 | 418.8992 | 26724
15585 | 415.3373 | 26724
15586 | 416.3667 | 26724
15587 | 412.7523 | 26724
15588 | 422.8337 | 26724
15589 | 423.771 | 26724
15590 | 417.4356 | 26724
15591 | 408.7208 | 26724
15592 | 414.3098 | 26724
15593 | 429.8822 | 26724
15594 | 419.1541 | 26724
15595 | 408.9314 | 26724
15596 | 420.9284 | 26724
15597 | 426.2494 | 26724
15598 | 407.0728 | 26724
15599 | 418.3749 | 26724
15600 | 407.1759 | 26724
15601 | 426.0919 | 26724
15602 | 419.2575 | 26724
15603 | 415.5027 | 26724
15604 | 411.2107 | 26724
15605 | 410.6356 | 26724
15606 | 428.6447 | 26724
15607 | 413.5353 | 26724
15608 | 401.3839 | 26724
15609 | 414.3939 | 26724
15610 | 423.1327 | 26724
15611 | 417.2197 | 26724
15612 | 416.1323 | 26724
15613 | 426.7384 | 26724
15614 | 407.5346 | 26724
15615 | 415.5215 | 26724
15616 | 405.9733 | 26724
15617 | 423.4162 | 26724
15618 | 412.0127 | 26724
15619 | 407.045 | 26724
15620 | 420.5075 | 26724
15621 | 410.1219 | 26724
15622 | 425.3258 | 26724
15623 | 421.8809 | 26724
15624 | 415.535 | 26724
15625 | 413.8634 | 26724
15626 | 418.8757 | 26724
15627 | 411.7481 | 26724
15628 | 411.7835 | 26724
15629 | 418.5433 | 26724
15630 | 431.7793 | 26724
15631 | 409.6901 | 26724
15632 | 415.5879 | 26724
15633 | 418.0299 | 26724
15634 | 418.5078 | 26724
15635 | 421.7438 | 26724
15636 | 439.9186 | 26724
15637 | 416.001 | 26724
15638 | 409.9551 | 26724
15639 | 412.7184 | 26724
15640 | 428.2426 | 26724
15641 | 427.3594 | 26724
15642 | 394.5139 | 26724
15643 | 413.3688 | 26724
15644 | 413.3333 | 26724
15645 | 413.3941 | 26724
15646 | 408.6517 | 26724
15647 | 411.0006 | 26724
15648 | 408.1816 | 26724
15649 | 420.0591 | 26724
15650 | 405.0759 | 26724
15651 | 408.3869 | 26724
15652 | 415.5778 | 26724
15653 | 425.5583 | 26724
15654 | 429.3198 | 26724
15655 | 417.9418 | 26724
15656 | 424.0726 | 26724
15657 | 428.2313 | 26724
15658 | 414.0539 | 26724
15659 | 433.7432 | 26724
15660 | 411.5915 | 26724
15661 | 401.7501 | 26724
15662 | 409.7263 | 26724
15663 | 425.2014 | 26724
15664 | 427.6821 | 26724
15665 | 423.3346 | 26724
15666 | 402.9009 | 26724
15667 | 416.483 | 26724
15668 | 406.7378 | 26724
15669 | 427.9293 | 26724
15670 | 416.566 | 26724
15671 | 412.6346 | 26724
15672 | 414.8844 | 26724
15673 | 413.4539 | 26724
15674 | 414.3239 | 26724
15675 | 429.557 | 26724
15676 | 410.1673 | 26724
15677 | 420.3143 | 26724
15678 | 428.9491 | 26724
15679 | 425.4974 | 26724
15680 | 426.9596 | 26724
15681 | 417.8707 | 26724
15682 | 414.7325 | 26724
15683 | 399.5335 | 26724
15684 | 434.0467 | 26724
15685 | 406.6154 | 26724
15686 | 416.7163 | 26724
15687 | 404.8018 | 26724
15688 | 402.3141 | 26724
15689 | 393.6959 | 26724
15690 | 409.6524 | 26724
15691 | 412.7018 | 26724
15692 | 424.6115 | 26724
15693 | 413.1987 | 26724
15694 | 433.1858 | 26724
15695 | 427.1427 | 26724
15696 | 431.2791 | 26724
15697 | 415.067 | 26724
15698 | 415.5229 | 26724
15699 | 403.3389 | 26724
15700 | 422.1176 | 26724
15701 | 415.503 | 26724
15702 | 414.5108 | 26724
15703 | 408.0091 | 26724
15704 | 411.3653 | 26724
15705 | 427.1576 | 26724
15706 | 417.5146 | 26724
15707 | 414.2187 | 26724
15708 | 408.5894 | 26724
15709 | 429.9568 | 26724
15710 | 416.2414 | 26724
15711 | 398.4738 | 26724
15712 | 428.5237 | 26724
15713 | 408.2179 | 26724
15714 | 410.9215 | 26724
15715 | 413.8527 | 26724
15716 | 407.0368 | 26724
15717 | 426.9023 | 26724
15718 | 417.4445 | 26724
15719 | 415.9525 | 26724
15720 | 420.269 | 26724
15721 | 423.8397 | 26724
15722 | 414.8453 | 26724
15723 | 410.2765 | 26724
15724 | 421.5077 | 26724
15725 | 410.0989 | 26724
15726 | 406.5476 | 26724
15727 | 424.3885 | 26724
15728 | 406.8074 | 26724
15729 | 422.3708 | 26724
15730 | 416.6318 | 26724
15731 | 423.227 | 26724
15732 | 415.5691 | 26724
15733 | 412.2983 | 26724
15734 | 413.4009 | 26724
15735 | 427.9682 | 26724
15736 | 425.9596 | 26724
15737 | 422.8348 | 26724
15738 | 416.7721 | 26724
15739 | 409.7977 | 26724
15740 | 416.7145 | 26724
15741 | 409.0963 | 26724
15742 | 421.8129 | 26724
15743 | 421.58 | 26724
15744 | 405.6269 | 26724
15745 | 417.2317 | 26724
15746 | 410.265 | 26724
15747 | 409.6971 | 26724
15748 | 417.0367 | 26724
15749 | 412.1778 | 26724
15750 | 413.6281 | 26724
15751 | 400.2053 | 26724
15752 | 423.3901 | 26724
15753 | 408.6784 | 26724
15754 | 420.7484 | 26724
15755 | 415.234 | 26724
15756 | 436.8749 | 26724
15757 | 412.1353 | 26724
15758 | 402.8381 | 26724
15759 | 408.9749 | 26724
15760 | 412.6314 | 26724
15761 | 429.2461 | 26724
15762 | 416.7578 | 26724
15763 | 399.7949 | 26724
15764 | 403.659 | 26724
15765 | 412.5154 | 26724
15766 | 412.8126 | 26724
15767 | 408.3471 | 26724
15768 | 417.2406 | 26724
15769 | 419.043 | 26724
15770 | 408.446 | 26724
15771 | 413.4444 | 26724
15772 | 418.9751 | 26724
15773 | 417.8963 | 26724
15774 | 416.126 | 26724
15775 | 424.7298 | 26724
15776 | 415.2869 | 26724
15777 | 424.5621 | 26724
15778 | 415.0347 | 26724
15779 | 418.4341 | 26724
15780 | 410.1956 | 26724
15781 | 420.0283 | 26724
15782 | 405.2927 | 26724
15783 | 418.6078 | 26724
15784 | 410.0141 | 26724
15785 | 413.6736 | 26724
15786 | 415.5081 | 26724
15787 | 412.5291 | 26724
15788 | 418.848 | 26724
15789 | 418.6668 | 26724
15790 | 409.3177 | 26724
15791 | 417.6908 | 26724
15792 | 403.2366 | 26724
15793 | 413.1702 | 26724
15794 | 418.3707 | 26724
15795 | 417.8866 | 26724
15796 | 421.5726 | 26724
15797 | 413.9883 | 26724
15798 | 412.8042 | 26724
15799 | 423.7774 | 26724
15800 | 414.5697 | 26724
15801 | 412.8889 | 26724
15802 | 418.6479 | 26724
15803 | 419.9197 | 26724
15804 | 415.1946 | 26724
15805 | 416.0622 | 26724
15806 | 414.8541 | 26724
15807 | 415.374 | 26724
15808 | 402.4769 | 26724
15809 | 411.0077 | 26724
15810 | 404.1606 | 26724
15811 | 411.8393 | 26724
15812 | 423.6578 | 26724
15813 | 420.1738 | 26724
15814 | 434.4757 | 26724
15815 | 409.7801 | 26724
15816 | 425.8264 | 26724
15817 | 414.0092 | 26724
15818 | 413.6626 | 26724
15819 | 396.1304 | 26724
15820 | 420.2111 | 26724
15821 | 421.4997 | 26724
15822 | 409.3946 | 26724
15823 | 426.5104 | 26724
15824 | 425.7841 | 26724
15825 | 415.651 | 26724
15826 | 414.0339 | 26724
15827 | 426.9147 | 26724
15828 | 411.5478 | 26724
15829 | 409.9145 | 26724
15830 | 413.5958 | 26724
15831 | 420.6308 | 26724
15832 | 409.3757 | 26724
15833 | 417.1178 | 26724
15834 | 414.7936 | 26724
15835 | 410.0879 | 26724
15836 | 415.2748 | 26724
15837 | 424.601 | 26724
15838 | 409.7335 | 26724
15839 | 401.5725 | 26724
15840 | 426.3504 | 26724
15841 | 405.1325 | 26724
15842 | 416.2187 | 26724
15843 | 418.5199 | 26724
15844 | 395.8235 | 26724
15845 | 424.325 | 26724
15846 | 422.5954 | 26724
15847 | 421.6032 | 26724
15848 | 441.7717 | 26724
15849 | 428.4435 | 26724
15850 | 406.0419 | 26724
15851 | 416.7955 | 26724
15852 | 425.2817 | 26724
15853 | 409.954 | 26724
15854 | 417.511 | 26724
15855 | 407.2085 | 26724
15856 | 424.7148 | 26724
15857 | 416.1295 | 26724
15858 | 414.8251 | 26724
15859 | 410.9703 | 26724
15860 | 414.1103 | 26724
15861 | 401.0276 | 26724
15862 | 405.3414 | 26724
15863 | 416.9387 | 26724
15864 | 414.1143 | 26724
15865 | 419.2777 | 26724
15866 | 423.082 | 26724
15867 | 399.9892 | 26724
15868 | 417.6604 | 26724
15869 | 417.9056 | 26724
15870 | 426.0636 | 26724
15871 | 424.9101 | 26724
15872 | 408.7975 | 26724
15873 | 405.5264 | 26724
15874 | 414.8415 | 26724
15875 | 412.8229 | 26724
15876 | 414.3141 | 26724
15877 | 413.1981 | 26724
15878 | 406.753 | 26724
15879 | 420.1461 | 26724
15880 | 427.7501 | 26724
15881 | 422.2082 | 26724
15882 | 424.8695 | 26724
15883 | 433.4713 | 26724
15884 | 417.5625 | 26724
15885 | 421.4252 | 26724
15886 | 404.0984 | 26724
15887 | 400.5356 | 26724
15888 | 412.9772 | 26724
15889 | 425.7204 | 26724
15890 | 417.7826 | 26724
15891 | 420.4131 | 26724
15892 | 422.3941 | 26724
15893 | 409.5373 | 26724
15894 | 418.1696 | 26724
15895 | 425.4187 | 26724
15896 | 408.0247 | 26724
15897 | 415.4971 | 26724
15898 | 403.7406 | 26724
15899 | 418.7094 | 26724
15900 | 412.0725 | 26724
15901 | 413.8658 | 26724
15902 | 428.1107 | 26724
15903 | 419.4166 | 26724
15904 | 416.2374 | 26724
15905 | 412.8669 | 26724
15906 | 417.2755 | 26724
15907 | 411.4053 | 26724
15908 | 422.0942 | 26724
15909 | 396.9282 | 26724
15910 | 412.3057 | 26724
15911 | 417.0749 | 26724
15912 | 403.3263 | 26724
15913 | 416.345 | 26724
15914 | 422.0538 | 26724
15915 | 422.7271 | 26724
15916 | 427.2477 | 26724
15917 | 417.149 | 26724
15918 | 428.0389 | 26724
15919 | 416.8166 | 26724
15920 | 422.1036 | 26724
15921 | 412.2665 | 26724
15922 | 409.2428 | 26724
15923 | 407.9427 | 26724
15924 | 422.0272 | 26724
15925 | 419.9644 | 26724
15926 | 405.6483 | 26724
15927 | 417.9256 | 26724
15928 | 422.717 | 26724
15929 | 408.4713 | 26724
15930 | 427.7606 | 26724
15931 | 405.481 | 26724
15932 | 419.3984 | 26724
15933 | 412.2626 | 26724
15934 | 420.034 | 26724
15935 | 410.4014 | 26724
15936 | 424.1037 | 26724
15937 | 424.1805 | 26724
15938 | 413.867 | 26724
15939 | 424.1628 | 26724
15940 | 416.2022 | 26724
15941 | 413.2523 | 26724
15942 | 404.1631 | 26724
15943 | 419.7404 | 26724
15944 | 415.0578 | 26724
15945 | 415.4628 | 26724
15946 | 417.6962 | 26724
15947 | 416.7528 | 26724
15948 | 429.7776 | 26724
15949 | 413.2436 | 26724
15950 | 407.0388 | 26724
15951 | 420.6762 | 26724
15952 | 414.883 | 26724
15953 | 423.196 | 26724
15954 | 416.6123 | 26724
15955 | 413.4167 | 26724
15956 | 408.6264 | 26724
15957 | 414.3595 | 26724
15958 | 420.5801 | 26724
15959 | 423.464 | 26724
15960 | 423.7277 | 26724
15961 | 404.9675 | 26724
15962 | 424.3833 | 26724
15963 | 425.1953 | 26724
15964 | 408.1703 | 26724
15965 | 408.2967 | 26724
15966 | 403.8161 | 26724
15967 | 417.0651 | 26724
15968 | 414.0486 | 26724
15969 | 413.3849 | 26724
15970 | 419.5616 | 26724
15971 | 427.0599 | 26724
15972 | 408.3006 | 26724
15973 | 410.8556 | 26724
15974 | 413.19 | 26724
15975 | 406.6036 | 26724
15976 | 415.5476 | 26724
15977 | 424.9837 | 26724
15978 | 411.2931 | 26724
15979 | 409.7687 | 26724
15980 | 428.4227 | 26724
15981 | 404.7658 | 26724
15982 | 416.748 | 26724
15983 | 419.7809 | 26724
15984 | 415.3094 | 26724
15985 | 416.5809 | 26724
15986 | 412.7775 | 26724
15987 | 410.9029 | 26724
15988 | 430.8918 | 26724
15989 | 399.8336 | 26724
15990 | 411.7989 | 26724
15991 | 403.4962 | 26724
15992 | 435.4405 | 26724
15993 | 412.1829 | 26724
15994 | 420.841 | 26724
15995 | 415.6998 | 26724
15996 | 395.5484 | 26724
15997 | 408.2911 | 26724
15998 | 422.6468 | 26724
15999 | 402.3069 | 26724
16000 | 415.5348 | 26724
16001 | 416.8557 | 26724
16002 | 408.0865 | 26724
16003 | 397.942 | 26724
16004 | 418.1832 | 26724
16005 | 414.2589 | 26724
16006 | 413.98 | 26724
16007 | 411.407 | 26724
16008 | 412.7967 | 26724
16009 | 421.6223 | 26724
16010 | 416.3803 | 26724
16011 | 419.9383 | 26724
16012 | 403.5764 | 26724
16013 | 419.3067 | 26724
16014 | 425.7207 | 26724
16015 | 415.0011 | 26724
16016 | 413.0261 | 26724
16017 | 419.3956 | 26724
16018 | 416.2649 | 26724
16019 | 398.8258 | 26724
16020 | 425.1261 | 26724
16021 | 409.283 | 26724
16022 | 416.3183 | 26724
16023 | 410.4442 | 26724
16024 | 407.2779 | 26724
16025 | 421.4024 | 26724
16026 | 416.8782 | 26724
16027 | 415.0774 | 26724
16028 | 426.1146 | 26724
16029 | 423.5559 | 26724
16030 | 423.7405 | 26724
16031 | 426.8787 | 26724
16032 | 429.8259 | 26724
16033 | 397.0128 | 26724
16034 | 419.3983 | 26724
16035 | 423.3543 | 26724
16036 | 429.2126 | 26724
16037 | 418.1073 | 26724
16038 | 418.0491 | 26724
16039 | 411.7191 | 26724
16040 | 406.5173 | 26724
16041 | 421.1133 | 26724
16042 | 415.7022 | 26724
16043 | 412.7096 | 26724
16044 | 410.4559 | 26724
16045 | 421.413 | 26724
16046 | 421.7428 | 26724
16047 | 406.5617 | 26724
16048 | 413.2041 | 26724
16049 | 424.0246 | 26724
16050 | 410.9522 | 26724
16051 | 417.9991 | 26724
16052 | 417.5046 | 26724
16053 | 416.1196 | 26724
16054 | 402.9405 | 26724
16055 | 408.1556 | 26724
16056 | 401.7988 | 26724
16057 | 414.8467 | 26724
16058 | 406.9039 | 26724
16059 | 410.4627 | 26724
16060 | 409.5582 | 26724
16061 | 424.5846 | 26724
16062 | 420.5798 | 26724
16063 | 410.0166 | 26724
16064 | 419.3705 | 26724
16065 | 409.9096 | 26724
16066 | 413.6506 | 26724
16067 | 428.5335 | 26724
16068 | 404.0653 | 26724
16069 | 418.4055 | 26724
16070 | 424.0582 | 26724
16071 | 417.1772 | 26724
16072 | 414.6195 | 26724
16073 | 435.6051 | 26724
16074 | 411.13 | 26724
16075 | 410.0901 | 26724
16076 | 413.3957 | 26724
16077 | 412.3377 | 26724
16078 | 409.7659 | 26724
16079 | 434.243 | 26724
16080 | 404.0877 | 26724
16081 | 413.2975 | 26724
16082 | 415.9409 | 26724
16083 | 421.9007 | 26724
16084 | 424.3916 | 26724
16085 | 413.5235 | 26724
16086 | 411.7446 | 26724
16087 | 419.5642 | 26724
16088 | 421.0664 | 26724
16089 | 426.2882 | 26724
16090 | 419.9541 | 26724
16091 | 413.0164 | 26724
16092 | 411.2493 | 26724
16093 | 422.232 | 26724
16094 | 409.8097 | 26724
16095 | 417.7475 | 26724
16096 | 405.4425 | 26724
16097 | 411.0621 | 26724
16098 | 401.6859 | 26724
16099 | 423.5763 | 26724
16100 | 430.0929 | 26724
16101 | 420.272 | 26724
16102 | 427.9191 | 26724
16103 | 408.2214 | 26724
16104 | 419.4199 | 26724
16105 | 414.4958 | 26724
16106 | 402.5624 | 26724
16107 | 418.0645 | 26724
16108 | 401.3293 | 26724
16109 | 408.8912 | 26724
16110 | 413.5178 | 26724
16111 | 415.7689 | 26724
16112 | 404.9503 | 26724
16113 | 416.4475 | 26724
16114 | 421.4092 | 26724
16115 | 403.2022 | 26724
16116 | 408.1383 | 26724
16117 | 414.2798 | 26724
16118 | 415.7861 | 26724
16119 | 417.5149 | 26724
16120 | 408.3355 | 26724
16121 | 428.2032 | 26724
16122 | 426.8824 | 26724
16123 | 408.9417 | 26724
16124 | 424.2651 | 26724
16125 | 401.0007 | 26724
16126 | 420.4638 | 26724
16127 | 423.6243 | 26724
16128 | 403.2854 | 26724
16129 | 404.1498 | 26724
16130 | 401.9369 | 26724
16131 | 396.8375 | 26724
16132 | 412.1155 | 26724
16133 | 416.534 | 26724
16134 | 415.9038 | 26724
16135 | 422.0903 | 26724
16136 | 419.6999 | 26724
16137 | 403.3028 | 26724
16138 | 423.3693 | 26724
16139 | 422.084 | 26724
16140 | 409.5627 | 26724
16141 | 418.4761 | 26724
16142 | 413.0397 | 26724
16143 | 419.8739 | 26724
16144 | 416.7126 | 26724
16145 | 406.7624 | 26724
16146 | 410.3781 | 26724
16147 | 425.5618 | 26724
16148 | 407.5467 | 26724
16149 | 420.5358 | 26724
16150 | 430.2576 | 26724
16151 | 415.4335 | 26724
16152 | 422.7609 | 26724
16153 | 421.7873 | 26724
16154 | 421.4333 | 26724
16155 | 425.6746 | 26724
16156 | 427.5871 | 26724
16157 | 405.4158 | 26724
16158 | 414.9016 | 26724
16159 | 416.8223 | 26724
16160 | 419.8762 | 26724
16161 | 413.6983 | 26724
16162 | 423.7286 | 26724
16163 | 407.171 | 26724
16164 | 410.7413 | 26724
16165 | 406.2796 | 26724
16166 | 421.6585 | 26724
16167 | 408.6265 | 26724
16168 | 419.9342 | 26724
16169 | 417.844 | 26724
16170 | 417.4289 | 26724
16171 | 414.7771 | 26724
16172 | 422.9183 | 26724
16173 | 414.6964 | 26724
16174 | 429.4057 | 26724
16175 | 410.6413 | 26724
16176 | 415.1565 | 26724
16177 | 415.8911 | 26724
16178 | 431.6791 | 26724
16179 | 408.6211 | 26724
16180 | 426.9592 | 26724
16181 | 418.4049 | 26724
16182 | 403.8161 | 26724
16183 | 422.2463 | 26724
16184 | 407.1394 | 26724
16185 | 423.691 | 26724
16186 | 426.6648 | 26724
16187 | 433.2962 | 26724
16188 | 414.0041 | 26724
16189 | 413.2428 | 26724
16190 | 420.1744 | 26724
16191 | 413.9824 | 26724
16192 | 429.2687 | 26724
16193 | 414.0371 | 26724
16194 | 425.5047 | 26724
16195 | 425.1542 | 26724
16196 | 413.3393 | 26724
16197 | 419.7215 | 26724
16198 | 420.6438 | 26724
16199 | 409.12 | 26724
16200 | 429.3957 | 26724
16201 | 430.0529 | 26724
16202 | 407.1388 | 26724
16203 | 414.2476 | 26724
16204 | 430.0715 | 26724
16205 | 415.6081 | 26724
16206 | 440.042 | 26724
16207 | 415.6047 | 26724
16208 | 409.1235 | 26724
16209 | 414.7001 | 26724
16210 | 412.3236 | 26724
16211 | 429.7298 | 26724
16212 | 415.3885 | 26724
16213 | 404.7857 | 26724
16214 | 419.1167 | 26724
16215 | 412.8757 | 26724
16216 | 410.3646 | 26724
16217 | 416.5075 | 26724
16218 | 426.7743 | 26724
16219 | 419.6242 | 26724
16220 | 424.8088 | 26724
16221 | 398.9305 | 26724
16222 | 410.1739 | 26724
16223 | 418.4445 | 26724
16224 | 416.4806 | 26724
16225 | 431.5297 | 26724
16226 | 409.7739 | 26724
16227 | 435.77 | 26724
16228 | 419.3104 | 26724
16229 | 422.9072 | 26724
16230 | 414.4601 | 26724
16231 | 399.8782 | 26724
16232 | 409.4697 | 26724
16233 | 413.9913 | 26724
16234 | 421.808 | 26724
16235 | 406.1784 | 26724
16236 | 413.4224 | 26724
16237 | 418.7071 | 26724
16238 | 406.3358 | 26724
16239 | 422.0663 | 26724
16240 | 422.2631 | 26724
16241 | 436.4615 | 26724
16242 | 423.5277 | 26724
16243 | 422.4376 | 26724
16244 | 427.6892 | 26724
16245 | 422.0156 | 26724
16246 | 421.4469 | 26724
16247 | 417.7402 | 26724
16248 | 417.9457 | 26724
16249 | 429.2569 | 26724
16250 | 423.5196 | 26724
16251 | 424.6765 | 26724
16252 | 424.2687 | 26724
16253 | 413.1453 | 26724
16254 | 416.8127 | 26724
16255 | 417.4044 | 26724
16256 | 416.108 | 26724
16257 | 414.2884 | 26724
16258 | 416.9572 | 26724
16259 | 405.4389 | 26724
16260 | 431.7177 | 26724
16261 | 425.0293 | 26724
16262 | 416.0267 | 26724
16263 | 426.4484 | 26724
16264 | 418.0452 | 26724
16265 | 420.5066 | 26724
16266 | 433.9937 | 26724
16267 | 407.1356 | 26724
16268 | 409.9853 | 26724
16269 | 408.7679 | 26724
16270 | 400.5496 | 26724
16271 | 418.9949 | 26724
16272 | 428.4277 | 26724
16273 | 405.5595 | 26724
16274 | 415.6675 | 26724
16275 | 411.2954 | 26724
16276 | 414.0209 | 26724
16277 | 401.955 | 26724
16278 | 418.524 | 26724
16279 | 418.4915 | 26724
16280 | 419.2113 | 26724
16281 | 407.2433 | 26724
16282 | 420.026 | 26724
16283 | 431.6528 | 26724
16284 | 418.9131 | 26724
16285 | 410.7272 | 26724
16286 | 425.9899 | 26724
16287 | 407.0446 | 26724
16288 | 401.7944 | 26724
16289 | 410.6369 | 26724
16290 | 409.9767 | 26724
16291 | 421.3449 | 26724
16292 | 417.8577 | 26724
16293 | 409.8935 | 26724
16294 | 415.1494 | 26724
16295 | 400.5291 | 26724
16296 | 413.0507 | 26724
16297 | 408.1465 | 26724
16298 | 413.2465 | 26724
16299 | 419.5236 | 26724
16300 | 405.2688 | 26724
16301 | 422.7845 | 26724
16302 | 411.0184 | 26724
16303 | 420.2586 | 26724
16304 | 403.249 | 26724
16305 | 435.4202 | 26724
16306 | 400.7651 | 26724
16307 | 408.8492 | 26724
16308 | 409.4788 | 26724
16309 | 422.0697 | 26724
16310 | 417.2523 | 26724
16311 | 421.6659 | 26724
16312 | 417.5901 | 26724
16313 | 405.3395 | 26724
16314 | 414.3704 | 26724
16315 | 423.9413 | 26724
16316 | 421.6867 | 26724
16317 | 408.8531 | 26724
16318 | 418.2616 | 26724
16319 | 415.8814 | 26724
16320 | 429.1587 | 26724
16321 | 419.617 | 26724
16322 | 416.2006 | 26724
16323 | 421.4973 | 26724
16324 | 424.4073 | 26724
16325 | 394.3365 | 26724
16326 | 417.3007 | 26724
16327 | 420.7191 | 26724
16328 | 417.4416 | 26724
16329 | 403.3063 | 26724
16330 | 416.769 | 26724
16331 | 410.3618 | 26724
16332 | 420.0373 | 26724
16333 | 429.8261 | 26724
16334 | 414.2579 | 26724
16335 | 405.0303 | 26724
16336 | 425.7648 | 26724
16337 | 409.8164 | 26724
16338 | 417.3732 | 26724
16339 | 406.9407 | 26724
16340 | 423.4857 | 26724
16341 | 408.1754 | 26724
16342 | 412.2432 | 26724
16343 | 413.5623 | 26724
16344 | 400.7385 | 26724
16345 | 420.7606 | 26724
16346 | 408.3391 | 26724
16347 | 423.3619 | 26724
16348 | 412.0943 | 26724
16349 | 420.7261 | 26724
16350 | 432.7209 | 26724
16351 | 414.0034 | 26724
16352 | 403.4282 | 26724
16353 | 420.0486 | 26724
16354 | 428.3702 | 26724
16355 | 416.7678 | 26724
16356 | 407.5264 | 26724
16357 | 407.2911 | 26724
16358 | 399.8322 | 26724
16359 | 419.3757 | 26724
16360 | 410.6171 | 26724
16361 | 420.839 | 26724
16362 | 418.7655 | 26724
16363 | 414.1672 | 26724
16364 | 412.1304 | 26724
16365 | 412.0797 | 26724
16366 | 430.8606 | 26724
16367 | 417.0109 | 26724
16368 | 409.3985 | 26724
16369 | 416.7858 | 26724
16370 | 399.5504 | 26724
16371 | 422.3603 | 26724
16372 | 415.0212 | 26724
16373 | 422.392 | 26724
16374 | 425.6054 | 26724
16375 | 420.4287 | 26724
16376 | 434.3079 | 26724
16377 | 416.5638 | 26724
16378 | 407.345 | 26724
16379 | 418.135 | 26724
16380 | 421.1937 | 26724
16381 | 429.6563 | 26724
16382 | 417.063 | 26724
16383 | 409.8701 | 26724
16384 | 419.3425 | 26724
16385 | 412.104 | 26724
16386 | 416.8048 | 26724
16387 | 416.4947 | 26724
16388 | 433.7322 | 26724
16389 | 416.8945 | 26724
16390 | 430.8813 | 26724
16391 | 411.5953 | 26724
16392 | 420.0609 | 26724
16393 | 407.6453 | 26724
16394 | 412.7981 | 26724
16395 | 416.3728 | 26724
16396 | 403.4794 | 26724
16397 | 403.5532 | 26724
16398 | 403.4297 | 26724
16399 | 414.492 | 26724
16400 | 422.7864 | 26724
16401 | 431.0863 | 26724
16402 | 418.3923 | 26724
16403 | 420.7207 | 26724
16404 | 422.0918 | 26724
16405 | 423.8004 | 26724
16406 | 407.0727 | 26724
16407 | 433.9091 | 26724
16408 | 417.1555 | 26724
16409 | 415.9794 | 26724
16410 | 418.0607 | 26724
16411 | 421.4764 | 26724
16412 | 423.8383 | 26724
16413 | 422.1864 | 26724
16414 | 402.5624 | 26724
16415 | 413.4546 | 26724
16416 | 424.2034 | 26724
16417 | 401.1993 | 26724
16418 | 412.506 | 26724
16419 | 407.2616 | 26724
16420 | 428.6495 | 26724
16421 | 418.7225 | 26724
16422 | 411.7683 | 26724
16423 | 422.0794 | 26724
16424 | 417.8318 | 26724
16425 | 418.0435 | 26724
16426 | 424.1021 | 26724
16427 | 401.1903 | 26724
16428 | 421.2805 | 26724
16429 | 420.5424 | 26724
16430 | 418.7372 | 26724
16431 | 409.8009 | 26724
16432 | 422.5936 | 26724
16433 | 413.013 | 26724
16434 | 421.311 | 26724
16435 | 409.4838 | 26724
16436 | 426.4671 | 26724
16437 | 396.6444 | 26724
16438 | 396.5705 | 26724
16439 | 411.8041 | 26724
16440 | 416.1312 | 26724
16441 | 415.3275 | 26724
16442 | 406.3967 | 26724
16443 | 398.8113 | 26724
16444 | 429.1168 | 26724
16445 | 409.6766 | 26724
16446 | 417.085 | 26724
16447 | 416.2589 | 26724
16448 | 409.9768 | 26724
16449 | 424.1703 | 26724
16450 | 430.5491 | 26724
16451 | 417.2626 | 26724
16452 | 404.3291 | 26724
16453 | 413.7113 | 26724
16454 | 415.2886 | 26724
16455 | 420.5195 | 26724
16456 | 422.1424 | 26724
16457 | 416.5484 | 26724
16458 | 413.4094 | 26724
16459 | 413.2676 | 26724
16460 | 424.9309 | 26724
16461 | 418.4067 | 26724
16462 | 399.0769 | 26724
16463 | 412.4939 | 26724
16464 | 411.2995 | 26724
16465 | 421.1599 | 26724
16466 | 420.5851 | 26724
16467 | 403.7516 | 26724
16468 | 411.9978 | 26724
16469 | 419.8852 | 26724
16470 | 423.5991 | 26724
16471 | 410.2568 | 26724
16472 | 416.0303 | 26724
16473 | 420.8901 | 26724
16474 | 412.3119 | 26724
16475 | 416.4493 | 26724
16476 | 410.6889 | 26724
16477 | 417.2703 | 26724
16478 | 425.2274 | 26724
16479 | 418.4967 | 26724
16480 | 428.2895 | 26724
16481 | 409.7964 | 26724
16482 | 399.2408 | 26724
16483 | 432.1138 | 26724
16484 | 427.6917 | 26724
16485 | 414.4952 | 26724
16486 | 430.5154 | 26724
16487 | 420.5315 | 26724
16488 | 402.6591 | 26724
16489 | 420.4908 | 26724
16490 | 418.6387 | 26724
16491 | 401.8299 | 26724
16492 | 420.9589 | 26724
16493 | 423.78 | 26724
16494 | 414.0163 | 26724
16495 | 410.6867 | 26724
16496 | 416.2994 | 26724
16497 | 415.5469 | 26724
16498 | 419.6976 | 26724
16499 | 422.395 | 26724
16500 | 411.0616 | 26724
16501 | 400.3939 | 26724
16502 | 424.6875 | 26724
16503 | 421.3874 | 26724
16504 | 419.7161 | 26724
16505 | 407.383 | 26724
16506 | 407.5563 | 26724
16507 | 408.7227 | 26724
16508 | 412.8345 | 26724
16509 | 412.9685 | 26724
16510 | 404.472 | 26724
16511 | 412.8425 | 26724
16512 | 424.2127 | 26724
16513 | 413.3786 | 26724
16514 | 406.5517 | 26724
16515 | 415.4501 | 26724
16516 | 428.5956 | 26724
16517 | 406.0785 | 26724
16518 | 417.1846 | 26724
16519 | 425.9839 | 26724
16520 | 423.7139 | 26724
16521 | 407.5081 | 26724
16522 | 428.1742 | 26724
16523 | 423.2628 | 26724
16524 | 427.3514 | 26724
16525 | 407.7697 | 26724
16526 | 412.0471 | 26724
16527 | 404.2191 | 26724
16528 | 417.8479 | 26724
16529 | 422.1704 | 26724
16530 | 424.819 | 26724
16531 | 429.0808 | 26724
16532 | 406.0937 | 26724
16533 | 415.0743 | 26724
16534 | 411.0375 | 26724
16535 | 430.6679 | 26724
16536 | 413.2013 | 26724
16537 | 416.4727 | 26724
16538 | 414.571 | 26724
16539 | 404.2764 | 26724
16540 | 421.657 | 26724
16541 | 422.5928 | 26724
16542 | 420.6684 | 26724
16543 | 411.3089 | 26724
16544 | 412.6068 | 26724
16545 | 425.0018 | 26724
16546 | 417.0633 | 26724
16547 | 417.7735 | 26724
16548 | 424.9626 | 26724
16549 | 420.225 | 26724
16550 | 416.2694 | 26724
16551 | 406.9458 | 26724
16552 | 400.1994 | 26724
16553 | 399.6897 | 26724
16554 | 400.9605 | 26724
16555 | 418.9103 | 26724
16556 | 437.4529 | 26724
16557 | 416.4161 | 26724
16558 | 425.0842 | 26724
16559 | 401.6546 | 26724
16560 | 411.1616 | 26724
16561 | 417.8127 | 26724
16562 | 429.5263 | 26724
16563 | 416.1893 | 26724
16564 | 409.0353 | 26724
16565 | 409.5866 | 26724
16566 | 422.5156 | 26724
16567 | 412.006 | 26724
16568 | 418.7537 | 26724
16569 | 411.9972 | 26724
16570 | 406.3247 | 26724
16571 | 414.1782 | 26724
16572 | 423.6905 | 26724
16573 | 403.1225 | 26724
16574 | 427.8541 | 26724
16575 | 407.2472 | 26724
16576 | 419.827 | 26724
16577 | 416.7642 | 26724
16578 | 416.6448 | 26724
16579 | 415.6689 | 26724
16580 | 429.2551 | 26724
16581 | 413.234 | 26724
16582 | 427.0847 | 26724
16583 | 403.0948 | 26724
16584 | 415.7387 | 26724
16585 | 400.8713 | 26724
16586 | 422.3044 | 26724
16587 | 408.2309 | 26724
16588 | 414.8343 | 26724
16589 | 412.1386 | 26724
16590 | 416.0759 | 26724
16591 | 423.5137 | 26724
16592 | 423.6639 | 26724
16593 | 419.436 | 26724
16594 | 423.3019 | 26724
16595 | 415.1812 | 26724
16596 | 419.8962 | 26724
16597 | 420.9314 | 26724
16598 | 407.3237 | 26724
16599 | 423.7811 | 26724
16600 | 433.8539 | 26724
16601 | 411.6667 | 26724
16602 | 429.5076 | 26724
16603 | 410.9038 | 26724
16604 | 422.1871 | 26724
16605 | 416.8311 | 26724
16606 | 402.2808 | 26724
16607 | 410.9076 | 26724
16608 | 403.1533 | 26724
16609 | 422.6078 | 26724
16610 | 407.981 | 26724
16611 | 407.7894 | 26724
16612 | 414.5924 | 26724
16613 | 413.2882 | 26724
16614 | 418.8115 | 26724
16615 | 407.6203 | 26724
16616 | 409.742 | 26724
16617 | 431.0361 | 26724
16618 | 426.6728 | 26724
16619 | 431.0348 | 26724
16620 | 412.9754 | 26724
16621 | 414.1827 | 26724
16622 | 433.1638 | 26724
16623 | 407.6691 | 26724
16624 | 412.0383 | 26724
16625 | 404.6156 | 26724
16626 | 406.1916 | 26724
16627 | 413.5609 | 26724
16628 | 422.2805 | 26724
16629 | 416.2 | 26724
16630 | 402.0595 | 26724
16631 | 419.4045 | 26724
16632 | 421.2095 | 26724
16633 | 404.4419 | 26724
16634 | 414.8483 | 26724
16635 | 413.2189 | 26724
16636 | 416.9738 | 26724
16637 | 408.6537 | 26724
16638 | 418.557 | 26724
16639 | 407.3698 | 26724
16640 | 423.2656 | 26724
16641 | 425.7613 | 26724
16642 | 406.9369 | 26724
16643 | 412.3897 | 26724
16644 | 418.4998 | 26724
16645 | 410.7616 | 26724
16646 | 421.8011 | 26724
16647 | 427.8843 | 26724
16648 | 415.9802 | 26724
16649 | 414.4028 | 26724
16650 | 421.6878 | 26724
16651 | 421.5315 | 26724
16652 | 412.7439 | 26724
16653 | 409.2122 | 26724
16654 | 413.4781 | 26724
16655 | 423.2103 | 26724
16656 | 413.3211 | 26724
16657 | 416.3711 | 26724
16658 | 402.8674 | 26724
16659 | 416.6249 | 26724
16660 | 403.0964 | 26724
16661 | 414.6711 | 26724
16662 | 422.9063 | 26724
16663 | 422.4056 | 26724
16664 | 429.3752 | 26724
16665 | 424.0631 | 26724
16666 | 409.2002 | 26724
16667 | 411.7979 | 26724
16668 | 412.6135 | 26724
16669 | 420.3192 | 26724
16670 | 404.5165 | 26724
16671 | 414.1561 | 26724
16672 | 433.1072 | 26724
16673 | 419.5994 | 26724
16674 | 415.4628 | 26724
16675 | 412.9285 | 26724
16676 | 420.887 | 26724
16677 | 418.4394 | 26724
16678 | 427.9992 | 26724
16679 | 406.8283 | 26724
16680 | 413.7433 | 26724
16681 | 414.6131 | 26724
16682 | 418.067 | 26724
16683 | 411.0112 | 26724
16684 | 411.5106 | 26724
16685 | 397.6685 | 26724
16686 | 410.3973 | 26724
16687 | 413.9263 | 26724
16688 | 419.835 | 26724
16689 | 426.4674 | 26724
16690 | 413.9076 | 26724
16691 | 416.7533 | 26724
16692 | 406.6837 | 26724
16693 | 428.9873 | 26724
16694 | 410.8876 | 26724
16695 | 430.1291 | 26724
16696 | 413.582 | 26724
16697 | 413.9989 | 26724
16698 | 409.0165 | 26724
16699 | 420.4456 | 26724
16700 | 413.3554 | 26724
16701 | 419.2198 | 26724
16702 | 410.6749 | 26724
16703 | 406.1626 | 26724
16704 | 412.779 | 26724
16705 | 417.4876 | 26724
16706 | 422.5505 | 26724
16707 | 423.2443 | 26724
16708 | 417.3707 | 26724
16709 | 414.9671 | 26724
16710 | 417.3484 | 26724
16711 | 428.86 | 26724
16712 | 403.6049 | 26724
16713 | 406.1643 | 26724
16714 | 423.0581 | 26724
16715 | 413.3962 | 26724
16716 | 419.4298 | 26724
16717 | 404.7281 | 26724
16718 | 422.9531 | 26724
16719 | 413.0631 | 26724
16720 | 420.6887 | 26724
16721 | 411.086 | 26724
16722 | 422.1168 | 26724
16723 | 407.8859 | 26724
16724 | 404.9937 | 26724
16725 | 405.491 | 26724
16726 | 422.9501 | 26724
16727 | 420.3981 | 26724
16728 | 413.3145 | 26724
16729 | 415.6345 | 26724
16730 | 418.4471 | 26724
16731 | 417.1068 | 26724
16732 | 412.65 | 26724
16733 | 415.6874 | 26724
16734 | 404.8264 | 26724
16735 | 416.0541 | 26724
16736 | 425.3756 | 26724
16737 | 405.7609 | 26724
16738 | 410.7878 | 26724
16739 | 419.4344 | 26724
16740 | 418.8282 | 26724
16741 | 423.2765 | 26724
16742 | 414.5532 | 26724
16743 | 412.2479 | 26724
16744 | 412.323 | 26724
16745 | 417.2053 | 26724
16746 | 418.5053 | 26724
16747 | 406.9053 | 26724
16748 | 414.8522 | 26724
16749 | 423.8344 | 26724
16750 | 406.9179 | 26724
16751 | 417.339 | 26724
16752 | 403.5567 | 26724
16753 | 419.0431 | 26724
16754 | 414.7694 | 26724
16755 | 404.7971 | 26724
16756 | 415.2846 | 26724
16757 | 410.2162 | 26724
16758 | 416.7514 | 26724
16759 | 431.0289 | 26724
16760 | 417.4437 | 26724
16761 | 417.6678 | 26724
16762 | 420.1107 | 26724
16763 | 409.1722 | 26724
16764 | 415.8049 | 26724
16765 | 416.5327 | 26724
16766 | 426.0948 | 26724
16767 | 403.4606 | 26724
16768 | 415.882 | 26724
16769 | 419.0028 | 26724
16770 | 427.8759 | 26724
16771 | 410.5287 | 26724
16772 | 414.4669 | 26724
16773 | 410.6831 | 26724
16774 | 422.075 | 26724
16775 | 416.2182 | 26724
16776 | 419.983 | 26724
16777 | 415.8844 | 26724
16778 | 427.8887 | 26724
16779 | 416.0547 | 26724
16780 | 429.8808 | 26724
16781 | 404.2143 | 26724
16782 | 406.8772 | 26724
16783 | 418.3362 | 26724
16784 | 414.3058 | 26724
16785 | 412.4746 | 26724
16786 | 405.3549 | 26724
16787 | 429.1197 | 26724
16788 | 410.9878 | 26724
16789 | 407.1207 | 26724
16790 | 408.1378 | 26724
16791 | 413.8699 | 26724
16792 | 418.2098 | 26724
16793 | 416.6458 | 26724
16794 | 423.5219 | 26724
16795 | 406.215 | 26724
16796 | 415.8884 | 26724
16797 | 404.4335 | 26724
16798 | 429.2063 | 26724
16799 | 427.3705 | 26724
16800 | 415.767 | 26724
16801 | 422.6377 | 26724
16802 | 436.1572 | 26724
16803 | 409.4714 | 26724
16804 | 420.7522 | 26724
16805 | 437.202 | 26724
16806 | 432.5003 | 26724
16807 | 415.1985 | 26724
16808 | 413.1343 | 26724
16809 | 410.6307 | 26724
16810 | 413.1549 | 26724
16811 | 409.2396 | 26724
16812 | 406.6895 | 26724
16813 | 418.1492 | 26724
16814 | 397.8412 | 26724
16815 | 413.7879 | 26724
16816 | 405.5215 | 26724
16817 | 424.6769 | 26724
16818 | 414.7072 | 26724
16819 | 411.3529 | 26724
16820 | 400.3564 | 26724
16821 | 418.4347 | 26724
16822 | 418.4841 | 26724
16823 | 415.8001 | 26724
16824 | 428.0436 | 26724
16825 | 412.9976 | 26724
16826 | 426.9619 | 26724
16827 | 427.5777 | 26724
16828 | 415.4015 | 26724
16829 | 419.044 | 26724
16830 | 415.026 | 26724
16831 | 414.9621 | 26724
16832 | 428.1063 | 26724
16833 | 411.705 | 26724
16834 | 398.4646 | 26724
16835 | 406.996 | 26724
16836 | 393.6281 | 26724
16837 | 420.6746 | 26724
16838 | 413.0256 | 26724
16839 | 431.7324 | 26724
16840 | 414.5859 | 26724
16841 | 428.6454 | 26724
16842 | 418.1282 | 26724
16843 | 405.7577 | 26724
16844 | 413.2343 | 26724
16845 | 420.141 | 26724
16846 | 416.6931 | 26724
16847 | 413.3954 | 26724
16848 | 410.1979 | 26724
16849 | 415.176 | 26724
16850 | 416.0293 | 26724
16851 | 423.2362 | 26724
16852 | 424.6265 | 26724
16853 | 405.5661 | 26724
16854 | 413.3988 | 26724
16855 | 429.5998 | 26724
16856 | 419.8425 | 26724
16857 | 413.8334 | 26724
16858 | 409.321 | 26724
16859 | 427.1331 | 26724
16860 | 417.112 | 26724
16861 | 421.3731 | 26724
16862 | 422.1874 | 26724
16863 | 409.2442 | 26724
16864 | 406.2025 | 26724
16865 | 417.7679 | 26724
16866 | 413.99 | 26724
16867 | 429.0724 | 26724
16868 | 418.3316 | 26724
16869 | 409.6086 | 26724
16870 | 429.3976 | 26724
16871 | 416.0945 | 26724
16872 | 430.3178 | 26724
16873 | 422.8844 | 26724
16874 | 419.4935 | 26724
16875 | 428.6313 | 26724
16876 | 426.2388 | 26724
16877 | 424.4591 | 26724
16878 | 415.4549 | 26724
16879 | 408.3607 | 26724
16880 | 415.6126 | 26724
16881 | 410.8155 | 26724
16882 | 425.1908 | 26724
16883 | 418.5583 | 26724
16884 | 423.8556 | 26724
16885 | 413.0862 | 26724
16886 | 413.669 | 26724
16887 | 410.9609 | 26724
16888 | 424.6901 | 26724
16889 | 428.1816 | 26724
16890 | 422.1963 | 26724
16891 | 412.3336 | 26724
16892 | 399.1346 | 26724
16893 | 412.9786 | 26724
16894 | 434.7384 | 26724
16895 | 403.799 | 26724
16896 | 427.1903 | 26724
16897 | 413.9251 | 26724
16898 | 428.1484 | 26724
16899 | 410.0828 | 26724
16900 | 421.6856 | 26724
16901 | 417.7481 | 26724
16902 | 418.988 | 26724
16903 | 410.7037 | 26724
16904 | 419.7585 | 26724
16905 | 426.6967 | 26724
16906 | 412.3356 | 26724
16907 | 423.7258 | 26724
16908 | 414.6471 | 26724
16909 | 424.476 | 26724
16910 | 415.699 | 26724
16911 | 427.3572 | 26724
16912 | 417.2731 | 26724
16913 | 424.5722 | 26724
16914 | 409.3552 | 26724
16915 | 420.2705 | 26724
16916 | 422.2277 | 26724
16917 | 408.6915 | 26724
16918 | 430.441 | 26724
16919 | 428.4904 | 26724
16920 | 432.4781 | 26724
16921 | 416.0337 | 26724
16922 | 408.1818 | 26724
16923 | 417.6172 | 26724
16924 | 423.7003 | 26724
16925 | 412.9843 | 26724
16926 | 425.8972 | 26724
16927 | 419.4906 | 26724
16928 | 424.6996 | 26724
16929 | 423.298 | 26724
16930 | 411.9361 | 26724
16931 | 419.3362 | 26724
16932 | 412.2496 | 26724
16933 | 413.173 | 26724
16934 | 429.3532 | 26724
16935 | 409.9093 | 26724
16936 | 420.8039 | 26724
16937 | 410.4159 | 26724
16938 | 415.0379 | 26724
16939 | 413.9359 | 26724
16940 | 413.124 | 26724
16941 | 420.4251 | 26724
16942 | 400.7827 | 26724
16943 | 415.1819 | 26724
16944 | 417.1614 | 26724
16945 | 415.6139 | 26724
16946 | 413.011 | 26724
16947 | 405.4617 | 26724
16948 | 410.6787 | 26724
16949 | 413.5745 | 26724
16950 | 435.5612 | 26724
16951 | 417.9308 | 26724
16952 | 428.1652 | 26724
16953 | 425.0783 | 26724
16954 | 415.6093 | 26724
16955 | 429.7889 | 26724
16956 | 418.5612 | 26724
16957 | 406.2665 | 26724
16958 | 406.4836 | 26724
16959 | 412.372 | 26724
16960 | 416.448 | 26724
16961 | 415.0223 | 26724
16962 | 419.9316 | 26724
16963 | 401.3514 | 26724
16964 | 416.3866 | 26724
16965 | 410.6961 | 26724
16966 | 399.4721 | 26724
16967 | 419.8202 | 26724
16968 | 409.3917 | 26724
16969 | 404.4948 | 26724
16970 | 427.8244 | 26724
16971 | 414.2777 | 26724
16972 | 412.4473 | 26724
16973 | 417.4604 | 26724
16974 | 414.1554 | 26724
16975 | 410.9366 | 26724
16976 | 415.6085 | 26724
16977 | 399.505 | 26724
16978 | 406.7877 | 26724
16979 | 417.2584 | 26724
16980 | 410.141 | 26724
16981 | 428.1194 | 26724
16982 | 407.1592 | 26724
16983 | 418.0251 | 26724
16984 | 406.2497 | 26724
16985 | 424.8121 | 26724
16986 | 402.9588 | 26724
16987 | 419.7127 | 26724
16988 | 424.3904 | 26724
16989 | 413.458 | 26724
16990 | 424.3005 | 26724
16991 | 414.7751 | 26724
16992 | 403.1515 | 26724
16993 | 407.1353 | 26724
16994 | 425.8449 | 26724
16995 | 419.2067 | 26724
16996 | 422.2634 | 26724
16997 | 411.8433 | 26724
16998 | 414.0518 | 26724
16999 | 411.8413 | 26724
17000 | 393.1537 | 26724
17001 | 408.9283 | 26724
17002 | 414.5695 | 26724
17003 | 422.5037 | 26724
17004 | 417.1779 | 26724
17005 | 424.0035 | 26724
17006 | 418.2833 | 26724
17007 | 422.4057 | 26724
17008 | 411.6504 | 26724
17009 | 410.9235 | 26724
17010 | 418.9728 | 26724
17011 | 417.8277 | 26724
17012 | 405.4454 | 26724
17013 | 411.2165 | 26724
17014 | 423.6116 | 26724
17015 | 404.4343 | 26724
17016 | 419.0445 | 26724
17017 | 414.593 | 26724
17018 | 418.9632 | 26724
17019 | 405.3004 | 26724
17020 | 420.1695 | 26724
17021 | 428.6453 | 26724
17022 | 406.7927 | 26724
17023 | 423.5859 | 26724
17024 | 412.8487 | 26724
17025 | 410.3391 | 26724
17026 | 410.6759 | 26724
17027 | 419.454 | 26724
17028 | 405.3277 | 26724
17029 | 413.5792 | 26724
17030 | 417.6634 | 26724
17031 | 431.2648 | 26724
17032 | 415.8007 | 26724
17033 | 412.8894 | 26724
17034 | 431.291 | 26724
17035 | 401.2543 | 26724
17036 | 409.2363 | 26724
17037 | 429.1852 | 26724
17038 | 422.8516 | 26724
17039 | 401.821 | 26724
17040 | 411.2198 | 26724
17041 | 409.9989 | 26724
17042 | 415.5793 | 26724
17043 | 414.0655 | 26724
17044 | 408.8723 | 26724
17045 | 416.0975 | 26724
17046 | 419.7277 | 26724
17047 | 414.7924 | 26724
17048 | 428.0383 | 26724
17049 | 423.9661 | 26724
17050 | 420.681 | 26724
17051 | 424.5958 | 26724
17052 | 415.7091 | 26724
17053 | 426.1831 | 26724
17054 | 410.5223 | 26724
17055 | 426.5379 | 26724
17056 | 419.3267 | 26724
17057 | 419.1107 | 26724
17058 | 427.0117 | 26724
17059 | 421.8291 | 26724
17060 | 411.6053 | 26724
17061 | 420.3901 | 26724
17062 | 418.7534 | 26724
17063 | 405.947 | 26724
17064 | 410.7403 | 26724
17065 | 413.9009 | 26724
17066 | 411.1722 | 26724
17067 | 414.1932 | 26724
17068 | 417.1647 | 26724
17069 | 428.1027 | 26724
17070 | 413.3231 | 26724
17071 | 413.2196 | 26724
17072 | 422.334 | 26724
17073 | 422.5936 | 26724
17074 | 407.3912 | 26724
17075 | 415.5033 | 26724
17076 | 412.5088 | 26724
17077 | 407.3891 | 26724
17078 | 423.1839 | 26724
17079 | 411.0693 | 26724
17080 | 422.9783 | 26724
17081 | 413.3139 | 26724
17082 | 413.6143 | 26724
17083 | 431.6387 | 26724
17084 | 419.2147 | 26724
17085 | 412.5136 | 26724
17086 | 425.1892 | 26724
17087 | 411.7334 | 26724
17088 | 423.6398 | 26724
17089 | 412.3653 | 26724
17090 | 409.6937 | 26724
17091 | 414.604 | 26724
17092 | 404.9342 | 26724
17093 | 422.3428 | 26724
17094 | 421.8312 | 26724
17095 | 416.8555 | 26724
17096 | 409.3009 | 26724
17097 | 416.0623 | 26724
17098 | 394.6583 | 26724
17099 | 415.2251 | 26724
17100 | 410.2346 | 26724
17101 | 428.0233 | 26724
17102 | 419.8931 | 26724
17103 | 410.1253 | 26724
17104 | 420.1514 | 26724
17105 | 406.8613 | 26724
17106 | 419.9437 | 26724
17107 | 420.7449 | 26724
17108 | 403.6538 | 26724
17109 | 412.5905 | 26724
17110 | 407.5521 | 26724
17111 | 412.0612 | 26724
17112 | 402.5941 | 26724
17113 | 415.8136 | 26724
17114 | 422.4872 | 26724
17115 | 412.7983 | 26724
17116 | 420.5887 | 26724
17117 | 427.2072 | 26724
17118 | 403.0365 | 26724
17119 | 415.295 | 26724
17120 | 412.4873 | 26724
17121 | 424.7188 | 26724
17122 | 417.758 | 26724
17123 | 424.0681 | 26724
17124 | 410.1603 | 26724
17125 | 422.5451 | 26724
17126 | 425.1342 | 26724
17127 | 412.0793 | 26724
17128 | 423.0861 | 26724
17129 | 412.3466 | 26724
17130 | 422.4476 | 26724
17131 | 416.2643 | 26724
17132 | 418.2242 | 26724
17133 | 416.4666 | 26724
17134 | 425.5054 | 26724
17135 | 418.8584 | 26724
17136 | 415.941 | 26724
17137 | 409.1375 | 26724
17138 | 401.2639 | 26724
17139 | 416.6399 | 26724
17140 | 405.046 | 26724
17141 | 415.5994 | 26724
17142 | 419.3181 | 26724
17143 | 414.2132 | 26724
17144 | 426.6742 | 26724
17145 | 426.8678 | 26724
17146 | 405.6621 | 26724
17147 | 411.0829 | 26724
17148 | 406.2782 | 26724
17149 | 420.4902 | 26724
17150 | 422.0153 | 26724
17151 | 412.7917 | 26724
17152 | 426.6367 | 26724
17153 | 421.4365 | 26724
17154 | 398.3829 | 26724
17155 | 428.1543 | 26724
17156 | 426.2821 | 26724
17157 | 422.4355 | 26724
17158 | 422.7096 | 26724
17159 | 408.4134 | 26724
17160 | 422.7714 | 26724
17161 | 405.3761 | 26724
17162 | 419.37 | 26724
17163 | 429.655 | 26724
17164 | 425.3219 | 26724
17165 | 418.2081 | 26724
17166 | 420.5756 | 26724
17167 | 434.6626 | 26724
17168 | 435.6336 | 26724
17169 | 406.1314 | 26724
17170 | 410.6853 | 26724
17171 | 417.0108 | 26724
17172 | 428.083 | 26724
17173 | 408.0435 | 26724
17174 | 422.9182 | 26724
17175 | 409.6791 | 26724
17176 | 417.1401 | 26724
17177 | 424.6933 | 26724
17178 | 416.0256 | 26724
17179 | 422.6196 | 26724
17180 | 409.2758 | 26724
17181 | 432.3562 | 26724
17182 | 428.6231 | 26724
17183 | 405.3205 | 26724
17184 | 418.4795 | 26724
17185 | 416.1998 | 26724
17186 | 414.6736 | 26724
17187 | 421.4843 | 26724
17188 | 398.8064 | 26724
17189 | 403.5991 | 26724
17190 | 415.1202 | 26724
17191 | 409.2033 | 26724
17192 | 411.2812 | 26724
17193 | 419.8486 | 26724
17194 | 431.1722 | 26724
17195 | 410.7027 | 26724
17196 | 413.5532 | 26724
17197 | 433.0368 | 26724
17198 | 422.1705 | 26724
17199 | 409.7985 | 26724
17200 | 415.1341 | 26724
17201 | 432.4047 | 26724
17202 | 398.5143 | 26724
17203 | 425.9736 | 26724
17204 | 420.8404 | 26724
17205 | 423.9434 | 26724
17206 | 412.9933 | 26724
17207 | 415.302 | 26724
17208 | 420.6428 | 26724
17209 | 407.7275 | 26724
17210 | 415.072 | 26724
17211 | 420.9505 | 26724
17212 | 415.3881 | 26724
17213 | 417.6206 | 26724
17214 | 406.6714 | 26724
17215 | 421.5074 | 26724
17216 | 409.8506 | 26724
17217 | 425.0478 | 26724
17218 | 415.6326 | 26724
17219 | 420.2191 | 26724
17220 | 409.1221 | 26724
17221 | 428.0578 | 26724
17222 | 428.1933 | 26724
17223 | 408.6632 | 26724
17224 | 407.9496 | 26724
17225 | 416.1069 | 26724
17226 | 411.375 | 26724
17227 | 412.0102 | 26724
17228 | 416.9829 | 26724
17229 | 410.9768 | 26724
17230 | 425.1562 | 26724
17231 | 416.8926 | 26724
17232 | 423.5401 | 26724
17233 | 410.2218 | 26724
17234 | 421.8061 | 26724
17235 | 430.7155 | 26724
17236 | 412.9051 | 26724
17237 | 412.0165 | 26724
17238 | 411.9027 | 26724
17239 | 405.6157 | 26724
17240 | 407.0167 | 26724
17241 | 413.8071 | 26724
17242 | 413.6221 | 26724
17243 | 414.3105 | 26724
17244 | 421.3641 | 26724
17245 | 422.8467 | 26724
17246 | 428.8709 | 26724
17247 | 412.7885 | 26724
17248 | 401.4606 | 26724
17249 | 416.9506 | 26724
17250 | 417.5469 | 26724
17251 | 413.8239 | 26724
17252 | 423.9783 | 26724
17253 | 416.553 | 26724
17254 | 423.5866 | 26724
17255 | 425.8581 | 26724
17256 | 415.7937 | 26724
17257 | 410.0447 | 26724
17258 | 426.1395 | 26724
17259 | 425.1736 | 26724
17260 | 420.0316 | 26724
17261 | 417.0583 | 26724
17262 | 417.2341 | 26724
17263 | 401.0111 | 26724
17264 | 410.4683 | 26724
17265 | 426.2156 | 26724
17266 | 421.1457 | 26724
17267 | 403.3972 | 26724
17268 | 417.6731 | 26724
17269 | 411.8616 | 26724
17270 | 410.4498 | 26724
17271 | 423.0233 | 26724
17272 | 419.1979 | 26724
17273 | 424.0108 | 26724
17274 | 419.6378 | 26724
17275 | 395.4315 | 26724
17276 | 429.8415 | 26724
17277 | 423.3667 | 26724
17278 | 414.8292 | 26724
17279 | 417.0221 | 26724
17280 | 402.3182 | 26724
17281 | 432.3146 | 26724
17282 | 413.4749 | 26724
17283 | 420.8372 | 26724
17284 | 421.5904 | 26724
17285 | 426.8357 | 26724
17286 | 413.7016 | 26724
17287 | 414.4892 | 26724
17288 | 414.4689 | 26724
17289 | 407.7079 | 26724
17290 | 413.4599 | 26724
17291 | 414.5466 | 26724
17292 | 423.5138 | 26724
17293 | 424.5621 | 26724
17294 | 426.382 | 26724
17295 | 415.1844 | 26724
17296 | 417.6745 | 26724
17297 | 430.7765 | 26724
17298 | 409.9852 | 26724
17299 | 415.0415 | 26724
17300 | 429.1067 | 26724
17301 | 415.977 | 26724
17302 | 419.9928 | 26724
17303 | 424.9195 | 26724
17304 | 429.514 | 26724
17305 | 399.3294 | 26724
17306 | 414.1462 | 26724
17307 | 402.7801 | 26724
17308 | 419.0168 | 26724
17309 | 423.186 | 26724
17310 | 405.7151 | 26724
17311 | 407.0457 | 26724
17312 | 416.768 | 26724
17313 | 420.2912 | 26724
17314 | 420.6072 | 26724
17315 | 407.7137 | 26724
17316 | 429.2135 | 26724
17317 | 422.7656 | 26724
17318 | 405.9823 | 26724
17319 | 401.9072 | 26724
17320 | 420.8613 | 26724
17321 | 420.1247 | 26724
17322 | 406.9704 | 26724
17323 | 428.904 | 26724
17324 | 419.9845 | 26724
17325 | 418.6762 | 26724
17326 | 421.8505 | 26724
17327 | 432.0091 | 26724
17328 | 425.3 | 26724
17329 | 426.5093 | 26724
17330 | 427.1311 | 26724
17331 | 401.6976 | 26724
17332 | 408.1106 | 26724
17333 | 406.6173 | 26724
17334 | 408.1184 | 26724
17335 | 411.4452 | 26724
17336 | 420.8226 | 26724
17337 | 420.0469 | 26724
17338 | 416.7292 | 26724
17339 | 415.6621 | 26724
17340 | 420.1958 | 26724
17341 | 412.1913 | 26724
17342 | 411.9013 | 26724
17343 | 430.6036 | 26724
17344 | 406.5029 | 26724
17345 | 417.1387 | 26724
17346 | 414.6895 | 26724
17347 | 425.4353 | 26724
17348 | 410.6524 | 26724
17349 | 417.5477 | 26724
17350 | 420.5908 | 26724
17351 | 424.1977 | 26724
17352 | 412.8324 | 26724
17353 | 413.4153 | 26724
17354 | 413.156 | 26724
17355 | 421.2973 | 26724
17356 | 415.3267 | 26724
17357 | 407.4496 | 26724
17358 | 405.5757 | 26724
17359 | 402.2428 | 26724
17360 | 424.4804 | 26724
17361 | 419.8968 | 26724
17362 | 414.1518 | 26724
17363 | 414.1103 | 26724
17364 | 425.1948 | 26724
17365 | 408.2261 | 26724
17366 | 422.175 | 26724
17367 | 413.8964 | 26724
17368 | 411.1478 | 26724
17369 | 437.7652 | 26724
17370 | 413.4591 | 26724
17371 | 408.8401 | 26724
17372 | 409.754 | 26724
17373 | 416.1413 | 26724
17374 | 413.7188 | 26724
17375 | 426.3007 | 26724
17376 | 416.4585 | 26724
17377 | 432.2205 | 26724
17378 | 419.9592 | 26724
17379 | 438.3628 | 26724
17380 | 425.0532 | 26724
17381 | 414.0351 | 26724
17382 | 409.158 | 26724
17383 | 411.2782 | 26724
17384 | 418.4202 | 26724
17385 | 400.1513 | 26724
17386 | 415.9377 | 26724
17387 | 418.2433 | 26724
17388 | 421.0843 | 26724
17389 | 414.1041 | 26724
17390 | 430.6625 | 26724
17391 | 420.3827 | 26724
17392 | 414.5832 | 26724
17393 | 411.0537 | 26724
17394 | 417.8308 | 26724
17395 | 423.1364 | 26724
17396 | 402.7324 | 26724
17397 | 412.6745 | 26724
17398 | 415.1819 | 26724
17399 | 410.1835 | 26724
17400 | 400.9632 | 26724
17401 | 412.0786 | 26724
17402 | 414.2076 | 26724
17403 | 428.4461 | 26724
17404 | 404.0564 | 26724
17405 | 418.6223 | 26724
17406 | 406.41 | 26724
17407 | 416.9494 | 26724
17408 | 415.5959 | 26724
17409 | 410.3417 | 26724
17410 | 411.8038 | 26724
17411 | 416.6049 | 26724
17412 | 412.177 | 26724
17413 | 415.0132 | 26724
17414 | 416.8503 | 26724
17415 | 407.4307 | 26724
17416 | 411.0198 | 26724
17417 | 404.6176 | 26724
17418 | 413.4468 | 26724
17419 | 411.4028 | 26724
17420 | 408.5435 | 26724
17421 | 408.6068 | 26724
17422 | 424.3422 | 26724
17423 | 414.2187 | 26724
17424 | 414.5995 | 26724
17425 | 408.6429 | 26724
17426 | 418.8232 | 26724
17427 | 417.6591 | 26724
17428 | 425.5848 | 26724
17429 | 406.9652 | 26724
17430 | 414.0254 | 26724
17431 | 421.1796 | 26724
17432 | 411.9811 | 26724
17433 | 411.0484 | 26724
17434 | 415.1288 | 26724
17435 | 413.6375 | 26724
17436 | 416.3038 | 26724
17437 | 417.2514 | 26724
17438 | 403.3668 | 26724
17439 | 418.0023 | 26724
17440 | 413.773 | 26724
17441 | 396.432 | 26724
17442 | 411.5332 | 26724
17443 | 422.4698 | 26724
17444 | 413.1407 | 26724
17445 | 420.0124 | 26724
17446 | 411.6514 | 26724
17447 | 419.2876 | 26724
17448 | 408.9865 | 26724
17449 | 414.1801 | 26724
17450 | 422.8338 | 26724
17451 | 412.5914 | 26724
17452 | 420.3175 | 26724
17453 | 413.9374 | 26724
17454 | 415.2243 | 26724
17455 | 431.7704 | 26724
17456 | 406.4361 | 26724
17457 | 414.7453 | 26724
17458 | 415.4986 | 26724
17459 | 420.3036 | 26724
17460 | 407.7133 | 26724
17461 | 413.592 | 26724
17462 | 412.5137 | 26724
17463 | 408.8018 | 26724
17464 | 415.4723 | 26724
17465 | 399.9673 | 26724
17466 | 416.9882 | 26724
17467 | 412.8129 | 26724
17468 | 416.9138 | 26724
17469 | 418.3828 | 26724
17470 | 428.543 | 26724
17471 | 420.3644 | 26724
17472 | 428.6667 | 26724
17473 | 423.1542 | 26724
17474 | 409.9089 | 26724
17475 | 412.2323 | 26724
17476 | 418.3287 | 26724
17477 | 418.6275 | 26724
17478 | 410.6528 | 26724
17479 | 410.4396 | 26724
17480 | 423.7516 | 26724
17481 | 405.6457 | 26724
17482 | 417.0382 | 26724
17483 | 407.4938 | 26724
17484 | 426.6057 | 26724
17485 | 421.4375 | 26724
17486 | 409.6388 | 26724
17487 | 425.5471 | 26724
17488 | 416.1757 | 26724
17489 | 406.4014 | 26724
17490 | 418.2296 | 26724
17491 | 415.4756 | 26724
17492 | 413.7786 | 26724
17493 | 430.7881 | 26724
17494 | 413.5115 | 26724
17495 | 410.0094 | 26724
17496 | 409.7047 | 26724
17497 | 409.6549 | 26724
17498 | 406.5537 | 26724
17499 | 410.2616 | 26724
17500 | 415.5971 | 26724
17501 | 432.0359 | 26724
17502 | 405.719 | 26724
17503 | 413.5725 | 26724
17504 | 409.6089 | 26724
17505 | 419.4257 | 26724
17506 | 426.376 | 26724
17507 | 413.0495 | 26724
17508 | 420.4049 | 26724
17509 | 409.0892 | 26724
17510 | 413.4776 | 26724
17511 | 408.4775 | 26724
17512 | 408.2123 | 26724
17513 | 416.3907 | 26724
17514 | 412.3667 | 26724
17515 | 405.5168 | 26724
17516 | 410.3648 | 26724
17517 | 417.5911 | 26724
17518 | 432.7423 | 26724
17519 | 428.0513 | 26724
17520 | 409.9754 | 26724
17521 | 415.5291 | 26724
17522 | 407.8773 | 26724
17523 | 410.7979 | 26724
17524 | 420.6582 | 26724
17525 | 414.6396 | 26724
17526 | 404.4468 | 26724
17527 | 433.0179 | 26724
17528 | 413.3085 | 26724
17529 | 419.552 | 26724
17530 | 409.5003 | 26724
17531 | 411.9994 | 26724
17532 | 411.8067 | 26724
17533 | 416.262 | 26724
17534 | 415.2312 | 26724
17535 | 421.3601 | 26724
17536 | 409.7768 | 26724
17537 | 423.1039 | 26724
17538 | 415.4827 | 26724
17539 | 428.5302 | 26724
17540 | 416.0971 | 26724
17541 | 410.601 | 26724
17542 | 406.8145 | 26724
17543 | 410.5851 | 26724
17544 | 418.9976 | 26724
17545 | 416.1935 | 26724
17546 | 409.0211 | 26724
17547 | 417.1052 | 26724
17548 | 425.6504 | 26724
17549 | 421.5192 | 26724
17550 | 415.8328 | 26724
17551 | 410.373 | 26724
17552 | 416.088 | 26724
17553 | 419.5026 | 26724
17554 | 426.0918 | 26724
17555 | 396.9801 | 26724
17556 | 410.9436 | 26724
17557 | 422.5418 | 26724
17558 | 416.7928 | 26724
17559 | 424.1577 | 26724
17560 | 423.095 | 26724
17561 | 417.9651 | 26724
17562 | 396.1441 | 26724
17563 | 420.6112 | 26724
17564 | 425.8766 | 26724
17565 | 415.3879 | 26724
17566 | 421.2701 | 26724
17567 | 411.5625 | 26724
17568 | 407.5271 | 26724
17569 | 422.318 | 26724
17570 | 417.0638 | 26724
17571 | 404.086 | 26724
17572 | 423.3744 | 26724
17573 | 419.7909 | 26724
17574 | 418.4892 | 26724
17575 | 423.9654 | 26724
17576 | 421.7983 | 26724
17577 | 417.0866 | 26724
17578 | 420.2145 | 26724
17579 | 433.3521 | 26724
17580 | 424.098 | 26724
17581 | 426.2802 | 26724
17582 | 414.3581 | 26724
17583 | 411.9435 | 26724
17584 | 403.672 | 26724
17585 | 421.9902 | 26724
17586 | 407.3394 | 26724
17587 | 417.9948 | 26724
17588 | 417.6764 | 26724
17589 | 417.0109 | 26724
17590 | 415.8305 | 26724
17591 | 419.6217 | 26724
17592 | 420.1792 | 26724
17593 | 407.2188 | 26724
17594 | 417.514 | 26724
17595 | 411.3099 | 26724
17596 | 418.8284 | 26724
17597 | 426.2062 | 26724
17598 | 421.8139 | 26724
17599 | 418.1162 | 26724
17600 | 405.1311 | 26724
17601 | 432.158 | 26724
17602 | 420.7073 | 26724
17603 | 397.2779 | 26724
17604 | 423.7095 | 26724
17605 | 421.6258 | 26724
17606 | 426.9987 | 26724
17607 | 416.3572 | 26724
17608 | 407.8702 | 26724
17609 | 419.6174 | 26724
17610 | 413.6755 | 26724
17611 | 410.6804 | 26724
17612 | 419.2979 | 26724
17613 | 416.0651 | 26724
17614 | 411.2959 | 26724
17615 | 420.4345 | 26724
17616 | 412.6361 | 26724
17617 | 404.8977 | 26724
17618 | 417.7362 | 26724
17619 | 422.5773 | 26724
17620 | 405.9671 | 26724
17621 | 414.5367 | 26724
17622 | 432.5493 | 26724
17623 | 409.0084 | 26724
17624 | 403.4167 | 26724
17625 | 426.1476 | 26724
17626 | 419.9943 | 26724
17627 | 420.193 | 26724
17628 | 423.6275 | 26724
17629 | 426.3428 | 26724
17630 | 416.3989 | 26724
17631 | 419.9058 | 26724
17632 | 423.8527 | 26724
17633 | 436.015 | 26724
17634 | 414.3039 | 26724
17635 | 411.9888 | 26724
17636 | 418.9062 | 26724
17637 | 422.165 | 26724
17638 | 421.3197 | 26724
17639 | 409.1539 | 26724
17640 | 408.0921 | 26724
17641 | 415.1224 | 26724
17642 | 413.2892 | 26724
17643 | 427.3629 | 26724
17644 | 428.7768 | 26724
17645 | 410.2855 | 26724
17646 | 417.8863 | 26724
17647 | 434.2838 | 26724
17648 | 412.6702 | 26724
17649 | 416.159 | 26724
17650 | 401.4177 | 26724
17651 | 416.0932 | 26724
17652 | 429.4097 | 26724
17653 | 412.7493 | 26724
17654 | 415.611 | 26724
17655 | 409.1942 | 26724
17656 | 418.4968 | 26724
17657 | 406.6957 | 26724
17658 | 410.404 | 26724
17659 | 431.6441 | 26724
17660 | 414.1913 | 26724
17661 | 415.1804 | 26724
17662 | 409.2427 | 26724
17663 | 418.1654 | 26724
17664 | 401.2555 | 26724
17665 | 422.5869 | 26724
17666 | 416.8552 | 26724
17667 | 412.2498 | 26724
17668 | 427.866 | 26724
17669 | 406.3332 | 26724
17670 | 414.4655 | 26724
17671 | 418.8246 | 26724
17672 | 430.4198 | 26724
17673 | 426.7946 | 26724
17674 | 421.5661 | 26724
17675 | 410.9936 | 26724
17676 | 415.4084 | 26724
17677 | 420.3177 | 26724
17678 | 413.1708 | 26724
17679 | 401.4629 | 26724
17680 | 416.811 | 26724
17681 | 412.2842 | 26724
17682 | 415.3623 | 26724
17683 | 393.5684 | 26724
17684 | 416.6276 | 26724
17685 | 415.3381 | 26724
17686 | 412.2213 | 26724
17687 | 412.9289 | 26724
17688 | 423.9066 | 26724
17689 | 428.4353 | 26724
17690 | 412.2187 | 26724
17691 | 413.8048 | 26724
17692 | 415.9095 | 26724
17693 | 410.2178 | 26724
17694 | 412.1649 | 26724
17695 | 409.9519 | 26724
17696 | 416.5481 | 26724
17697 | 425.1698 | 26724
17698 | 420.8105 | 26724
17699 | 439.0059 | 26724
17700 | 419.9669 | 26724
17701 | 407.053 | 26724
17702 | 413.6573 | 26724
17703 | 402.3446 | 26724
17704 | 411.7005 | 26724
17705 | 417.4632 | 26724
17706 | 419.9309 | 26724
17707 | 419.7613 | 26724
17708 | 415.271 | 26724
17709 | 421.6037 | 26724
17710 | 411.747 | 26724
17711 | 420.5503 | 26724
17712 | 431.6865 | 26724
17713 | 422.0104 | 26724
17714 | 415.8715 | 26724
17715 | 429.561 | 26724
17716 | 401.3245 | 26724
17717 | 402.3022 | 26724
17718 | 403.378 | 26724
17719 | 418.992 | 26724
17720 | 408.8836 | 26724
17721 | 418.1877 | 26724
17722 | 423.2731 | 26724
17723 | 424.7514 | 26724
17724 | 421.7413 | 26724
17725 | 406.6264 | 26724
17726 | 422.1428 | 26724
17727 | 404.0165 | 26724
17728 | 412.2962 | 26724
17729 | 418.9458 | 26724
17730 | 423.0202 | 26724
17731 | 413.2245 | 26724
17732 | 428.5194 | 26724
17733 | 420.2935 | 26724
17734 | 403.0548 | 26724
17735 | 426.0965 | 26724
17736 | 429.9104 | 26724
17737 | 430.253 | 26724
17738 | 418.2896 | 26724
17739 | 406.0977 | 26724
17740 | 419.4909 | 26724
17741 | 402.2207 | 26724
17742 | 416.8917 | 26724
17743 | 419.1994 | 26724
17744 | 419.6885 | 26724
17745 | 429.0345 | 26724
17746 | 409.2209 | 26724
17747 | 417.8617 | 26724
17748 | 422.8293 | 26724
17749 | 418.5847 | 26724
17750 | 417.7381 | 26724
17751 | 424.8754 | 26724
17752 | 407.9967 | 26724
17753 | 413.9654 | 26724
17754 | 411.6774 | 26724
17755 | 418.3655 | 26724
17756 | 412.7722 | 26724
17757 | 416.7511 | 26724
17758 | 423.0142 | 26724
17759 | 422.4533 | 26724
17760 | 421.4404 | 26724
17761 | 422.6475 | 26724
17762 | 411.781 | 26724
17763 | 419.2903 | 26724
17764 | 411.793 | 26724
17765 | 413.4206 | 26724
17766 | 410.1256 | 26724
17767 | 417.5924 | 26724
17768 | 424.4895 | 26724
17769 | 424.4718 | 26724
17770 | 407.798 | 26724
17771 | 422.8723 | 26724
17772 | 423.6329 | 26724
17773 | 413.5125 | 26724
17774 | 411.099 | 26724
17775 | 418.148 | 26724
17776 | 421.3572 | 26724
17777 | 422.5398 | 26724
17778 | 427.9608 | 26724
17779 | 430.3005 | 26724
17780 | 410.9881 | 26724
17781 | 405.0557 | 26724
17782 | 399.3895 | 26724
17783 | 418.9216 | 26724
17784 | 405.3767 | 26724
17785 | 423.6698 | 26724
17786 | 425.0201 | 26724
17787 | 423.6655 | 26724
17788 | 420.1893 | 26724
17789 | 419.7097 | 26724
17790 | 418.2085 | 26724
17791 | 418.9707 | 26724
17792 | 409.5625 | 26724
17793 | 409.1499 | 26724
17794 | 406.619 | 26724
17795 | 427.524 | 26724
17796 | 407.0833 | 26724
17797 | 411.9157 | 26724
17798 | 428.0771 | 26724
17799 | 433.6091 | 26724
17800 | 404.8691 | 26724
17801 | 402.7874 | 26724
17802 | 412.2481 | 26724
17803 | 418.6757 | 26724
17804 | 423.8448 | 26724
17805 | 422.5775 | 26724
17806 | 422.8931 | 26724
17807 | 414.7695 | 26724
17808 | 412.2381 | 26724
17809 | 427.7571 | 26724
17810 | 432.1854 | 26724
17811 | 407.168 | 26724
17812 | 424.1709 | 26724
17813 | 431.1911 | 26724
17814 | 425.4261 | 26724
17815 | 410.906 | 26724
17816 | 428.7582 | 26724
17817 | 407.8144 | 26724
17818 | 419.3398 | 26724
17819 | 411.147 | 26724
17820 | 411.7428 | 26724
17821 | 403.8994 | 26724
17822 | 415.5136 | 26724
17823 | 407.1671 | 26724
17824 | 417.7324 | 26724
17825 | 414.2304 | 26724
17826 | 418.8406 | 26724
17827 | 407.3221 | 26724
17828 | 414.9817 | 26724
17829 | 405.5934 | 26724
17830 | 408.4472 | 26724
17831 | 410.1347 | 26724
17832 | 409.4704 | 26724
17833 | 418.3739 | 26724
17834 | 414.7428 | 26724
17835 | 421.8007 | 26724
17836 | 409.491 | 26724
17837 | 419.397 | 26724
17838 | 423.6693 | 26724
17839 | 413.3302 | 26724
17840 | 415.7047 | 26724
17841 | 406.325 | 26724
17842 | 402.2122 | 26724
17843 | 402.6392 | 26724
17844 | 408.7369 | 26724
17845 | 414.9914 | 26724
17846 | 417.665 | 26724
17847 | 422.8532 | 26724
17848 | 410.5634 | 26724
17849 | 419.8671 | 26724
17850 | 408.5967 | 26724
17851 | 399.526 | 26724
17852 | 410.6454 | 26724
17853 | 425.7408 | 26724
17854 | 412.9042 | 26724
17855 | 413.7793 | 26724
17856 | 410.495 | 26724
17857 | 429.8984 | 26724
17858 | 410.2366 | 26724
17859 | 430.1054 | 26724
17860 | 420.1245 | 26724
17861 | 420.793 | 26724
17862 | 416.958 | 26724
17863 | 422.7731 | 26724
17864 | 433.5823 | 26724
17865 | 411.5772 | 26724
17866 | 418.974 | 26724
17867 | 419.8909 | 26724
17868 | 409.3728 | 26724
17869 | 435.15 | 26724
17870 | 417.377 | 26724
17871 | 439.9101 | 26724
17872 | 416.3334 | 26724
17873 | 422.7848 | 26724
17874 | 418.2624 | 26724
17875 | 409.2065 | 26724
17876 | 409.7589 | 26724
17877 | 420.8747 | 26724
17878 | 426.3317 | 26724
17879 | 410.7277 | 26724
17880 | 417.4044 | 26724
17881 | 409.3696 | 26724
17882 | 425.706 | 26724
17883 | 420.9527 | 26724
17884 | 409.8628 | 26724
17885 | 423.0116 | 26724
17886 | 420.1521 | 26724
17887 | 429.947 | 26724
17888 | 423.8186 | 26724
17889 | 415.8287 | 26724
17890 | 413.4927 | 26724
17891 | 419.7797 | 26724
17892 | 419.98 | 26724
17893 | 427.2225 | 26724
17894 | 413.8338 | 26724
17895 | 419.3819 | 26724
17896 | 416.3329 | 26724
17897 | 430.0841 | 26724
17898 | 415.7333 | 26724
17899 | 410.4035 | 26724
17900 | 410.3647 | 26724
17901 | 436.6878 | 26724
17902 | 415.0138 | 26724
17903 | 416.4247 | 26724
17904 | 420.1627 | 26724
17905 | 418.2429 | 26724
17906 | 416.8395 | 26724
17907 | 427.2238 | 26724
17908 | 429.0327 | 26724
17909 | 398.3292 | 26724
17910 | 430.3231 | 26724
17911 | 421.3292 | 26724
17912 | 414.4901 | 26724
17913 | 411.4903 | 26724
17914 | 411.6924 | 26724
17915 | 425.1194 | 26724
17916 | 421.1362 | 26724
17917 | 417.0937 | 26724
17918 | 413.898 | 26724
17919 | 415.1043 | 26724
17920 | 424.8005 | 26724
17921 | 423.0818 | 26724
17922 | 409.2364 | 26724
17923 | 410.078 | 26724
17924 | 427.1821 | 26724
17925 | 424.2646 | 26724
17926 | 425.2219 | 26724
17927 | 415.5741 | 26724
17928 | 419.3862 | 26724
17929 | 417.5852 | 26724
17930 | 423.4015 | 26724
17931 | 422.632 | 26724
17932 | 424.589 | 26724
17933 | 424.1554 | 26724
17934 | 418.4723 | 26724
17935 | 403.9141 | 26724
17936 | 413.7043 | 26724
17937 | 428.7744 | 26724
17938 | 417.9816 | 26724
17939 | 427.9285 | 26724
17940 | 424.2821 | 26724
17941 | 419.2651 | 26724
17942 | 414.5187 | 26724
17943 | 415.9714 | 26724
17944 | 425.4059 | 26724
17945 | 405.97 | 26724
17946 | 423.5389 | 26724
17947 | 412.0985 | 26724
17948 | 404.547 | 26724
17949 | 403.0557 | 26724
17950 | 414.4934 | 26724
17951 | 423.4657 | 26724
17952 | 418.2519 | 26724
17953 | 418.0579 | 26724
17954 | 407.9913 | 26724
17955 | 403.0376 | 26724
17956 | 417.7445 | 26724
17957 | 414.1876 | 26724
17958 | 421.9671 | 26724
17959 | 409.7091 | 26724
17960 | 420.547 | 26724
17961 | 414.216 | 26724
17962 | 425.2674 | 26724
17963 | 412.102 | 26724
17964 | 419.2813 | 26724
17965 | 409.032 | 26724
17966 | 417.4204 | 26724
17967 | 415.6181 | 26724
17968 | 411.5649 | 26724
17969 | 405.9959 | 26724
17970 | 415.676 | 26724
17971 | 426.3455 | 26724
17972 | 413.1598 | 26724
17973 | 423.4997 | 26724
17974 | 404.6542 | 26724
17975 | 423.0485 | 26724
17976 | 416.9402 | 26724
17977 | 411.9777 | 26724
17978 | 420.5908 | 26724
17979 | 414.989 | 26724
17980 | 408.2003 | 26724
17981 | 405.8238 | 26724
17982 | 425.0535 | 26724
17983 | 412.6232 | 26724
17984 | 409.0124 | 26724
17985 | 413.7307 | 26724
17986 | 413.1424 | 26724
17987 | 416.5936 | 26724
17988 | 398.1053 | 26724
17989 | 426.9968 | 26724
17990 | 430.0368 | 26724
17991 | 419.7304 | 26724
17992 | 406.7282 | 26724
17993 | 405.5213 | 26724
17994 | 419.336 | 26724
17995 | 417.4489 | 26724
17996 | 422.1746 | 26724
17997 | 417.668 | 26724
17998 | 410.0166 | 26724
17999 | 428.8205 | 26724
18000 | 413.8093 | 26724
18001 | 422.7686 | 26724
18002 | 412.9226 | 26724
18003 | 407.3323 | 26724
18004 | 423.0009 | 26724
18005 | 413.2272 | 26724
18006 | 412.0998 | 26724
18007 | 415.7085 | 26724
18008 | 418.7578 | 26724
18009 | 412.0406 | 26724
18010 | 408.1845 | 26724
18011 | 412.7865 | 26724
18012 | 410.7578 | 26724
18013 | 402.0673 | 26724
18014 | 425.421 | 26724
18015 | 422.9706 | 26724
18016 | 403.5747 | 26724
18017 | 425.4549 | 26724
18018 | 424.6584 | 26724
18019 | 413.422 | 26724
18020 | 414.0697 | 26724
18021 | 421.5477 | 26724
18022 | 420.1498 | 26724
18023 | 419.2192 | 26724
18024 | 424.9041 | 26724
18025 | 421.7677 | 26724
18026 | 408.2678 | 26724
18027 | 425.7412 | 26724
18028 | 401.9452 | 26724
18029 | 412.8189 | 26724
18030 | 408.8949 | 26724
18031 | 424.0591 | 26724
18032 | 414.1968 | 26724
18033 | 418.6912 | 26724
18034 | 411.4278 | 26724
18035 | 407.9702 | 26724
18036 | 417.4106 | 26724
18037 | 413.9778 | 26724
18038 | 427.6876 | 26724
18039 | 408.2608 | 26724
18040 | 412.1573 | 26724
18041 | 415.283 | 26724
18042 | 403.5894 | 26724
18043 | 413.3851 | 26724
18044 | 420.9512 | 26724
18045 | 400.5996 | 26724
18046 | 411.6409 | 26724
18047 | 416.12 | 26724
18048 | 396.4801 | 26724
18049 | 413.8945 | 26724
18050 | 401.4825 | 26724
18051 | 409.2422 | 26724
18052 | 402.8838 | 26724
18053 | 411.0814 | 26724
18054 | 419.5388 | 26724
18055 | 409.9174 | 26724
18056 | 432.7895 | 26724
18057 | 425.854 | 26724
18058 | 427.886 | 26724
18059 | 413.1283 | 26724
18060 | 404.5546 | 26724
18061 | 408.6622 | 26724
18062 | 410.7505 | 26724
18063 | 409.2132 | 26724
18064 | 431.9458 | 26724
18065 | 425.7045 | 26724
18066 | 414.1536 | 26724
18067 | 412.3139 | 26724
18068 | 416.2197 | 26724
18069 | 415.3562 | 26724
18070 | 410.0425 | 26724
18071 | 419.123 | 26724
18072 | 419.2472 | 26724
18073 | 418.7666 | 26724
18074 | 423.4396 | 26724
18075 | 407.0739 | 26724
18076 | 420.654 | 26724
18077 | 410.2798 | 26724
18078 | 427.8085 | 26724
18079 | 400.1684 | 26724
18080 | 414.4657 | 26724
18081 | 417.8401 | 26724
18082 | 410.9905 | 26724
18083 | 411.5342 | 26724
18084 | 415.3046 | 26724
18085 | 428.9718 | 26724
18086 | 410.4507 | 26724
18087 | 423.1289 | 26724
18088 | 423.9619 | 26724
18089 | 407.3358 | 26724
18090 | 418.9476 | 26724
18091 | 405.2015 | 26724
18092 | 415.9925 | 26724
18093 | 431.7175 | 26724
18094 | 419.143 | 26724
18095 | 404.0407 | 26724
18096 | 419.6295 | 26724
18097 | 409.7872 | 26724
18098 | 418.7002 | 26724
18099 | 411.7763 | 26724
18100 | 402.6532 | 26724
18101 | 409.8878 | 26724
18102 | 410.2158 | 26724
18103 | 420.4915 | 26724
18104 | 403.7206 | 26724
18105 | 404.7065 | 26724
18106 | 413.1871 | 26724
18107 | 416.1727 | 26724
18108 | 417.655 | 26724
18109 | 427.0721 | 26724
18110 | 409.9409 | 26724
18111 | 407.8104 | 26724
18112 | 405.7432 | 26724
18113 | 423.7662 | 26724
18114 | 431.8387 | 26724
18115 | 404.2188 | 26724
18116 | 409.2997 | 26724
18117 | 431.5271 | 26724
18118 | 423.8075 | 26724
18119 | 413.16 | 26724
18120 | 406.5816 | 26724
18121 | 425.6378 | 26724
18122 | 425.4972 | 26724
18123 | 412.6952 | 26724
18124 | 411.4529 | 26724
18125 | 416.1035 | 26724
18126 | 429.2503 | 26724
18127 | 415.1315 | 26724
18128 | 405.7788 | 26724
18129 | 430.3273 | 26724
18130 | 427.7764 | 26724
18131 | 411.7859 | 26724
18132 | 419.1521 | 26724
18133 | 406.3052 | 26724
18134 | 432.494 | 26724
18135 | 423.0395 | 26724
18136 | 426.2552 | 26724
18137 | 414.4376 | 26724
18138 | 432.5486 | 26724
18139 | 403.3984 | 26724
18140 | 411.7416 | 26724
18141 | 406.7871 | 26724
18142 | 427.2826 | 26724
18143 | 404.8468 | 26724
18144 | 416.7552 | 26724
18145 | 421.1532 | 26724
18146 | 424.1292 | 26724
18147 | 412.7204 | 26724
18148 | 402.6565 | 26724
18149 | 424.7836 | 26724
18150 | 427.8316 | 26724
18151 | 428.1778 | 26724
18152 | 425.2685 | 26724
18153 | 421.6977 | 26724
18154 | 416.7269 | 26724
18155 | 429.0217 | 26724
18156 | 427.9551 | 26724
18157 | 425.8796 | 26724
18158 | 413.7226 | 26724
18159 | 420.2716 | 26724
18160 | 413.6752 | 26724
18161 | 407.0235 | 26724
18162 | 418.2416 | 26724
18163 | 415.9603 | 26724
18164 | 408.2657 | 26724
18165 | 426.12 | 26724
18166 | 425.3106 | 26724
18167 | 412.5039 | 26724
18168 | 423.147 | 26724
18169 | 427.0771 | 26724
18170 | 418.7772 | 26724
18171 | 425.1113 | 26724
18172 | 433.3758 | 26724
18173 | 414.1823 | 26724
18174 | 405.0064 | 26724
18175 | 411.0223 | 26724
18176 | 412.5842 | 26724
18177 | 411.4359 | 26724
18178 | 411.0641 | 26724
18179 | 417.5146 | 26724
18180 | 409.1853 | 26724
18181 | 415.7427 | 26724
18182 | 408.8952 | 26724
18183 | 408.5255 | 26724
18184 | 416.8097 | 26724
18185 | 410.6743 | 26724
18186 | 410.1257 | 26724
18187 | 399.0527 | 26724
18188 | 424.2729 | 26724
18189 | 403.074 | 26724
18190 | 407.236 | 26724
18191 | 421.2986 | 26724
18192 | 413.8808 | 26724
18193 | 408.7241 | 26724
18194 | 418.7958 | 26724
18195 | 422.2504 | 26724
18196 | 401.4547 | 26724
18197 | 416.048 | 26724
18198 | 416.3375 | 26724
18199 | 409.1994 | 26724
18200 | 438.9014 | 26724
18201 | 412.2686 | 26724
18202 | 414.8687 | 26724
18203 | 419.1007 | 26724
18204 | 411.9901 | 26724
18205 | 415.8897 | 26724
18206 | 419.5396 | 26724
18207 | 426.9133 | 26724
18208 | 434.1156 | 26724
18209 | 421.3978 | 26724
18210 | 414.9123 | 26724
18211 | 421.2223 | 26724
18212 | 406.1341 | 26724
18213 | 407.5387 | 26724
18214 | 407.9924 | 26724
18215 | 415.0283 | 26724
18216 | 428.3169 | 26724
18217 | 414.2534 | 26724
18218 | 424.2474 | 26724
18219 | 418.2652 | 26724
18220 | 404.6449 | 26724
18221 | 397.2084 | 26724
18222 | 409.8022 | 26724
18223 | 414.5528 | 26724
18224 | 426.8479 | 26724
18225 | 423.4929 | 26724
18226 | 434.502 | 26724
18227 | 420.7706 | 26724
18228 | 402.924 | 26724
18229 | 407.2504 | 26724
18230 | 437.0597 | 26724
18231 | 425.8133 | 26724
18232 | 436.0172 | 26724
18233 | 431.5769 | 26724
18234 | 417.1691 | 26724
18235 | 417.1302 | 26724
18236 | 414.0092 | 26724
18237 | 415.4479 | 26724
18238 | 425.2476 | 26724
18239 | 423.4789 | 26724
18240 | 414.9446 | 26724
18241 | 414.9019 | 26724
18242 | 433.1346 | 26724
18243 | 409.4398 | 26724
18244 | 423.1209 | 26724
18245 | 403.2741 | 26724
18246 | 419.9962 | 26724
18247 | 414.087 | 26724
18248 | 411.8039 | 26724
18249 | 398.7511 | 26724
18250 | 397.978 | 26724
18251 | 422.0797 | 26724
18252 | 419.5024 | 26724
18253 | 417.0073 | 26724
18254 | 410.5465 | 26724
18255 | 403.8544 | 26724
18256 | 421.6303 | 26724
18257 | 414.9904 | 26724
18258 | 409.1797 | 26724
18259 | 432.5526 | 26724
18260 | 418.5465 | 26724
18261 | 418.4342 | 26724
18262 | 421.869 | 26724
18263 | 419.3624 | 26724
18264 | 415.6549 | 26724
18265 | 422.9288 | 26724
18266 | 415.6987 | 26724
18267 | 415.4839 | 26724
18268 | 414.1044 | 26724
18269 | 428.4124 | 26724
18270 | 412.1168 | 26724
18271 | 416.4072 | 26724
18272 | 420.0422 | 26724
18273 | 425.3062 | 26724
18274 | 430.0664 | 26724
18275 | 408.3847 | 26724
18276 | 434.7891 | 26724
18277 | 417.2431 | 26724
18278 | 430.3031 | 26724
18279 | 417.1902 | 26724
18280 | 416.9236 | 26724
18281 | 422.7538 | 26724
18282 | 426.3913 | 26724
18283 | 417.8816 | 26724
18284 | 407.0357 | 26724
18285 | 416.7621 | 26724
18286 | 415.7635 | 26724
18287 | 419.1185 | 26724
18288 | 417.0603 | 26724
18289 | 421.045 | 26724
18290 | 412.1685 | 26724
18291 | 402.7585 | 26724
18292 | 419.6333 | 26724
18293 | 423.0727 | 26724
18294 | 416.173 | 26724
18295 | 402.264 | 26724
18296 | 431.2653 | 26724
18297 | 414.9623 | 26724
18298 | 426.5217 | 26724
18299 | 405.6155 | 26724
18300 | 400.9943 | 26724
18301 | 410.3488 | 26724
18302 | 412.2084 | 26724
18303 | 405.9352 | 26724
18304 | 419.8115 | 26724
18305 | 409.7043 | 26724
18306 | 421.266 | 26724
18307 | 419.5327 | 26724
18308 | 427.6907 | 26724
18309 | 420.7579 | 26724
18310 | 428.7477 | 26724
18311 | 419.5924 | 26724
18312 | 417.7193 | 26724
18313 | 427.3958 | 26724
18314 | 421.8662 | 26724
18315 | 431.7367 | 26724
18316 | 408.8864 | 26724
18317 | 425.4241 | 26724
18318 | 432.7873 | 26724
18319 | 420.4469 | 26724
18320 | 417.4552 | 26724
18321 | 417.8528 | 26724
18322 | 398.0781 | 26724
18323 | 423.5194 | 26724
18324 | 417.6831 | 26724
18325 | 404.8922 | 26724
18326 | 426.1744 | 26724
18327 | 421.4696 | 26724
18328 | 411.3947 | 26724
18329 | 423.2615 | 26724
18330 | 414.3283 | 26724
18331 | 416.6106 | 26724
18332 | 411.2064 | 26724
18333 | 419.6676 | 26724
18334 | 411.033 | 26724
18335 | 409.7458 | 26724
18336 | 412.4599 | 26724
18337 | 417.4755 | 26724
18338 | 414.9169 | 26724
18339 | 417.7625 | 26724
18340 | 432.1564 | 26724
18341 | 429.1665 | 26724
18342 | 418.5561 | 26724
18343 | 412.5807 | 26724
18344 | 418.8877 | 26724
18345 | 415.5655 | 26724
18346 | 409.9878 | 26724
18347 | 412.1852 | 26724
18348 | 400.7909 | 26724
18349 | 428.468 | 26724
18350 | 407.857 | 26724
18351 | 412.8654 | 26724
18352 | 417.0732 | 26724
18353 | 419.2565 | 26724
18354 | 409.567 | 26724
18355 | 417.4038 | 26724
18356 | 436.7157 | 26724
18357 | 410.6611 | 26724
18358 | 400.6221 | 26724
18359 | 421.0351 | 26724
18360 | 406.1491 | 26724
18361 | 418.8124 | 26724
18362 | 424.5493 | 26724
18363 | 421.1499 | 26724
18364 | 412.8766 | 26724
18365 | 413.6844 | 26724
18366 | 426.1734 | 26724
18367 | 427.2334 | 26724
18368 | 406.7562 | 26724
18369 | 416.6697 | 26724
18370 | 410.3702 | 26724
18371 | 425.7746 | 26724
18372 | 405.1856 | 26724
18373 | 402.1218 | 26724
18374 | 409.684 | 26724
18375 | 433.5815 | 26724
18376 | 424.7019 | 26724
18377 | 419.4233 | 26724
18378 | 425.7444 | 26724
18379 | 422.2546 | 26724
18380 | 399.7694 | 26724
18381 | 426.8819 | 26724
18382 | 417.5132 | 26724
18383 | 412.0053 | 26724
18384 | 429.3368 | 26724
18385 | 413.3798 | 26724
18386 | 426.6212 | 26724
18387 | 423.1831 | 26724
18388 | 427.6964 | 26724
18389 | 415.1193 | 26724
18390 | 414.6605 | 26724
18391 | 426.008 | 26724
18392 | 408.6599 | 26724
18393 | 401.9693 | 26724
18394 | 422.642 | 26724
18395 | 421.3961 | 26724
18396 | 432.8405 | 26724
18397 | 409.6099 | 26724
18398 | 424.3252 | 26724
18399 | 427.8993 | 26724
18400 | 421.7562 | 26724
18401 | 413.6365 | 26724
18402 | 417.236 | 26724
18403 | 433.1091 | 26724
18404 | 413.3366 | 26724
18405 | 420.2282 | 26724
18406 | 419.7571 | 26724
18407 | 420.7355 | 26724
18408 | 417.1192 | 26724
18409 | 418.6163 | 26724
18410 | 416.4387 | 26724
18411 | 417.6786 | 26724
18412 | 421.1016 | 26724
18413 | 425.8892 | 26724
18414 | 415.9598 | 26724
18415 | 407.84 | 26724
18416 | 430.5531 | 26724
18417 | 417.045 | 26724
18418 | 423.6167 | 26724
18419 | 414.7598 | 26724
18420 | 414.8612 | 26724
18421 | 408.3242 | 26724
18422 | 412.9974 | 26724
18423 | 427.2866 | 26724
18424 | 426.112 | 26724
18425 | 420.6436 | 26724
18426 | 419.0268 | 26724
18427 | 412.8279 | 26724
18428 | 413.7562 | 26724
18429 | 408.6769 | 26724
18430 | 412.4481 | 26724
18431 | 408.7195 | 26724
18432 | 417.4909 | 26724
18433 | 426.358 | 26724
18434 | 437.9004 | 26724
18435 | 426.6312 | 26724
18436 | 426.2629 | 26724
18437 | 419.7563 | 26724
18438 | 436.3656 | 26724
18439 | 416.872 | 26724
18440 | 413.7623 | 26724
18441 | 419.4541 | 26724
18442 | 409.2762 | 26724
18443 | 412.0774 | 26724
18444 | 425.4625 | 26724
18445 | 422.402 | 26724
18446 | 401.7999 | 26724
18447 | 412.5645 | 26724
18448 | 429.5992 | 26724
18449 | 425.5736 | 26724
18450 | 412.4357 | 26724
18451 | 419.3184 | 26724
18452 | 400.6329 | 26724
18453 | 414.8799 | 26724
18454 | 414.8944 | 26724
18455 | 409.2194 | 26724
18456 | 427.9523 | 26724
18457 | 415.0012 | 26724
18458 | 405.1551 | 26724
18459 | 404.7602 | 26724
18460 | 410.1886 | 26724
18461 | 421.8326 | 26724
18462 | 419.1262 | 26724
18463 | 422.615 | 26724
18464 | 416.1292 | 26724
18465 | 406.4242 | 26724
18466 | 413.5196 | 26724
18467 | 411.2175 | 26724
18468 | 425.948 | 26724
18469 | 414.3021 | 26724
18470 | 408.2792 | 26724
18471 | 410.7867 | 26724
18472 | 419.4125 | 26724
18473 | 423.8977 | 26724
18474 | 420.4434 | 26724
18475 | 423.8054 | 26724
18476 | 406.116 | 26724
18477 | 407.1491 | 26724
18478 | 418.7997 | 26724
18479 | 423.6097 | 26724
18480 | 410.7442 | 26724
18481 | 426.8465 | 26724
18482 | 416.6027 | 26724
18483 | 411.7881 | 26724
18484 | 412.515 | 26724
18485 | 423.8225 | 26724
18486 | 414.1785 | 26724
18487 | 417.2419 | 26724
18488 | 414.8531 | 26724
18489 | 409.3031 | 26724
18490 | 421.24 | 26724
18491 | 400.2537 | 26724
18492 | 420.5908 | 26724
18493 | 422.8772 | 26724
18494 | 415.3939 | 26724
18495 | 413.9691 | 26724
18496 | 415.586 | 26724
18497 | 426.0009 | 26724
18498 | 421.4433 | 26724
18499 | 426.2178 | 26724
18500 | 421.956 | 26724
18501 | 428.6262 | 26724
18502 | 409.2861 | 26724
18503 | 424.0879 | 26724
18504 | 402.6391 | 26724
18505 | 408.0626 | 26724
18506 | 415.8288 | 26724
18507 | 421.3349 | 26724
18508 | 410.6289 | 26724
18509 | 415.2524 | 26724
18510 | 413.2779 | 26724
18511 | 422.4984 | 26724
18512 | 419.348 | 26724
18513 | 419.2644 | 26724
18514 | 419.684 | 26724
18515 | 418.8546 | 26724
18516 | 408.3525 | 26724
18517 | 411.5344 | 26724
18518 | 424.7519 | 26724
18519 | 429.2272 | 26724
18520 | 425.5317 | 26724
18521 | 420.6983 | 26724
18522 | 405.6265 | 26724
18523 | 426.2199 | 26724
18524 | 421.5664 | 26724
18525 | 416.3877 | 26724
18526 | 398.4547 | 26724
18527 | 410.7032 | 26724
18528 | 420.4597 | 26724
18529 | 417.2613 | 26724
18530 | 413.3247 | 26724
18531 | 434.0575 | 26724
18532 | 425.658 | 26724
18533 | 421.6222 | 26724
18534 | 433.6612 | 26724
18535 | 413.7132 | 26724
18536 | 421.4253 | 26724
18537 | 429.0678 | 26724
18538 | 409.922 | 26724
18539 | 416.9602 | 26724
18540 | 405.7477 | 26724
18541 | 420.5986 | 26724
18542 | 401.1721 | 26724
18543 | 432.1183 | 26724
18544 | 415.0128 | 26724
18545 | 421.1556 | 26724
18546 | 420.5106 | 26724
18547 | 414.2438 | 26724
18548 | 412.6325 | 26724
18549 | 407.6726 | 26724
18550 | 433.222 | 26724
18551 | 408.6511 | 26724
18552 | 417.6898 | 26724
18553 | 418.8141 | 26724
18554 | 403.769 | 26724
18555 | 433.5463 | 26724
18556 | 417.5401 | 26724
18557 | 426.3614 | 26724
18558 | 405.2819 | 26724
18559 | 411.4579 | 26724
18560 | 420.6351 | 26724
18561 | 423.3525 | 26724
18562 | 419.0529 | 26724
18563 | 411.1733 | 26724
18564 | 424.4217 | 26724
18565 | 437.9365 | 26724
18566 | 399.4936 | 26724
18567 | 411.2019 | 26724
18568 | 421.4912 | 26724
18569 | 420.875 | 26724
18570 | 419.645 | 26724
18571 | 420.4276 | 26724
18572 | 425.6705 | 26724
18573 | 421.2905 | 26724
18574 | 414.5291 | 26724
18575 | 420.5718 | 26724
18576 | 423.9304 | 26724
18577 | 430.4195 | 26724
18578 | 432.9324 | 26724
18579 | 420.174 | 26724
18580 | 426.0812 | 26724
18581 | 407.5429 | 26724
18582 | 409.279 | 26724
18583 | 426.6726 | 26724
18584 | 410.9393 | 26724
18585 | 416.7999 | 26724
18586 | 405.7885 | 26724
18587 | 418.5356 | 26724
18588 | 411.6061 | 26724
18589 | 399.0111 | 26724
18590 | 409.333 | 26724
18591 | 416.5271 | 26724
18592 | 427.7989 | 26724
18593 | 416.0551 | 26724
18594 | 422.4495 | 26724
18595 | 426.5451 | 26724
18596 | 420.5175 | 26724
18597 | 408.2782 | 26724
18598 | 421.3143 | 26724
18599 | 424.6798 | 26724
18600 | 420.7376 | 26724
18601 | 425.3705 | 26724
18602 | 402.0632 | 26724
18603 | 419.3981 | 26724
18604 | 420.0103 | 26724
18605 | 400.5918 | 26724
18606 | 433.1564 | 26724
18607 | 403.0382 | 26724
18608 | 417.8582 | 26724
18609 | 411.2237 | 26724
18610 | 425.8221 | 26724
18611 | 409.3786 | 26724
18612 | 422.0828 | 26724
18613 | 431.8073 | 26724
18614 | 422.3354 | 26724
18615 | 409.1299 | 26724
18616 | 412.7308 | 26724
18617 | 408.4385 | 26724
18618 | 421.2928 | 26724
18619 | 413.4537 | 26724
18620 | 418.6207 | 26724
18621 | 409.1833 | 26724
18622 | 412.2931 | 26724
18623 | 411.6356 | 26724
18624 | 412.049 | 26724
18625 | 417.8726 | 26724
18626 | 404.5955 | 26724
18627 | 436.1643 | 26724
18628 | 420.3676 | 26724
18629 | 420.8501 | 26724
18630 | 406.2158 | 26724
18631 | 428.7357 | 26724
18632 | 421.1703 | 26724
18633 | 421.4021 | 26724
18634 | 416.765 | 26724
18635 | 414.5423 | 26724
18636 | 407.176 | 26724
18637 | 419.2498 | 26724
18638 | 418.6619 | 26724
18639 | 403.4338 | 26724
18640 | 429.5952 | 26724
18641 | 412.9732 | 26724
18642 | 407.7081 | 26724
18643 | 419.6 | 26724
18644 | 404.6934 | 26724
18645 | 411.2077 | 26724
18646 | 425.2834 | 26724
18647 | 414.6729 | 26724
18648 | 411.3088 | 26724
18649 | 402.8291 | 26724
18650 | 406.4569 | 26724
18651 | 407.3287 | 26724
18652 | 425.784 | 26724
18653 | 421.24 | 26724
18654 | 424.0386 | 26724
18655 | 419.7854 | 26724
18656 | 416.7542 | 26724
18657 | 418.3375 | 26724
18658 | 413.0357 | 26724
18659 | 417.9425 | 26724
18660 | 422.2412 | 26724
18661 | 405.8207 | 26724
18662 | 413.7912 | 26724
18663 | 403.0402 | 26724
18664 | 422.2735 | 26724
18665 | 421.0534 | 26724
18666 | 400.551 | 26724
18667 | 410.0241 | 26724
18668 | 411.1054 | 26724
18669 | 409.3855 | 26724
18670 | 410.7025 | 26724
18671 | 408.4415 | 26724
18672 | 405.4845 | 26724
18673 | 432.2173 | 26724
18674 | 423.6677 | 26724
18675 | 427.7743 | 26724
18676 | 415.1817 | 26724
18677 | 411.8939 | 26724
18678 | 420.4724 | 26724
18679 | 409.7813 | 26724
18680 | 404.7349 | 26724
18681 | 414.9104 | 26724
18682 | 423.8368 | 26724
18683 | 425.0805 | 26724
18684 | 419.0235 | 26724
18685 | 414.6568 | 26724
18686 | 422.5151 | 26724
18687 | 416.1713 | 26724
18688 | 414.3653 | 26724
18689 | 398.0202 | 26724
18690 | 406.0953 | 26724
18691 | 419.8698 | 26724
18692 | 402.5668 | 26724
18693 | 407.307 | 26724
18694 | 419.3675 | 26724
18695 | 424.7136 | 26724
18696 | 417.2014 | 26724
18697 | 413.3836 | 26724
18698 | 422.6442 | 26724
18699 | 421.3985 | 26724
18700 | 428.4734 | 26724
18701 | 420.8103 | 26724
18702 | 422.6912 | 26724
18703 | 429.7037 | 26724
18704 | 408.1547 | 26724
18705 | 402.6811 | 26724
18706 | 402.354 | 26724
18707 | 422.7222 | 26724
18708 | 407.0227 | 26724
18709 | 417.1871 | 26724
18710 | 412.3941 | 26724
18711 | 426.7998 | 26724
18712 | 406.6784 | 26724
18713 | 420.4391 | 26724
18714 | 424.7934 | 26724
18715 | 407.6043 | 26724
18716 | 426.8159 | 26724
18717 | 428.732 | 26724
18718 | 422.7271 | 26724
18719 | 411.3684 | 26724
18720 | 401.5402 | 26724
18721 | 423.6059 | 26724
18722 | 415.8395 | 26724
18723 | 422.619 | 26724
18724 | 428.5827 | 26724
18725 | 409.9962 | 26724
18726 | 415.0395 | 26724
18727 | 412.6503 | 26724
18728 | 422.2286 | 26724
18729 | 431.8411 | 26724
18730 | 420.9523 | 26724
18731 | 425.5104 | 26724
18732 | 426.2287 | 26724
18733 | 406.9017 | 26724
18734 | 425.2071 | 26724
18735 | 430.493 | 26724
18736 | 418.9721 | 26724
18737 | 412.7992 | 26724
18738 | 419.2079 | 26724
18739 | 424.8769 | 26724
18740 | 418.9013 | 26724
18741 | 420.1034 | 26724
18742 | 421.8263 | 26724
18743 | 424.1731 | 26724
18744 | 419.7144 | 26724
18745 | 429.1949 | 26724
18746 | 407.4526 | 26724
18747 | 417.2479 | 26724
18748 | 410.7075 | 26724
18749 | 417.215 | 26724
18750 | 419.4258 | 26724
18751 | 402.5902 | 26724
18752 | 405.1801 | 26724
18753 | 418.1973 | 26724
18754 | 400.3857 | 26724
18755 | 429.0444 | 26724
18756 | 421.1187 | 26724
18757 | 435.0964 | 26724
18758 | 412.1207 | 26724
18759 | 407.7327 | 26724
18760 | 412.2646 | 26724
18761 | 418.979 | 26724
18762 | 420.0892 | 26724
18763 | 416.596 | 26724
18764 | 417.0206 | 26724
18765 | 415.8345 | 26724
18766 | 412.6808 | 26724
18767 | 426.9822 | 26724
18768 | 422.9545 | 26724
18769 | 420.3335 | 26724
18770 | 402.9887 | 26724
18771 | 420.4496 | 26724
18772 | 418.3236 | 26724
18773 | 406.2217 | 26724
18774 | 427.4136 | 26724
18775 | 416.49 | 26724
18776 | 407.1044 | 26724
18777 | 412.6416 | 26724
18778 | 415.3077 | 26724
18779 | 413.6096 | 26724
18780 | 406.6348 | 26724
18781 | 410.6718 | 26724
18782 | 432.8135 | 26724
18783 | 416.9914 | 26724
18784 | 414.0964 | 26724
18785 | 412.2769 | 26724
18786 | 407.5631 | 26724
18787 | 421.2318 | 26724
18788 | 417.6793 | 26724
18789 | 427.2141 | 26724
18790 | 407.3002 | 26724
18791 | 435.8292 | 26724
18792 | 409.4475 | 26724
18793 | 418.8801 | 26724
18794 | 414.5019 | 26724
18795 | 412.5745 | 26724
18796 | 406.7561 | 26724
18797 | 429.3853 | 26724
18798 | 421.687 | 26724
18799 | 418.7831 | 26724
18800 | 418.4852 | 26724
18801 | 419.2799 | 26724
18802 | 424.669 | 26724
18803 | 411.0432 | 26724
18804 | 428.5444 | 26724
18805 | 428.8235 | 26724
18806 | 409.9289 | 26724
18807 | 409.5591 | 26724
18808 | 414.835 | 26724
18809 | 414.6613 | 26724
18810 | 417.9328 | 26724
18811 | 410.4703 | 26724
18812 | 419.5135 | 26724
18813 | 418.7351 | 26724
18814 | 421.6884 | 26724
18815 | 427.78 | 26724
18816 | 419.7447 | 26724
18817 | 424.9004 | 26724
18818 | 422.6857 | 26724
18819 | 410.0504 | 26724
18820 | 406.2062 | 26724
18821 | 418.9704 | 26724
18822 | 412.1869 | 26724
18823 | 429.7315 | 26724
18824 | 412.3829 | 26724
18825 | 400.0374 | 26724
18826 | 409.3818 | 26724
18827 | 421.4882 | 26724
18828 | 417.9125 | 26724
18829 | 429.792 | 26724
18830 | 414.7547 | 26724
18831 | 415.4824 | 26724
18832 | 415.8969 | 26724
18833 | 397.5362 | 26724
18834 | 421.043 | 26724
18835 | 422.3743 | 26724
18836 | 416.6633 | 26724
18837 | 409.6722 | 26724
18838 | 425.9 | 26724
18839 | 418.2049 | 26724
18840 | 419.1009 | 26724
18841 | 402.9196 | 26724
18842 | 420.8571 | 26724
18843 | 411.0589 | 26724
18844 | 421.9265 | 26724
18845 | 400.5616 | 26724
18846 | 414.3121 | 26724
18847 | 428.1857 | 26724
18848 | 407.7048 | 26724
18849 | 422.8494 | 26724
18850 | 411.9747 | 26724
18851 | 419.3241 | 26724
18852 | 409.7428 | 26724
18853 | 417.0252 | 26724
18854 | 417.8083 | 26724
18855 | 422.035 | 26724
18856 | 416.8818 | 26724
18857 | 425.4542 | 26724
18858 | 421.5643 | 26724
18859 | 420.0507 | 26724
18860 | 412.3716 | 26724
18861 | 419.7759 | 26724
18862 | 400.2822 | 26724
18863 | 425.3897 | 26724
18864 | 409.5062 | 26724
18865 | 421.8716 | 26724
18866 | 405.5853 | 26724
18867 | 422.5778 | 26724
18868 | 415.4115 | 26724
18869 | 399.5873 | 26724
18870 | 413.5158 | 26724
18871 | 418.0276 | 26724
18872 | 420.6599 | 26724
18873 | 404.201 | 26724
18874 | 412.1411 | 26724
18875 | 411.9189 | 26724
18876 | 410.6338 | 26724
18877 | 403.4936 | 26724
18878 | 408.6417 | 26724
18879 | 416.9093 | 26724
18880 | 426.1937 | 26724
18881 | 426.0752 | 26724
18882 | 409.5478 | 26724
18883 | 411.0708 | 26724
18884 | 423.492 | 26724
18885 | 421.2689 | 26724
18886 | 432.5813 | 26724
18887 | 417.9257 | 26724
18888 | 401.8463 | 26724
18889 | 412.636 | 26724
18890 | 417.1573 | 26724
18891 | 403.2501 | 26724
18892 | 412.3425 | 26724
18893 | 396.4022 | 26724
18894 | 420.4053 | 26724
18895 | 429.9222 | 26724
18896 | 422.2664 | 26724
18897 | 420.5607 | 26724
18898 | 420.2877 | 26724
18899 | 417.9861 | 26724
18900 | 421.9739 | 26724
18901 | 408.6695 | 26724
18902 | 413.6236 | 26724
18903 | 421.07 | 26724
18904 | 416.8836 | 26724
18905 | 419.0925 | 26724
18906 | 421.9854 | 26724
18907 | 420.506 | 26724
18908 | 411.9091 | 26724
18909 | 417.5125 | 26724
18910 | 426.2873 | 26724
18911 | 420.1933 | 26724
18912 | 419.4617 | 26724
18913 | 420.1453 | 26724
18914 | 413.1984 | 26724
18915 | 423.9654 | 26724
18916 | 423.7313 | 26724
18917 | 424.044 | 26724
18918 | 413.561 | 26724
18919 | 422.898 | 26724
18920 | 419.518 | 26724
18921 | 420.5975 | 26724
18922 | 425.8352 | 26724
18923 | 410.3329 | 26724
18924 | 415.6838 | 26724
18925 | 421.2806 | 26724
18926 | 415.137 | 26724
18927 | 426.6206 | 26724
18928 | 412.9054 | 26724
18929 | 418.0936 | 26724
18930 | 428.4964 | 26724
18931 | 424.3995 | 26724
18932 | 417.8579 | 26724
18933 | 413.6926 | 26724
18934 | 411.9556 | 26724
18935 | 423.4717 | 26724
18936 | 416.2332 | 26724
18937 | 413.024 | 26724
18938 | 422.267 | 26724
18939 | 419.0785 | 26724
18940 | 425.771 | 26724
18941 | 430.3307 | 26724
18942 | 419.2473 | 26724
18943 | 403.0731 | 26724
18944 | 426.251 | 26724
18945 | 420.8683 | 26724
18946 | 420.7589 | 26724
18947 | 419.518 | 26724
18948 | 414.4628 | 26724
18949 | 414.6725 | 26724
18950 | 428.4176 | 26724
18951 | 414.6042 | 26724
18952 | 424.2709 | 26724
18953 | 433.2801 | 26724
18954 | 403.9428 | 26724
18955 | 401.2146 | 26724
18956 | 417.1121 | 26724
18957 | 411.979 | 26724
18958 | 420.0904 | 26724
18959 | 411.8377 | 26724
18960 | 429.4376 | 26724
18961 | 420.2974 | 26724
18962 | 425.7817 | 26724
18963 | 420.8455 | 26724
18964 | 412.748 | 26724
18965 | 421.4713 | 26724
18966 | 418.7618 | 26724
18967 | 417.4891 | 26724
18968 | 421.7337 | 26724
18969 | 420.5098 | 26724
18970 | 421.0273 | 26724
18971 | 416.4708 | 26724
18972 | 421.5199 | 26724
18973 | 410.5287 | 26724
18974 | 428.1353 | 26724
18975 | 403.1125 | 26724
18976 | 415.1567 | 26724
18977 | 418.0748 | 26724
18978 | 412.8016 | 26724
18979 | 421.457 | 26724
18980 | 426.8791 | 26724
18981 | 414.8615 | 26724
18982 | 403.0768 | 26724
18983 | 415.2996 | 26724
18984 | 407.3635 | 26724
18985 | 415.7313 | 26724
18986 | 402.4339 | 26724
18987 | 422.3105 | 26724
18988 | 416.1975 | 26724
18989 | 419.0407 | 26724
18990 | 414.0928 | 26724
18991 | 437.3419 | 26724
18992 | 415.5094 | 26724
18993 | 404.6077 | 26724
18994 | 423.5279 | 26724
18995 | 411.5665 | 26724
18996 | 424.3913 | 26724
18997 | 406.1819 | 26724
18998 | 421.6264 | 26724
18999 | 413.4092 | 26724
19000 | 413.2109 | 26724
19001 | 413.1604 | 26724
19002 | 416.1147 | 26724
19003 | 409.2698 | 26724
19004 | 421.3075 | 26724
19005 | 418.4372 | 26724
19006 | 431.7378 | 26724
19007 | 419.8633 | 26724
19008 | 416.0537 | 26724
19009 | 419.7705 | 26724
19010 | 413.8468 | 26724
19011 | 416.1195 | 26724
19012 | 415.4281 | 26724
19013 | 420.7011 | 26724
19014 | 409.2831 | 26724
19015 | 404.1961 | 26724
19016 | 413.9467 | 26724
19017 | 422.4757 | 26724
19018 | 411.2558 | 26724
19019 | 423.7606 | 26724
19020 | 422.8987 | 26724
19021 | 413.537 | 26724
19022 | 421.4069 | 26724
19023 | 413.2182 | 26724
19024 | 418.2599 | 26724
19025 | 414.761 | 26724
19026 | 415.1446 | 26724
19027 | 405.009 | 26724
19028 | 421.4155 | 26724
19029 | 431.3393 | 26724
19030 | 410.377 | 26724
19031 | 428.1834 | 26724
19032 | 424.6142 | 26724
19033 | 412.8613 | 26724
19034 | 414.5201 | 26724
19035 | 406.0184 | 26724
19036 | 412.6679 | 26724
19037 | 412.6129 | 26724
19038 | 416.7504 | 26724
19039 | 411.2045 | 26724
19040 | 415.6575 | 26724
19041 | 419.8151 | 26724
19042 | 412.7291 | 26724
19043 | 410.3452 | 26724
19044 | 414.7309 | 26724
19045 | 431.4729 | 26724
19046 | 409.4517 | 26724
19047 | 408.6244 | 26724
19048 | 401.4305 | 26724
19049 | 403.1446 | 26724
19050 | 413.9411 | 26724
19051 | 419.6879 | 26724
19052 | 432.6311 | 26724
19053 | 420.1124 | 26724
19054 | 416.8274 | 26724
19055 | 413.8495 | 26724
19056 | 432.216 | 26724
19057 | 423.6711 | 26724
19058 | 419.7553 | 26724
19059 | 417.035 | 26724
19060 | 408.1447 | 26724
19061 | 419.6287 | 26724
19062 | 415.4417 | 26724
19063 | 424.1893 | 26724
19064 | 409.049 | 26724
19065 | 433.4425 | 26724
19066 | 427.6194 | 26724
19067 | 404.005 | 26724
19068 | 403.0906 | 26724
19069 | 419.3916 | 26724
19070 | 418.5389 | 26724
19071 | 420.9926 | 26724
19072 | 417.9233 | 26724
19073 | 421.6504 | 26724
19074 | 422.0501 | 26724
19075 | 439.5714 | 26724
19076 | 426.9891 | 26724
19077 | 413.0528 | 26724
19078 | 418.9333 | 26724
19079 | 425.4908 | 26724
19080 | 424.2861 | 26724
19081 | 415.2845 | 26724
19082 | 416.4243 | 26724
19083 | 407.1685 | 26724
19084 | 420.6007 | 26724
19085 | 410.3202 | 26724
19086 | 415.1937 | 26724
19087 | 416.4393 | 26724
19088 | 427.6427 | 26724
19089 | 418.4928 | 26724
19090 | 410.4928 | 26724
19091 | 417.1755 | 26724
19092 | 417.4959 | 26724
19093 | 418.6806 | 26724
19094 | 415.8184 | 26724
19095 | 420.4709 | 26724
19096 | 392.2188 | 26724
19097 | 433.1425 | 26724
19098 | 408.6796 | 26724
19099 | 410.4986 | 26724
19100 | 411.2552 | 26724
19101 | 417.8983 | 26724
19102 | 413.4983 | 26724
19103 | 427.6662 | 26724
19104 | 416.3414 | 26724
19105 | 421.1974 | 26724
19106 | 423.7022 | 26724
19107 | 414.0653 | 26724
19108 | 415.8149 | 26724
19109 | 417.4444 | 26724
19110 | 416.3682 | 26724
19111 | 406.1594 | 26724
19112 | 413.066 | 26724
19113 | 426.3772 | 26724
19114 | 407.0861 | 26724
19115 | 410.898 | 26724
19116 | 400.0179 | 26724
19117 | 405.4055 | 26724
19118 | 416.4685 | 26724
19119 | 415.4817 | 26724
19120 | 398.3275 | 26724
19121 | 401.7264 | 26724
19122 | 403.6936 | 26724
19123 | 423.4611 | 26724
19124 | 419.607 | 26724
19125 | 422.1722 | 26724
19126 | 410.875 | 26724
19127 | 411.4578 | 26724
19128 | 422.6213 | 26724
19129 | 404.7886 | 26724
19130 | 415.2638 | 26724
19131 | 423.5621 | 26724
19132 | 425.1357 | 26724
19133 | 416.7528 | 26724
19134 | 420.8285 | 26724
19135 | 428.3473 | 26724
19136 | 422.9689 | 26724
19137 | 403.7702 | 26724
19138 | 413.0242 | 26724
19139 | 428.9644 | 26724
19140 | 420.7685 | 26724
19141 | 412.2422 | 26724
19142 | 407.334 | 26724
19143 | 423.0454 | 26724
19144 | 432.328 | 26724
19145 | 420.0636 | 26724
19146 | 417.9544 | 26724
19147 | 411.5262 | 26724
19148 | 402.3096 | 26724
19149 | 410.2411 | 26724
19150 | 416.7946 | 26724
19151 | 419.4964 | 26724
19152 | 431.5626 | 26724
19153 | 430.5672 | 26724
19154 | 411.2871 | 26724
19155 | 414.4697 | 26724
19156 | 427.5604 | 26724
19157 | 406.0468 | 26724
19158 | 433.0558 | 26724
19159 | 407.2247 | 26724
19160 | 409.3419 | 26724
19161 | 414.0616 | 26724
19162 | 417.365 | 26724
19163 | 405.3794 | 26724
19164 | 420.6447 | 26724
19165 | 410.4679 | 26724
19166 | 412.3377 | 26724
19167 | 419.2958 | 26724
19168 | 428.4596 | 26724
19169 | 413.9517 | 26724
19170 | 418.4835 | 26724
19171 | 423.6044 | 26724
19172 | 419.9572 | 26724
19173 | 411.1594 | 26724
19174 | 421.2466 | 26724
19175 | 414.0432 | 26724
19176 | 429.7587 | 26724
19177 | 425.5788 | 26724
19178 | 414.3166 | 26724
19179 | 404.8783 | 26724
19180 | 422.3753 | 26724
19181 | 407.5558 | 26724
19182 | 414.4865 | 26724
19183 | 428.5909 | 26724
19184 | 426.1863 | 26724
19185 | 422.891 | 26724
19186 | 411.6609 | 26724
19187 | 421.9231 | 26724
19188 | 410.7344 | 26724
19189 | 414.2037 | 26724
19190 | 403.0877 | 26724
19191 | 400.5515 | 26724
19192 | 418.5414 | 26724
19193 | 414.3985 | 26724
19194 | 425.3006 | 26724
19195 | 420.724 | 26724
19196 | 414.8726 | 26724
19197 | 423.6263 | 26724
19198 | 399.0603 | 26724
19199 | 406.6202 | 26724
19200 | 427.1971 | 26724
19201 | 417.4657 | 26724
19202 | 412.094 | 26724
19203 | 424.522 | 26724
19204 | 419.3857 | 26724
19205 | 411.0606 | 26724
19206 | 425.7649 | 26724
19207 | 406.6184 | 26724
19208 | 416.6884 | 26724
19209 | 420.8578 | 26724
19210 | 421.9693 | 26724
19211 | 414.4205 | 26724
19212 | 426.6729 | 26724
19213 | 412.4078 | 26724
19214 | 406.4181 | 26724
19215 | 415.6866 | 26724
19216 | 403.549 | 26724
19217 | 400.0828 | 26724
19218 | 420.0047 | 26724
19219 | 428.5607 | 26724
19220 | 428.0219 | 26724
19221 | 423.93 | 26724
19222 | 404.1405 | 26724
19223 | 416.1253 | 26724
19224 | 418.275 | 26724
19225 | 413.2223 | 26724
19226 | 432.6775 | 26724
19227 | 407.5861 | 26724
19228 | 420.2062 | 26724
19229 | 424.4922 | 26724
19230 | 416.1738 | 26724
19231 | 420.1341 | 26724
19232 | 402.4933 | 26724
19233 | 410.6086 | 26724
19234 | 407.0859 | 26724
19235 | 421.3222 | 26724
19236 | 422.5257 | 26724
19237 | 433.9637 | 26724
19238 | 430.2951 | 26724
19239 | 423.7222 | 26724
19240 | 411.8738 | 26724
19241 | 405.5141 | 26724
19242 | 427.0681 | 26724
19243 | 416.3106 | 26724
19244 | 411.9784 | 26724
19245 | 426.2383 | 26724
19246 | 412.2453 | 26724
19247 | 409.3361 | 26724
19248 | 421.5076 | 26724
19249 | 412.5415 | 26724
19250 | 429.7827 | 26724
19251 | 424.7708 | 26724
19252 | 407.9324 | 26724
19253 | 416.9636 | 26724
19254 | 426.0494 | 26724
19255 | 418.2706 | 26724
19256 | 414.8322 | 26724
19257 | 411.7795 | 26724
19258 | 427.3923 | 26724
19259 | 429.5574 | 26724
19260 | 420.8534 | 26724
19261 | 416.8281 | 26724
19262 | 399.5236 | 26724
19263 | 412.1769 | 26724
19264 | 406.8102 | 26724
19265 | 420.6383 | 26724
19266 | 425.7082 | 26724
19267 | 429.4447 | 26724
19268 | 417.8783 | 26724
19269 | 412.4352 | 26724
19270 | 422.6126 | 26724
19271 | 411.505 | 26724
19272 | 426.5149 | 26724
19273 | 409.9866 | 26724
19274 | 413.5996 | 26724
19275 | 419.1407 | 26724
19276 | 426.8252 | 26724
19277 | 413.7367 | 26724
19278 | 415.1073 | 26724
19279 | 407.959 | 26724
19280 | 407.1641 | 26724
19281 | 422.4823 | 26724
19282 | 432.0033 | 26724
19283 | 426.8948 | 26724
19284 | 416.6501 | 26724
19285 | 416.347 | 26724
19286 | 415.3099 | 26724
19287 | 419.2197 | 26724
19288 | 405.0971 | 26724
19289 | 408.2353 | 26724
19290 | 417.5261 | 26724
19291 | 410.3554 | 26724
19292 | 409.2867 | 26724
19293 | 404.7261 | 26724
19294 | 428.3427 | 26724
19295 | 422.8702 | 26724
19296 | 421.7611 | 26724
19297 | 413.0556 | 26724
19298 | 426.2237 | 26724
19299 | 425.7721 | 26724
19300 | 423.5681 | 26724
19301 | 418.1363 | 26724
19302 | 413.9489 | 26724
19303 | 419.462 | 26724
19304 | 416.7875 | 26724
19305 | 422.7329 | 26724
19306 | 417.1611 | 26724
19307 | 426.3168 | 26724
19308 | 416.3534 | 26724
19309 | 401.3855 | 26724
19310 | 409.0362 | 26724
19311 | 426.8891 | 26724
19312 | 415.9875 | 26724
19313 | 421.5029 | 26724
19314 | 426.6481 | 26724
19315 | 417.651 | 26724
19316 | 414.8767 | 26724
19317 | 402.312 | 26724
19318 | 423.5614 | 26724
19319 | 412.9708 | 26724
19320 | 406.2493 | 26724
19321 | 418.3455 | 26724
19322 | 420.5926 | 26724
19323 | 427.7761 | 26724
19324 | 405.9106 | 26724
19325 | 414.9233 | 26724
19326 | 428.7091 | 26724
19327 | 413.1927 | 26724
19328 | 407.1428 | 26724
19329 | 425.7105 | 26724
19330 | 411.5849 | 26724
19331 | 427.4395 | 26724
19332 | 432.2263 | 26724
19333 | 419.3656 | 26724
19334 | 416.7961 | 26724
19335 | 429.0075 | 26724
19336 | 413.79 | 26724
19337 | 421.2691 | 26724
19338 | 411.4151 | 26724
19339 | 401.5341 | 26724
19340 | 429.6541 | 26724
19341 | 417.325 | 26724
19342 | 409.8611 | 26724
19343 | 415.1242 | 26724
19344 | 422.0073 | 26724
19345 | 418.1884 | 26724
19346 | 408.6412 | 26724
19347 | 425.7859 | 26724
19348 | 403.9672 | 26724
19349 | 406.1047 | 26724
19350 | 434.3692 | 26724
19351 | 405.5021 | 26724
19352 | 423.1887 | 26724
19353 | 425.0772 | 26724
19354 | 433.1129 | 26724
19355 | 408.26 | 26724
19356 | 410.4215 | 26724
19357 | 414.8246 | 26724
19358 | 398.6393 | 26724
19359 | 418.9464 | 26724
19360 | 416.9458 | 26724
19361 | 407.8991 | 26724
19362 | 422.4719 | 26724
19363 | 420.6161 | 26724
19364 | 412.3898 | 26724
19365 | 410.5697 | 26724
19366 | 404.8017 | 26724
19367 | 398.7303 | 26724
19368 | 417.9122 | 26724
19369 | 431.9604 | 26724
19370 | 413.5056 | 26724
19371 | 427.0776 | 26724
19372 | 437.0365 | 26724
19373 | 429.2335 | 26724
19374 | 423.387 | 26724
19375 | 431.4701 | 26724
19376 | 425.2948 | 26724
19377 | 425.0611 | 26724
19378 | 425.0585 | 26724
19379 | 407.1473 | 26724
19380 | 406.4149 | 26724
19381 | 421.8124 | 26724
19382 | 408.8642 | 26724
19383 | 416.8498 | 26724
19384 | 422.4237 | 26724
19385 | 423.6348 | 26724
19386 | 413.0808 | 26724
19387 | 420.1296 | 26724
19388 | 423.4387 | 26724
19389 | 428.1051 | 26724
19390 | 415.5851 | 26724
19391 | 416.5201 | 26724
19392 | 426.2882 | 26724
19393 | 417.7044 | 26724
19394 | 401.4263 | 26724
19395 | 425.4413 | 26724
19396 | 408.4097 | 26724
19397 | 421.0033 | 26724
19398 | 418.1883 | 26724
19399 | 422.9397 | 26724
19400 | 429.0702 | 26724
19401 | 410.9244 | 26724
19402 | 425.3243 | 26724
19403 | 423.0336 | 26724
19404 | 423.6064 | 26724
19405 | 417.6148 | 26724
19406 | 405.4516 | 26724
19407 | 420.9455 | 26724
19408 | 415.4317 | 26724
19409 | 400.2714 | 26724
19410 | 418.1663 | 26724
19411 | 418.0379 | 26724
19412 | 417.1209 | 26724
19413 | 422.357 | 26724
19414 | 405.7736 | 26724
19415 | 413.471 | 26724
19416 | 428.1082 | 26724
19417 | 427.8415 | 26724
19418 | 419.624 | 26724
19419 | 413.6254 | 26724
19420 | 417.8415 | 26724
19421 | 416.2162 | 26724
19422 | 423.1599 | 26724
19423 | 417.6951 | 26724
19424 | 418.2558 | 26724
19425 | 414.9724 | 26724
19426 | 411.3169 | 26724
19427 | 415.8352 | 26724
19428 | 413.5223 | 26724
19429 | 424.6836 | 26724
19430 | 424.9854 | 26724
19431 | 417.726 | 26724
19432 | 413.8172 | 26724
19433 | 426.4645 | 26724
19434 | 419.3415 | 26724
19435 | 415.254 | 26724
19436 | 409.2231 | 26724
19437 | 430.1628 | 26724
19438 | 421.0316 | 26724
19439 | 418.8464 | 26724
19440 | 426.6996 | 26724
19441 | 408.6767 | 26724
19442 | 416.1145 | 26724
19443 | 412.334 | 26724
19444 | 412.7143 | 26724
19445 | 414.2429 | 26724
19446 | 421.0108 | 26724
19447 | 410.7634 | 26724
19448 | 424.1229 | 26724
19449 | 402.4445 | 26724
19450 | 421.4962 | 26724
19451 | 413.3757 | 26724
19452 | 419.039 | 26724
19453 | 423.2176 | 26724
19454 | 418.2273 | 26724
19455 | 406.794 | 26724
19456 | 416.7065 | 26724
19457 | 408.1048 | 26724
19458 | 414.6053 | 26724
19459 | 423.9198 | 26724
19460 | 418.3064 | 26724
19461 | 433.1179 | 26724
19462 | 412.8301 | 26724
19463 | 419.089 | 26724
19464 | 404.8518 | 26724
19465 | 405.9699 | 26724
19466 | 431.9202 | 26724
19467 | 425.1301 | 26724
19468 | 421.8053 | 26724
19469 | 401.3814 | 26724
19470 | 430.0241 | 26724
19471 | 413.9171 | 26724
19472 | 425.0105 | 26724
19473 | 418.8238 | 26724
19474 | 409.1483 | 26724
19475 | 416.8855 | 26724
19476 | 417.3329 | 26724
19477 | 416.957 | 26724
19478 | 419.4727 | 26724
19479 | 400.9257 | 26724
19480 | 419.828 | 26724
19481 | 405.5236 | 26724
19482 | 413.9857 | 26724
19483 | 400.4769 | 26724
19484 | 429.582 | 26724
19485 | 402.2952 | 26724
19486 | 415.7483 | 26724
19487 | 421.8875 | 26724
19488 | 411.634 | 26724
19489 | 409.0977 | 26724
19490 | 417.7357 | 26724
19491 | 423.5581 | 26724
19492 | 411.04 | 26724
19493 | 423.1876 | 26724
19494 | 415.4148 | 26724
19495 | 415.9174 | 26724
19496 | 409.2837 | 26724
19497 | 404.1096 | 26724
19498 | 427.6055 | 26724
19499 | 410.1133 | 26724
19500 | 417.9552 | 26724
19501 | 413.7665 | 26724
19502 | 415.6203 | 26724
19503 | 414.8084 | 26724
19504 | 414.3388 | 26724
19505 | 406.2946 | 26724
19506 | 409.2866 | 26724
19507 | 429.5111 | 26724
19508 | 421.1205 | 26724
19509 | 426.7773 | 26724
19510 | 410.3156 | 26724
19511 | 418.0003 | 26724
19512 | 427.2904 | 26724
19513 | 408.2923 | 26724
19514 | 412.8504 | 26724
19515 | 423.4423 | 26724
19516 | 426.1214 | 26724
19517 | 410.3181 | 26724
19518 | 411.6352 | 26724
19519 | 421.9094 | 26724
19520 | 407.1233 | 26724
19521 | 433.9059 | 26724
19522 | 423.4685 | 26724
19523 | 420.9527 | 26724
19524 | 423.1331 | 26724
19525 | 421.7736 | 26724
19526 | 429.8558 | 26724
19527 | 422.7827 | 26724
19528 | 415.6751 | 26724
19529 | 413.1693 | 26724
19530 | 413.1149 | 26724
19531 | 411.1253 | 26724
19532 | 415.0049 | 26724
19533 | 424.675 | 26724
19534 | 416.2594 | 26724
19535 | 412.1449 | 26724
19536 | 412.6801 | 26724
19537 | 414.4661 | 26724
19538 | 414.21 | 26724
19539 | 419.3347 | 26724
19540 | 422.3886 | 26724
19541 | 414.7458 | 26724
19542 | 420.1016 | 26724
19543 | 406.5503 | 26724
19544 | 416.666 | 26724
19545 | 418.1247 | 26724
19546 | 422.4193 | 26724
19547 | 413.2502 | 26724
19548 | 422.9583 | 26724
19549 | 413.9716 | 26724
19550 | 412.4772 | 26724
19551 | 427.4278 | 26724
19552 | 427.1542 | 26724
19553 | 411.9756 | 26724
19554 | 418.8218 | 26724
19555 | 421.5919 | 26724
19556 | 419.4815 | 26724
19557 | 409.2166 | 26724
19558 | 416.0314 | 26724
19559 | 401.8769 | 26724
19560 | 415.1598 | 26724
19561 | 419.2907 | 26724
19562 | 410.9729 | 26724
19563 | 416.3795 | 26724
19564 | 416.592 | 26724
19565 | 412.728 | 26724
19566 | 404.2095 | 26724
19567 | 419.4821 | 26724
19568 | 421.3154 | 26724
19569 | 403.3536 | 26724
19570 | 421.031 | 26724
19571 | 421.1714 | 26724
19572 | 421.605 | 26724
19573 | 412.4736 | 26724
19574 | 405.3387 | 26724
19575 | 428.915 | 26724
19576 | 405.7562 | 26724
19577 | 417.4253 | 26724
19578 | 417.8317 | 26724
19579 | 416.8175 | 26724
19580 | 415.1553 | 26724
19581 | 422.1256 | 26724
19582 | 394.037 | 26724
19583 | 423.9366 | 26724
19584 | 418.4995 | 26724
19585 | 406.328 | 26724
19586 | 426.0033 | 26724
19587 | 412.9568 | 26724
19588 | 411.5006 | 26724
19589 | 407.2974 | 26724
19590 | 421.4755 | 26724
19591 | 421.6245 | 26724
19592 | 413.8349 | 26724
19593 | 425.8873 | 26724
19594 | 399.5711 | 26724
19595 | 417.9928 | 26724
19596 | 410.9716 | 26724
19597 | 435.0171 | 26724
19598 | 416.8679 | 26724
19599 | 413.4582 | 26724
19600 | 415.1656 | 26724
19601 | 411.0103 | 26724
19602 | 418.249 | 26724
19603 | 412.6295 | 26724
19604 | 399.7095 | 26724
19605 | 418.4157 | 26724
19606 | 409.8528 | 26724
19607 | 409.1318 | 26724
19608 | 422.2041 | 26724
19609 | 414.976 | 26724
19610 | 414.7685 | 26724
19611 | 400.4085 | 26724
19612 | 402.153 | 26724
19613 | 419.812 | 26724
19614 | 435.037 | 26724
19615 | 426.2069 | 26724
19616 | 395.1248 | 26724
19617 | 429.0351 | 26724
19618 | 418.2599 | 26724
19619 | 408.376 | 26724
19620 | 423.5726 | 26724
19621 | 407.7037 | 26724
19622 | 415.7124 | 26724
19623 | 420.0947 | 26724
19624 | 425.7925 | 26724
19625 | 425.185 | 26724
19626 | 410.4861 | 26724
19627 | 414.7185 | 26724
19628 | 419.7552 | 26724
19629 | 419.9194 | 26724
19630 | 420.0679 | 26724
19631 | 412.5429 | 26724
19632 | 411.114 | 26724
19633 | 397.1066 | 26724
19634 | 408.9682 | 26724
19635 | 423.7186 | 26724
19636 | 423.3975 | 26724
19637 | 414.3856 | 26724
19638 | 422.2411 | 26724
19639 | 409.6127 | 26724
19640 | 430.9153 | 26724
19641 | 424.0626 | 26724
19642 | 420.553 | 26724
19643 | 415.1561 | 26724
19644 | 418.1234 | 26724
19645 | 420.2987 | 26724
19646 | 405.5804 | 26724
19647 | 409.8226 | 26724
19648 | 408.6994 | 26724
19649 | 409.9136 | 26724
19650 | 423.3269 | 26724
19651 | 407.4346 | 26724
19652 | 419.841 | 26724
19653 | 422.4444 | 26724
19654 | 427.8147 | 26724
19655 | 422.536 | 26724
19656 | 413.3228 | 26724
19657 | 424.9247 | 26724
19658 | 422.9392 | 26724
19659 | 429.8384 | 26724
19660 | 421.9812 | 26724
19661 | 411.0284 | 26724
19662 | 413.1171 | 26724
19663 | 409.7531 | 26724
19664 | 419.4118 | 26724
19665 | 424.3079 | 26724
19666 | 438.7071 | 26724
19667 | 406.9606 | 26724
19668 | 403.584 | 26724
19669 | 400.801 | 26724
19670 | 408.3696 | 26724
19671 | 417.4478 | 26724
19672 | 405.6928 | 26724
19673 | 432.5063 | 26724
19674 | 427.6688 | 26724
19675 | 409.4709 | 26724
19676 | 400.0091 | 26724
19677 | 425.1644 | 26724
19678 | 416.4742 | 26724
19679 | 408.6125 | 26724
19680 | 423.8445 | 26724
19681 | 410.2449 | 26724
19682 | 410.3147 | 26724
19683 | 410.3703 | 26724
19684 | 420.1427 | 26724
19685 | 419.4056 | 26724
19686 | 415.0531 | 26724
19687 | 428.9066 | 26724
19688 | 397.4222 | 26724
19689 | 417.9841 | 26724
19690 | 427.7124 | 26724
19691 | 422.6306 | 26724
19692 | 418.1085 | 26724
19693 | 408.7818 | 26724
19694 | 420.8253 | 26724
19695 | 411.8882 | 26724
19696 | 410.6091 | 26724
19697 | 435.7805 | 26724
19698 | 433.3469 | 26724
19699 | 413.2971 | 26724
19700 | 407.4867 | 26724
19701 | 414.8732 | 26724
19702 | 415.8146 | 26724
19703 | 420.5637 | 26724
19704 | 414.863 | 26724
19705 | 414.5714 | 26724
19706 | 417.0567 | 26724
19707 | 423.2473 | 26724
19708 | 408.8873 | 26724
19709 | 412.3514 | 26724
19710 | 420.4031 | 26724
19711 | 413.1682 | 26724
19712 | 404.7572 | 26724
19713 | 430.4531 | 26724
19714 | 421.9745 | 26724
19715 | 412.9819 | 26724
19716 | 423.4678 | 26724
19717 | 412.3123 | 26724
19718 | 416.9269 | 26724
19719 | 421.3746 | 26724
19720 | 409.6485 | 26724
19721 | 404.2342 | 26724
19722 | 416.9485 | 26724
19723 | 414.9114 | 26724
19724 | 420.3369 | 26724
19725 | 406.7052 | 26724
19726 | 402.8194 | 26724
19727 | 426.0622 | 26724
19728 | 411.9964 | 26724
19729 | 417.8554 | 26724
19730 | 411.2685 | 26724
19731 | 403.7114 | 26724
19732 | 402.3383 | 26724
19733 | 425.0071 | 26724
19734 | 423.8981 | 26724
19735 | 413.201 | 26724
19736 | 419.0203 | 26724
19737 | 417.0682 | 26724
19738 | 431.1201 | 26724
19739 | 417.0659 | 26724
19740 | 409.7905 | 26724
19741 | 405.2663 | 26724
19742 | 416.3468 | 26724
19743 | 416.1127 | 26724
19744 | 422.745 | 26724
19745 | 426.2431 | 26724
19746 | 415.5759 | 26724
19747 | 408.0824 | 26724
19748 | 427.8816 | 26724
19749 | 420.464 | 26724
19750 | 402.9524 | 26724
19751 | 422.6891 | 26724
19752 | 424.9016 | 26724
19753 | 415.706 | 26724
19754 | 413.4165 | 26724
19755 | 409.7959 | 26724
19756 | 417.858 | 26724
19757 | 431.1123 | 26724
19758 | 410.6275 | 26724
19759 | 416.4314 | 26724
19760 | 418.6917 | 26724
19761 | 427.0332 | 26724
19762 | 418.3628 | 26724
19763 | 418.9423 | 26724
19764 | 419.8122 | 26724
19765 | 420.8605 | 26724
19766 | 429.3629 | 26724
19767 | 408.5685 | 26724
19768 | 397.9193 | 26724
19769 | 418.3253 | 26724
19770 | 426.6025 | 26724
19771 | 410.1424 | 26724
19772 | 422.07 | 26724
19773 | 415.6286 | 26724
19774 | 426.5887 | 26724
19775 | 406.314 | 26724
19776 | 436.0331 | 26724
19777 | 421.1998 | 26724
19778 | 401.47 | 26724
19779 | 401.4816 | 26724
19780 | 421.2561 | 26724
19781 | 408.8397 | 26724
19782 | 411.739 | 26724
19783 | 402.9336 | 26724
19784 | 413.9836 | 26724
19785 | 422.2925 | 26724
19786 | 430.1367 | 26724
19787 | 418.2871 | 26724
19788 | 410.7055 | 26724
19789 | 420.6803 | 26724
19790 | 405.4273 | 26724
19791 | 414.6186 | 26724
19792 | 413.1377 | 26724
19793 | 433.2959 | 26724
19794 | 417.1448 | 26724
19795 | 399.6576 | 26724
19796 | 417.8956 | 26724
19797 | 410.7781 | 26724
19798 | 405.1213 | 26724
19799 | 425.474 | 26724
19800 | 414.0006 | 26724
19801 | 412.273 | 26724
19802 | 416.138 | 26724
19803 | 422.8714 | 26724
19804 | 425.8495 | 26724
19805 | 394.4418 | 26724
19806 | 419.2948 | 26724
19807 | 416.3774 | 26724
19808 | 405.9585 | 26724
19809 | 418.025 | 26724
19810 | 421.2106 | 26724
19811 | 421.7022 | 26724
19812 | 412.3377 | 26724
19813 | 416.2873 | 26724
19814 | 402.2366 | 26724
19815 | 407.5635 | 26724
19816 | 434.3531 | 26724
19817 | 423.2167 | 26724
19818 | 404.6978 | 26724
19819 | 408.3504 | 26724
19820 | 408.4632 | 26724
19821 | 403.6814 | 26724
19822 | 425.9097 | 26724
19823 | 427.5169 | 26724
19824 | 412.9777 | 26724
19825 | 415.918 | 26724
19826 | 421.4331 | 26724
19827 | 416.456 | 26724
19828 | 409.4724 | 26724
19829 | 408.3814 | 26724
19830 | 411.9474 | 26724
19831 | 409.7467 | 26724
19832 | 400.0825 | 26724
19833 | 426.2265 | 26724
19834 | 407.4241 | 26724
19835 | 420.6558 | 26724
19836 | 416.2836 | 26724
19837 | 418.5246 | 26724
19838 | 420.3853 | 26724
19839 | 407.799 | 26724
19840 | 423.3685 | 26724
19841 | 421.0148 | 26724
19842 | 400.6461 | 26724
19843 | 413.6793 | 26724
19844 | 409.2785 | 26724
19845 | 413.4758 | 26724
19846 | 414.1355 | 26724
19847 | 423.5724 | 26724
19848 | 412.6373 | 26724
19849 | 421.9125 | 26724
19850 | 406.6268 | 26724
19851 | 420.1995 | 26724
19852 | 416.2479 | 26724
19853 | 416.3003 | 26724
19854 | 411.3009 | 26724
19855 | 418.8252 | 26724
19856 | 405.3779 | 26724
19857 | 411.6714 | 26724
19858 | 413.0038 | 26724
19859 | 409.3951 | 26724
19860 | 425.5383 | 26724
19861 | 426.3913 | 26724
19862 | 429.983 | 26724
19863 | 414.406 | 26724
19864 | 419.7916 | 26724
19865 | 423.0095 | 26724
19866 | 409.0665 | 26724
19867 | 421.7208 | 26724
19868 | 413.6487 | 26724
19869 | 402.768 | 26724
19870 | 422.3544 | 26724
19871 | 423.6531 | 26724
19872 | 427.7302 | 26724
19873 | 404.7277 | 26724
19874 | 406.4876 | 26724
19875 | 417.3939 | 26724
19876 | 436.1547 | 26724
19877 | 414.1926 | 26724
19878 | 422.8788 | 26724
19879 | 430.6939 | 26724
19880 | 415.3553 | 26724
19881 | 421.9733 | 26724
19882 | 413.3616 | 26724
19883 | 398.1141 | 26724
19884 | 408.5793 | 26724
19885 | 423.2687 | 26724
19886 | 407.364 | 26724
19887 | 408.6571 | 26724
19888 | 408.2066 | 26724
19889 | 415.2416 | 26724
19890 | 420.7295 | 26724
19891 | 423.5784 | 26724
19892 | 417.6143 | 26724
19893 | 427.6609 | 26724
19894 | 420.4319 | 26724
19895 | 407.3273 | 26724
19896 | 423.6841 | 26724
19897 | 400.8021 | 26724
19898 | 409.7297 | 26724
19899 | 426.0803 | 26724
19900 | 410.7245 | 26724
19901 | 430.6407 | 26724
19902 | 414.0695 | 26724
19903 | 413.6538 | 26724
19904 | 425.5275 | 26724
19905 | 411.1408 | 26724
19906 | 408.303 | 26724
19907 | 414.3094 | 26724
19908 | 417.226 | 26724
19909 | 420.3734 | 26724
19910 | 422.0785 | 26724
19911 | 412.3194 | 26724
19912 | 417.4384 | 26724
19913 | 424.0696 | 26724
19914 | 420.5822 | 26724
19915 | 414.8617 | 26724
19916 | 428.8489 | 26724
19917 | 420.5576 | 26724
19918 | 420.189 | 26724
19919 | 415.4315 | 26724
19920 | 426.7229 | 26724
19921 | 411.4322 | 26724
19922 | 418.1598 | 26724
19923 | 406.3682 | 26724
19924 | 430.2531 | 26724
19925 | 408.9878 | 26724
19926 | 402.6623 | 26724
19927 | 429.8664 | 26724
19928 | 418.3035 | 26724
19929 | 417.0536 | 26724
19930 | 409.2265 | 26724
19931 | 413.9911 | 26724
19932 | 407.4445 | 26724
19933 | 426.503 | 26724
19934 | 417.3799 | 26724
19935 | 415.4176 | 26724
19936 | 406.5549 | 26724
19937 | 429.5587 | 26724
19938 | 420.3114 | 26724
19939 | 421.1438 | 26724
19940 | 401.8598 | 26724
19941 | 409.3588 | 26724
19942 | 420.9694 | 26724
19943 | 416.3585 | 26724
19944 | 414.9122 | 26724
19945 | 425.8938 | 26724
19946 | 421.3422 | 26724
19947 | 420.1784 | 26724
19948 | 441.9534 | 26724
19949 | 416.276 | 26724
19950 | 411.0086 | 26724
19951 | 417.7715 | 26724
19952 | 418.8691 | 26724
19953 | 404.7835 | 26724
19954 | 406.912 | 26724
19955 | 400.8146 | 26724
19956 | 418.5582 | 26724
19957 | 419.7524 | 26724
19958 | 422.3723 | 26724
19959 | 409.6337 | 26724
19960 | 414.3823 | 26724
19961 | 398.583 | 26724
19962 | 422.8624 | 26724
19963 | 423.5316 | 26724
19964 | 419.2988 | 26724
19965 | 412.8074 | 26724
19966 | 420.6664 | 26724
19967 | 414.1275 | 26724
19968 | 412.5986 | 26724
19969 | 405.4381 | 26724
19970 | 416.2649 | 26724
19971 | 410.8769 | 26724
19972 | 417.6244 | 26724
19973 | 414.6714 | 26724
19974 | 418.2381 | 26724
19975 | 420.8306 | 26724
19976 | 427.184 | 26724
19977 | 424.89 | 26724
19978 | 416.7703 | 26724
19979 | 424.5927 | 26724
19980 | 414.312 | 26724
19981 | 430.1059 | 26724
19982 | 406.3525 | 26724
19983 | 396.313 | 26724
19984 | 419.8724 | 26724
19985 | 417.5182 | 26724
19986 | 420.5571 | 26724
19987 | 416.5905 | 26724
19988 | 418.7582 | 26724
19989 | 409.692 | 26724
19990 | 422.3489 | 26724
19991 | 418.567 | 26724
19992 | 424.6308 | 26724
19993 | 417.8688 | 26724
19994 | 412.4471 | 26724
19995 | 414.6848 | 26724
19996 | 413.1116 | 26724
19997 | 412.7943 | 26724
19998 | 420.2428 | 26724
19999 | 420.4629 | 26724
20000 | 417.8587 | 26724
20001 | 418.5786 | 26724
20002 | 409.5782 | 26724
20003 | 424.7592 | 26724
20004 | 418.9048 | 26724
20005 | 416.5046 | 26724
20006 | 420.1431 | 26724
20007 | 420.6272 | 26724
20008 | 407.761 | 26724
20009 | 408.5148 | 26724
20010 | 420.2169 | 26724
20011 | 411.9439 | 26724
20012 | 410.7751 | 26724
20013 | 430.4094 | 26724
20014 | 422.4764 | 26724
20015 | 417.696 | 26724
20016 | 429.4585 | 26724
20017 | 403.6173 | 26724
20018 | 427.3131 | 26724
20019 | 420.9017 | 26724
20020 | 415.9255 | 26724
20021 | 409.5322 | 26724
20022 | 401.3776 | 26724
20023 | 410.4111 | 26724
20024 | 405.6777 | 26724
20025 | 420.6349 | 26724
20026 | 420.9327 | 26724
20027 | 422.4192 | 26724
20028 | 397.8753 | 26724
20029 | 407.9888 | 26724
20030 | 396.2444 | 26724
20031 | 406.4935 | 26724
20032 | 422.1311 | 26724
20033 | 417.5801 | 26724
20034 | 409.7694 | 26724
20035 | 418.2691 | 26724
20036 | 409.5223 | 26724
20037 | 416.872 | 26724
20038 | 395.639 | 26724
20039 | 422.6403 | 26724
20040 | 420.4127 | 26724
20041 | 414.8045 | 26724
20042 | 420.7171 | 26724
20043 | 427.2165 | 26724
20044 | 416.2168 | 26724
20045 | 411.1893 | 26724
20046 | 403.2234 | 26724
20047 | 425.2767 | 26724
20048 | 422.1292 | 26724
20049 | 410.6426 | 26724
20050 | 421.3255 | 26724
20051 | 414.2408 | 26724
20052 | 419.3705 | 26724
20053 | 412.1699 | 26724
20054 | 409.2042 | 26724
20055 | 412.8399 | 26724
20056 | 408.4998 | 26724
20057 | 420.8799 | 26724
20058 | 395.5825 | 26724
20059 | 408.767 | 26724
20060 | 423.7887 | 26724
20061 | 420.3817 | 26724
20062 | 418.7862 | 26724
20063 | 417.3881 | 26724
20064 | 404.4996 | 26724
20065 | 423.9295 | 26724
20066 | 419.5767 | 26724
20067 | 421.1797 | 26724
20068 | 426.9798 | 26724
20069 | 399.1425 | 26724
20070 | 426.0531 | 26724
20071 | 411.3412 | 26724
20072 | 417.4155 | 26724
20073 | 405.6674 | 26724
20074 | 406.8408 | 26724
20075 | 424.6819 | 26724
20076 | 415.2657 | 26724
20077 | 411.5178 | 26724
20078 | 412.7389 | 26724
20079 | 402.6338 | 26724
20080 | 408.0335 | 26724
20081 | 409.1999 | 26724
20082 | 417.0555 | 26724
20083 | 424.3933 | 26724
20084 | 413.0487 | 26724
20085 | 415.6886 | 26724
20086 | 421.522 | 26724
20087 | 410.7844 | 26724
20088 | 410.2711 | 26724
20089 | 410.3009 | 26724
20090 | 432.5224 | 26724
20091 | 426.6901 | 26724
20092 | 433.5424 | 26724
20093 | 411.5656 | 26724
20094 | 417.5155 | 26724
20095 | 416.122 | 26724
20096 | 424.1776 | 26724
20097 | 417.6238 | 26724
20098 | 414.6101 | 26724
20099 | 411.4966 | 26724
20100 | 418.3183 | 26724
20101 | 415.2268 | 26724
20102 | 427.0881 | 26724
20103 | 421.5678 | 26724
20104 | 415.0489 | 26724
20105 | 413.3295 | 26724
20106 | 423.1085 | 26724
20107 | 412.0037 | 26724
20108 | 410.1207 | 26724
20109 | 417.979 | 26724
20110 | 408.0951 | 26724
20111 | 425.0015 | 26724
20112 | 417.242 | 26724
20113 | 432.1621 | 26724
20114 | 418.9703 | 26724
20115 | 420.3226 | 26724
20116 | 424.4349 | 26724
20117 | 416.0703 | 26724
20118 | 430.1503 | 26724
20119 | 420.4688 | 26724
20120 | 413.6157 | 26724
20121 | 394.5708 | 26724
20122 | 409.0967 | 26724
20123 | 421.9095 | 26724
20124 | 422.9248 | 26724
20125 | 404.9084 | 26724
20126 | 420.45 | 26724
20127 | 419.7162 | 26724
20128 | 420.1325 | 26724
20129 | 409.2917 | 26724
20130 | 410.1017 | 26724
20131 | 408.7202 | 26724
20132 | 412.1078 | 26724
20133 | 414.3913 | 26724
20134 | 422.004 | 26724
20135 | 408.1802 | 26724
20136 | 429.1465 | 26724
20137 | 405.9838 | 26724
20138 | 421.3529 | 26724
20139 | 414.0308 | 26724
20140 | 411.9202 | 26724
20141 | 418.1414 | 26724
20142 | 406.6071 | 26724
20143 | 420.0895 | 26724
20144 | 421.8809 | 26724
20145 | 413.8728 | 26724
20146 | 420.0703 | 26724
20147 | 424.8401 | 26724
20148 | 433.7091 | 26724
20149 | 417.6566 | 26724
20150 | 429.8656 | 26724
20151 | 415.0404 | 26724
20152 | 420.5966 | 26724
20153 | 418.8117 | 26724
20154 | 411.8425 | 26724
20155 | 414.1998 | 26724
20156 | 408.7447 | 26724
20157 | 423.5141 | 26724
20158 | 412.9436 | 26724
20159 | 407.4879 | 26724
20160 | 417.3293 | 26724
20161 | 426.6606 | 26724
20162 | 426.0642 | 26724
20163 | 421.5457 | 26724
20164 | 412.2129 | 26724
20165 | 414.1439 | 26724
20166 | 407.4429 | 26724
20167 | 408.6185 | 26724
20168 | 427.642 | 26724
20169 | 410.7679 | 26724
20170 | 424.6575 | 26724
20171 | 421.7612 | 26724
20172 | 424.742 | 26724
20173 | 413.2905 | 26724
20174 | 426.5189 | 26724
20175 | 419.4997 | 26724
20176 | 408.7224 | 26724
20177 | 410.9563 | 26724
20178 | 409.9379 | 26724
20179 | 408.2424 | 26724
20180 | 423.2834 | 26724
20181 | 414.1876 | 26724
20182 | 428.1267 | 26724
20183 | 402.7968 | 26724
20184 | 413.5445 | 26724
20185 | 435.2718 | 26724
20186 | 416.2025 | 26724
20187 | 409.5731 | 26724
20188 | 416.5051 | 26724
20189 | 408.864 | 26724
20190 | 399.5043 | 26724
20191 | 402.3106 | 26724
20192 | 424.677 | 26724
20193 | 419.3273 | 26724
20194 | 409.2457 | 26724
20195 | 418.2073 | 26724
20196 | 436.9227 | 26724
20197 | 419.9307 | 26724
20198 | 418.2817 | 26724
20199 | 423.5084 | 26724
20200 | 413.6748 | 26724
20201 | 427.1859 | 26724
20202 | 425.2787 | 26724
20203 | 430.7608 | 26724
20204 | 426.9682 | 26724
20205 | 431.628 | 26724
20206 | 400.4993 | 26724
20207 | 413.046 | 26724
20208 | 411.703 | 26724
20209 | 393.3962 | 26724
20210 | 414.436 | 26724
20211 | 407.3564 | 26724
20212 | 415.4402 | 26724
20213 | 418.4953 | 26724
20214 | 421.2309 | 26724
20215 | 407.1124 | 26724
20216 | 407.6233 | 26724
20217 | 411.5694 | 26724
20218 | 428.6474 | 26724
20219 | 424.1018 | 26724
20220 | 421.3288 | 26724
20221 | 413.3637 | 26724
20222 | 403.8152 | 26724
20223 | 402.7743 | 26724
20224 | 413.4914 | 26724
20225 | 428.9943 | 26724
20226 | 430.4718 | 26724
20227 | 420.5887 | 26724
20228 | 396.6597 | 26724
20229 | 425.0356 | 26724
20230 | 423.6907 | 26724
20231 | 415.9971 | 26724
20232 | 418.3812 | 26724
20233 | 417.4979 | 26724
20234 | 422.2616 | 26724
20235 | 417.0973 | 26724
20236 | 410.5731 | 26724
20237 | 414.2499 | 26724
20238 | 424.7392 | 26724
20239 | 407.7189 | 26724
20240 | 421.1676 | 26724
20241 | 422.2425 | 26724
20242 | 425.0271 | 26724
20243 | 414.1776 | 26724
20244 | 431.754 | 26724
20245 | 416.5625 | 26724
20246 | 414.2803 | 26724
20247 | 415.7698 | 26724
20248 | 421.7826 | 26724
20249 | 422.7097 | 26724
20250 | 420.3661 | 26724
20251 | 411.6082 | 26724
20252 | 424.4056 | 26724
20253 | 418.552 | 26724
20254 | 414.6239 | 26724
20255 | 423.4302 | 26724
20256 | 413.3665 | 26724
20257 | 413.7507 | 26724
20258 | 418.3129 | 26724
20259 | 410.1703 | 26724
20260 | 402.7118 | 26724
20261 | 409.3324 | 26724
20262 | 420.2929 | 26724
20263 | 408.8683 | 26724
20264 | 429.0441 | 26724
20265 | 410.1231 | 26724
20266 | 411.1557 | 26724
20267 | 405.4222 | 26724
20268 | 422.2768 | 26724
20269 | 420.0026 | 26724
20270 | 419.0157 | 26724
20271 | 422.8799 | 26724
20272 | 409.8021 | 26724
20273 | 408.0669 | 26724
20274 | 420.9174 | 26724
20275 | 404.3035 | 26724
20276 | 424.5131 | 26724
20277 | 402.206 | 26724
20278 | 414.5219 | 26724
20279 | 407.9502 | 26724
20280 | 418.6692 | 26724
20281 | 426.2537 | 26724
20282 | 420.3366 | 26724
20283 | 422.5474 | 26724
20284 | 414.3399 | 26724
20285 | 421.678 | 26724
20286 | 424.1302 | 26724
20287 | 407.4798 | 26724
20288 | 408.2445 | 26724
20289 | 409.8984 | 26724
20290 | 423.7352 | 26724
20291 | 415.6996 | 26724
20292 | 413.2254 | 26724
20293 | 415.3923 | 26724
20294 | 427.5488 | 26724
20295 | 421.5083 | 26724
20296 | 425.0391 | 26724
20297 | 419.3015 | 26724
20298 | 422.042 | 26724
20299 | 399.6108 | 26724
20300 | 424.7742 | 26724
20301 | 425.9536 | 26724
20302 | 420.8706 | 26724
20303 | 416.0601 | 26724
20304 | 407.852 | 26724
20305 | 426.7849 | 26724
20306 | 426.6026 | 26724
20307 | 421.2091 | 26724
20308 | 422.6091 | 26724
20309 | 415.7726 | 26724
20310 | 432.6769 | 26724
20311 | 415.7971 | 26724
20312 | 411.4517 | 26724
20313 | 417.404 | 26724
20314 | 412.5999 | 26724
20315 | 415.4079 | 26724
20316 | 426.4808 | 26724
20317 | 426.899 | 26724
20318 | 414.6358 | 26724
20319 | 411.2872 | 26724
20320 | 423.3997 | 26724
20321 | 419.3445 | 26724
20322 | 413.0641 | 26724
20323 | 423.335 | 26724
20324 | 428.1218 | 26724
20325 | 404.8503 | 26724
20326 | 418.7513 | 26724
20327 | 401.2826 | 26724
20328 | 405.4317 | 26724
20329 | 419.26 | 26724
20330 | 420.3568 | 26724
20331 | 410.7624 | 26724
20332 | 411.8356 | 26724
20333 | 419.0647 | 26724
20334 | 419.4256 | 26724
20335 | 412.5416 | 26724
20336 | 421.3067 | 26724
20337 | 405.6363 | 26724
20338 | 409.1775 | 26724
20339 | 400.9129 | 26724
20340 | 429.3185 | 26724
20341 | 418.8519 | 26724
20342 | 409.8761 | 26724
20343 | 423.1872 | 26724
20344 | 418.5823 | 26724
20345 | 421.3907 | 26724
20346 | 415.4287 | 26724
20347 | 409.8271 | 26724
20348 | 423.6879 | 26724
20349 | 402.0644 | 26724
20350 | 428.9478 | 26724
20351 | 401.6278 | 26724
20352 | 414.5785 | 26724
20353 | 412.213 | 26724
20354 | 422.9575 | 26724
20355 | 428.546 | 26724
20356 | 413.0294 | 26724
20357 | 409.8958 | 26724
20358 | 411.6321 | 26724
20359 | 423.6916 | 26724
20360 | 414.367 | 26724
20361 | 406.8804 | 26724
20362 | 416.0886 | 26724
20363 | 419.7103 | 26724
20364 | 417.9839 | 26724
20365 | 423.6874 | 26724
20366 | 415.5768 | 26724
20367 | 413.1577 | 26724
20368 | 437.0307 | 26724
20369 | 414.7123 | 26724
20370 | 413.4907 | 26724
20371 | 403.0975 | 26724
20372 | 403.8777 | 26724
20373 | 433.6204 | 26724
20374 | 421.8877 | 26724
20375 | 431.544 | 26724
20376 | 431.8545 | 26724
20377 | 421.0731 | 26724
20378 | 418.8938 | 26724
20379 | 424.0297 | 26724
20380 | 406.8584 | 26724
20381 | 411.6405 | 26724
20382 | 416.0124 | 26724
20383 | 412.0445 | 26724
20384 | 415.7268 | 26724
20385 | 420.1956 | 26724
20386 | 419.8217 | 26724
20387 | 415.3815 | 26724
20388 | 414.9037 | 26724
20389 | 418.2998 | 26724
20390 | 406.8522 | 26724
20391 | 424.7878 | 26724
20392 | 403.7448 | 26724
20393 | 414.4927 | 26724
20394 | 420.8394 | 26724
20395 | 409.9307 | 26724
20396 | 418.6753 | 26724
20397 | 416.4361 | 26724
20398 | 408.0859 | 26724
20399 | 413.1902 | 26724
20400 | 418.3542 | 26724
20401 | 420.9682 | 26724
20402 | 413.735 | 26724
20403 | 405.0264 | 26724
20404 | 401.0804 | 26724
20405 | 417.3097 | 26724
20406 | 409.348 | 26724
20407 | 430.953 | 26724
20408 | 407.3354 | 26724
20409 | 419.9262 | 26724
20410 | 423.0476 | 26724
20411 | 429.7922 | 26724
20412 | 428.0061 | 26724
20413 | 401.0486 | 26724
20414 | 421.5758 | 26724
20415 | 410.0032 | 26724
20416 | 412.8721 | 26724
20417 | 402.6285 | 26724
20418 | 421.6423 | 26724
20419 | 422.2029 | 26724
20420 | 397.7307 | 26724
20421 | 413.3711 | 26724
20422 | 429.7592 | 26724
20423 | 429.1213 | 26724
20424 | 410.0612 | 26724
20425 | 424.3533 | 26724
20426 | 418.1861 | 26724
20427 | 420.5841 | 26724
20428 | 404.284 | 26724
20429 | 393.7595 | 26724
20430 | 432.1885 | 26724
20431 | 413.5581 | 26724
20432 | 400.8813 | 26724
20433 | 408.9182 | 26724
20434 | 410.4756 | 26724
20435 | 428.8484 | 26724
20436 | 427.5391 | 26724
20437 | 409.1564 | 26724
20438 | 425.8967 | 26724
20439 | 412.9896 | 26724
20440 | 424.9153 | 26724
20441 | 407.4744 | 26724
20442 | 421.4001 | 26724
20443 | 418.5791 | 26724
20444 | 417.8241 | 26724
20445 | 412.8298 | 26724
20446 | 420.1266 | 26724
20447 | 412.7322 | 26724
20448 | 423.1329 | 26724
20449 | 411.6035 | 26724
20450 | 409.1235 | 26724
20451 | 402.1717 | 26724
20452 | 419.307 | 26724
20453 | 406.9606 | 26724
20454 | 416.5046 | 26724
20455 | 418.0045 | 26724
20456 | 432.3828 | 26724
20457 | 407.1226 | 26724
20458 | 406.5198 | 26724
20459 | 420.373 | 26724
20460 | 413.6865 | 26724
20461 | 421.7756 | 26724
20462 | 421.5765 | 26724
20463 | 430.1289 | 26724
20464 | 430.1596 | 26724
20465 | 427.6432 | 26724
20466 | 418.171 | 26724
20467 | 419.4586 | 26724
20468 | 409.6855 | 26724
20469 | 397.751 | 26724
20470 | 425.2301 | 26724
20471 | 425.987 | 26724
20472 | 417.8785 | 26724
20473 | 418.2095 | 26724
20474 | 415.2979 | 26724
20475 | 420.8884 | 26724
20476 | 415.7172 | 26724
20477 | 401.8488 | 26724
20478 | 426.6947 | 26724
20479 | 414.1595 | 26724
20480 | 420.5264 | 26724
20481 | 411.5699 | 26724
20482 | 415.4508 | 26724
20483 | 412.4763 | 26724
20484 | 418.5038 | 26724
20485 | 411.6018 | 26724
20486 | 413.923 | 26724
20487 | 406.1541 | 26724
20488 | 427.6291 | 26724
20489 | 412.6425 | 26724
20490 | 428.7646 | 26724
20491 | 405.3621 | 26724
20492 | 406.2019 | 26724
20493 | 402.6303 | 26724
20494 | 406.0741 | 26724
20495 | 409.1108 | 26724
20496 | 406.0391 | 26724
20497 | 422.7763 | 26724
20498 | 409.7223 | 26724
20499 | 407.5182 | 26724
20500 | 424.2583 | 26724
20501 | 421.888 | 26724
20502 | 414.6014 | 26724
20503 | 408.1145 | 26724
20504 | 428.7558 | 26724
20505 | 424.2774 | 26724
20506 | 413.9391 | 26724
20507 | 429.654 | 26724
20508 | 430.377 | 26724
20509 | 429.978 | 26724
20510 | 412.8581 | 26724
20511 | 416.7907 | 26724
20512 | 418.3844 | 26724
20513 | 410.4833 | 26724
20514 | 417.1619 | 26724
20515 | 425.5751 | 26724
20516 | 421.6188 | 26724
20517 | 424.1278 | 26724
20518 | 412.7086 | 26724
20519 | 410.1897 | 26724
20520 | 419.9794 | 26724
20521 | 415.2239 | 26724
20522 | 412.8931 | 26724
20523 | 437.315 | 26724
20524 | 423.1507 | 26724
20525 | 415.3655 | 26724
20526 | 423.6871 | 26724
20527 | 413.0152 | 26724
20528 | 422.8645 | 26724
20529 | 418.5428 | 26724
20530 | 406.6297 | 26724
20531 | 422.5704 | 26724
20532 | 421.8518 | 26724
20533 | 419.4738 | 26724
20534 | 427.8309 | 26724
20535 | 409.2707 | 26724
20536 | 406.4969 | 26724
20537 | 417.8882 | 26724
20538 | 402.0676 | 26724
20539 | 418.597 | 26724
20540 | 418.4432 | 26724
20541 | 423.4634 | 26724
20542 | 422.2476 | 26724
20543 | 405.158 | 26724
20544 | 425.1036 | 26724
20545 | 405.5302 | 26724
20546 | 421.5092 | 26724
20547 | 412.6848 | 26724
20548 | 408.5762 | 26724
20549 | 422.3536 | 26724
20550 | 420.5799 | 26724
20551 | 419.1013 | 26724
20552 | 417.433 | 26724
20553 | 407.6604 | 26724
20554 | 413.5845 | 26724
20555 | 421.1384 | 26724
20556 | 422.5033 | 26724
20557 | 416.1442 | 26724
20558 | 416.5953 | 26724
20559 | 413.0763 | 26724
20560 | 409.9684 | 26724
20561 | 416.6992 | 26724
20562 | 411.186 | 26724
20563 | 408.485 | 26724
20564 | 403.4517 | 26724
20565 | 416.7231 | 26724
20566 | 400.6223 | 26724
20567 | 438.6845 | 26724
20568 | 423.8692 | 26724
20569 | 412.7931 | 26724
20570 | 413.7018 | 26724
20571 | 407.3936 | 26724
20572 | 410.5974 | 26724
20573 | 412.1267 | 26724
20574 | 410.2877 | 26724
20575 | 411.2059 | 26724
20576 | 417.3122 | 26724
20577 | 417.618 | 26724
20578 | 418.045 | 26724
20579 | 417.8598 | 26724
20580 | 395.4157 | 26724
20581 | 422.1528 | 26724
20582 | 407.923 | 26724
20583 | 423.9475 | 26724
20584 | 412.2822 | 26724
20585 | 410.9372 | 26724
20586 | 421.9327 | 26724
20587 | 415.1564 | 26724
20588 | 429.7962 | 26724
20589 | 403.0462 | 26724
20590 | 407.133 | 26724
20591 | 412.6087 | 26724
20592 | 395.6807 | 26724
20593 | 421.9333 | 26724
20594 | 426.6338 | 26724
20595 | 418.1262 | 26724
20596 | 406.3522 | 26724
20597 | 424.0671 | 26724
20598 | 413.4897 | 26724
20599 | 409.2972 | 26724
20600 | 412.997 | 26724
20601 | 419.3161 | 26724
20602 | 415.2686 | 26724
20603 | 418.6559 | 26724
20604 | 423.2107 | 26724
20605 | 426.3277 | 26724
20606 | 431.9041 | 26724
20607 | 413.0562 | 26724
20608 | 407.2376 | 26724
20609 | 419.688 | 26724
20610 | 414.3842 | 26724
20611 | 417.566 | 26724
20612 | 393.3384 | 26724
20613 | 413.2639 | 26724
20614 | 420.5801 | 26724
20615 | 412.0775 | 26724
20616 | 418.0387 | 26724
20617 | 403.5536 | 26724
20618 | 423.9549 | 26724
20619 | 424.5766 | 26724
20620 | 427.7395 | 26724
20621 | 416.9722 | 26724
20622 | 424.0198 | 26724
20623 | 406.5283 | 26724
20624 | 412.5874 | 26724
20625 | 409.6352 | 26724
20626 | 419.0397 | 26724
20627 | 419.799 | 26724
20628 | 403.8366 | 26724
20629 | 431.0473 | 26724
20630 | 406.5101 | 26724
20631 | 410.1152 | 26724
20632 | 409.3488 | 26724
20633 | 407.6161 | 26724
20634 | 424.3866 | 26724
20635 | 400.681 | 26724
20636 | 415.7671 | 26724
20637 | 411.6614 | 26724
20638 | 408.1021 | 26724
20639 | 422.2903 | 26724
20640 | 417.9923 | 26724
20641 | 429.3216 | 26724
20642 | 412.0244 | 26724
20643 | 401.301 | 26724
20644 | 412.6196 | 26724
20645 | 422.7459 | 26724
20646 | 416.4986 | 26724
20647 | 405.7029 | 26724
20648 | 395.0335 | 26724
20649 | 422.4626 | 26724
20650 | 429.6698 | 26724
20651 | 406.8431 | 26724
20652 | 421.5477 | 26724
20653 | 411.7123 | 26724
20654 | 408.7764 | 26724
20655 | 407.6715 | 26724
20656 | 429.5455 | 26724
20657 | 427.4999 | 26724
20658 | 412.0081 | 26724
20659 | 426.0536 | 26724
20660 | 425.6442 | 26724
20661 | 422.0335 | 26724
20662 | 414.1349 | 26724
20663 | 410.1942 | 26724
20664 | 422.9122 | 26724
20665 | 421.3413 | 26724
20666 | 404.2983 | 26724
20667 | 406.6826 | 26724
20668 | 417.7759 | 26724
20669 | 425.2001 | 26724
20670 | 419.1188 | 26724
20671 | 407.3273 | 26724
20672 | 428.6814 | 26724
20673 | 431.0629 | 26724
20674 | 419.1924 | 26724
20675 | 428.7835 | 26724
20676 | 421.0174 | 26724
20677 | 424.2115 | 26724
20678 | 407.0716 | 26724
20679 | 413.4175 | 26724
20680 | 418.5285 | 26724
20681 | 409.4315 | 26724
20682 | 421.2464 | 26724
20683 | 421.0947 | 26724
20684 | 423.3355 | 26724
20685 | 425.2438 | 26724
20686 | 414.4828 | 26724
20687 | 433.4346 | 26724
20688 | 417.5535 | 26724
20689 | 405.7539 | 26724
20690 | 420.6331 | 26724
20691 | 419.574 | 26724
20692 | 409.3107 | 26724
20693 | 427.0543 | 26724
20694 | 409.9034 | 26724
20695 | 410.2677 | 26724
20696 | 432.4125 | 26724
20697 | 405.0191 | 26724
20698 | 405.7063 | 26724
20699 | 424.7468 | 26724
20700 | 415.2099 | 26724
20701 | 436.2122 | 26724
20702 | 415.7155 | 26724
20703 | 409.4592 | 26724
20704 | 398.0266 | 26724
20705 | 412.1799 | 26724
20706 | 412.4256 | 26724
20707 | 429.3986 | 26724
20708 | 408.7617 | 26724
20709 | 414.6527 | 26724
20710 | 431.4052 | 26724
20711 | 418.0214 | 26724
20712 | 424.0608 | 26724
20713 | 433.8575 | 26724
20714 | 421.9963 | 26724
20715 | 411.0831 | 26724
20716 | 429.4416 | 26724
20717 | 421.9104 | 26724
20718 | 413.1056 | 26724
20719 | 410.8884 | 26724
20720 | 408.88 | 26724
20721 | 421.4838 | 26724
20722 | 431.1869 | 26724
20723 | 429.8489 | 26724
20724 | 414.6164 | 26724
20725 | 416.2328 | 26724
20726 | 412.3162 | 26724
20727 | 420.6566 | 26724
20728 | 412.846 | 26724
20729 | 419.349 | 26724
20730 | 416.4408 | 26724
20731 | 428.5055 | 26724
20732 | 410.3789 | 26724
20733 | 402.5611 | 26724
20734 | 421.6555 | 26724
20735 | 421.4499 | 26724
20736 | 420.971 | 26724
20737 | 411.5785 | 26724
20738 | 421.5705 | 26724
20739 | 417.4289 | 26724
20740 | 421.8941 | 26724
20741 | 413.302 | 26724
20742 | 420.5971 | 26724
20743 | 403.1896 | 26724
20744 | 426.3253 | 26724
20745 | 421.0549 | 26724
20746 | 429.2587 | 26724
20747 | 411.4975 | 26724
20748 | 417.6391 | 26724
20749 | 421.1141 | 26724
20750 | 427.3734 | 26724
20751 | 395.796 | 26724
20752 | 408.6467 | 26724
20753 | 404.8268 | 26724
20754 | 407.6961 | 26724
20755 | 403.9249 | 26724
20756 | 402.3119 | 26724
20757 | 416.306 | 26724
20758 | 419.9997 | 26724
20759 | 399.4342 | 26724
20760 | 414.342 | 26724
20761 | 422.5351 | 26724
20762 | 405.1491 | 26724
20763 | 415.7745 | 26724
20764 | 425.2022 | 26724
20765 | 415.6135 | 26724
20766 | 417.4084 | 26724
20767 | 427.4935 | 26724
20768 | 405.81 | 26724
20769 | 423.7044 | 26724
20770 | 410.015 | 26724
20771 | 400.4244 | 26724
20772 | 425.2024 | 26724
20773 | 425.1872 | 26724
20774 | 412.0188 | 26724
20775 | 425.0529 | 26724
20776 | 417.5007 | 26724
20777 | 425.8047 | 26724
20778 | 411.9513 | 26724
20779 | 409.9236 | 26724
20780 | 420.1286 | 26724
20781 | 411.9399 | 26724
20782 | 426.2974 | 26724
20783 | 409.7016 | 26724
20784 | 407.0328 | 26724
20785 | 416.8773 | 26724
20786 | 418.8938 | 26724
20787 | 394.5751 | 26724
20788 | 420.3023 | 26724
20789 | 424.7685 | 26724
20790 | 415.6198 | 26724
20791 | 419.9142 | 26724
20792 | 414.7001 | 26724
20793 | 406.5983 | 26724
20794 | 410.1311 | 26724
20795 | 414.8226 | 26724
20796 | 405.7774 | 26724
20797 | 420.5252 | 26724
20798 | 416.3706 | 26724
20799 | 420.3355 | 26724
20800 | 407.2651 | 26724
20801 | 413.2997 | 26724
20802 | 422.5713 | 26724
20803 | 402.6904 | 26724
20804 | 418.0714 | 26724
20805 | 423.611 | 26724
20806 | 416.1517 | 26724
20807 | 414.195 | 26724
20808 | 416.0636 | 26724
20809 | 411.1789 | 26724
20810 | 410.1244 | 26724
20811 | 409.9439 | 26724
20812 | 403.5051 | 26724
20813 | 415.7344 | 26724
20814 | 422.0304 | 26724
20815 | 417.3815 | 26724
20816 | 413.2337 | 26724
20817 | 411.6114 | 26724
20818 | 425.1326 | 26724
20819 | 405.1861 | 26724
20820 | 416.1071 | 26724
20821 | 427.793 | 26724
20822 | 410.2851 | 26724
20823 | 407.568 | 26724
20824 | 398.9235 | 26724
20825 | 410.0787 | 26724
20826 | 415.1102 | 26724
20827 | 418.9812 | 26724
20828 | 430.1577 | 26724
20829 | 398.2894 | 26724
20830 | 424.6535 | 26724
20831 | 413.8173 | 26724
20832 | 424.9476 | 26724
20833 | 424.5168 | 26724
20834 | 411.7333 | 26724
20835 | 428.4141 | 26724
20836 | 422.561 | 26724
20837 | 400.458 | 26724
20838 | 421.688 | 26724
20839 | 407.753 | 26724
20840 | 425.0677 | 26724
20841 | 411.4695 | 26724
20842 | 426.9978 | 26724
20843 | 418.5866 | 26724
20844 | 417.0431 | 26724
20845 | 418.6858 | 26724
20846 | 423.89 | 26724
20847 | 421.6229 | 26724
20848 | 430.7023 | 26724
20849 | 418.9312 | 26724
20850 | 419.3054 | 26724
20851 | 423.1291 | 26724
20852 | 414.8132 | 26724
20853 | 402.7098 | 26724
20854 | 406.4755 | 26724
20855 | 417.4063 | 26724
20856 | 421.2693 | 26724
20857 | 415.6457 | 26724
20858 | 408.596 | 26724
20859 | 427.4418 | 26724
20860 | 428.9967 | 26724
20861 | 421.3138 | 26724
20862 | 420.4687 | 26724
20863 | 421.0854 | 26724
20864 | 420.9052 | 26724
20865 | 414.9936 | 26724
20866 | 439.9186 | 26724
20867 | 414.8212 | 26724
20868 | 415.4049 | 26724
20869 | 412.867 | 26724
20870 | 419.5347 | 26724
20871 | 425.8843 | 26724
20872 | 421.5298 | 26724
20873 | 413.8826 | 26724
20874 | 404.4385 | 26724
20875 | 416.8823 | 26724
20876 | 427.5215 | 26724
20877 | 410.9288 | 26724
20878 | 408.1186 | 26724
20879 | 412.3038 | 26724
20880 | 414.4954 | 26724
20881 | 416.0856 | 26724
20882 | 413.8737 | 26724
20883 | 418.1302 | 26724
20884 | 401.7531 | 26724
20885 | 419.4676 | 26724
20886 | 417.007 | 26724
20887 | 409.3107 | 26724
20888 | 418.51 | 26724
20889 | 410.0388 | 26724
20890 | 430.7801 | 26724
20891 | 417.4538 | 26724
20892 | 428.2493 | 26724
20893 | 411.1395 | 26724
20894 | 425.3715 | 26724
20895 | 413.1024 | 26724
20896 | 431.8521 | 26724
20897 | 416.9876 | 26724
20898 | 430.2588 | 26724
20899 | 404.8441 | 26724
20900 | 419.4045 | 26724
20901 | 409.2181 | 26724
20902 | 409.905 | 26724
20903 | 410.8726 | 26724
20904 | 430.3338 | 26724
20905 | 410.1039 | 26724
20906 | 411.1485 | 26724
20907 | 420.9924 | 26724
20908 | 416.0011 | 26724
20909 | 421.4172 | 26724
20910 | 407.7312 | 26724
20911 | 408.6755 | 26724
20912 | 420.2949 | 26724
20913 | 407.7303 | 26724
20914 | 411.7538 | 26724
20915 | 427.8234 | 26724
20916 | 420.2074 | 26724
20917 | 415.4519 | 26724
20918 | 402.4611 | 26724
20919 | 411.4265 | 26724
20920 | 409.2825 | 26724
20921 | 398.0683 | 26724
20922 | 424.5059 | 26724
20923 | 402.3679 | 26724
20924 | 416.0386 | 26724
20925 | 413.1266 | 26724
20926 | 424.077 | 26724
20927 | 407.5524 | 26724
20928 | 409.2978 | 26724
20929 | 404.1913 | 26724
20930 | 424.7461 | 26724
20931 | 407.8366 | 26724
20932 | 408.2229 | 26724
20933 | 407.8312 | 26724
20934 | 410.0881 | 26724
20935 | 404.1919 | 26724
20936 | 422.3714 | 26724
20937 | 411.8594 | 26724
20938 | 424.7529 | 26724
20939 | 416.5833 | 26724
20940 | 412.3791 | 26724
20941 | 431.1225 | 26724
20942 | 406.4991 | 26724
20943 | 415.5548 | 26724
20944 | 403.5877 | 26724
20945 | 413.5056 | 26724
20946 | 428.9466 | 26724
20947 | 402.4717 | 26724
20948 | 415.831 | 26724
20949 | 429.3395 | 26724
20950 | 416.3274 | 26724
20951 | 426.9958 | 26724
20952 | 419.8545 | 26724
20953 | 424.8997 | 26724
20954 | 408.2127 | 26724
20955 | 416.9831 | 26724
20956 | 415.6092 | 26724
20957 | 417.2919 | 26724
20958 | 412.2744 | 26724
20959 | 406.1788 | 26724
20960 | 412.3529 | 26724
20961 | 421.9026 | 26724
20962 | 417.4152 | 26724
20963 | 415.1653 | 26724
20964 | 416.6197 | 26724
20965 | 425.0095 | 26724
20966 | 422.0535 | 26724
20967 | 415.3182 | 26724
20968 | 418.3902 | 26724
20969 | 421.5521 | 26724
20970 | 404.8904 | 26724
20971 | 408.0728 | 26724
20972 | 429.0144 | 26724
20973 | 424.3821 | 26724
20974 | 423.6679 | 26724
20975 | 420.077 | 26724
20976 | 422.5419 | 26724
20977 | 429.5115 | 26724
20978 | 417.0043 | 26724
20979 | 406.4891 | 26724
20980 | 419.8998 | 26724
20981 | 421.2114 | 26724
20982 | 415.9954 | 26724
20983 | 412.7111 | 26724
20984 | 419.0031 | 26724
20985 | 428.0035 | 26724
20986 | 425.5318 | 26724
20987 | 425.3896 | 26724
20988 | 420.8346 | 26724
20989 | 415.0349 | 26724
20990 | 406.3628 | 26724
20991 | 414.0886 | 26724
20992 | 411.2015 | 26724
20993 | 417.7919 | 26724
20994 | 415.632 | 26724
20995 | 411.2308 | 26724
20996 | 419.2738 | 26724
20997 | 418.7478 | 26724
20998 | 416.7207 | 26724
20999 | 421.8768 | 26724
21000 | 417.32 | 26724
21001 | 420.9723 | 26724
21002 | 410.4478 | 26724
21003 | 412.2817 | 26724
21004 | 399.9958 | 26724
21005 | 412.4055 | 26724
21006 | 418.4119 | 26724
21007 | 413.5957 | 26724
21008 | 421.8879 | 26724
21009 | 419.7018 | 26724
21010 | 418.0772 | 26724
21011 | 435.4399 | 26724
21012 | 419.3947 | 26724
21013 | 425.2996 | 26724
21014 | 410.4835 | 26724
21015 | 436.592 | 26724
21016 | 426.5768 | 26724
21017 | 416.3632 | 26724
21018 | 422.3574 | 26724
21019 | 421.2494 | 26724
21020 | 422.0926 | 26724
21021 | 420.1233 | 26724
21022 | 434.3757 | 26724
21023 | 406.9703 | 26724
21024 | 412.536 | 26724
21025 | 415.8593 | 26724
21026 | 418.0174 | 26724
21027 | 418.8142 | 26724
21028 | 417.4337 | 26724
21029 | 421.8965 | 26724
21030 | 416.6723 | 26724
21031 | 421.3955 | 26724
21032 | 402.1184 | 26724
21033 | 409.4335 | 26724
21034 | 407.7944 | 26724
21035 | 420.3978 | 26724
21036 | 422.2354 | 26724
21037 | 434.101 | 26724
21038 | 401.2975 | 26724
21039 | 424.1612 | 26724
21040 | 414.4272 | 26724
21041 | 405.9921 | 26724
21042 | 412.9932 | 26724
21043 | 417.9346 | 26724
21044 | 418.8011 | 26724
21045 | 412.7356 | 26724
21046 | 422.7335 | 26724
21047 | 426.3017 | 26724
21048 | 408.7874 | 26724
21049 | 416.1787 | 26724
21050 | 409.9244 | 26724
21051 | 418.3318 | 26724
21052 | 424.8287 | 26724
21053 | 418.6136 | 26724
21054 | 422.6281 | 26724
21055 | 417.8046 | 26724
21056 | 417.8261 | 26724
21057 | 411.0166 | 26724
21058 | 409.4551 | 26724
21059 | 421.8107 | 26724
21060 | 419.6171 | 26724
21061 | 412.8339 | 26724
21062 | 417.4078 | 26724
21063 | 416.7216 | 26724
21064 | 419.8353 | 26724
21065 | 400.0641 | 26724
21066 | 419.3666 | 26724
21067 | 419.2005 | 26724
21068 | 428.4449 | 26724
21069 | 411.1512 | 26724
21070 | 413.5374 | 26724
21071 | 414.2632 | 26724
21072 | 407.8564 | 26724
21073 | 412.9582 | 26724
21074 | 413.6789 | 26724
21075 | 420.1008 | 26724
21076 | 410.6767 | 26724
21077 | 418.5883 | 26724
21078 | 423.1215 | 26724
21079 | 416.3303 | 26724
21080 | 421.7934 | 26724
21081 | 413.9766 | 26724
21082 | 395.2645 | 26724
21083 | 407.9749 | 26724
21084 | 421.3705 | 26724
21085 | 436.6942 | 26724
21086 | 413.8158 | 26724
21087 | 410.2858 | 26724
21088 | 401.3787 | 26724
21089 | 419.522 | 26724
21090 | 398.9931 | 26724
21091 | 415.8088 | 26724
21092 | 416.1362 | 26724
21093 | 414.9445 | 26724
21094 | 428.2161 | 26724
21095 | 413.1784 | 26724
21096 | 421.2012 | 26724
21097 | 414.0043 | 26724
21098 | 409.9053 | 26724
21099 | 412.57 | 26724
21100 | 414.4098 | 26724
21101 | 418.956 | 26724
21102 | 421.5417 | 26724
21103 | 403.0661 | 26724
21104 | 422.676 | 26724
21105 | 416.9811 | 26724
21106 | 404.7493 | 26724
21107 | 419.7375 | 26724
21108 | 406.8362 | 26724
21109 | 410.5095 | 26724
21110 | 420.7599 | 26724
21111 | 412.3394 | 26724
21112 | 424.7355 | 26724
21113 | 429.8633 | 26724
21114 | 416.8489 | 26724
21115 | 419.5375 | 26724
21116 | 407.951 | 26724
21117 | 421.6477 | 26724
21118 | 421.388 | 26724
21119 | 408.4515 | 26724
21120 | 420.7628 | 26724
21121 | 430.5861 | 26724
21122 | 413.9362 | 26724
21123 | 409.3821 | 26724
21124 | 417.6058 | 26724
21125 | 416.7054 | 26724
21126 | 420.4959 | 26724
21127 | 425.8195 | 26724
21128 | 411.1406 | 26724
21129 | 430.2009 | 26724
21130 | 418.2063 | 26724
21131 | 419.6954 | 26724
21132 | 412.7054 | 26724
21133 | 408.9623 | 26724
21134 | 414.8148 | 26724
21135 | 403.3065 | 26724
21136 | 413.6663 | 26724
21137 | 424.5864 | 26724
21138 | 426.0084 | 26724
21139 | 424.0655 | 26724
21140 | 410.3941 | 26724
21141 | 419.9462 | 26724
21142 | 426.2673 | 26724
21143 | 417.7202 | 26724
21144 | 420.9668 | 26724
21145 | 424.857 | 26724
21146 | 416.4213 | 26724
21147 | 411.443 | 26724
21148 | 425.5469 | 26724
21149 | 406.5444 | 26724
21150 | 421.4299 | 26724
21151 | 427.789 | 26724
21152 | 432.5473 | 26724
21153 | 421.3856 | 26724
21154 | 429.3401 | 26724
21155 | 411.4896 | 26724
21156 | 421.3791 | 26724
21157 | 421.8967 | 26724
21158 | 409.2582 | 26724
21159 | 417.3798 | 26724
21160 | 418.593 | 26724
21161 | 426.105 | 26724
21162 | 413.3937 | 26724
21163 | 418.4433 | 26724
21164 | 430.1432 | 26724
21165 | 421.2633 | 26724
21166 | 422.5894 | 26724
21167 | 410.5712 | 26724
21168 | 404.7096 | 26724
21169 | 424.6738 | 26724
21170 | 418.3165 | 26724
21171 | 413.2598 | 26724
21172 | 422.7528 | 26724
21173 | 429.7689 | 26724
21174 | 423.12 | 26724
21175 | 405.5419 | 26724
21176 | 411.419 | 26724
21177 | 413.681 | 26724
21178 | 417.7908 | 26724
21179 | 431.2373 | 26724
21180 | 416.2215 | 26724
21181 | 411.3009 | 26724
21182 | 412.7693 | 26724
21183 | 420.2894 | 26724
21184 | 414.9149 | 26724
21185 | 406.444 | 26724
21186 | 425.3586 | 26724
21187 | 410.043 | 26724
21188 | 418.2746 | 26724
21189 | 423.7401 | 26724
21190 | 417.8113 | 26724
21191 | 408.2124 | 26724
21192 | 417.8776 | 26724
21193 | 413.8091 | 26724
21194 | 417.1847 | 26724
21195 | 419.8488 | 26724
21196 | 423.1524 | 26724
21197 | 404.6941 | 26724
21198 | 413.3577 | 26724
21199 | 415.676 | 26724
21200 | 418.3838 | 26724
21201 | 399.0867 | 26724
21202 | 432.7785 | 26724
21203 | 411.1885 | 26724
21204 | 406.1507 | 26724
21205 | 412.4873 | 26724
21206 | 406.3398 | 26724
21207 | 420.7225 | 26724
21208 | 408.8372 | 26724
21209 | 410.247 | 26724
21210 | 424.1065 | 26724
21211 | 424.0944 | 26724
21212 | 419.0321 | 26724
21213 | 420.8755 | 26724
21214 | 402.5949 | 26724
21215 | 398.8429 | 26724
21216 | 430.558 | 26724
21217 | 425.9837 | 26724
21218 | 415.8435 | 26724
21219 | 432.428 | 26724
21220 | 429.7749 | 26724
21221 | 418.2585 | 26724
21222 | 407.9412 | 26724
21223 | 422.4757 | 26724
21224 | 416.5262 | 26724
21225 | 417.6287 | 26724
21226 | 405.1772 | 26724
21227 | 426.5739 | 26724
21228 | 419.043 | 26724
21229 | 399.868 | 26724
21230 | 423.6635 | 26724
21231 | 422.0197 | 26724
21232 | 407.1455 | 26724
21233 | 429.6604 | 26724
21234 | 401.7307 | 26724
21235 | 422.789 | 26724
21236 | 405.5884 | 26724
21237 | 419.4224 | 26724
21238 | 426.6393 | 26724
21239 | 424.3391 | 26724
21240 | 410.972 | 26724
21241 | 421.4819 | 26724
21242 | 398.9597 | 26724
21243 | 416.9545 | 26724
21244 | 423.2747 | 26724
21245 | 405.4747 | 26724
21246 | 421.3886 | 26724
21247 | 429.6147 | 26724
21248 | 412.2133 | 26724
21249 | 415.2582 | 26724
21250 | 429.6673 | 26724
21251 | 402.5601 | 26724
21252 | 414.8431 | 26724
21253 | 432.7103 | 26724
21254 | 418.2345 | 26724
21255 | 420.8514 | 26724
21256 | 430.4789 | 26724
21257 | 417.3778 | 26724
21258 | 423.6649 | 26724
21259 | 428.6966 | 26724
21260 | 426.3965 | 26724
21261 | 425.2682 | 26724
21262 | 413.262 | 26724
21263 | 422.7162 | 26724
21264 | 417.6853 | 26724
21265 | 416.5125 | 26724
21266 | 424.8402 | 26724
21267 | 408.2379 | 26724
21268 | 412.2907 | 26724
21269 | 409.819 | 26724
21270 | 414.4532 | 26724
21271 | 409.8889 | 26724
21272 | 424.7262 | 26724
21273 | 428.0094 | 26724
21274 | 415.874 | 26724
21275 | 419.5078 | 26724
21276 | 402.5027 | 26724
21277 | 432.3072 | 26724
21278 | 421.2052 | 26724
21279 | 416.291 | 26724
21280 | 417.1963 | 26724
21281 | 420.9949 | 26724
21282 | 421.5693 | 26724
21283 | 421.5092 | 26724
21284 | 414.5939 | 26724
21285 | 415.7481 | 26724
21286 | 425.314 | 26724
21287 | 420.1002 | 26724
21288 | 417.6397 | 26724
21289 | 416.7751 | 26724
21290 | 429.8946 | 26724
21291 | 407.872 | 26724
21292 | 427.4481 | 26724
21293 | 419.8877 | 26724
21294 | 421.7112 | 26724
21295 | 429.0958 | 26724
21296 | 416.3317 | 26724
21297 | 430.3168 | 26724
21298 | 406.9406 | 26724
21299 | 421.1149 | 26724
21300 | 398.6889 | 26724
21301 | 412.3349 | 26724
21302 | 416.5248 | 26724
21303 | 428.0957 | 26724
21304 | 410.8581 | 26724
21305 | 419.8621 | 26724
21306 | 420.2378 | 26724
21307 | 423.1727 | 26724
21308 | 420.1779 | 26724
21309 | 423.12 | 26724
21310 | 423.6235 | 26724
21311 | 417.092 | 26724
21312 | 425.6387 | 26724
21313 | 413.8947 | 26724
21314 | 422.9143 | 26724
21315 | 414.571 | 26724
21316 | 419.5607 | 26724
21317 | 412.562 | 26724
21318 | 416.5501 | 26724
21319 | 408.3563 | 26724
21320 | 415.7802 | 26724
21321 | 417.3667 | 26724
21322 | 424.3242 | 26724
21323 | 422.2508 | 26724
21324 | 419.5598 | 26724
21325 | 401.2636 | 26724
21326 | 416.3253 | 26724
21327 | 404.9046 | 26724
21328 | 407.7697 | 26724
21329 | 419.0951 | 26724
21330 | 416.2155 | 26724
21331 | 431.8312 | 26724
21332 | 412.1088 | 26724
21333 | 414.5018 | 26724
21334 | 419.6634 | 26724
21335 | 415.1185 | 26724
21336 | 408.2636 | 26724
21337 | 423.8722 | 26724
21338 | 411.6272 | 26724
21339 | 424.1242 | 26724
21340 | 411.5535 | 26724
21341 | 419.531 | 26724
21342 | 412.7128 | 26724
21343 | 424.1458 | 26724
21344 | 400.9787 | 26724
21345 | 419.104 | 26724
21346 | 426.9293 | 26724
21347 | 410.4315 | 26724
21348 | 410.8935 | 26724
21349 | 421.8279 | 26724
21350 | 421.0066 | 26724
21351 | 407.9444 | 26724
21352 | 415.8959 | 26724
21353 | 411.1373 | 26724
21354 | 413.9892 | 26724
21355 | 433.3936 | 26724
21356 | 424.3814 | 26724
21357 | 410.5928 | 26724
21358 | 424.3154 | 26724
21359 | 408.5727 | 26724
21360 | 409.3572 | 26724
21361 | 409.1369 | 26724
21362 | 404.3791 | 26724
21363 | 400.6306 | 26724
21364 | 411.2531 | 26724
21365 | 399.6629 | 26724
21366 | 407.56 | 26724
21367 | 407.05 | 26724
21368 | 405.8795 | 26724
21369 | 404.5778 | 26724
21370 | 404.5542 | 26724
21371 | 402.0662 | 26724
21372 | 407.4348 | 26724
21373 | 420.1897 | 26724
21374 | 422.5043 | 26724
21375 | 430.2234 | 26724
21376 | 431.1948 | 26724
21377 | 406.0828 | 26724
21378 | 415.6983 | 26724
21379 | 426.2983 | 26724
21380 | 405.7789 | 26724
21381 | 407.8158 | 26724
21382 | 424.6503 | 26724
21383 | 423.9691 | 26724
21384 | 422.6506 | 26724
21385 | 413.0515 | 26724
21386 | 418.0322 | 26724
21387 | 413.4088 | 26724
21388 | 412.5909 | 26724
21389 | 427.9139 | 26724
21390 | 434.0197 | 26724
21391 | 405.3744 | 26724
21392 | 430.5515 | 26724
21393 | 418.0481 | 26724
21394 | 414.2101 | 26724
21395 | 420.9001 | 26724
21396 | 420.1224 | 26724
21397 | 420.1513 | 26724
21398 | 423.4174 | 26724
21399 | 420.4746 | 26724
21400 | 420.3239 | 26724
21401 | 426.9691 | 26724
21402 | 425.7931 | 26724
21403 | 414.3678 | 26724
21404 | 405.7802 | 26724
21405 | 422.278 | 26724
21406 | 417.7541 | 26724
21407 | 421.9759 | 26724
21408 | 427.747 | 26724
21409 | 410.1043 | 26724
21410 | 420.8368 | 26724
21411 | 424.5239 | 26724
21412 | 418.8321 | 26724
21413 | 417.3979 | 26724
21414 | 405.8026 | 26724
21415 | 425.4273 | 26724
21416 | 411.4025 | 26724
21417 | 418.8528 | 26724
21418 | 408.866 | 26724
21419 | 414.273 | 26724
21420 | 405.7855 | 26724
21421 | 415.9694 | 26724
21422 | 407.8463 | 26724
21423 | 416.194 | 26724
21424 | 417.1536 | 26724
21425 | 413.8939 | 26724
21426 | 417.5847 | 26724
21427 | 409.6193 | 26724
21428 | 415.4115 | 26724
21429 | 426.5161 | 26724
21430 | 413.8346 | 26724
21431 | 413.8914 | 26724
21432 | 418.2738 | 26724
21433 | 419.2998 | 26724
21434 | 404.5328 | 26724
21435 | 404.6426 | 26724
21436 | 405.4037 | 26724
21437 | 418.1486 | 26724
21438 | 407.9335 | 26724
21439 | 422.0461 | 26724
21440 | 422.692 | 26724
21441 | 416.915 | 26724
21442 | 425.8728 | 26724
21443 | 414.2392 | 26724
21444 | 412.3508 | 26724
21445 | 413.44 | 26724
21446 | 422.8131 | 26724
21447 | 407.9695 | 26724
21448 | 410.6431 | 26724
21449 | 431.0948 | 26724
21450 | 410.7867 | 26724
21451 | 408.02 | 26724
21452 | 414.2582 | 26724
21453 | 423.5845 | 26724
21454 | 412.0317 | 26724
21455 | 410.9393 | 26724
21456 | 435.7773 | 26724
21457 | 426.466 | 26724
21458 | 431.426 | 26724
21459 | 405.0977 | 26724
21460 | 433.5499 | 26724
21461 | 417.8374 | 26724
21462 | 419.1792 | 26724
21463 | 427.9403 | 26724
21464 | 418.9859 | 26724
21465 | 418.2351 | 26724
21466 | 422.8005 | 26724
21467 | 418.211 | 26724
21468 | 421.3275 | 26724
21469 | 410.6262 | 26724
21470 | 418.4935 | 26724
21471 | 418.2692 | 26724
21472 | 433.7065 | 26724
21473 | 423.188 | 26724
21474 | 401.8778 | 26724
21475 | 413.4735 | 26724
21476 | 414.2737 | 26724
21477 | 424.9206 | 26724
21478 | 426.686 | 26724
21479 | 417.9238 | 26724
21480 | 411.7624 | 26724
21481 | 414.864 | 26724
21482 | 424.9039 | 26724
21483 | 412.4481 | 26724
21484 | 419.5672 | 26724
21485 | 412.6572 | 26724
21486 | 405.0643 | 26724
21487 | 436.8009 | 26724
21488 | 418.248 | 26724
21489 | 421.8591 | 26724
21490 | 402.6131 | 26724
21491 | 421.6148 | 26724
21492 | 423.407 | 26724
21493 | 418.2359 | 26724
21494 | 426.5211 | 26724
21495 | 415.9372 | 26724
21496 | 404.6375 | 26724
21497 | 429.9161 | 26724
21498 | 419.8193 | 26724
21499 | 403.753 | 26724
21500 | 417.4508 | 26724
21501 | 417.0291 | 26724
21502 | 420.962 | 26724
21503 | 416.5845 | 26724
21504 | 421.4088 | 26724
21505 | 414.7798 | 26724
21506 | 427.8231 | 26724
21507 | 405.1314 | 26724
21508 | 437.9861 | 26724
21509 | 407.9108 | 26724
21510 | 418.8616 | 26724
21511 | 402.1233 | 26724
21512 | 409.0764 | 26724
21513 | 414.577 | 26724
21514 | 422.3313 | 26724
21515 | 418.0634 | 26724
21516 | 425.0848 | 26724
21517 | 399.0278 | 26724
21518 | 413.7342 | 26724
21519 | 403.7903 | 26724
21520 | 436.0202 | 26724
21521 | 397.924 | 26724
21522 | 408.1339 | 26724
21523 | 404.6395 | 26724
21524 | 430.0659 | 26724
21525 | 420.8423 | 26724
21526 | 421.6599 | 26724
21527 | 407.1011 | 26724
21528 | 398.9331 | 26724
21529 | 417.8111 | 26724
21530 | 419.7205 | 26724
21531 | 413.8087 | 26724
21532 | 425.8559 | 26724
21533 | 429.2322 | 26724
21534 | 423.8352 | 26724
21535 | 415.8885 | 26724
21536 | 425.1936 | 26724
21537 | 420.542 | 26724
21538 | 422.466 | 26724
21539 | 410.2534 | 26724
21540 | 422.288 | 26724
21541 | 421.9503 | 26724
21542 | 419.5725 | 26724
21543 | 409.2643 | 26724
21544 | 420.7622 | 26724
21545 | 420.0614 | 26724
21546 | 420.8465 | 26724
21547 | 414.1775 | 26724
21548 | 418.883 | 26724
21549 | 408.8954 | 26724
21550 | 419.6837 | 26724
21551 | 418.8568 | 26724
21552 | 421.0396 | 26724
21553 | 420.6411 | 26724
21554 | 417.1441 | 26724
21555 | 399.9333 | 26724
21556 | 410.1553 | 26724
21557 | 427.0649 | 26724
21558 | 405.7034 | 26724
21559 | 418.4816 | 26724
21560 | 422.258 | 26724
21561 | 418.7954 | 26724
21562 | 418.7775 | 26724
21563 | 418.3985 | 26724
21564 | 429.12 | 26724
21565 | 414.6651 | 26724
21566 | 412.9144 | 26724
21567 | 414.3174 | 26724
21568 | 406.9122 | 26724
21569 | 425.5169 | 26724
21570 | 415.3109 | 26724
21571 | 412.0586 | 26724
21572 | 412.18 | 26724
21573 | 402.9565 | 26724
21574 | 413.4849 | 26724
21575 | 411.9804 | 26724
21576 | 407.9952 | 26724
21577 | 423.0465 | 26724
21578 | 412.4043 | 26724
21579 | 413.2319 | 26724
21580 | 420.6376 | 26724
21581 | 422.7774 | 26724
21582 | 406.2986 | 26724
21583 | 415.2362 | 26724
21584 | 407.4918 | 26724
21585 | 428.9617 | 26724
21586 | 403.8234 | 26724
21587 | 435.0028 | 26724
21588 | 419.4818 | 26724
21589 | 411.1713 | 26724
21590 | 425.3102 | 26724
21591 | 428.5864 | 26724
21592 | 416.5615 | 26724
21593 | 427.4401 | 26724
21594 | 414.3195 | 26724
21595 | 407.742 | 26724
21596 | 417.0057 | 26724
21597 | 416.1394 | 26724
21598 | 422.7117 | 26724
21599 | 410.1732 | 26724
21600 | 409.6928 | 26724
21601 | 431.2628 | 26724
21602 | 409.4527 | 26724
21603 | 420.7227 | 26724
21604 | 410.6063 | 26724
21605 | 414.8971 | 26724
21606 | 419.4543 | 26724
21607 | 414.5204 | 26724
21608 | 407.7304 | 26724
21609 | 403.1396 | 26724
21610 | 417.6502 | 26724
21611 | 429.5551 | 26724
21612 | 424.9575 | 26724
21613 | 407.0316 | 26724
21614 | 415.0217 | 26724
21615 | 417.1803 | 26724
21616 | 417.7931 | 26724
21617 | 412.0887 | 26724
21618 | 412.1067 | 26724
21619 | 417.6882 | 26724
21620 | 417.5692 | 26724
21621 | 425.5766 | 26724
21622 | 432.8936 | 26724
21623 | 415.1526 | 26724
21624 | 407.6937 | 26724
21625 | 409.7175 | 26724
21626 | 400.3427 | 26724
21627 | 430.1746 | 26724
21628 | 414.5421 | 26724
21629 | 421.2771 | 26724
21630 | 398.8137 | 26724
21631 | 418.2806 | 26724
21632 | 419.0288 | 26724
21633 | 408.2465 | 26724
21634 | 404.1911 | 26724
21635 | 400.2329 | 26724
21636 | 419.312 | 26724
21637 | 410.696 | 26724
21638 | 423.5337 | 26724
21639 | 408.5549 | 26724
21640 | 415.3013 | 26724
21641 | 400.1276 | 26724
21642 | 415.4292 | 26724
21643 | 410.7966 | 26724
21644 | 410.9991 | 26724
21645 | 418.462 | 26724
21646 | 423.0577 | 26724
21647 | 416.2823 | 26724
21648 | 406.9801 | 26724
21649 | 415.9439 | 26724
21650 | 412.4607 | 26724
21651 | 419.8155 | 26724
21652 | 413.4235 | 26724
21653 | 405.8983 | 26724
21654 | 415.9749 | 26724
21655 | 421.3837 | 26724
21656 | 425.1903 | 26724
21657 | 411.7247 | 26724
21658 | 408.2455 | 26724
21659 | 422.1859 | 26724
21660 | 410.5135 | 26724
21661 | 432.1248 | 26724
21662 | 405.0111 | 26724
21663 | 414.9225 | 26724
21664 | 426.4369 | 26724
21665 | 406.1654 | 26724
21666 | 416.6087 | 26724
21667 | 420.76 | 26724
21668 | 416.3641 | 26724
21669 | 422.0263 | 26724
21670 | 419.185 | 26724
21671 | 432.5171 | 26724
21672 | 409.6853 | 26724
21673 | 418.9166 | 26724
21674 | 418.7824 | 26724
21675 | 420.1052 | 26724
21676 | 413.5794 | 26724
21677 | 411.1731 | 26724
21678 | 412.6131 | 26724
21679 | 415.4495 | 26724
21680 | 412.3062 | 26724
21681 | 406.4252 | 26724
21682 | 409.4235 | 26724
21683 | 424.6012 | 26724
21684 | 396.9828 | 26724
21685 | 413.0952 | 26724
21686 | 403.0402 | 26724
21687 | 410.1308 | 26724
21688 | 414.5203 | 26724
21689 | 413.3305 | 26724
21690 | 429.3038 | 26724
21691 | 407.8198 | 26724
21692 | 419.4217 | 26724
21693 | 419.5363 | 26724
21694 | 428.3858 | 26724
21695 | 418.5141 | 26724
21696 | 407.2738 | 26724
21697 | 403.1358 | 26724
21698 | 416.909 | 26724
21699 | 415.7557 | 26724
21700 | 418.6679 | 26724
21701 | 412.5393 | 26724
21702 | 419.3156 | 26724
21703 | 417.6189 | 26724
21704 | 419.0335 | 26724
21705 | 417.5769 | 26724
21706 | 420.5201 | 26724
21707 | 410.3496 | 26724
21708 | 407.5049 | 26724
21709 | 422.3798 | 26724
21710 | 425.8012 | 26724
21711 | 415.708 | 26724
21712 | 425.011 | 26724
21713 | 427.2942 | 26724
21714 | 418.8586 | 26724
21715 | 411.1275 | 26724
21716 | 405.697 | 26724
21717 | 423.6185 | 26724
21718 | 431.0437 | 26724
21719 | 409.8792 | 26724
21720 | 426.2567 | 26724
21721 | 419.2813 | 26724
21722 | 422.7781 | 26724
21723 | 414.0337 | 26724
21724 | 422.5225 | 26724
21725 | 415.0746 | 26724
21726 | 424.7427 | 26724
21727 | 410.2331 | 26724
21728 | 418.4105 | 26724
21729 | 429.836 | 26724
21730 | 417.7412 | 26724
21731 | 424.015 | 26724
21732 | 411.8283 | 26724
21733 | 405.2399 | 26724
21734 | 422.2781 | 26724
21735 | 418.5633 | 26724
21736 | 421.0419 | 26724
21737 | 417.9076 | 26724
21738 | 415.2414 | 26724
21739 | 417.7864 | 26724
21740 | 414.8762 | 26724
21741 | 416.8191 | 26724
21742 | 419.4332 | 26724
21743 | 423.2856 | 26724
21744 | 423.1491 | 26724
21745 | 410.3516 | 26724
21746 | 410.7083 | 26724
21747 | 422.4344 | 26724
21748 | 426.5592 | 26724
21749 | 416.5431 | 26724
21750 | 425.6754 | 26724
21751 | 424.387 | 26724
21752 | 412.8804 | 26724
21753 | 417.3148 | 26724
21754 | 414.1783 | 26724
21755 | 420.7472 | 26724
21756 | 420.2032 | 26724
21757 | 422.8659 | 26724
21758 | 408.3284 | 26724
21759 | 409.26 | 26724
21760 | 397.562 | 26724
21761 | 426.9813 | 26724
21762 | 409.6699 | 26724
21763 | 412.6279 | 26724
21764 | 415.8491 | 26724
21765 | 429.1653 | 26724
21766 | 428.0199 | 26724
21767 | 410.1056 | 26724
21768 | 406.9296 | 26724
21769 | 413.1968 | 26724
21770 | 399.7582 | 26724
21771 | 396.2673 | 26724
21772 | 416.6506 | 26724
21773 | 401.6904 | 26724
21774 | 410.6896 | 26724
21775 | 407.9326 | 26724
21776 | 436.3098 | 26724
21777 | 406.7697 | 26724
21778 | 411.6005 | 26724
21779 | 427.3601 | 26724
21780 | 415.9524 | 26724
21781 | 417.2733 | 26724
21782 | 412.4874 | 26724
21783 | 417.4538 | 26724
21784 | 410.7661 | 26724
21785 | 432.3376 | 26724
21786 | 416.0824 | 26724
21787 | 428.5279 | 26724
21788 | 427.1831 | 26724
21789 | 425.5254 | 26724
21790 | 406.1796 | 26724
21791 | 405.4262 | 26724
21792 | 428.1002 | 26724
21793 | 412.1239 | 26724
21794 | 412.2164 | 26724
21795 | 413.8518 | 26724
21796 | 428.8365 | 26724
21797 | 414.4415 | 26724
21798 | 412.7029 | 26724
21799 | 416.0673 | 26724
21800 | 422.5886 | 26724
21801 | 401.5777 | 26724
21802 | 420.5814 | 26724
21803 | 404.8302 | 26724
21804 | 412.921 | 26724
21805 | 415.3425 | 26724
21806 | 416.9251 | 26724
21807 | 418.6958 | 26724
21808 | 404.5103 | 26724
21809 | 415.9636 | 26724
21810 | 420.2217 | 26724
21811 | 413.8713 | 26724
21812 | 414.9728 | 26724
21813 | 416.3856 | 26724
21814 | 406.8923 | 26724
21815 | 426.4017 | 26724
21816 | 420.4456 | 26724
21817 | 422.6556 | 26724
21818 | 395.1949 | 26724
21819 | 415.2034 | 26724
21820 | 414.106 | 26724
21821 | 409.8835 | 26724
21822 | 420.0386 | 26724
21823 | 432.8069 | 26724
21824 | 405.2328 | 26724
21825 | 414.4011 | 26724
21826 | 414.64 | 26724
21827 | 424.16 | 26724
21828 | 422.1312 | 26724
21829 | 411.1427 | 26724
21830 | 415.6284 | 26724
21831 | 418.9958 | 26724
21832 | 413.0198 | 26724
21833 | 410.3053 | 26724
21834 | 422.9484 | 26724
21835 | 426.485 | 26724
21836 | 403.5633 | 26724
21837 | 413.2498 | 26724
21838 | 407.7829 | 26724
21839 | 419.864 | 26724
21840 | 407.7292 | 26724
21841 | 432.2794 | 26724
21842 | 421.3061 | 26724
21843 | 415.6429 | 26724
21844 | 407.8192 | 26724
21845 | 412.8571 | 26724
21846 | 416.2389 | 26724
21847 | 410.3804 | 26724
21848 | 407.6419 | 26724
21849 | 435.7696 | 26724
21850 | 406.5431 | 26724
21851 | 430.3497 | 26724
21852 | 411.0219 | 26724
21853 | 417.9074 | 26724
21854 | 413.0359 | 26724
21855 | 407.69 | 26724
21856 | 419.1052 | 26724
21857 | 413.2628 | 26724
21858 | 415.6029 | 26724
21859 | 414.3342 | 26724
21860 | 405.3928 | 26724
21861 | 415.1806 | 26724
21862 | 411.7523 | 26724
21863 | 414.7971 | 26724
21864 | 410.6407 | 26724
21865 | 412.3046 | 26724
21866 | 427.1148 | 26724
21867 | 416.2564 | 26724
21868 | 426.5062 | 26724
21869 | 412.3867 | 26724
21870 | 416.0148 | 26724
21871 | 405.0208 | 26724
21872 | 409.9381 | 26724
21873 | 420.9226 | 26724
21874 | 424.2597 | 26724
21875 | 427.0945 | 26724
21876 | 415.15 | 26724
21877 | 404.5857 | 26724
21878 | 426.7457 | 26724
21879 | 409.0311 | 26724
21880 | 422.8561 | 26724
21881 | 423.247 | 26724
21882 | 406.2331 | 26724
21883 | 420.5328 | 26724
21884 | 408.9527 | 26724
21885 | 425.4153 | 26724
21886 | 400.3649 | 26724
21887 | 416.7257 | 26724
21888 | 409.7058 | 26724
21889 | 424.3699 | 26724
21890 | 414.1787 | 26724
21891 | 424.5677 | 26724
21892 | 411.0929 | 26724
21893 | 426.0586 | 26724
21894 | 419.3017 | 26724
21895 | 422.3325 | 26724
21896 | 410.7446 | 26724
21897 | 414.9781 | 26724
21898 | 415.422 | 26724
21899 | 410.7384 | 26724
21900 | 411.8666 | 26724
21901 | 415.0035 | 26724
21902 | 399.909 | 26724
21903 | 409.9407 | 26724
21904 | 412.8734 | 26724
21905 | 420.7957 | 26724
21906 | 423.7731 | 26724
21907 | 426.9343 | 26724
21908 | 415.526 | 26724
21909 | 409.5362 | 26724
21910 | 423.1278 | 26724
21911 | 428.3048 | 26724
21912 | 425.1195 | 26724
21913 | 417.0409 | 26724
21914 | 414.9939 | 26724
21915 | 411.138 | 26724
21916 | 419.1547 | 26724
21917 | 407.8323 | 26724
21918 | 419.3828 | 26724
21919 | 412.6889 | 26724
21920 | 425.5908 | 26724
21921 | 413.3436 | 26724
21922 | 425.4543 | 26724
21923 | 428.6912 | 26724
21924 | 403.7571 | 26724
21925 | 420.3092 | 26724
21926 | 413.652 | 26724
21927 | 409.4966 | 26724
21928 | 414.0029 | 26724
21929 | 431.8141 | 26724
21930 | 428.1564 | 26724
21931 | 427.6482 | 26724
21932 | 414.6902 | 26724
21933 | 412.1132 | 26724
21934 | 399.0788 | 26724
21935 | 410.1554 | 26724
21936 | 414.3721 | 26724
21937 | 404.2553 | 26724
21938 | 403.3248 | 26724
21939 | 402.5588 | 26724
21940 | 415.0249 | 26724
21941 | 412.859 | 26724
21942 | 403.484 | 26724
21943 | 419.9688 | 26724
21944 | 414.6586 | 26724
21945 | 412.2078 | 26724
21946 | 414.5447 | 26724
21947 | 416.2283 | 26724
21948 | 426.3172 | 26724
21949 | 423.4404 | 26724
21950 | 415.6924 | 26724
21951 | 403.7469 | 26724
21952 | 414.6341 | 26724
21953 | 426.65 | 26724
21954 | 418.5518 | 26724
21955 | 429.5718 | 26724
21956 | 424.0641 | 26724
21957 | 427.3359 | 26724
21958 | 411.158 | 26724
21959 | 413.7787 | 26724
21960 | 422.4187 | 26724
21961 | 413.7625 | 26724
21962 | 413.654 | 26724
21963 | 423.1316 | 26724
21964 | 413.9964 | 26724
21965 | 428.4988 | 26724
21966 | 409.8377 | 26724
21967 | 410.1932 | 26724
21968 | 410.5247 | 26724
21969 | 434.565 | 26724
21970 | 411.0552 | 26724
21971 | 404.8286 | 26724
21972 | 407.7465 | 26724
21973 | 423.5361 | 26724
21974 | 425.9119 | 26724
21975 | 432.2343 | 26724
21976 | 406.5966 | 26724
21977 | 411.7246 | 26724
21978 | 405.4925 | 26724
21979 | 413.9307 | 26724
21980 | 403.686 | 26724
21981 | 405.2393 | 26724
21982 | 438.4306 | 26724
21983 | 411.5867 | 26724
21984 | 418.4074 | 26724
21985 | 407.1352 | 26724
21986 | 406.7924 | 26724
21987 | 418.5908 | 26724
21988 | 408.1345 | 26724
21989 | 412.0547 | 26724
21990 | 426.7945 | 26724
21991 | 406.3903 | 26724
21992 | 417.0893 | 26724
21993 | 412.0042 | 26724
21994 | 411.0312 | 26724
21995 | 421.9828 | 26724
21996 | 422.1521 | 26724
21997 | 409.9348 | 26724
21998 | 415.9618 | 26724
21999 | 411.5723 | 26724
22000 | 419.1391 | 26724
22001 | 426.3444 | 26724
22002 | 418.3324 | 26724
22003 | 419.8383 | 26724
22004 | 417.4333 | 26724
22005 | 409.0816 | 26724
22006 | 413.3721 | 26724
22007 | 417.4719 | 26724
22008 | 424.7321 | 26724
22009 | 411.8961 | 26724
22010 | 423.7227 | 26724
22011 | 434.2066 | 26724
22012 | 421.7994 | 26724
22013 | 407.4273 | 26724
22014 | 393.9132 | 26724
22015 | 425.8388 | 26724
22016 | 411.2201 | 26724
22017 | 402.0924 | 26724
22018 | 424.2894 | 26724
22019 | 403.9902 | 26724
22020 | 415.8475 | 26724
22021 | 418.0814 | 26724
22022 | 424.6438 | 26724
22023 | 427.6627 | 26724
22024 | 415.0083 | 26724
22025 | 403.8613 | 26724
22026 | 422.0476 | 26724
22027 | 417.1529 | 26724
22028 | 421.7867 | 26724
22029 | 416.6003 | 26724
22030 | 405.9137 | 26724
22031 | 420.7793 | 26724
22032 | 406.4232 | 26724
22033 | 416.6626 | 26724
22034 | 406.7053 | 26724
22035 | 421.9195 | 26724
22036 | 416.0913 | 26724
22037 | 420.9103 | 26724
22038 | 425.1373 | 26724
22039 | 428.6529 | 26724
22040 | 424.2054 | 26724
22041 | 419.4647 | 26724
22042 | 421.7797 | 26724
22043 | 415.9324 | 26724
22044 | 431.9023 | 26724
22045 | 406.0249 | 26724
22046 | 405.25 | 26724
22047 | 411.1235 | 26724
22048 | 419.6188 | 26724
22049 | 421.3357 | 26724
22050 | 411.0321 | 26724
22051 | 407.9645 | 26724
22052 | 407.1298 | 26724
22053 | 424.8018 | 26724
22054 | 430.3268 | 26724
22055 | 418.8301 | 26724
22056 | 429.2529 | 26724
22057 | 424.4322 | 26724
22058 | 410.7369 | 26724
22059 | 415.125 | 26724
22060 | 413.1053 | 26724
22061 | 406.9116 | 26724
22062 | 420.8966 | 26724
22063 | 413.1165 | 26724
22064 | 428.8725 | 26724
22065 | 410.4998 | 26724
22066 | 426.7003 | 26724
22067 | 414.9031 | 26724
22068 | 405.9418 | 26724
22069 | 421.567 | 26724
22070 | 410.1378 | 26724
22071 | 401.3048 | 26724
22072 | 407.4466 | 26724
22073 | 421.8188 | 26724
22074 | 418.3701 | 26724
22075 | 423.4211 | 26724
22076 | 411.3976 | 26724
22077 | 428.6384 | 26724
22078 | 404.7511 | 26724
22079 | 436.227 | 26724
22080 | 420.2201 | 26724
22081 | 404.1735 | 26724
22082 | 411.5426 | 26724
22083 | 420.6258 | 26724
22084 | 416.2497 | 26724
22085 | 426.1799 | 26724
22086 | 419.5342 | 26724
22087 | 414.1097 | 26724
22088 | 418.8683 | 26724
22089 | 413.3101 | 26724
22090 | 420.4153 | 26724
22091 | 416.8435 | 26724
22092 | 411.6052 | 26724
22093 | 430.1589 | 26724
22094 | 410.7299 | 26724
22095 | 410.4503 | 26724
22096 | 411.9005 | 26724
22097 | 405.3629 | 26724
22098 | 416.5254 | 26724
22099 | 424.6595 | 26724
22100 | 402.7868 | 26724
22101 | 425.1346 | 26724
22102 | 398.6886 | 26724
22103 | 407.3248 | 26724
22104 | 425.5223 | 26724
22105 | 404.3317 | 26724
22106 | 407.1508 | 26724
22107 | 419.2836 | 26724
22108 | 410.3431 | 26724
22109 | 423.7712 | 26724
22110 | 425.3119 | 26724
22111 | 414.0974 | 26724
22112 | 413.3954 | 26724
22113 | 427.5538 | 26724
22114 | 433.3992 | 26724
22115 | 423.1404 | 26724
22116 | 411.9979 | 26724
22117 | 438.0939 | 26724
22118 | 424.4079 | 26724
22119 | 422.5235 | 26724
22120 | 413.3593 | 26724
22121 | 428.2573 | 26724
22122 | 406.4633 | 26724
22123 | 426.558 | 26724
22124 | 420.9065 | 26724
22125 | 416.6657 | 26724
22126 | 407.5311 | 26724
22127 | 413.3584 | 26724
22128 | 406.1806 | 26724
22129 | 412.0275 | 26724
22130 | 422.49 | 26724
22131 | 408.7295 | 26724
22132 | 409.4348 | 26724
22133 | 416.6169 | 26724
22134 | 414.4056 | 26724
22135 | 423.9482 | 26724
22136 | 415.207 | 26724
22137 | 423.5268 | 26724
22138 | 409.1503 | 26724
22139 | 431.3496 | 26724
22140 | 412.0256 | 26724
22141 | 418.1914 | 26724
22142 | 434.3365 | 26724
22143 | 415.6698 | 26724
22144 | 423.8244 | 26724
22145 | 409.0449 | 26724
22146 | 410.0351 | 26724
22147 | 422.4576 | 26724
22148 | 410.8124 | 26724
22149 | 424.138 | 26724
22150 | 428.9538 | 26724
22151 | 428.3944 | 26724
22152 | 411.8599 | 26724
22153 | 410.5333 | 26724
22154 | 424.2468 | 26724
22155 | 406.2955 | 26724
22156 | 438.2733 | 26724
22157 | 434.4896 | 26724
22158 | 420.1566 | 26724
22159 | 419.465 | 26724
22160 | 425.0474 | 26724
22161 | 408.4464 | 26724
22162 | 418.7775 | 26724
22163 | 416.265 | 26724
22164 | 406.7582 | 26724
22165 | 402.6769 | 26724
22166 | 413.6941 | 26724
22167 | 419.185 | 26724
22168 | 412.9293 | 26724
22169 | 404.027 | 26724
22170 | 425.6455 | 26724
22171 | 414.7725 | 26724
22172 | 409.4091 | 26724
22173 | 423.1811 | 26724
22174 | 416.3599 | 26724
22175 | 430.1495 | 26724
22176 | 423.1058 | 26724
22177 | 419.7075 | 26724
22178 | 417.6729 | 26724
22179 | 417.2754 | 26724
22180 | 425.7804 | 26724
22181 | 422.8393 | 26724
22182 | 417.9775 | 26724
22183 | 418.9335 | 26724
22184 | 420.3277 | 26724
22185 | 409.5016 | 26724
22186 | 425.6268 | 26724
22187 | 417.7813 | 26724
22188 | 404.067 | 26724
22189 | 407.3239 | 26724
22190 | 412.8595 | 26724
22191 | 420.4993 | 26724
22192 | 417.3342 | 26724
22193 | 421.1746 | 26724
22194 | 426.9599 | 26724
22195 | 412.9956 | 26724
22196 | 417.8369 | 26724
22197 | 411.9799 | 26724
22198 | 433.681 | 26724
22199 | 409.2823 | 26724
22200 | 412.1454 | 26724
22201 | 414.8194 | 26724
22202 | 428.3837 | 26724
22203 | 405.7984 | 26724
22204 | 412.479 | 26724
22205 | 401.8402 | 26724
22206 | 405.4508 | 26724
22207 | 418.4007 | 26724
22208 | 403.8503 | 26724
22209 | 402.6181 | 26724
22210 | 413.5772 | 26724
22211 | 414.0192 | 26724
22212 | 416.2186 | 26724
22213 | 415.9757 | 26724
22214 | 402.5665 | 26724
22215 | 414.2042 | 26724
22216 | 407.3641 | 26724
22217 | 430.6932 | 26724
22218 | 405.5868 | 26724
22219 | 420.5466 | 26724
22220 | 413.7902 | 26724
22221 | 425.4675 | 26724
22222 | 419.6444 | 26724
22223 | 414.4498 | 26724
22224 | 418.8573 | 26724
22225 | 415.8058 | 26724
22226 | 428.9687 | 26724
22227 | 422.0632 | 26724
22228 | 410.3437 | 26724
22229 | 423.4615 | 26724
22230 | 421.7204 | 26724
22231 | 422.7006 | 26724
22232 | 412.9187 | 26724
22233 | 421.8044 | 26724
22234 | 423.9492 | 26724
22235 | 409.7617 | 26724
22236 | 423.4124 | 26724
22237 | 404.1227 | 26724
22238 | 425.4157 | 26724
22239 | 404.9094 | 26724
22240 | 412.6169 | 26724
22241 | 410.2392 | 26724
22242 | 418.5743 | 26724
22243 | 427.3652 | 26724
22244 | 411.3255 | 26724
22245 | 416.7322 | 26724
22246 | 425.0133 | 26724
22247 | 424.1171 | 26724
22248 | 408.2919 | 26724
22249 | 428.2769 | 26724
22250 | 416.3498 | 26724
22251 | 418.975 | 26724
22252 | 414.4657 | 26724
22253 | 424.8867 | 26724
22254 | 417.6442 | 26724
22255 | 406.9333 | 26724
22256 | 413.0254 | 26724
22257 | 424.3286 | 26724
22258 | 416.243 | 26724
22259 | 421.1242 | 26724
22260 | 408.992 | 26724
22261 | 415.992 | 26724
22262 | 413.2431 | 26724
22263 | 432.7506 | 26724
22264 | 411.4801 | 26724
22265 | 415.6041 | 26724
22266 | 409.719 | 26724
22267 | 407.9787 | 26724
22268 | 423.859 | 26724
22269 | 436.5485 | 26724
22270 | 419.803 | 26724
22271 | 424.0148 | 26724
22272 | 440.3917 | 26724
22273 | 427.3304 | 26724
22274 | 427.084 | 26724
22275 | 405.2176 | 26724
22276 | 411.7366 | 26724
22277 | 409.8586 | 26724
22278 | 421.7367 | 26724
22279 | 415.015 | 26724
22280 | 412.6798 | 26724
22281 | 426.8881 | 26724
22282 | 429.1383 | 26724
22283 | 429.5192 | 26724
22284 | 412.0853 | 26724
22285 | 411.589 | 26724
22286 | 413.2521 | 26724
22287 | 418.8731 | 26724
22288 | 420.897 | 26724
22289 | 420.528 | 26724
22290 | 419.053 | 26724
22291 | 409.1545 | 26724
22292 | 430.01 | 26724
22293 | 415.494 | 26724
22294 | 414.1465 | 26724
22295 | 421.1753 | 26724
22296 | 413.4632 | 26724
22297 | 415.4135 | 26724
22298 | 418.2236 | 26724
22299 | 420.4778 | 26724
22300 | 397.7433 | 26724
22301 | 416.9836 | 26724
22302 | 417.6729 | 26724
22303 | 399.7458 | 26724
22304 | 401.7568 | 26724
22305 | 417.6576 | 26724
22306 | 419.0024 | 26724
22307 | 422.7576 | 26724
22308 | 430.0573 | 26724
22309 | 432.4154 | 26724
22310 | 420.6284 | 26724
22311 | 421.9755 | 26724
22312 | 426.017 | 26724
22313 | 427.1881 | 26724
22314 | 409.7786 | 26724
22315 | 425.6357 | 26724
22316 | 413.6155 | 26724
22317 | 421.7834 | 26724
22318 | 416.039 | 26724
22319 | 415.4992 | 26724
22320 | 410.6819 | 26724
22321 | 414.6286 | 26724
22322 | 411.2915 | 26724
22323 | 424.5961 | 26724
22324 | 403.2284 | 26724
22325 | 428.3862 | 26724
22326 | 415.8108 | 26724
22327 | 410.2955 | 26724
22328 | 406.5909 | 26724
22329 | 415.1296 | 26724
22330 | 419.7226 | 26724
22331 | 408.415 | 26724
22332 | 425.967 | 26724
22333 | 414.3685 | 26724
22334 | 421.4733 | 26724
22335 | 424.8199 | 26724
22336 | 414.8413 | 26724
22337 | 410.1925 | 26724
22338 | 424.1073 | 26724
22339 | 421.4426 | 26724
22340 | 417.7151 | 26724
22341 | 409.8432 | 26724
22342 | 418.2451 | 26724
22343 | 399.4031 | 26724
22344 | 394.3931 | 26724
22345 | 427.7321 | 26724
22346 | 412.6315 | 26724
22347 | 415.34 | 26724
22348 | 415.2762 | 26724
22349 | 404.0944 | 26724
22350 | 417.0327 | 26724
22351 | 417.5603 | 26724
22352 | 405.8581 | 26724
22353 | 417.4357 | 26724
22354 | 409.4234 | 26724
22355 | 424.3906 | 26724
22356 | 412.1409 | 26724
22357 | 404.5851 | 26724
22358 | 411.9528 | 26724
22359 | 415.9787 | 26724
22360 | 419.2508 | 26724
22361 | 415.1305 | 26724
22362 | 418.0858 | 26724
22363 | 428.4662 | 26724
22364 | 416.6411 | 26724
22365 | 417.057 | 26724
22366 | 407.2711 | 26724
22367 | 406.4498 | 26724
22368 | 412.0317 | 26724
22369 | 425.1935 | 26724
22370 | 408.4717 | 26724
22371 | 424.9054 | 26724
22372 | 421.7638 | 26724
22373 | 404.6165 | 26724
22374 | 407.4892 | 26724
22375 | 422.2536 | 26724
22376 | 420.6725 | 26724
22377 | 408.4602 | 26724
22378 | 413.7124 | 26724
22379 | 416.0914 | 26724
22380 | 416.5991 | 26724
22381 | 421.7319 | 26724
22382 | 412.9852 | 26724
22383 | 415.4454 | 26724
22384 | 414.2904 | 26724
22385 | 414.7184 | 26724
22386 | 433.5392 | 26724
22387 | 421.4842 | 26724
22388 | 413.3588 | 26724
22389 | 396.2383 | 26724
22390 | 414.5185 | 26724
22391 | 426.2916 | 26724
22392 | 407.8513 | 26724
22393 | 410.2764 | 26724
22394 | 426.8029 | 26724
22395 | 416.7141 | 26724
22396 | 418.3078 | 26724
22397 | 411.2144 | 26724
22398 | 406.4474 | 26724
22399 | 408.0871 | 26724
22400 | 413.4572 | 26724
22401 | 422.7616 | 26724
22402 | 425.385 | 26724
22403 | 417.5606 | 26724
22404 | 402.8743 | 26724
22405 | 402.9938 | 26724
22406 | 423.8155 | 26724
22407 | 411.8211 | 26724
22408 | 421.3916 | 26724
22409 | 405.3968 | 26724
22410 | 427.177 | 26724
22411 | 417.4307 | 26724
22412 | 409.8394 | 26724
22413 | 423.4081 | 26724
22414 | 421.0886 | 26724
22415 | 429.774 | 26724
22416 | 416.5504 | 26724
22417 | 403.8085 | 26724
22418 | 423.5329 | 26724
22419 | 418.7137 | 26724
22420 | 409.4118 | 26724
22421 | 420.861 | 26724
22422 | 412.1976 | 26724
22423 | 404.2628 | 26724
22424 | 423.3454 | 26724
22425 | 421.2815 | 26724
22426 | 424.3435 | 26724
22427 | 427.9345 | 26724
22428 | 413.271 | 26724
22429 | 409.5682 | 26724
22430 | 404.3218 | 26724
22431 | 410.5129 | 26724
22432 | 409.2319 | 26724
22433 | 411.9901 | 26724
22434 | 420.0279 | 26724
22435 | 421.8209 | 26724
22436 | 399.6375 | 26724
22437 | 420.1821 | 26724
22438 | 414.5759 | 26724
22439 | 423.1532 | 26724
22440 | 414.9482 | 26724
22441 | 412.4503 | 26724
22442 | 411.1643 | 26724
22443 | 419.8994 | 26724
22444 | 406.2338 | 26724
22445 | 422.6446 | 26724
22446 | 402.2695 | 26724
22447 | 423.1492 | 26724
22448 | 417.0738 | 26724
22449 | 401.42 | 26724
22450 | 413.796 | 26724
22451 | 407.0191 | 26724
22452 | 403.3177 | 26724
22453 | 408.3937 | 26724
22454 | 399.0171 | 26724
22455 | 429.9998 | 26724
22456 | 418.3379 | 26724
22457 | 429.265 | 26724
22458 | 421.1701 | 26724
22459 | 410.5236 | 26724
22460 | 404.2268 | 26724
22461 | 399.4061 | 26724
22462 | 432.9501 | 26724
22463 | 420.4434 | 26724
22464 | 402.9035 | 26724
22465 | 410.2845 | 26724
22466 | 427.8499 | 26724
22467 | 424.1135 | 26724
22468 | 412.6 | 26724
22469 | 403.9235 | 26724
22470 | 413.7546 | 26724
22471 | 408.7843 | 26724
22472 | 406.4 | 26724
22473 | 413.4996 | 26724
22474 | 413.3103 | 26724
22475 | 430.0734 | 26724
22476 | 419.0486 | 26724
22477 | 411.1627 | 26724
22478 | 420.4629 | 26724
22479 | 410.1218 | 26724
22480 | 407.6376 | 26724
22481 | 416.763 | 26724
22482 | 402.4449 | 26724
22483 | 417.5391 | 26724
22484 | 399.1824 | 26724
22485 | 432.6962 | 26724
22486 | 404.5537 | 26724
22487 | 430.0774 | 26724
22488 | 420.689 | 26724
22489 | 408.2344 | 26724
22490 | 406.9416 | 26724
22491 | 412.4865 | 26724
22492 | 413.6708 | 26724
22493 | 404.1795 | 26724
22494 | 408.9331 | 26724
22495 | 415.7861 | 26724
22496 | 426.2646 | 26724
22497 | 412.3111 | 26724
22498 | 408.0415 | 26724
22499 | 425.2688 | 26724
22500 | 408.2134 | 26724
22501 | 399.0748 | 26724
22502 | 411.2064 | 26724
22503 | 426.6422 | 26724
22504 | 418.6512 | 26724
22505 | 409.371 | 26724
22506 | 420.3607 | 26724
22507 | 415.7509 | 26724
22508 | 418.674 | 26724
22509 | 411.266 | 26724
22510 | 410.2992 | 26724
22511 | 414.5463 | 26724
22512 | 434.1526 | 26724
22513 | 409.5475 | 26724
22514 | 415.2544 | 26724
22515 | 416.1636 | 26724
22516 | 421.1471 | 26724
22517 | 416.1243 | 26724
22518 | 421.5425 | 26724
22519 | 409.0732 | 26724
22520 | 415.154 | 26724
22521 | 398.1985 | 26724
22522 | 406.8929 | 26724
22523 | 405.7802 | 26724
22524 | 401.0435 | 26724
22525 | 413.1717 | 26724
22526 | 397.6773 | 26724
22527 | 416.9182 | 26724
22528 | 410.2476 | 26724
22529 | 420.7359 | 26724
22530 | 424.0611 | 26724
22531 | 421.8988 | 26724
22532 | 413.7795 | 26724
22533 | 421.8535 | 26724
22534 | 414.8259 | 26724
22535 | 433.0964 | 26724
22536 | 419.5727 | 26724
22537 | 425.1077 | 26724
22538 | 407.1935 | 26724
22539 | 407.4058 | 26724
22540 | 406.464 | 26724
22541 | 412.7676 | 26724
22542 | 425.8367 | 26724
22543 | 406.2168 | 26724
22544 | 411.6398 | 26724
22545 | 409.891 | 26724
22546 | 415.7656 | 26724
22547 | 416.4714 | 26724
22548 | 420.0936 | 26724
22549 | 408.9036 | 26724
22550 | 422.0581 | 26724
22551 | 421.008 | 26724
22552 | 414.5007 | 26724
22553 | 412.7058 | 26724
22554 | 419.2189 | 26724
22555 | 418.0947 | 26724
22556 | 427.5039 | 26724
22557 | 400.0741 | 26724
22558 | 419.7231 | 26724
22559 | 403.9355 | 26724
22560 | 405.3159 | 26724
22561 | 418.3347 | 26724
22562 | 416.6542 | 26724
22563 | 411.3823 | 26724
22564 | 406.3091 | 26724
22565 | 420.6899 | 26724
22566 | 417.3778 | 26724
22567 | 416.8119 | 26724
22568 | 407.8458 | 26724
22569 | 426.769 | 26724
22570 | 428.7015 | 26724
22571 | 408.2718 | 26724
22572 | 428.2468 | 26724
22573 | 407.2385 | 26724
22574 | 423.7609 | 26724
22575 | 414.735 | 26724
22576 | 415.956 | 26724
22577 | 406.1545 | 26724
22578 | 415.938 | 26724
22579 | 409.353 | 26724
22580 | 411.7822 | 26724
22581 | 415.7541 | 26724
22582 | 412.1301 | 26724
22583 | 418.4392 | 26724
22584 | 407.6996 | 26724
22585 | 419.2902 | 26724
22586 | 410.0038 | 26724
22587 | 428.2316 | 26724
22588 | 413.4213 | 26724
22589 | 418.0152 | 26724
22590 | 420.9147 | 26724
22591 | 424.7805 | 26724
22592 | 420.5633 | 26724
22593 | 409.9002 | 26724
22594 | 430.3572 | 26724
22595 | 425.7384 | 26724
22596 | 426.5924 | 26724
22597 | 412.8783 | 26724
22598 | 414.3679 | 26724
22599 | 417.2486 | 26724
22600 | 419.1025 | 26724
22601 | 414.3154 | 26724
22602 | 421.3934 | 26724
22603 | 421.1681 | 26724
22604 | 417.4484 | 26724
22605 | 397.498 | 26724
22606 | 426.5472 | 26724
22607 | 417.7862 | 26724
22608 | 429.143 | 26724
22609 | 428.8504 | 26724
22610 | 423.768 | 26724
22611 | 417.1328 | 26724
22612 | 417.1917 | 26724
22613 | 404.4129 | 26724
22614 | 425.0777 | 26724
22615 | 426.6089 | 26724
22616 | 420.1053 | 26724
22617 | 422.1883 | 26724
22618 | 422.8365 | 26724
22619 | 411.1237 | 26724
22620 | 396.6454 | 26724
22621 | 407.5305 | 26724
22622 | 429.716 | 26724
22623 | 421.7501 | 26724
22624 | 422.4128 | 26724
22625 | 430.954 | 26724
22626 | 416.2468 | 26724
22627 | 424.2455 | 26724
22628 | 417.0185 | 26724
22629 | 413.0563 | 26724
22630 | 415.4817 | 26724
22631 | 418.4905 | 26724
22632 | 402.3025 | 26724
22633 | 420.8264 | 26724
22634 | 425.7194 | 26724
22635 | 417.7974 | 26724
22636 | 419.9049 | 26724
22637 | 407.6986 | 26724
22638 | 417.4733 | 26724
22639 | 416.5758 | 26724
22640 | 408.07 | 26724
22641 | 421.3404 | 26724
22642 | 412.8985 | 26724
22643 | 421.5564 | 26724
22644 | 422.7913 | 26724
22645 | 405.3927 | 26724
22646 | 402.064 | 26724
22647 | 412.7224 | 26724
22648 | 414.2171 | 26724
22649 | 413.2853 | 26724
22650 | 405.9273 | 26724
22651 | 426.9071 | 26724
22652 | 428.2127 | 26724
22653 | 405.3967 | 26724
22654 | 430.9702 | 26724
22655 | 433.4307 | 26724
22656 | 412.6967 | 26724
22657 | 426.9109 | 26724
22658 | 415.82 | 26724
22659 | 423.7895 | 26724
22660 | 414.931 | 26724
22661 | 404.9657 | 26724
22662 | 414.5392 | 26724
22663 | 415.4234 | 26724
22664 | 419.0801 | 26724
22665 | 402.1441 | 26724
22666 | 410.1412 | 26724
22667 | 425.1643 | 26724
22668 | 433.5449 | 26724
22669 | 420.3728 | 26724
22670 | 421.3698 | 26724
22671 | 419.7626 | 26724
22672 | 423.4077 | 26724
22673 | 405.3352 | 26724
22674 | 419.6716 | 26724
22675 | 403.2688 | 26724
22676 | 427.8674 | 26724
22677 | 410.9966 | 26724
22678 | 415.8864 | 26724
22679 | 418.6323 | 26724
22680 | 422.5167 | 26724
22681 | 409.8021 | 26724
22682 | 415.7903 | 26724
22683 | 419.6806 | 26724
22684 | 419.2729 | 26724
22685 | 416.6892 | 26724
22686 | 408.994 | 26724
22687 | 417.6491 | 26724
22688 | 404.8842 | 26724
22689 | 426.9722 | 26724
22690 | 409.2502 | 26724
22691 | 432.7987 | 26724
22692 | 430.5703 | 26724
22693 | 414.1691 | 26724
22694 | 435.1542 | 26724
22695 | 415.9357 | 26724
22696 | 412.0026 | 26724
22697 | 414.7917 | 26724
22698 | 403.0195 | 26724
22699 | 417.5388 | 26724
22700 | 422.5523 | 26724
22701 | 410.3943 | 26724
22702 | 424.331 | 26724
22703 | 424.5553 | 26724
22704 | 408.7999 | 26724
22705 | 410.2835 | 26724
22706 | 421.6756 | 26724
22707 | 424.9459 | 26724
22708 | 423.7616 | 26724
22709 | 396.5307 | 26724
22710 | 408.6866 | 26724
22711 | 414.9437 | 26724
22712 | 410.3683 | 26724
22713 | 417.85 | 26724
22714 | 436.1872 | 26724
22715 | 411.8311 | 26724
22716 | 416.6174 | 26724
22717 | 411.871 | 26724
22718 | 412.747 | 26724
22719 | 417.5366 | 26724
22720 | 400.104 | 26724
22721 | 401.8047 | 26724
22722 | 429.5417 | 26724
22723 | 424.0435 | 26724
22724 | 412.2309 | 26724
22725 | 417.2785 | 26724
22726 | 405.4022 | 26724
22727 | 425.1097 | 26724
22728 | 403.5004 | 26724
22729 | 425.7652 | 26724
22730 | 414.4141 | 26724
22731 | 411.4728 | 26724
22732 | 405.2858 | 26724
22733 | 418.139 | 26724
22734 | 416.4862 | 26724
22735 | 433.1319 | 26724
22736 | 425.1026 | 26724
22737 | 419.6854 | 26724
22738 | 417.7997 | 26724
22739 | 400.4832 | 26724
22740 | 415.0161 | 26724
22741 | 426.0103 | 26724
22742 | 430.6386 | 26724
22743 | 417.7747 | 26724
22744 | 432.7363 | 26724
22745 | 411.2187 | 26724
22746 | 423.071 | 26724
22747 | 394.2852 | 26724
22748 | 401.9425 | 26724
22749 | 414.2051 | 26724
22750 | 422.0902 | 26724
22751 | 409.9547 | 26724
22752 | 428.2853 | 26724
22753 | 427.0849 | 26724
22754 | 414.0494 | 26724
22755 | 426.459 | 26724
22756 | 426.6372 | 26724
22757 | 414.5808 | 26724
22758 | 422.7975 | 26724
22759 | 429.6411 | 26724
22760 | 427.0591 | 26724
22761 | 406.8133 | 26724
22762 | 425.9149 | 26724
22763 | 408.1042 | 26724
22764 | 415.6457 | 26724
22765 | 402.1568 | 26724
22766 | 428.2971 | 26724
22767 | 424.299 | 26724
22768 | 414.6458 | 26724
22769 | 411.9641 | 26724
22770 | 412.3029 | 26724
22771 | 423.437 | 26724
22772 | 427.9921 | 26724
22773 | 412.994 | 26724
22774 | 421.0846 | 26724
22775 | 417.1543 | 26724
22776 | 400.8546 | 26724
22777 | 418.5625 | 26724
22778 | 414.415 | 26724
22779 | 408.0838 | 26724
22780 | 413.8932 | 26724
22781 | 397.788 | 26724
22782 | 424.5372 | 26724
22783 | 412.5807 | 26724
22784 | 421.1679 | 26724
22785 | 420.1459 | 26724
22786 | 410.5273 | 26724
22787 | 427.939 | 26724
22788 | 403.836 | 26724
22789 | 411.9209 | 26724
22790 | 410.2891 | 26724
22791 | 412.3527 | 26724
22792 | 425.8949 | 26724
22793 | 406.4799 | 26724
22794 | 430.5574 | 26724
22795 | 406.4352 | 26724
22796 | 418.9763 | 26724
22797 | 421.5517 | 26724
22798 | 411.5778 | 26724
22799 | 405.5687 | 26724
22800 | 404.7639 | 26724
22801 | 411.9516 | 26724
22802 | 425.7612 | 26724
22803 | 423.1385 | 26724
22804 | 409.0542 | 26724
22805 | 416.6706 | 26724
22806 | 409.4206 | 26724
22807 | 419.9268 | 26724
22808 | 419.3831 | 26724
22809 | 420.5121 | 26724
22810 | 422.2837 | 26724
22811 | 420.5469 | 26724
22812 | 423.2056 | 26724
22813 | 430.8712 | 26724
22814 | 431.2095 | 26724
22815 | 422.0369 | 26724
22816 | 396.9811 | 26724
22817 | 423.6302 | 26724
22818 | 420.7337 | 26724
22819 | 420.3375 | 26724
22820 | 435.2517 | 26724
22821 | 422.2098 | 26724
22822 | 400.3855 | 26724
22823 | 424.4867 | 26724
22824 | 417.9446 | 26724
22825 | 403.893 | 26724
22826 | 409.3853 | 26724
22827 | 411.9991 | 26724
22828 | 425.0307 | 26724
22829 | 428.9778 | 26724
22830 | 416.5595 | 26724
22831 | 412.0706 | 26724
22832 | 414.9333 | 26724
22833 | 412.1314 | 26724
22834 | 422.5498 | 26724
22835 | 413.8684 | 26724
22836 | 409.8512 | 26724
22837 | 421.5253 | 26724
22838 | 409.8085 | 26724
22839 | 417.7875 | 26724
22840 | 422.3818 | 26724
22841 | 425.9158 | 26724
22842 | 410.97 | 26724
22843 | 414.1942 | 26724
22844 | 417.4105 | 26724
22845 | 411.5339 | 26724
22846 | 415.0524 | 26724
22847 | 407.3789 | 26724
22848 | 404.1807 | 26724
22849 | 430.7667 | 26724
22850 | 415.8811 | 26724
22851 | 410.6234 | 26724
22852 | 425.1928 | 26724
22853 | 430.3924 | 26724
22854 | 417.6096 | 26724
22855 | 409.7787 | 26724
22856 | 412.3265 | 26724
22857 | 425.5473 | 26724
22858 | 414.9789 | 26724
22859 | 409.122 | 26724
22860 | 412.3188 | 26724
22861 | 418.5984 | 26724
22862 | 413.1724 | 26724
22863 | 412.4196 | 26724
22864 | 425.3046 | 26724
22865 | 412.6862 | 26724
22866 | 420.6886 | 26724
22867 | 409.1566 | 26724
22868 | 425.288 | 26724
22869 | 414.0227 | 26724
22870 | 416.787 | 26724
22871 | 402.0313 | 26724
22872 | 413.0668 | 26724
22873 | 410.6372 | 26724
22874 | 421.8656 | 26724
22875 | 415.582 | 26724
22876 | 403.0035 | 26724
22877 | 426.1949 | 26724
22878 | 407.0662 | 26724
22879 | 409.0602 | 26724
22880 | 414.1357 | 26724
22881 | 395.6282 | 26724
22882 | 426.2869 | 26724
22883 | 407.4865 | 26724
22884 | 414.0001 | 26724
22885 | 411.4177 | 26724
22886 | 423.1342 | 26724
22887 | 413.8329 | 26724
22888 | 428.5351 | 26724
22889 | 416.1182 | 26724
22890 | 414.1613 | 26724
22891 | 397.9068 | 26724
22892 | 419.1469 | 26724
22893 | 420.5897 | 26724
22894 | 419.7911 | 26724
22895 | 412.898 | 26724
22896 | 414.9535 | 26724
22897 | 410.5823 | 26724
22898 | 419.5371 | 26724
22899 | 412.196 | 26724
22900 | 410.4943 | 26724
22901 | 421.9279 | 26724
22902 | 425.3783 | 26724
22903 | 413.3418 | 26724
22904 | 416.3108 | 26724
22905 | 415.8026 | 26724
22906 | 412.3964 | 26724
22907 | 410.6692 | 26724
22908 | 415.6741 | 26724
22909 | 433.8009 | 26724
22910 | 431.0023 | 26724
22911 | 422.7017 | 26724
22912 | 413.2172 | 26724
22913 | 423.3829 | 26724
22914 | 418.4739 | 26724
22915 | 408.1231 | 26724
22916 | 405.297 | 26724
22917 | 414.3744 | 26724
22918 | 417.942 | 26724
22919 | 427.6054 | 26724
22920 | 408.8897 | 26724
22921 | 415.8119 | 26724
22922 | 418.8225 | 26724
22923 | 403.731 | 26724
22924 | 398.6089 | 26724
22925 | 413.2093 | 26724
22926 | 403.9967 | 26724
22927 | 418.5642 | 26724
22928 | 408.9925 | 26724
22929 | 415.6509 | 26724
22930 | 420.8515 | 26724
22931 | 406.1415 | 26724
22932 | 435.3676 | 26724
22933 | 432.1886 | 26724
22934 | 417.6313 | 26724
22935 | 423.4647 | 26724
22936 | 420.3207 | 26724
22937 | 424.1921 | 26724
22938 | 419.686 | 26724
22939 | 432.9082 | 26724
22940 | 418.135 | 26724
22941 | 420.0537 | 26724
22942 | 412.878 | 26724
22943 | 419.0723 | 26724
22944 | 418.7573 | 26724
22945 | 430.4389 | 26724
22946 | 424.4231 | 26724
22947 | 423.0943 | 26724
22948 | 428.6431 | 26724
22949 | 418.4556 | 26724
22950 | 414.9583 | 26724
22951 | 415.47 | 26724
22952 | 411.0678 | 26724
22953 | 403.6115 | 26724
22954 | 414.5049 | 26724
22955 | 417.1374 | 26724
22956 | 415.677 | 26724
22957 | 422.4551 | 26724
22958 | 417.9732 | 26724
22959 | 421.7628 | 26724
22960 | 416.1222 | 26724
22961 | 413.1555 | 26724
22962 | 426.2649 | 26724
22963 | 420.4698 | 26724
22964 | 424.3832 | 26724
22965 | 421.2863 | 26724
22966 | 419.8654 | 26724
22967 | 432.8255 | 26724
22968 | 409.0235 | 26724
22969 | 405.1601 | 26724
22970 | 417.0745 | 26724
22971 | 421.0049 | 26724
22972 | 417.3164 | 26724
22973 | 416.803 | 26724
22974 | 415.192 | 26724
22975 | 418.3945 | 26724
22976 | 412.8152 | 26724
22977 | 407.4101 | 26724
22978 | 411.0664 | 26724
22979 | 408.9248 | 26724
22980 | 423.4195 | 26724
22981 | 413.6279 | 26724
22982 | 417.2315 | 26724
22983 | 412.4298 | 26724
22984 | 419.2739 | 26724
22985 | 414.362 | 26724
22986 | 416.7409 | 26724
22987 | 408.7405 | 26724
22988 | 419.3108 | 26724
22989 | 414.8726 | 26724
22990 | 419.517 | 26724
22991 | 434.8173 | 26724
22992 | 417.7488 | 26724
22993 | 413.0109 | 26724
22994 | 421.5085 | 26724
22995 | 405.1878 | 26724
22996 | 408.7629 | 26724
22997 | 409.5752 | 26724
22998 | 416.4891 | 26724
22999 | 415.0065 | 26724
23000 | 420.659 | 26724
23001 | 419.6698 | 26724
23002 | 412.4948 | 26724
23003 | 416.2229 | 26724
23004 | 419.5559 | 26724
23005 | 414.8836 | 26724
23006 | 423.0564 | 26724
23007 | 416.3834 | 26724
23008 | 419.2028 | 26724
23009 | 420.6414 | 26724
23010 | 421.6777 | 26724
23011 | 408.472 | 26724
23012 | 424.6317 | 26724
23013 | 407.2454 | 26724
23014 | 409.1567 | 26724
23015 | 404.3665 | 26724
23016 | 413.5414 | 26724
23017 | 424.9792 | 26724
23018 | 422.9631 | 26724
23019 | 425.78 | 26724
23020 | 419.9911 | 26724
23021 | 419.5337 | 26724
23022 | 402.8601 | 26724
23023 | 414.9985 | 26724
23024 | 431.4834 | 26724
23025 | 414.2585 | 26724
23026 | 416.4824 | 26724
23027 | 421.3268 | 26724
23028 | 411.5927 | 26724
23029 | 411.0755 | 26724
23030 | 416.2662 | 26724
23031 | 431.6576 | 26724
23032 | 423.1232 | 26724
23033 | 427.5903 | 26724
23034 | 425.691 | 26724
23035 | 411.3323 | 26724
23036 | 414.3861 | 26724
23037 | 415.6045 | 26724
23038 | 416.2195 | 26724
23039 | 431.6564 | 26724
23040 | 413.7141 | 26724
23041 | 413.3877 | 26724
23042 | 415.4615 | 26724
23043 | 422.055 | 26724
23044 | 427.0078 | 26724
23045 | 412.3941 | 26724
23046 | 426.638 | 26724
23047 | 409.1525 | 26724
23048 | 417.9397 | 26724
23049 | 413.1984 | 26724
23050 | 414.6663 | 26724
23051 | 424.9175 | 26724
23052 | 414.4149 | 26724
23053 | 413.1154 | 26724
23054 | 400.0772 | 26724
23055 | 402.2195 | 26724
23056 | 419.3986 | 26724
23057 | 414.5417 | 26724
23058 | 409.2071 | 26724
23059 | 431.5174 | 26724
23060 | 411.4529 | 26724
23061 | 419.8959 | 26724
23062 | 409.9318 | 26724
23063 | 410.4048 | 26724
23064 | 422.0877 | 26724
23065 | 413.6625 | 26724
23066 | 424.1682 | 26724
23067 | 412.2652 | 26724
23068 | 409.7803 | 26724
23069 | 410.5384 | 26724
23070 | 416.883 | 26724
23071 | 420.1894 | 26724
23072 | 421.8247 | 26724
23073 | 413.7868 | 26724
23074 | 406.1567 | 26724
23075 | 411.3299 | 26724
23076 | 424.0603 | 26724
23077 | 427.047 | 26724
23078 | 430.8506 | 26724
23079 | 409.405 | 26724
23080 | 419.8741 | 26724
23081 | 419.4459 | 26724
23082 | 414.5245 | 26724
23083 | 419.4138 | 26724
23084 | 420.8055 | 26724
23085 | 417.8763 | 26724
23086 | 412.4702 | 26724
23087 | 413.1132 | 26724
23088 | 409.843 | 26724
23089 | 413.2404 | 26724
23090 | 426.4373 | 26724
23091 | 421.4958 | 26724
23092 | 427.114 | 26724
23093 | 405.9357 | 26724
23094 | 420.6887 | 26724
23095 | 404.6271 | 26724
23096 | 416.3383 | 26724
23097 | 404.3465 | 26724
23098 | 410.5112 | 26724
23099 | 414.8267 | 26724
23100 | 400.1767 | 26724
23101 | 420.5576 | 26724
23102 | 413.4952 | 26724
23103 | 409.5259 | 26724
23104 | 410.8366 | 26724
23105 | 414.6266 | 26724
23106 | 417.8839 | 26724
23107 | 413.5332 | 26724
23108 | 406.0655 | 26724
23109 | 418.5165 | 26724
23110 | 435.133 | 26724
23111 | 424.2779 | 26724
23112 | 420.5492 | 26724
23113 | 418.7679 | 26724
23114 | 418.627 | 26724
23115 | 412.9813 | 26724
23116 | 411.0297 | 26724
23117 | 414.8001 | 26724
23118 | 423.817 | 26724
23119 | 417.6531 | 26724
23120 | 412.8965 | 26724
23121 | 417.8137 | 26724
23122 | 410.4341 | 26724
23123 | 417.5269 | 26724
23124 | 408.3668 | 26724
23125 | 421.5195 | 26724
23126 | 407.4879 | 26724
23127 | 426.3524 | 26724
23128 | 416.8072 | 26724
23129 | 422.9403 | 26724
23130 | 417.3532 | 26724
23131 | 412.7565 | 26724
23132 | 399.3484 | 26724
23133 | 422.1582 | 26724
23134 | 410.5225 | 26724
23135 | 434.7603 | 26724
23136 | 421.6114 | 26724
23137 | 404.155 | 26724
23138 | 425.4194 | 26724
23139 | 424.1996 | 26724
23140 | 409.7525 | 26724
23141 | 406.2832 | 26724
23142 | 409.0941 | 26724
23143 | 412.607 | 26724
23144 | 410.145 | 26724
23145 | 410.5522 | 26724
23146 | 415.4113 | 26724
23147 | 405.322 | 26724
23148 | 416.5648 | 26724
23149 | 428.4204 | 26724
23150 | 405.3887 | 26724
23151 | 418.9117 | 26724
23152 | 414.553 | 26724
23153 | 426.3429 | 26724
23154 | 410.3346 | 26724
23155 | 414.831 | 26724
23156 | 416.0581 | 26724
23157 | 415.2646 | 26724
23158 | 413.994 | 26724
23159 | 418.4156 | 26724
23160 | 410.7771 | 26724
23161 | 418.2548 | 26724
23162 | 407.9685 | 26724
23163 | 407.526 | 26724
23164 | 414.786 | 26724
23165 | 418.9845 | 26724
23166 | 411.0666 | 26724
23167 | 419.9911 | 26724
23168 | 421.5959 | 26724
23169 | 428.1744 | 26724
23170 | 417.9239 | 26724
23171 | 414.1214 | 26724
23172 | 420.4769 | 26724
23173 | 420.2937 | 26724
23174 | 416.3187 | 26724
23175 | 425.6813 | 26724
23176 | 399.5744 | 26724
23177 | 405.8978 | 26724
23178 | 415.6821 | 26724
23179 | 410.1964 | 26724
23180 | 411.9396 | 26724
23181 | 413.637 | 26724
23182 | 418.1038 | 26724
23183 | 411.0578 | 26724
23184 | 411.833 | 26724
23185 | 403.7729 | 26724
23186 | 409.4516 | 26724
23187 | 412.9315 | 26724
23188 | 418.3822 | 26724
23189 | 414.9087 | 26724
23190 | 421.0195 | 26724
23191 | 428.4945 | 26724
23192 | 425.5109 | 26724
23193 | 402.918 | 26724
23194 | 415.0726 | 26724
23195 | 409.972 | 26724
23196 | 418.2193 | 26724
23197 | 431.2059 | 26724
23198 | 425.4269 | 26724
23199 | 406.9209 | 26724
23200 | 435.16 | 26724
23201 | 411.8293 | 26724
23202 | 408.7777 | 26724
23203 | 413.9239 | 26724
23204 | 409.5897 | 26724
23205 | 403.0959 | 26724
23206 | 416.7943 | 26724
23207 | 405.4405 | 26724
23208 | 410.3209 | 26724
23209 | 424.3184 | 26724
23210 | 412.9912 | 26724
23211 | 406.4739 | 26724
23212 | 417.2967 | 26724
23213 | 420.7814 | 26724
23214 | 430.3912 | 26724
23215 | 408.5245 | 26724
23216 | 405.5912 | 26724
23217 | 418.4601 | 26724
23218 | 411.8856 | 26724
23219 | 411.1624 | 26724
23220 | 407.2964 | 26724
23221 | 418.9031 | 26724
23222 | 405.2837 | 26724
23223 | 410.7809 | 26724
23224 | 430.9512 | 26724
23225 | 414.2253 | 26724
23226 | 426.5785 | 26724
23227 | 420.171 | 26724
23228 | 420.5913 | 26724
23229 | 406.4242 | 26724
23230 | 406.2649 | 26724
23231 | 401.5537 | 26724
23232 | 412.7405 | 26724
23233 | 405.1391 | 26724
23234 | 394.8277 | 26724
23235 | 427.2764 | 26724
23236 | 416.2561 | 26724
23237 | 409.3416 | 26724
23238 | 419.1485 | 26724
23239 | 423.446 | 26724
23240 | 422.1682 | 26724
23241 | 421.7934 | 26724
23242 | 408.9402 | 26724
23243 | 407.0506 | 26724
23244 | 416.5429 | 26724
23245 | 432.7616 | 26724
23246 | 411.3486 | 26724
23247 | 419.5299 | 26724
23248 | 413.3103 | 26724
23249 | 426.845 | 26724
23250 | 431.6682 | 26724
23251 | 420.1961 | 26724
23252 | 414.6467 | 26724
23253 | 416.086 | 26724
23254 | 424.2941 | 26724
23255 | 428.273 | 26724
23256 | 412.7453 | 26724
23257 | 397.9903 | 26724
23258 | 427.0219 | 26724
23259 | 418.2113 | 26724
23260 | 414.9212 | 26724
23261 | 411.3259 | 26724
23262 | 400.1292 | 26724
23263 | 415.8071 | 26724
23264 | 428.0324 | 26724
23265 | 412.0589 | 26724
23266 | 409.0857 | 26724
23267 | 412.5598 | 26724
23268 | 411.695 | 26724
23269 | 409.8391 | 26724
23270 | 400.8974 | 26724
23271 | 417.5596 | 26724
23272 | 419.3203 | 26724
23273 | 407.2062 | 26724
23274 | 415.2087 | 26724
23275 | 411.0396 | 26724
23276 | 408.7684 | 26724
23277 | 411.7613 | 26724
23278 | 417.2216 | 26724
23279 | 414.9562 | 26724
23280 | 424.12 | 26724
23281 | 430.8214 | 26724
23282 | 422.9308 | 26724
23283 | 422.6848 | 26724
23284 | 403.5466 | 26724
23285 | 412.685 | 26724
23286 | 397.3308 | 26724
23287 | 422.9347 | 26724
23288 | 404.8129 | 26724
23289 | 410.412 | 26724
23290 | 401.4108 | 26724
23291 | 418.7693 | 26724
23292 | 421.8647 | 26724
23293 | 416.0603 | 26724
23294 | 416.7343 | 26724
23295 | 424.7444 | 26724
23296 | 417.5733 | 26724
23297 | 419.2163 | 26724
23298 | 429.4599 | 26724
23299 | 416.8708 | 26724
23300 | 403.4576 | 26724
23301 | 406.4557 | 26724
23302 | 410.3687 | 26724
23303 | 429.4905 | 26724
23304 | 415.4286 | 26724
23305 | 399.9932 | 26724
23306 | 431.7185 | 26724
23307 | 410.912 | 26724
23308 | 424.6302 | 26724
23309 | 403.1269 | 26724
23310 | 415.4266 | 26724
23311 | 412.7962 | 26724
23312 | 427.6987 | 26724
23313 | 413.455 | 26724
23314 | 423.4015 | 26724
23315 | 401.9438 | 26724
23316 | 419.4657 | 26724
23317 | 414.7381 | 26724
23318 | 419.3337 | 26724
23319 | 408.7273 | 26724
23320 | 416.9179 | 26724
23321 | 415.2845 | 26724
23322 | 409.635 | 26724
23323 | 422.0218 | 26724
23324 | 409.5433 | 26724
23325 | 416.5575 | 26724
23326 | 413.6564 | 26724
23327 | 409.911 | 26724
23328 | 418.2869 | 26724
23329 | 412.5908 | 26724
23330 | 420.336 | 26724
23331 | 407.3867 | 26724
23332 | 419.6928 | 26724
23333 | 431.1852 | 26724
23334 | 429.8426 | 26724
23335 | 414.0557 | 26724
23336 | 420.9076 | 26724
23337 | 426.7593 | 26724
23338 | 411.4662 | 26724
23339 | 413.3786 | 26724
23340 | 416.8314 | 26724
23341 | 405.9955 | 26724
23342 | 412.8329 | 26724
23343 | 408.1181 | 26724
23344 | 431.3731 | 26724
23345 | 430.2551 | 26724
23346 | 410.3629 | 26724
23347 | 421.1352 | 26724
23348 | 425.9133 | 26724
23349 | 419.8829 | 26724
23350 | 415.2023 | 26724
23351 | 401.8577 | 26724
23352 | 410.6457 | 26724
23353 | 426.6046 | 26724
23354 | 401.9412 | 26724
23355 | 427.8521 | 26724
23356 | 409.9457 | 26724
23357 | 416.2739 | 26724
23358 | 417.2875 | 26724
23359 | 418.2265 | 26724
23360 | 421.1608 | 26724
23361 | 426.939 | 26724
23362 | 414.5529 | 26724
23363 | 418.3787 | 26724
23364 | 417.3994 | 26724
23365 | 410.213 | 26724
23366 | 406.8767 | 26724
23367 | 419.6753 | 26724
23368 | 413.1968 | 26724
23369 | 410.9907 | 26724
23370 | 414.8843 | 26724
23371 | 412.1839 | 26724
23372 | 415.9834 | 26724
23373 | 423.2857 | 26724
23374 | 413.2198 | 26724
23375 | 421.2184 | 26724
23376 | 423.1893 | 26724
23377 | 395.3294 | 26724
23378 | 414.0753 | 26724
23379 | 416.2447 | 26724
23380 | 412.3596 | 26724
23381 | 416.0293 | 26724
23382 | 418.7866 | 26724
23383 | 423.5067 | 26724
23384 | 416.6481 | 26724
23385 | 424.8126 | 26724
23386 | 415.2766 | 26724
23387 | 420.5736 | 26724
23388 | 407.6438 | 26724
23389 | 397.6515 | 26724
23390 | 423.6264 | 26724
23391 | 408.7932 | 26724
23392 | 412.1987 | 26724
23393 | 416.3385 | 26724
23394 | 408.1947 | 26724
23395 | 418.616 | 26724
23396 | 427.9495 | 26724
23397 | 414.7782 | 26724
23398 | 419.519 | 26724
23399 | 424.5616 | 26724
23400 | 419.6286 | 26724
23401 | 421.3575 | 26724
23402 | 430.331 | 26724
23403 | 405.2326 | 26724
23404 | 415.4732 | 26724
23405 | 420.9737 | 26724
23406 | 416.3765 | 26724
23407 | 416.0365 | 26724
23408 | 425.6747 | 26724
23409 | 427.8439 | 26724
23410 | 419.6172 | 26724
23411 | 403.3405 | 26724
23412 | 402.984 | 26724
23413 | 429.5377 | 26724
23414 | 414.8195 | 26724
23415 | 416.5018 | 26724
23416 | 415.5343 | 26724
23417 | 401.4075 | 26724
23418 | 418.8781 | 26724
23419 | 419.5369 | 26724
23420 | 413.9177 | 26724
23421 | 415.1345 | 26724
23422 | 412.0889 | 26724
23423 | 413.6076 | 26724
23424 | 418.8374 | 26724
23425 | 410.7915 | 26724
23426 | 415.7173 | 26724
23427 | 417.974 | 26724
23428 | 418.7412 | 26724
23429 | 421.8147 | 26724
23430 | 424.4804 | 26724
23431 | 404.9588 | 26724
23432 | 402.7603 | 26724
23433 | 408.5858 | 26724
23434 | 402.78 | 26724
23435 | 412.8571 | 26724
23436 | 412.3706 | 26724
23437 | 426.1191 | 26724
23438 | 417.8072 | 26724
23439 | 417.5609 | 26724
23440 | 423.536 | 26724
23441 | 419.2846 | 26724
23442 | 416.9186 | 26724
23443 | 425.1379 | 26724
23444 | 427.437 | 26724
23445 | 419.1478 | 26724
23446 | 418.1812 | 26724
23447 | 416.6106 | 26724
23448 | 417.9091 | 26724
23449 | 431.8713 | 26724
23450 | 413.1681 | 26724
23451 | 412.8499 | 26724
23452 | 421.4469 | 26724
23453 | 408.8789 | 26724
23454 | 404.1411 | 26724
23455 | 420.7228 | 26724
23456 | 402.7585 | 26724
23457 | 416.6139 | 26724
23458 | 396.8602 | 26724
23459 | 424.5803 | 26724
23460 | 406.1517 | 26724
23461 | 425.7373 | 26724
23462 | 426.3702 | 26724
23463 | 413.4676 | 26724
23464 | 418.7898 | 26724
23465 | 413.7168 | 26724
23466 | 420.5325 | 26724
23467 | 427.5786 | 26724
23468 | 400.6852 | 26724
23469 | 418.2811 | 26724
23470 | 416.6817 | 26724
23471 | 419.9233 | 26724
23472 | 419.2749 | 26724
23473 | 415.2995 | 26724
23474 | 420.995 | 26724
23475 | 402.7236 | 26724
23476 | 416.5241 | 26724
23477 | 405.1049 | 26724
23478 | 418.3654 | 26724
23479 | 418.6102 | 26724
23480 | 424.1695 | 26724
23481 | 422.8544 | 26724
23482 | 434.4806 | 26724
23483 | 417.3617 | 26724
23484 | 415.617 | 26724
23485 | 421.1374 | 26724
23486 | 415.9239 | 26724
23487 | 423.0993 | 26724
23488 | 410.4702 | 26724
23489 | 424.8773 | 26724
23490 | 416.9769 | 26724
23491 | 421.5789 | 26724
23492 | 417.0352 | 26724
23493 | 415.1516 | 26724
23494 | 419.8246 | 26724
23495 | 416.74 | 26724
23496 | 410.0083 | 26724
23497 | 411.085 | 26724
23498 | 413.7056 | 26724
23499 | 414.0709 | 26724
23500 | 406.0284 | 26724
23501 | 401.6001 | 26724
23502 | 423.7908 | 26724
23503 | 417.6037 | 26724
23504 | 409.8879 | 26724
23505 | 414.1467 | 26724
23506 | 408.8684 | 26724
23507 | 402.6473 | 26724
23508 | 425.3131 | 26724
23509 | 408.4223 | 26724
23510 | 419.5621 | 26724
23511 | 420.4379 | 26724
23512 | 401.7111 | 26724
23513 | 413.5253 | 26724
23514 | 414.3324 | 26724
23515 | 417.2882 | 26724
23516 | 419.0272 | 26724
23517 | 408.9616 | 26724
23518 | 413.3249 | 26724
23519 | 427.0078 | 26724
23520 | 431.6286 | 26724
23521 | 411.8403 | 26724
23522 | 415.5362 | 26724
23523 | 406.8147 | 26724
23524 | 423.303 | 26724
23525 | 421.1874 | 26724
23526 | 413.7583 | 26724
23527 | 424.6473 | 26724
23528 | 428.1261 | 26724
23529 | 416.0298 | 26724
23530 | 425.3345 | 26724
23531 | 418.6172 | 26724
23532 | 406.4762 | 26724
23533 | 412.251 | 26724
23534 | 422.0923 | 26724
23535 | 413.1134 | 26724
23536 | 412.945 | 26724
23537 | 403.763 | 26724
23538 | 418.9416 | 26724
23539 | 415.6668 | 26724
23540 | 420.7464 | 26724
23541 | 431.1175 | 26724
23542 | 417.7947 | 26724
23543 | 410.9813 | 26724
23544 | 411.7155 | 26724
23545 | 418.6154 | 26724
23546 | 415.3091 | 26724
23547 | 426.3077 | 26724
23548 | 410.5082 | 26724
23549 | 416.8988 | 26724
23550 | 410.8052 | 26724
23551 | 425.3402 | 26724
23552 | 409.5108 | 26724
23553 | 422.2152 | 26724
23554 | 426.3107 | 26724
23555 | 411.9112 | 26724
23556 | 425.2381 | 26724
23557 | 431.9294 | 26724
23558 | 421.7786 | 26724
23559 | 408.1544 | 26724
23560 | 431.1256 | 26724
23561 | 424.4163 | 26724
23562 | 414.2265 | 26724
23563 | 415.1752 | 26724
23564 | 425.7709 | 26724
23565 | 419.8029 | 26724
23566 | 419.2401 | 26724
23567 | 423.3869 | 26724
23568 | 419.5322 | 26724
23569 | 413.6791 | 26724
23570 | 413.9818 | 26724
23571 | 411.8865 | 26724
23572 | 402.2453 | 26724
23573 | 419.5443 | 26724
23574 | 435.5306 | 26724
23575 | 429.7606 | 26724
23576 | 426.7139 | 26724
23577 | 421.4763 | 26724
23578 | 418.9272 | 26724
23579 | 413.3107 | 26724
23580 | 429.2802 | 26724
23581 | 430.0038 | 26724
23582 | 420.6806 | 26724
23583 | 411.6302 | 26724
23584 | 407.5292 | 26724
23585 | 422.3899 | 26724
23586 | 410.3164 | 26724
23587 | 418.3696 | 26724
23588 | 420.9531 | 26724
23589 | 415.4167 | 26724
23590 | 415.9504 | 26724
23591 | 418.5584 | 26724
23592 | 427.2876 | 26724
23593 | 414.7326 | 26724
23594 | 409.7847 | 26724
23595 | 407.7552 | 26724
23596 | 423.2586 | 26724
23597 | 420.465 | 26724
23598 | 415.8117 | 26724
23599 | 413.0193 | 26724
23600 | 417.0409 | 26724
23601 | 420.909 | 26724
23602 | 415.9064 | 26724
23603 | 420.8604 | 26724
23604 | 420.768 | 26724
23605 | 407.0413 | 26724
23606 | 430.4081 | 26724
23607 | 417.4552 | 26724
23608 | 423.3926 | 26724
23609 | 407.3599 | 26724
23610 | 419.257 | 26724
23611 | 394.3864 | 26724
23612 | 410.723 | 26724
23613 | 419.8953 | 26724
23614 | 429.4623 | 26724
23615 | 410.0392 | 26724
23616 | 412.2062 | 26724
23617 | 413.6705 | 26724
23618 | 425.5063 | 26724
23619 | 416.5976 | 26724
23620 | 422.2247 | 26724
23621 | 421.8787 | 26724
23622 | 413.8647 | 26724
23623 | 423.5031 | 26724
23624 | 417.1908 | 26724
23625 | 420.8863 | 26724
23626 | 417.7295 | 26724
23627 | 412.742 | 26724
23628 | 421.8117 | 26724
23629 | 415.4981 | 26724
23630 | 417.7903 | 26724
23631 | 415.8241 | 26724
23632 | 420.1715 | 26724
23633 | 423.2294 | 26724
23634 | 413.5559 | 26724
23635 | 424.955 | 26724
23636 | 425.4545 | 26724
23637 | 422.289 | 26724
23638 | 412.1438 | 26724
23639 | 417.6824 | 26724
23640 | 429.4495 | 26724
23641 | 430.8057 | 26724
23642 | 413.0715 | 26724
23643 | 429.1159 | 26724
23644 | 426.5223 | 26724
23645 | 422.7458 | 26724
23646 | 422.5258 | 26724
23647 | 406.4368 | 26724
23648 | 404.3215 | 26724
23649 | 418.2524 | 26724
23650 | 417.9058 | 26724
23651 | 414.7266 | 26724
23652 | 418.9451 | 26724
23653 | 399.5897 | 26724
23654 | 415.6476 | 26724
23655 | 393.9635 | 26724
23656 | 401.8497 | 26724
23657 | 410.656 | 26724
23658 | 418.9711 | 26724
23659 | 420.3493 | 26724
23660 | 418.9954 | 26724
23661 | 417.0253 | 26724
23662 | 416.505 | 26724
23663 | 415.1987 | 26724
23664 | 410.6238 | 26724
23665 | 424.1966 | 26724
23666 | 416.4039 | 26724
23667 | 418.1046 | 26724
23668 | 397.3411 | 26724
23669 | 423.2929 | 26724
23670 | 417.7719 | 26724
23671 | 416.511 | 26724
23672 | 401.7193 | 26724
23673 | 409.9559 | 26724
23674 | 431.6833 | 26724
23675 | 403.7825 | 26724
23676 | 410.5605 | 26724
23677 | 425.7055 | 26724
23678 | 433.9369 | 26724
23679 | 407.2286 | 26724
23680 | 404.7464 | 26724
23681 | 424.6211 | 26724
23682 | 416.0651 | 26724
23683 | 404.9264 | 26724
23684 | 411.6813 | 26724
23685 | 418.9054 | 26724
23686 | 417.98 | 26724
23687 | 419.5005 | 26724
23688 | 415.5012 | 26724
23689 | 420.6035 | 26724
23690 | 421.335 | 26724
23691 | 401.045 | 26724
23692 | 427.125 | 26724
23693 | 412.05 | 26724
23694 | 409.8497 | 26724
23695 | 406.1293 | 26724
23696 | 406.4835 | 26724
23697 | 408.8714 | 26724
23698 | 412.9512 | 26724
23699 | 418.1957 | 26724
23700 | 420.7499 | 26724
23701 | 411.0914 | 26724
23702 | 423.9163 | 26724
23703 | 438.0186 | 26724
23704 | 397.5196 | 26724
23705 | 418.5862 | 26724
23706 | 417.4739 | 26724
23707 | 428.4204 | 26724
23708 | 401.1234 | 26724
23709 | 416.6829 | 26724
23710 | 422.6943 | 26724
23711 | 422.5973 | 26724
23712 | 424.2133 | 26724
23713 | 410.0616 | 26724
23714 | 427.8986 | 26724
23715 | 409.2663 | 26724
23716 | 415.5998 | 26724
23717 | 431.474 | 26724
23718 | 414.2952 | 26724
23719 | 407.1975 | 26724
23720 | 422.9979 | 26724
23721 | 411.9473 | 26724
23722 | 408.8973 | 26724
23723 | 413.4122 | 26724
23724 | 416.4688 | 26724
23725 | 425.0059 | 26724
23726 | 407.6783 | 26724
23727 | 422.1539 | 26724
23728 | 428.7734 | 26724
23729 | 423.1647 | 26724
23730 | 411.4664 | 26724
23731 | 410.4801 | 26724
23732 | 409.7926 | 26724
23733 | 405.7194 | 26724
23734 | 412.0061 | 26724
23735 | 411.0208 | 26724
23736 | 419.8992 | 26724
23737 | 407.4328 | 26724
23738 | 412.0452 | 26724
23739 | 418.2091 | 26724
23740 | 419.3982 | 26724
23741 | 417.5797 | 26724
23742 | 408.2124 | 26724
23743 | 420.5989 | 26724
23744 | 420.7051 | 26724
23745 | 421.4697 | 26724
23746 | 431.8071 | 26724
23747 | 416.0837 | 26724
23748 | 420.2717 | 26724
23749 | 433.2815 | 26724
23750 | 418.0585 | 26724
23751 | 396.3966 | 26724
23752 | 408.5458 | 26724
23753 | 401.6845 | 26724
23754 | 415.7819 | 26724
23755 | 405.5225 | 26724
23756 | 431.072 | 26724
23757 | 414.0979 | 26724
23758 | 426.0123 | 26724
23759 | 407.2779 | 26724
23760 | 416.9471 | 26724
23761 | 405.3148 | 26724
23762 | 418.4595 | 26724
23763 | 420.3162 | 26724
23764 | 424.8745 | 26724
23765 | 410.0294 | 26724
23766 | 414.4504 | 26724
23767 | 418.9659 | 26724
23768 | 428.4576 | 26724
23769 | 406.46 | 26724
23770 | 429.3918 | 26724
23771 | 419.5388 | 26724
23772 | 410.8253 | 26724
23773 | 422.4244 | 26724
23774 | 414.3307 | 26724
23775 | 415.2311 | 26724
23776 | 427.5757 | 26724
23777 | 417.8042 | 26724
23778 | 426.415 | 26724
23779 | 423.343 | 26724
23780 | 414.1754 | 26724
23781 | 415.736 | 26724
23782 | 411.6478 | 26724
23783 | 412.7418 | 26724
23784 | 407.2543 | 26724
23785 | 415.203 | 26724
23786 | 403.1684 | 26724
23787 | 425.1294 | 26724
23788 | 395.8239 | 26724
23789 | 409.792 | 26724
23790 | 433.7788 | 26724
23791 | 415.9368 | 26724
23792 | 413.8193 | 26724
23793 | 410.0238 | 26724
23794 | 417.1479 | 26724
23795 | 433.0656 | 26724
23796 | 407.5394 | 26724
23797 | 408.9195 | 26724
23798 | 420.6215 | 26724
23799 | 407.5053 | 26724
23800 | 415.3635 | 26724
23801 | 403.7535 | 26724
23802 | 412.2377 | 26724
23803 | 419.4144 | 26724
23804 | 408.6181 | 26724
23805 | 427.0535 | 26724
23806 | 426.0743 | 26724
23807 | 415.4572 | 26724
23808 | 422.5595 | 26724
23809 | 415.8665 | 26724
23810 | 431.7703 | 26724
23811 | 430.0914 | 26724
23812 | 422.2143 | 26724
23813 | 404.6135 | 26724
23814 | 406.6548 | 26724
23815 | 426.7812 | 26724
23816 | 406.7271 | 26724
23817 | 415.127 | 26724
23818 | 413.0062 | 26724
23819 | 412.5356 | 26724
23820 | 425.6099 | 26724
23821 | 419.7701 | 26724
23822 | 405.2631 | 26724
23823 | 425.4369 | 26724
23824 | 410.3454 | 26724
23825 | 405.0035 | 26724
23826 | 434.9681 | 26724
23827 | 426.9588 | 26724
23828 | 423.4075 | 26724
23829 | 421.543 | 26724
23830 | 419.3557 | 26724
23831 | 400.6673 | 26724
23832 | 424.0719 | 26724
23833 | 420.4167 | 26724
23834 | 412.3026 | 26724
23835 | 420.5165 | 26724
23836 | 420.9558 | 26724
23837 | 427.4565 | 26724
23838 | 410.2829 | 26724
23839 | 419.74 | 26724
23840 | 418.1142 | 26724
23841 | 426.2492 | 26724
23842 | 406.1595 | 26724
23843 | 417.6051 | 26724
23844 | 414.7519 | 26724
23845 | 412.866 | 26724
23846 | 408.4183 | 26724
23847 | 413.4069 | 26724
23848 | 418.2097 | 26724
23849 | 415.0214 | 26724
23850 | 407.5266 | 26724
23851 | 411.3873 | 26724
23852 | 412.5049 | 26724
23853 | 414.3966 | 26724
23854 | 411.988 | 26724
23855 | 412.9388 | 26724
23856 | 423.9533 | 26724
23857 | 412.8803 | 26724
23858 | 405.4008 | 26724
23859 | 412.9532 | 26724
23860 | 424.4246 | 26724
23861 | 411.9364 | 26724
23862 | 411.9086 | 26724
23863 | 416.1462 | 26724
23864 | 423.6128 | 26724
23865 | 408.5329 | 26724
23866 | 418.0753 | 26724
23867 | 420.0462 | 26724
23868 | 419.9112 | 26724
23869 | 402.3105 | 26724
23870 | 430.651 | 26724
23871 | 426.7973 | 26724
23872 | 407.5048 | 26724
23873 | 421.0666 | 26724
23874 | 410.6262 | 26724
23875 | 406.2795 | 26724
23876 | 407.5818 | 26724
23877 | 429.4193 | 26724
23878 | 414.2805 | 26724
23879 | 407.268 | 26724
23880 | 418.2085 | 26724
23881 | 421.5754 | 26724
23882 | 425.0295 | 26724
23883 | 419.6671 | 26724
23884 | 436.8704 | 26724
23885 | 416.8406 | 26724
23886 | 409.9288 | 26724
23887 | 426.7022 | 26724
23888 | 419.9581 | 26724
23889 | 420.2019 | 26724
23890 | 406.4078 | 26724
23891 | 411.3005 | 26724
23892 | 422.5491 | 26724
23893 | 423.0689 | 26724
23894 | 409.5888 | 26724
23895 | 425.6272 | 26724
23896 | 419.1183 | 26724
23897 | 419.0296 | 26724
23898 | 426.3637 | 26724
23899 | 410.6612 | 26724
23900 | 423.0906 | 26724
23901 | 416.1172 | 26724
23902 | 410.2844 | 26724
23903 | 398.8221 | 26724
23904 | 424.4097 | 26724
23905 | 422.2567 | 26724
23906 | 433.5982 | 26724
23907 | 413.9525 | 26724
23908 | 422.6549 | 26724
23909 | 428.4504 | 26724
23910 | 419.2587 | 26724
23911 | 418.7619 | 26724
23912 | 404.5867 | 26724
23913 | 399.8339 | 26724
23914 | 416.8267 | 26724
23915 | 415.9727 | 26724
23916 | 398.1916 | 26724
23917 | 410.6185 | 26724
23918 | 418.6342 | 26724
23919 | 411.444 | 26724
23920 | 421.7956 | 26724
23921 | 413.627 | 26724
23922 | 412.9452 | 26724
23923 | 420.6599 | 26724
23924 | 432.3733 | 26724
23925 | 411.0233 | 26724
23926 | 415.4669 | 26724
23927 | 420.3433 | 26724
23928 | 403.8754 | 26724
23929 | 425.2001 | 26724
23930 | 411.9803 | 26724
23931 | 436.1462 | 26724
23932 | 409.9044 | 26724
23933 | 403.7293 | 26724
23934 | 420.2736 | 26724
23935 | 408.6374 | 26724
23936 | 409.371 | 26724
23937 | 404.1353 | 26724
23938 | 409.2897 | 26724
23939 | 422.1953 | 26724
23940 | 410.3979 | 26724
23941 | 408.1603 | 26724
23942 | 413.192 | 26724
23943 | 411.162 | 26724
23944 | 399.2318 | 26724
23945 | 408.7237 | 26724
23946 | 413.3364 | 26724
23947 | 412.7502 | 26724
23948 | 412.4789 | 26724
23949 | 429.6306 | 26724
23950 | 433.439 | 26724
23951 | 423.7896 | 26724
23952 | 405.7307 | 26724
23953 | 410.9713 | 26724
23954 | 411.2583 | 26724
23955 | 410.7579 | 26724
23956 | 418.9555 | 26724
23957 | 428.309 | 26724
23958 | 428.0523 | 26724
23959 | 413.5961 | 26724
23960 | 412.375 | 26724
23961 | 406.2371 | 26724
23962 | 413.3051 | 26724
23963 | 417.7378 | 26724
23964 | 411.5699 | 26724
23965 | 422.1967 | 26724
23966 | 413.5795 | 26724
23967 | 421.1186 | 26724
23968 | 425.0325 | 26724
23969 | 419.7212 | 26724
23970 | 421.61 | 26724
23971 | 415.8018 | 26724
23972 | 429.8438 | 26724
23973 | 418.2799 | 26724
23974 | 409.6692 | 26724
23975 | 429.1676 | 26724
23976 | 435.7369 | 26724
23977 | 417.2512 | 26724
23978 | 429.5384 | 26724
23979 | 417.4935 | 26724
23980 | 397.1938 | 26724
23981 | 415.2599 | 26724
23982 | 413.4869 | 26724
23983 | 407.8775 | 26724
23984 | 416.2181 | 26724
23985 | 405.5086 | 26724
23986 | 427.9343 | 26724
23987 | 414.6303 | 26724
23988 | 408.4349 | 26724
23989 | 419.7228 | 26724
23990 | 417.6494 | 26724
23991 | 420.9885 | 26724
23992 | 420.2976 | 26724
23993 | 412.9943 | 26724
23994 | 421.0083 | 26724
23995 | 412.3197 | 26724
23996 | 408.9424 | 26724
23997 | 418.0182 | 26724
23998 | 415.1362 | 26724
23999 | 418.6275 | 26724
24000 | 419.9048 | 26724
24001 | 428.5251 | 26724
24002 | 425.9584 | 26724
24003 | 425.3795 | 26724
24004 | 399.5485 | 26724
24005 | 408.2724 | 26724
24006 | 404.8824 | 26724
24007 | 411.6575 | 26724
24008 | 412.9152 | 26724
24009 | 419.8233 | 26724
24010 | 417.7861 | 26724
24011 | 405.852 | 26724
24012 | 407.7325 | 26724
24013 | 421.1635 | 26724
24014 | 422.7873 | 26724
24015 | 410.6495 | 26724
24016 | 416.5357 | 26724
24017 | 424.5938 | 26724
24018 | 406.7466 | 26724
24019 | 404.9222 | 26724
24020 | 415.2259 | 26724
24021 | 414.6289 | 26724
24022 | 422.4672 | 26724
24023 | 421.8476 | 26724
24024 | 405.9211 | 26724
24025 | 430.7034 | 26724
24026 | 409.1085 | 26724
24027 | 428.6687 | 26724
24028 | 418.2429 | 26724
24029 | 429.7745 | 26724
24030 | 400.8506 | 26724
24031 | 424.0591 | 26724
24032 | 416.2299 | 26724
24033 | 418.0775 | 26724
24034 | 413.4113 | 26724
24035 | 414.2288 | 26724
24036 | 410.3136 | 26724
24037 | 421.0285 | 26724
24038 | 408.8008 | 26724
24039 | 402.9126 | 26724
24040 | 425.9558 | 26724
24041 | 412.889 | 26724
24042 | 423.0769 | 26724
24043 | 413.2854 | 26724
24044 | 402.3076 | 26724
24045 | 402.9179 | 26724
24046 | 414.6733 | 26724
24047 | 421.7745 | 26724
24048 | 424.5141 | 26724
24049 | 411.9103 | 26724
24050 | 421.4399 | 26724
24051 | 423.9175 | 26724
24052 | 420.5485 | 26724
24053 | 421.6224 | 26724
24054 | 423.72 | 26724
24055 | 406.5752 | 26724
24056 | 421.195 | 26724
24057 | 404.068 | 26724
24058 | 419.8513 | 26724
24059 | 421.077 | 26724
24060 | 399.7114 | 26724
24061 | 430.0041 | 26724
24062 | 414.2997 | 26724
24063 | 423.9145 | 26724
24064 | 435.8539 | 26724
24065 | 428.4335 | 26724
24066 | 419.4973 | 26724
24067 | 409.1984 | 26724
24068 | 426.2592 | 26724
24069 | 426.428 | 26724
24070 | 403.9647 | 26724
24071 | 408.6583 | 26724
24072 | 408.9011 | 26724
24073 | 422.183 | 26724
24074 | 418.7808 | 26724
24075 | 412.5831 | 26724
24076 | 427.1511 | 26724
24077 | 410.7059 | 26724
24078 | 408.4425 | 26724
24079 | 422.407 | 26724
24080 | 410.5456 | 26724
24081 | 409.8503 | 26724
24082 | 422.8336 | 26724
24083 | 420.3248 | 26724
24084 | 423.5686 | 26724
24085 | 429.5312 | 26724
24086 | 412.4482 | 26724
24087 | 419.4332 | 26724
24088 | 419.0752 | 26724
24089 | 418.8093 | 26724
24090 | 414.5513 | 26724
24091 | 393.5531 | 26724
24092 | 414.5902 | 26724
24093 | 410.5576 | 26724
24094 | 423.1154 | 26724
24095 | 423.9014 | 26724
24096 | 403.8432 | 26724
24097 | 416.1412 | 26724
24098 | 423.4016 | 26724
24099 | 413.0051 | 26724
24100 | 417.2596 | 26724
24101 | 411.6291 | 26724
24102 | 416.5971 | 26724
24103 | 416.5034 | 26724
24104 | 411.7065 | 26724
24105 | 401.4463 | 26724
24106 | 416.4014 | 26724
24107 | 430.9573 | 26724
24108 | 414.6527 | 26724
24109 | 416.6536 | 26724
24110 | 413.8056 | 26724
24111 | 411.6288 | 26724
24112 | 420.9154 | 26724
24113 | 420.2717 | 26724
24114 | 410.5711 | 26724
24115 | 423.6619 | 26724
24116 | 419.5253 | 26724
24117 | 401.966 | 26724
24118 | 415.9151 | 26724
24119 | 409.8813 | 26724
24120 | 407.041 | 26724
24121 | 420.0809 | 26724
24122 | 409.9751 | 26724
24123 | 414.1035 | 26724
24124 | 435.9799 | 26724
24125 | 411.3823 | 26724
24126 | 415.9208 | 26724
24127 | 412.9089 | 26724
24128 | 410.9943 | 26724
24129 | 415.4852 | 26724
24130 | 414.175 | 26724
24131 | 411.195 | 26724
24132 | 410.417 | 26724
24133 | 414.6411 | 26724
24134 | 423.2441 | 26724
24135 | 418.6656 | 26724
24136 | 429.0056 | 26724
24137 | 409.244 | 26724
24138 | 411.7879 | 26724
24139 | 412.2905 | 26724
24140 | 419.8727 | 26724
24141 | 426.9248 | 26724
24142 | 421.7782 | 26724
24143 | 417.1269 | 26724
24144 | 412.4434 | 26724
24145 | 405.757 | 26724
24146 | 419.8386 | 26724
24147 | 418.5886 | 26724
24148 | 408.4526 | 26724
24149 | 416.4966 | 26724
24150 | 415.3641 | 26724
24151 | 410.2626 | 26724
24152 | 413.8411 | 26724
24153 | 410.4576 | 26724
24154 | 411.4794 | 26724
24155 | 413.6197 | 26724
24156 | 421.9682 | 26724
24157 | 401.8933 | 26724
24158 | 419.8183 | 26724
24159 | 401.6272 | 26724
24160 | 417.561 | 26724
24161 | 419.9534 | 26724
24162 | 409.3211 | 26724
24163 | 402.4973 | 26724
24164 | 412.8337 | 26724
24165 | 417.9153 | 26724
24166 | 422.5124 | 26724
24167 | 411.3334 | 26724
24168 | 418.8589 | 26724
24169 | 436.1962 | 26724
24170 | 416.0895 | 26724
24171 | 415.988 | 26724
24172 | 422.6258 | 26724
24173 | 411.1149 | 26724
24174 | 420.4119 | 26724
24175 | 406.0279 | 26724
24176 | 420.558 | 26724
24177 | 415.6067 | 26724
24178 | 429.569 | 26724
24179 | 414.5962 | 26724
24180 | 425.8315 | 26724
24181 | 406.847 | 26724
24182 | 421.627 | 26724
24183 | 412.5841 | 26724
24184 | 419.7832 | 26724
24185 | 424.8961 | 26724
24186 | 406.3805 | 26724
24187 | 416.8816 | 26724
24188 | 415.2205 | 26724
24189 | 427.0538 | 26724
24190 | 414.5304 | 26724
24191 | 407.1114 | 26724
24192 | 412.8058 | 26724
24193 | 400.9901 | 26724
24194 | 415.5534 | 26724
24195 | 415.2394 | 26724
24196 | 421.6367 | 26724
24197 | 415.0224 | 26724
24198 | 411.7541 | 26724
24199 | 404.5682 | 26724
24200 | 423.174 | 26724
24201 | 403.9775 | 26724
24202 | 414.6673 | 26724
24203 | 413.0198 | 26724
24204 | 413.1009 | 26724
24205 | 432.344 | 26724
24206 | 423.4202 | 26724
24207 | 426.2953 | 26724
24208 | 404.4459 | 26724
24209 | 420.0669 | 26724
24210 | 423.7464 | 26724
24211 | 415.0259 | 26724
24212 | 422.7252 | 26724
24213 | 416.9484 | 26724
24214 | 401.6316 | 26724
24215 | 424.8493 | 26724
24216 | 414.3832 | 26724
24217 | 431.8256 | 26724
24218 | 421.2098 | 26724
24219 | 427.3962 | 26724
24220 | 414.5195 | 26724
24221 | 419.8403 | 26724
24222 | 421.3429 | 26724
24223 | 419.4158 | 26724
24224 | 411.0293 | 26724
24225 | 404.8084 | 26724
24226 | 407.7737 | 26724
24227 | 413.6842 | 26724
24228 | 402.1282 | 26724
24229 | 417.4898 | 26724
24230 | 410.5307 | 26724
24231 | 415.7562 | 26724
24232 | 412.3964 | 26724
24233 | 422.1141 | 26724
24234 | 432.4985 | 26724
24235 | 419.6681 | 26724
24236 | 422.4174 | 26724
24237 | 415.1268 | 26724
24238 | 415.9063 | 26724
24239 | 415.1274 | 26724
24240 | 396.1368 | 26724
24241 | 411.4056 | 26724
24242 | 412.3534 | 26724
24243 | 422.4905 | 26724
24244 | 430.5834 | 26724
24245 | 413.6078 | 26724
24246 | 420.0485 | 26724
24247 | 418.3711 | 26724
24248 | 408.2524 | 26724
24249 | 416.5584 | 26724
24250 | 425.3616 | 26724
24251 | 407.374 | 26724
24252 | 429.5831 | 26724
24253 | 420.5789 | 26724
24254 | 420.5287 | 26724
24255 | 424.484 | 26724
24256 | 419.3154 | 26724
24257 | 427.9161 | 26724
24258 | 405.8319 | 26724
24259 | 427.3625 | 26724
24260 | 409.3089 | 26724
24261 | 428.9299 | 26724
24262 | 423.0864 | 26724
24263 | 410.2204 | 26724
24264 | 419.9269 | 26724
24265 | 420.4649 | 26724
24266 | 402.8654 | 26724
24267 | 409.6293 | 26724
24268 | 410.5185 | 26724
24269 | 438.9525 | 26724
24270 | 410.1279 | 26724
24271 | 405.3632 | 26724
24272 | 404.3959 | 26724
24273 | 416.9681 | 26724
24274 | 420.5281 | 26724
24275 | 415.0909 | 26724
24276 | 409.4081 | 26724
24277 | 423.761 | 26724
24278 | 423.5012 | 26724
24279 | 423.9165 | 26724
24280 | 417.4819 | 26724
24281 | 421.2043 | 26724
24282 | 419.7122 | 26724
24283 | 402.7673 | 26724
24284 | 412.9236 | 26724
24285 | 410.9024 | 26724
24286 | 413.9516 | 26724
24287 | 401.0392 | 26724
24288 | 406.4087 | 26724
24289 | 417.5905 | 26724
24290 | 406.286 | 26724
24291 | 415.5651 | 26724
24292 | 413.4936 | 26724
24293 | 419.2172 | 26724
24294 | 425.7444 | 26724
24295 | 419.4505 | 26724
24296 | 400.1179 | 26724
24297 | 417.2803 | 26724
24298 | 434.5346 | 26724
24299 | 408.8086 | 26724
24300 | 402.4188 | 26724
24301 | 410.3066 | 26724
24302 | 408.9225 | 26724
24303 | 424.2266 | 26724
24304 | 414.7228 | 26724
24305 | 424.6796 | 26724
24306 | 419.4121 | 26724
24307 | 414.3291 | 26724
24308 | 405.4634 | 26724
24309 | 408.7699 | 26724
24310 | 424.0838 | 26724
24311 | 413.0209 | 26724
24312 | 414.9918 | 26724
24313 | 417.5612 | 26724
24314 | 417.4951 | 26724
24315 | 425.2985 | 26724
24316 | 414.9632 | 26724
24317 | 414.0055 | 26724
24318 | 420.5333 | 26724
24319 | 427.1709 | 26724
24320 | 428.1043 | 26724
24321 | 402.9728 | 26724
24322 | 421.35 | 26724
24323 | 424.752 | 26724
24324 | 409.5544 | 26724
24325 | 413.3006 | 26724
24326 | 415.4927 | 26724
24327 | 426.3901 | 26724
24328 | 425.7235 | 26724
24329 | 414.788 | 26724
24330 | 423.5361 | 26724
24331 | 400.5161 | 26724
24332 | 411.4734 | 26724
24333 | 416.1279 | 26724
24334 | 428.7411 | 26724
24335 | 414.7986 | 26724
24336 | 408.7058 | 26724
24337 | 406.1123 | 26724
24338 | 408.596 | 26724
24339 | 412.9407 | 26724
24340 | 413.7043 | 26724
24341 | 410.6674 | 26724
24342 | 417.0301 | 26724
24343 | 414.2638 | 26724
24344 | 405.432 | 26724
24345 | 428.4638 | 26724
24346 | 418.293 | 26724
24347 | 421.9902 | 26724
24348 | 401.1264 | 26724
24349 | 416.3761 | 26724
24350 | 407.1163 | 26724
24351 | 408.2916 | 26724
24352 | 420.7075 | 26724
24353 | 401.5788 | 26724
24354 | 427.7131 | 26724
24355 | 417.6565 | 26724
24356 | 414.2918 | 26724
24357 | 422.5011 | 26724
24358 | 415.334 | 26724
24359 | 424.0696 | 26724
24360 | 420.5849 | 26724
24361 | 421.4432 | 26724
24362 | 413.5066 | 26724
24363 | 428.8661 | 26724
24364 | 410.4811 | 26724
24365 | 428.6082 | 26724
24366 | 423.2577 | 26724
24367 | 421.8151 | 26724
24368 | 415.9375 | 26724
24369 | 409.4304 | 26724
24370 | 416.9101 | 26724
24371 | 415.9021 | 26724
24372 | 424.331 | 26724
24373 | 415.375 | 26724
24374 | 413.0459 | 26724
24375 | 422.0688 | 26724
24376 | 409.5524 | 26724
24377 | 423.0143 | 26724
24378 | 419.2875 | 26724
24379 | 418.3984 | 26724
24380 | 395.1503 | 26724
24381 | 414.7622 | 26724
24382 | 418.1874 | 26724
24383 | 409.4564 | 26724
24384 | 411.4548 | 26724
24385 | 425.529 | 26724
24386 | 431.2608 | 26724
24387 | 419.1361 | 26724
24388 | 419.08 | 26724
24389 | 409.1781 | 26724
24390 | 406.3646 | 26724
24391 | 426.4109 | 26724
24392 | 412.6716 | 26724
24393 | 414.3113 | 26724
24394 | 421.6782 | 26724
24395 | 418.5859 | 26724
24396 | 400.8544 | 26724
24397 | 420.9852 | 26724
24398 | 410.6748 | 26724
24399 | 408.027 | 26724
24400 | 421.4596 | 26724
24401 | 420.4349 | 26724
24402 | 418.6984 | 26724
24403 | 425.4857 | 26724
24404 | 414.2059 | 26724
24405 | 403.7552 | 26724
24406 | 405.2073 | 26724
24407 | 416.355 | 26724
24408 | 408.0385 | 26724
24409 | 396.8699 | 26724
24410 | 408.8229 | 26724
24411 | 413.1496 | 26724
24412 | 422.9893 | 26724
24413 | 414.2187 | 26724
24414 | 414.2319 | 26724
24415 | 417.7855 | 26724
24416 | 407.4242 | 26724
24417 | 418.4123 | 26724
24418 | 404.8661 | 26724
24419 | 411.6909 | 26724
24420 | 409.2466 | 26724
24421 | 400.7124 | 26724
24422 | 421.7265 | 26724
24423 | 422.9114 | 26724
24424 | 411.9663 | 26724
24425 | 434.2271 | 26724
24426 | 419.7481 | 26724
24427 | 409.2767 | 26724
24428 | 420.2218 | 26724
24429 | 421.987 | 26724
24430 | 423.1865 | 26724
24431 | 407.1984 | 26724
24432 | 417.456 | 26724
24433 | 401.344 | 26724
24434 | 424.4204 | 26724
24435 | 426.4402 | 26724
24436 | 421.7364 | 26724
24437 | 417.7536 | 26724
24438 | 411.0288 | 26724
24439 | 426.1374 | 26724
24440 | 414.0627 | 26724
24441 | 427.5681 | 26724
24442 | 410.7986 | 26724
24443 | 428.131 | 26724
24444 | 418.132 | 26724
24445 | 432.6161 | 26724
24446 | 410.9606 | 26724
24447 | 433.4275 | 26724
24448 | 403.3776 | 26724
24449 | 402.2247 | 26724
24450 | 421.8935 | 26724
24451 | 414.4434 | 26724
24452 | 419.6807 | 26724
24453 | 403.908 | 26724
24454 | 428.706 | 26724
24455 | 414.4774 | 26724
24456 | 432.1278 | 26724
24457 | 420.3138 | 26724
24458 | 430.6229 | 26724
24459 | 414.2507 | 26724
24460 | 410.6444 | 26724
24461 | 427.9068 | 26724
24462 | 401.8331 | 26724
24463 | 411.0286 | 26724
24464 | 414.4899 | 26724
24465 | 424.4637 | 26724
24466 | 421.4207 | 26724
24467 | 429.3662 | 26724
24468 | 421.5875 | 26724
24469 | 399.9784 | 26724
24470 | 418.279 | 26724
24471 | 403.4694 | 26724
24472 | 430.6875 | 26724
24473 | 416.7675 | 26724
24474 | 433.2057 | 26724
24475 | 409.7377 | 26724
24476 | 430.6778 | 26724
24477 | 412.6084 | 26724
24478 | 408.7775 | 26724
24479 | 420.6703 | 26724
24480 | 416.3698 | 26724
24481 | 407.4501 | 26724
24482 | 422.1424 | 26724
24483 | 412.2392 | 26724
24484 | 429.234 | 26724
24485 | 411.5812 | 26724
24486 | 405.6086 | 26724
24487 | 415.4999 | 26724
24488 | 420.7155 | 26724
24489 | 420.3571 | 26724
24490 | 409.465 | 26724
24491 | 411.4761 | 26724
24492 | 417.1885 | 26724
24493 | 425.1049 | 26724
24494 | 418.5559 | 26724
24495 | 405.6577 | 26724
24496 | 422.1332 | 26724
24497 | 413.6578 | 26724
24498 | 418.7119 | 26724
24499 | 410.595 | 26724
24500 | 408.8836 | 26724
24501 | 412.1054 | 26724
24502 | 425.9978 | 26724
24503 | 408.2998 | 26724
24504 | 424.1567 | 26724
24505 | 422.5887 | 26724
24506 | 428.267 | 26724
24507 | 429.0749 | 26724
24508 | 402.707 | 26724
24509 | 415.6456 | 26724
24510 | 430.7141 | 26724
24511 | 416.9671 | 26724
24512 | 413.8675 | 26724
24513 | 409.2725 | 26724
24514 | 416.7609 | 26724
24515 | 414.128 | 26724
24516 | 415.5341 | 26724
24517 | 427.9772 | 26724
24518 | 418.7402 | 26724
24519 | 415.896 | 26724
24520 | 421.7868 | 26724
24521 | 412.853 | 26724
24522 | 404.722 | 26724
24523 | 410.8375 | 26724
24524 | 414.5845 | 26724
24525 | 419.7446 | 26724
24526 | 417.1203 | 26724
24527 | 418.0918 | 26724
24528 | 412.937 | 26724
24529 | 420.1812 | 26724
24530 | 403.4994 | 26724
24531 | 417.7911 | 26724
24532 | 418.0467 | 26724
24533 | 430.9932 | 26724
24534 | 423.7515 | 26724
24535 | 415.5531 | 26724
24536 | 415.1452 | 26724
24537 | 428.4835 | 26724
24538 | 425.1891 | 26724
24539 | 410.1201 | 26724
24540 | 427.9504 | 26724
24541 | 416.3097 | 26724
24542 | 413.789 | 26724
24543 | 410.7729 | 26724
24544 | 411.218 | 26724
24545 | 413.9905 | 26724
24546 | 422.6337 | 26724
24547 | 419.9934 | 26724
24548 | 414.8756 | 26724
24549 | 420.0874 | 26724
24550 | 423.779 | 26724
24551 | 414.5836 | 26724
24552 | 408.7549 | 26724
24553 | 408.6905 | 26724
24554 | 422.7809 | 26724
24555 | 405.2116 | 26724
24556 | 415.943 | 26724
24557 | 418.5458 | 26724
24558 | 416.7657 | 26724
24559 | 415.645 | 26724
24560 | 423.6458 | 26724
24561 | 400.7407 | 26724
24562 | 416.2801 | 26724
24563 | 419.3568 | 26724
24564 | 412.0844 | 26724
24565 | 410.7177 | 26724
24566 | 407.473 | 26724
24567 | 402.9804 | 26724
24568 | 420.1384 | 26724
24569 | 423.5039 | 26724
24570 | 419.8654 | 26724
24571 | 402.7766 | 26724
24572 | 408.1117 | 26724
24573 | 403.6416 | 26724
24574 | 434.8079 | 26724
24575 | 413.4728 | 26724
24576 | 422.0928 | 26724
24577 | 416.4602 | 26724
24578 | 430.192 | 26724
24579 | 427.0427 | 26724
24580 | 416.542 | 26724
24581 | 413.9962 | 26724
24582 | 413.6322 | 26724
24583 | 418.221 | 26724
24584 | 414.8421 | 26724
24585 | 410.9286 | 26724
24586 | 411.4702 | 26724
24587 | 427.1228 | 26724
24588 | 403.8767 | 26724
24589 | 405.4832 | 26724
24590 | 409.6449 | 26724
24591 | 425.6239 | 26724
24592 | 416.8973 | 26724
24593 | 428.8145 | 26724
24594 | 428.7679 | 26724
24595 | 408.7382 | 26724
24596 | 411.7027 | 26724
24597 | 419.4954 | 26724
24598 | 422.2524 | 26724
24599 | 395.9702 | 26724
24600 | 418.0652 | 26724
24601 | 416.9605 | 26724
24602 | 403.1607 | 26724
24603 | 410.872 | 26724
24604 | 411.8141 | 26724
24605 | 414.8961 | 26724
24606 | 402.7137 | 26724
24607 | 413.1162 | 26724
24608 | 408.8312 | 26724
24609 | 418.8107 | 26724
24610 | 409.7744 | 26724
24611 | 412.1095 | 26724
24612 | 426.2147 | 26724
24613 | 415.0285 | 26724
24614 | 429.1545 | 26724
24615 | 421.8973 | 26724
24616 | 414.2646 | 26724
24617 | 409.6573 | 26724
24618 | 433.7685 | 26724
24619 | 419.1312 | 26724
24620 | 416.4798 | 26724
24621 | 403.1861 | 26724
24622 | 407.4253 | 26724
24623 | 420.2711 | 26724
24624 | 398.9565 | 26724
24625 | 426.5095 | 26724
24626 | 416.1589 | 26724
24627 | 423.063 | 26724
24628 | 399.5547 | 26724
24629 | 425.957 | 26724
24630 | 421.1082 | 26724
24631 | 423.9691 | 26724
24632 | 422.5159 | 26724
24633 | 419.7636 | 26724
24634 | 407.3537 | 26724
24635 | 422.8531 | 26724
24636 | 405.7999 | 26724
24637 | 418.2516 | 26724
24638 | 402.0503 | 26724
24639 | 422.4279 | 26724
24640 | 421.1081 | 26724
24641 | 406.7233 | 26724
24642 | 437.8143 | 26724
24643 | 401.0289 | 26724
24644 | 410.959 | 26724
24645 | 415.0505 | 26724
24646 | 406.6365 | 26724
24647 | 413.0208 | 26724
24648 | 429.8555 | 26724
24649 | 407.6022 | 26724
24650 | 412.785 | 26724
24651 | 404.6795 | 26724
24652 | 412.4948 | 26724
24653 | 413.8488 | 26724
24654 | 414.6705 | 26724
24655 | 412.5984 | 26724
24656 | 418.6267 | 26724
24657 | 412.8452 | 26724
24658 | 417.0437 | 26724
24659 | 422.0902 | 26724
24660 | 423.6134 | 26724
24661 | 409.4334 | 26724
24662 | 415.598 | 26724
24663 | 424.8878 | 26724
24664 | 419.3154 | 26724
24665 | 413.0885 | 26724
24666 | 418.7176 | 26724
24667 | 410.2948 | 26724
24668 | 410.9703 | 26724
24669 | 409.7059 | 26724
24670 | 430.116 | 26724
24671 | 409.4007 | 26724
24672 | 409.8882 | 26724
24673 | 409.1778 | 26724
24674 | 424.4093 | 26724
24675 | 435.2452 | 26724
24676 | 410.5639 | 26724
24677 | 413.4898 | 26724
24678 | 420.14 | 26724
24679 | 409.5311 | 26724
24680 | 417.3829 | 26724
24681 | 415.6317 | 26724
24682 | 430.6256 | 26724
24683 | 426.7527 | 26724
24684 | 413.9285 | 26724
24685 | 401.4393 | 26724
24686 | 413.004 | 26724
24687 | 426.467 | 26724
24688 | 415.9813 | 26724
24689 | 417.3453 | 26724
24690 | 424.309 | 26724
24691 | 428.9495 | 26724
24692 | 423.6966 | 26724
24693 | 425.607 | 26724
24694 | 416.0552 | 26724
24695 | 419.7103 | 26724
24696 | 420.1632 | 26724
24697 | 426.0072 | 26724
24698 | 412.3015 | 26724
24699 | 416.3877 | 26724
24700 | 417.218 | 26724
24701 | 426.0234 | 26724
24702 | 393.7583 | 26724
24703 | 430.4909 | 26724
24704 | 416.1107 | 26724
24705 | 422.3588 | 26724
24706 | 419.0026 | 26724
24707 | 423.6262 | 26724
24708 | 411.7791 | 26724
24709 | 409.7784 | 26724
24710 | 420.4549 | 26724
24711 | 411.898 | 26724
24712 | 422.0335 | 26724
24713 | 432.6121 | 26724
24714 | 402.5128 | 26724
24715 | 410.1684 | 26724
24716 | 421.6804 | 26724
24717 | 415.5721 | 26724
24718 | 407.9584 | 26724
24719 | 404.8678 | 26724
24720 | 414.1921 | 26724
24721 | 410.8812 | 26724
24722 | 415.3464 | 26724
24723 | 423.8266 | 26724
24724 | 411.2299 | 26724
24725 | 423.6275 | 26724
24726 | 415.2822 | 26724
24727 | 419.9914 | 26724
24728 | 416.5426 | 26724
24729 | 417.1994 | 26724
24730 | 418.726 | 26724
24731 | 420.9887 | 26724
24732 | 430.5073 | 26724
24733 | 401.568 | 26724
24734 | 427.0662 | 26724
24735 | 422.9555 | 26724
24736 | 427.8406 | 26724
24737 | 422.1723 | 26724
24738 | 426.808 | 26724
24739 | 405.185 | 26724
24740 | 413.2411 | 26724
24741 | 419.7773 | 26724
24742 | 425.2581 | 26724
24743 | 424.4153 | 26724
24744 | 418.4564 | 26724
24745 | 412.8326 | 26724
24746 | 420.5319 | 26724
24747 | 417.2186 | 26724
24748 | 422.6231 | 26724
24749 | 420.5589 | 26724
24750 | 404.967 | 26724
24751 | 426.6416 | 26724
24752 | 414.3468 | 26724
24753 | 409.7414 | 26724
24754 | 425.2219 | 26724
24755 | 411.4941 | 26724
24756 | 407.8279 | 26724
24757 | 403.4021 | 26724
24758 | 414.5377 | 26724
24759 | 401.8906 | 26724
24760 | 411.898 | 26724
24761 | 429.1413 | 26724
24762 | 418.3742 | 26724
24763 | 415.3591 | 26724
24764 | 413.3086 | 26724
24765 | 413.8016 | 26724
24766 | 424.0146 | 26724
24767 | 422.4782 | 26724
24768 | 410.4772 | 26724
24769 | 433.7425 | 26724
24770 | 428.0262 | 26724
24771 | 426.5744 | 26724
24772 | 410.593 | 26724
24773 | 423.0828 | 26724
24774 | 411.3226 | 26724
24775 | 406.5649 | 26724
24776 | 402.6572 | 26724
24777 | 426.9445 | 26724
24778 | 397.5681 | 26724
24779 | 422.3106 | 26724
24780 | 407.4048 | 26724
24781 | 428.9789 | 26724
24782 | 419.1816 | 26724
24783 | 415.8997 | 26724
24784 | 424.088 | 26724
24785 | 403.0169 | 26724
24786 | 415.6524 | 26724
24787 | 410.1844 | 26724
24788 | 411.9804 | 26724
24789 | 403.3321 | 26724
24790 | 408.3858 | 26724
24791 | 408.4318 | 26724
24792 | 402.4065 | 26724
24793 | 427.1446 | 26724
24794 | 402.0347 | 26724
24795 | 417.6864 | 26724
24796 | 418.3728 | 26724
24797 | 396.767 | 26724
24798 | 416.221 | 26724
24799 | 418.1895 | 26724
24800 | 428.0441 | 26724
24801 | 427.7841 | 26724
24802 | 412.5918 | 26724
24803 | 414.2007 | 26724
24804 | 440.5479 | 26724
24805 | 421.064 | 26724
24806 | 416.9009 | 26724
24807 | 407.6871 | 26724
24808 | 424.8021 | 26724
24809 | 417.3814 | 26724
24810 | 429.1911 | 26724
24811 | 430.7441 | 26724
24812 | 419.288 | 26724
24813 | 408.8171 | 26724
24814 | 426.1908 | 26724
24815 | 422.5922 | 26724
24816 | 410.3882 | 26724
24817 | 415.423 | 26724
24818 | 405.1008 | 26724
24819 | 415.9441 | 26724
24820 | 408.0538 | 26724
24821 | 425.469 | 26724
24822 | 428.4433 | 26724
24823 | 411.4063 | 26724
24824 | 406.3979 | 26724
24825 | 421.4803 | 26724
24826 | 407.2494 | 26724
24827 | 422.6048 | 26724
24828 | 430.2916 | 26724
24829 | 421.6458 | 26724
24830 | 412.1657 | 26724
24831 | 417.4213 | 26724
24832 | 406.2043 | 26724
24833 | 409.4207 | 26724
24834 | 427.7463 | 26724
24835 | 412.1922 | 26724
24836 | 409.5048 | 26724
24837 | 395.176 | 26724
24838 | 416.4973 | 26724
24839 | 409.4812 | 26724
24840 | 416.6984 | 26724
24841 | 427.8212 | 26724
24842 | 417.6674 | 26724
24843 | 428.6471 | 26724
24844 | 410.3447 | 26724
24845 | 407.3058 | 26724
24846 | 416.879 | 26724
24847 | 413.9128 | 26724
24848 | 420.7838 | 26724
24849 | 418.5147 | 26724
24850 | 422.0646 | 26724
24851 | 424.5513 | 26724
24852 | 410.2999 | 26724
24853 | 410.8263 | 26724
24854 | 415.4903 | 26724
24855 | 423.8441 | 26724
24856 | 419.6854 | 26724
24857 | 412.6883 | 26724
24858 | 423.8936 | 26724
24859 | 422.7252 | 26724
24860 | 427.6065 | 26724
24861 | 419.5932 | 26724
24862 | 421.178 | 26724
24863 | 426.8747 | 26724
24864 | 414.8388 | 26724
24865 | 414.9579 | 26724
24866 | 412.1953 | 26724
24867 | 416.5674 | 26724
24868 | 421.7701 | 26724
24869 | 414.2623 | 26724
24870 | 427.662 | 26724
24871 | 413.3959 | 26724
24872 | 416.6711 | 26724
24873 | 424.1513 | 26724
24874 | 407.0305 | 26724
24875 | 410.8051 | 26724
24876 | 419.7064 | 26724
24877 | 415.2634 | 26724
24878 | 416.0014 | 26724
24879 | 410.1249 | 26724
24880 | 406.8343 | 26724
24881 | 426.8047 | 26724
24882 | 420.0021 | 26724
24883 | 411.4529 | 26724
24884 | 431.5228 | 26724
24885 | 420.8621 | 26724
24886 | 401.3015 | 26724
24887 | 406.5495 | 26724
24888 | 407.2034 | 26724
24889 | 417.4318 | 26724
24890 | 409.6673 | 26724
24891 | 415.5037 | 26724
24892 | 414.357 | 26724
24893 | 426.8499 | 26724
24894 | 421.864 | 26724
24895 | 409.1444 | 26724
24896 | 414.1161 | 26724
24897 | 407.8434 | 26724
24898 | 410.4456 | 26724
24899 | 425.3627 | 26724
24900 | 419.555 | 26724
24901 | 422.58 | 26724
24902 | 410.9472 | 26724
24903 | 415.8659 | 26724
24904 | 403.3005 | 26724
24905 | 421.1328 | 26724
24906 | 407.4847 | 26724
24907 | 432.3159 | 26724
24908 | 424.4241 | 26724
24909 | 415.412 | 26724
24910 | 423.2633 | 26724
24911 | 413.2219 | 26724
24912 | 422.1111 | 26724
24913 | 406.5875 | 26724
24914 | 409.7289 | 26724
24915 | 417.4255 | 26724
24916 | 420.2913 | 26724
24917 | 425.2905 | 26724
24918 | 410.1733 | 26724
24919 | 420.289 | 26724
24920 | 413.6086 | 26724
24921 | 415.1826 | 26724
24922 | 426.7394 | 26724
24923 | 412.0027 | 26724
24924 | 434.785 | 26724
24925 | 415.6713 | 26724
24926 | 420.6816 | 26724
24927 | 413.2366 | 26724
24928 | 404.1072 | 26724
24929 | 408.0431 | 26724
24930 | 414.2918 | 26724
24931 | 429.8216 | 26724
24932 | 415.8568 | 26724
24933 | 419.1246 | 26724
24934 | 417.0918 | 26724
24935 | 411.4586 | 26724
24936 | 424.9286 | 26724
24937 | 415.7778 | 26724
24938 | 407.5045 | 26724
24939 | 408.0958 | 26724
24940 | 422.8857 | 26724
24941 | 428.0927 | 26724
24942 | 415.4866 | 26724
24943 | 420.5784 | 26724
24944 | 425.4163 | 26724
24945 | 413.6779 | 26724
24946 | 418.3366 | 26724
24947 | 418.3421 | 26724
24948 | 410.0375 | 26724
24949 | 419.4741 | 26724
24950 | 417.0809 | 26724
24951 | 414.0088 | 26724
24952 | 411.2385 | 26724
24953 | 418.5276 | 26724
24954 | 435.7015 | 26724
24955 | 416.6637 | 26724
24956 | 414.3686 | 26724
24957 | 411.3711 | 26724
24958 | 413.8263 | 26724
24959 | 402.8451 | 26724
24960 | 424.4342 | 26724
24961 | 414.2436 | 26724
24962 | 422.7763 | 26724
24963 | 420.683 | 26724
24964 | 403.956 | 26724
24965 | 408.9811 | 26724
24966 | 407.6141 | 26724
24967 | 413.1322 | 26724
24968 | 422.9296 | 26724
24969 | 419.3324 | 26724
24970 | 410.4528 | 26724
24971 | 415.3705 | 26724
24972 | 400.362 | 26724
24973 | 407.1403 | 26724
24974 | 419.0262 | 26724
24975 | 416.5237 | 26724
24976 | 412.557 | 26724
24977 | 403.7251 | 26724
24978 | 414.2676 | 26724
24979 | 412.1706 | 26724
24980 | 407.9832 | 26724
24981 | 433.6773 | 26724
24982 | 419.6773 | 26724
24983 | 412.333 | 26724
24984 | 406.1944 | 26724
24985 | 427.0769 | 26724
24986 | 419.8906 | 26724
24987 | 421.2463 | 26724
24988 | 426.025 | 26724
24989 | 416.6953 | 26724
24990 | 416.2138 | 26724
24991 | 421.8959 | 26724
24992 | 405.7983 | 26724
24993 | 409.7625 | 26724
24994 | 415.752 | 26724
24995 | 398.2111 | 26724
24996 | 422.205 | 26724
24997 | 405.7302 | 26724
24998 | 415.9188 | 26724
24999 | 409.6682 | 26724
25000 | 407.3011 | 26724
25001 | 420.0476 | 26724
25002 | 424.1306 | 26724
25003 | 408.5079 | 26724
25004 | 401.2612 | 26724
25005 | 423.7478 | 26724
25006 | 404.8923 | 26724
25007 | 399.9112 | 26724
25008 | 419.5925 | 26724
25009 | 396.4757 | 26724
25010 | 405.0501 | 26724
25011 | 424.079 | 26724
25012 | 417.2006 | 26724
25013 | 412.3994 | 26724
25014 | 404.8542 | 26724
25015 | 408.4926 | 26724
25016 | 429.8262 | 26724
25017 | 409.6074 | 26724
25018 | 413.0653 | 26724
25019 | 420.1384 | 26724
25020 | 419.1049 | 26724
25021 | 403.8827 | 26724
25022 | 408.5545 | 26724
25023 | 413.8391 | 26724
25024 | 419.0444 | 26724
25025 | 414.1515 | 26724
25026 | 415.3814 | 26724
25027 | 417.7242 | 26724
25028 | 418.1794 | 26724
25029 | 415.5747 | 26724
25030 | 426.0351 | 26724
25031 | 416.8185 | 26724
25032 | 411.7113 | 26724
25033 | 409.5275 | 26724
25034 | 412.7501 | 26724
25035 | 422.9476 | 26724
25036 | 415.3194 | 26724
25037 | 413.845 | 26724
25038 | 429.437 | 26724
25039 | 415.581 | 26724
25040 | 416.8547 | 26724
25041 | 424.7756 | 26724
25042 | 424.5263 | 26724
25043 | 413.5694 | 26724
25044 | 423.239 | 26724
25045 | 415.8572 | 26724
25046 | 406.4378 | 26724
25047 | 423.8777 | 26724
25048 | 435.7712 | 26724
25049 | 427.0075 | 26724
25050 | 417.958 | 26724
25051 | 420.2608 | 26724
25052 | 405.9849 | 26724
25053 | 409 | 26724
25054 | 430.1991 | 26724
25055 | 418.0097 | 26724
25056 | 429.6039 | 26724
25057 | 400.2312 | 26724
25058 | 422.2492 | 26724
25059 | 416.8115 | 26724
25060 | 415.1097 | 26724
25061 | 419.9056 | 26724
25062 | 420.9944 | 26724
25063 | 401.087 | 26724
25064 | 423.7469 | 26724
25065 | 424.2321 | 26724
25066 | 419.7863 | 26724
25067 | 418.4386 | 26724
25068 | 408.4852 | 26724
25069 | 413.7197 | 26724
25070 | 427.7394 | 26724
25071 | 412.985 | 26724
25072 | 422.1449 | 26724
25073 | 401.2772 | 26724
25074 | 406.1606 | 26724
25075 | 413.3491 | 26724
25076 | 411.1817 | 26724
25077 | 414.1469 | 26724
25078 | 430.2411 | 26724
25079 | 422.8801 | 26724
25080 | 434.8062 | 26724
25081 | 407.7695 | 26724
25082 | 420.0636 | 26724
25083 | 414.4748 | 26724
25084 | 414.0598 | 26724
25085 | 412.6038 | 26724
25086 | 414.3315 | 26724
25087 | 401.7761 | 26724
25088 | 409.4798 | 26724
25089 | 426.4481 | 26724
25090 | 414.2775 | 26724
25091 | 416.4436 | 26724
25092 | 423.9354 | 26724
25093 | 401.4022 | 26724
25094 | 410.3954 | 26724
25095 | 402.7558 | 26724
25096 | 427.2026 | 26724
25097 | 416.0473 | 26724
25098 | 417.4166 | 26724
25099 | 415.6273 | 26724
25100 | 416.6772 | 26724
25101 | 420.4031 | 26724
25102 | 425.1217 | 26724
25103 | 415.1543 | 26724
25104 | 414.898 | 26724
25105 | 419.771 | 26724
25106 | 420.5752 | 26724
25107 | 429.0749 | 26724
25108 | 411.3389 | 26724
25109 | 401.1183 | 26724
25110 | 415.7799 | 26724
25111 | 404.8984 | 26724
25112 | 404.234 | 26724
25113 | 417.4431 | 26724
25114 | 426.3238 | 26724
25115 | 435.1944 | 26724
25116 | 408.0222 | 26724
25117 | 426.2978 | 26724
25118 | 403.0879 | 26724
25119 | 404.6888 | 26724
25120 | 416.3874 | 26724
25121 | 411.0117 | 26724
25122 | 404.2988 | 26724
25123 | 417.231 | 26724
25124 | 403.8225 | 26724
25125 | 418.6905 | 26724
25126 | 412.3728 | 26724
25127 | 418.7266 | 26724
25128 | 423.0258 | 26724
25129 | 417.7249 | 26724
25130 | 416.0539 | 26724
25131 | 407.6917 | 26724
25132 | 411.181 | 26724
25133 | 414.3594 | 26724
25134 | 418.5929 | 26724
25135 | 414.4862 | 26724
25136 | 420.1568 | 26724
25137 | 396.427 | 26724
25138 | 418.562 | 26724
25139 | 417.0806 | 26724
25140 | 434.6963 | 26724
25141 | 417.2743 | 26724
25142 | 403.9305 | 26724
25143 | 415.0913 | 26724
25144 | 410.5908 | 26724
25145 | 429.4367 | 26724
25146 | 424.9207 | 26724
25147 | 406.2959 | 26724
25148 | 426.9804 | 26724
25149 | 422.9672 | 26724
25150 | 432.7438 | 26724
25151 | 406.2791 | 26724
25152 | 410.272 | 26724
25153 | 410.4669 | 26724
25154 | 411.658 | 26724
25155 | 421.9075 | 26724
25156 | 409.1727 | 26724
25157 | 411.9843 | 26724
25158 | 411.5109 | 26724
25159 | 422.4689 | 26724
25160 | 404.8748 | 26724
25161 | 419.2115 | 26724
25162 | 410.1996 | 26724
25163 | 405.6878 | 26724
25164 | 420.5828 | 26724
25165 | 400.9372 | 26724
25166 | 407.8588 | 26724
25167 | 416.3974 | 26724
25168 | 407.2926 | 26724
25169 | 414.9322 | 26724
25170 | 415.7355 | 26724
25171 | 424.1899 | 26724
25172 | 425.0037 | 26724
25173 | 423.3036 | 26724
25174 | 415.3052 | 26724
25175 | 411.3916 | 26724
25176 | 425.0069 | 26724
25177 | 413.9616 | 26724
25178 | 414.7997 | 26724
25179 | 415.7491 | 26724
25180 | 418.7375 | 26724
25181 | 424.1001 | 26724
25182 | 411.3176 | 26724
25183 | 414.7219 | 26724
25184 | 421.6049 | 26724
25185 | 417.8167 | 26724
25186 | 423.0598 | 26724
25187 | 408.3181 | 26724
25188 | 417.0176 | 26724
25189 | 411.3144 | 26724
25190 | 400.6572 | 26724
25191 | 421.8723 | 26724
25192 | 428.0859 | 26724
25193 | 427.2256 | 26724
25194 | 407.9728 | 26724
25195 | 421.8546 | 26724
25196 | 423.4991 | 26724
25197 | 406.3763 | 26724
25198 | 409.2118 | 26724
25199 | 421.3909 | 26724
25200 | 418.5311 | 26724
25201 | 411.5283 | 26724
25202 | 413.5149 | 26724
25203 | 426.2264 | 26724
25204 | 416.18 | 26724
25205 | 425.5316 | 26724
25206 | 434.5136 | 26724
25207 | 406.2677 | 26724
25208 | 419.2126 | 26724
25209 | 397.96 | 26724
25210 | 414.9372 | 26724
25211 | 422.1361 | 26724
25212 | 418.6331 | 26724
25213 | 429.7734 | 26724
25214 | 395.9012 | 26724
25215 | 413.7734 | 26724
25216 | 434.0453 | 26724
25217 | 414.8967 | 26724
25218 | 410.6718 | 26724
25219 | 419.6051 | 26724
25220 | 424.6177 | 26724
25221 | 425.5595 | 26724
25222 | 415.2108 | 26724
25223 | 415.7194 | 26724
25224 | 425.5726 | 26724
25225 | 417.5639 | 26724
25226 | 412.7103 | 26724
25227 | 412.2011 | 26724
25228 | 404.1534 | 26724
25229 | 412.7153 | 26724
25230 | 423.3477 | 26724
25231 | 417.1989 | 26724
25232 | 420.0994 | 26724
25233 | 411.0559 | 26724
25234 | 417.6673 | 26724
25235 | 419.3648 | 26724
25236 | 432.9169 | 26724
25237 | 415.5136 | 26724
25238 | 428.6027 | 26724
25239 | 416.8174 | 26724
25240 | 416.1374 | 26724
25241 | 421.5468 | 26724
25242 | 412.526 | 26724
25243 | 418.4565 | 26724
25244 | 403.8028 | 26724
25245 | 420.7108 | 26724
25246 | 423.9665 | 26724
25247 | 417.6878 | 26724
25248 | 420.7998 | 26724
25249 | 423.6904 | 26724
25250 | 426.8858 | 26724
25251 | 416.2669 | 26724
25252 | 415.0109 | 26724
25253 | 422.1809 | 26724
25254 | 413.5428 | 26724
25255 | 399.4328 | 26724
25256 | 418.4031 | 26724
25257 | 425.5945 | 26724
25258 | 424.3691 | 26724
25259 | 410.5412 | 26724
25260 | 413.8558 | 26724
25261 | 418.1723 | 26724
25262 | 428.7328 | 26724
25263 | 421.7809 | 26724
25264 | 411.0878 | 26724
25265 | 416.3944 | 26724
25266 | 415.3253 | 26724
25267 | 415.6645 | 26724
25268 | 426.2923 | 26724
25269 | 414.4297 | 26724
25270 | 406.3831 | 26724
25271 | 418.4777 | 26724
25272 | 412.6545 | 26724
25273 | 411.6931 | 26724
25274 | 428.9021 | 26724
25275 | 411.745 | 26724
25276 | 442.6626 | 26724
25277 | 410.4613 | 26724
25278 | 418.5174 | 26724
25279 | 412.2798 | 26724
25280 | 423.1185 | 26724
25281 | 410.091 | 26724
25282 | 406.487 | 26724
25283 | 409.5805 | 26724
25284 | 420.8237 | 26724
25285 | 428.2041 | 26724
25286 | 414.1562 | 26724
25287 | 418.5533 | 26724
25288 | 408.4069 | 26724
25289 | 406.4568 | 26724
25290 | 420.6825 | 26724
25291 | 428.0339 | 26724
25292 | 425.2548 | 26724
25293 | 431.6796 | 26724
25294 | 409.5088 | 26724
25295 | 424.905 | 26724
25296 | 407.5501 | 26724
25297 | 415.8394 | 26724
25298 | 416.9291 | 26724
25299 | 404.1944 | 26724
25300 | 422.9299 | 26724
25301 | 416.523 | 26724
25302 | 407.3805 | 26724
25303 | 415.4719 | 26724
25304 | 419.319 | 26724
25305 | 423.9672 | 26724
25306 | 418.6081 | 26724
25307 | 409.3081 | 26724
25308 | 415.751 | 26724
25309 | 408.5562 | 26724
25310 | 411.4083 | 26724
25311 | 405.6432 | 26724
25312 | 411.8355 | 26724
25313 | 422.7697 | 26724
25314 | 413.0928 | 26724
25315 | 416.8485 | 26724
25316 | 412.924 | 26724
25317 | 414.4863 | 26724
25318 | 408.3741 | 26724
25319 | 425.8374 | 26724
25320 | 420.2565 | 26724
25321 | 418.6645 | 26724
25322 | 412.4708 | 26724
25323 | 409.6412 | 26724
25324 | 408.7927 | 26724
25325 | 410.0221 | 26724
25326 | 418.1247 | 26724
25327 | 413.7339 | 26724
25328 | 413.8595 | 26724
25329 | 420.5528 | 26724
25330 | 433.1786 | 26724
25331 | 413.6614 | 26724
25332 | 405.9225 | 26724
25333 | 420.3579 | 26724
25334 | 399.234 | 26724
25335 | 404.2485 | 26724
25336 | 417.505 | 26724
25337 | 422.2815 | 26724
25338 | 425.2188 | 26724
25339 | 410.7883 | 26724
25340 | 400.4038 | 26724
25341 | 415.8062 | 26724
25342 | 400.8131 | 26724
25343 | 411.21 | 26724
25344 | 410.8335 | 26724
25345 | 406.2212 | 26724
25346 | 415.8143 | 26724
25347 | 418.9626 | 26724
25348 | 425.957 | 26724
25349 | 420.7145 | 26724
25350 | 408.6962 | 26724
25351 | 430.0131 | 26724
25352 | 421.6341 | 26724
25353 | 415.9779 | 26724
25354 | 415.685 | 26724
25355 | 407.9185 | 26724
25356 | 419.5638 | 26724
25357 | 420.3683 | 26724
25358 | 435.9641 | 26724
25359 | 417.8905 | 26724
25360 | 418.1064 | 26724
25361 | 413.5241 | 26724
25362 | 423.2447 | 26724
25363 | 423.0884 | 26724
25364 | 412.3077 | 26724
25365 | 430.3309 | 26724
25366 | 415.4826 | 26724
25367 | 414.0312 | 26724
25368 | 428.4488 | 26724
25369 | 416.2187 | 26724
25370 | 422.6188 | 26724
25371 | 424.6207 | 26724
25372 | 428.4953 | 26724
25373 | 420.2363 | 26724
25374 | 415.4573 | 26724
25375 | 419.8205 | 26724
25376 | 418.9461 | 26724
25377 | 402.7052 | 26724
25378 | 420.9637 | 26724
25379 | 403.6912 | 26724
25380 | 419.632 | 26724
25381 | 416.9961 | 26724
25382 | 430.1042 | 26724
25383 | 417.3899 | 26724
25384 | 411.4916 | 26724
25385 | 414.183 | 26724
25386 | 400.6209 | 26724
25387 | 419.1583 | 26724
25388 | 424.191 | 26724
25389 | 423.9235 | 26724
25390 | 424.0576 | 26724
25391 | 408.5588 | 26724
25392 | 423.7974 | 26724
25393 | 413.2952 | 26724
25394 | 409.4027 | 26724
25395 | 411.4364 | 26724
25396 | 428.5081 | 26724
25397 | 417.3514 | 26724
25398 | 402.3404 | 26724
25399 | 397.7392 | 26724
25400 | 424.2592 | 26724
25401 | 407.9178 | 26724
25402 | 405.7108 | 26724
25403 | 406.9094 | 26724
25404 | 410.6615 | 26724
25405 | 411.0729 | 26724
25406 | 416.0338 | 26724
25407 | 413.3603 | 26724
25408 | 418.7654 | 26724
25409 | 414.0632 | 26724
25410 | 411.1984 | 26724
25411 | 420.0423 | 26724
25412 | 420.2123 | 26724
25413 | 398.2705 | 26724
25414 | 421.6393 | 26724
25415 | 409.3987 | 26724
25416 | 422.3426 | 26724
25417 | 408.4101 | 26724
25418 | 419.925 | 26724
25419 | 415.3264 | 26724
25420 | 418.7132 | 26724
25421 | 404.3529 | 26724
25422 | 416.9384 | 26724
25423 | 421.9738 | 26724
25424 | 409.9229 | 26724
25425 | 412.7603 | 26724
25426 | 405.2884 | 26724
25427 | 403.4882 | 26724
25428 | 417.1864 | 26724
25429 | 403.4695 | 26724
25430 | 407.8751 | 26724
25431 | 416.7349 | 26724
25432 | 424.3536 | 26724
25433 | 412.3798 | 26724
25434 | 409.4445 | 26724
25435 | 401.1755 | 26724
25436 | 409.2296 | 26724
25437 | 410.9903 | 26724
25438 | 420.2718 | 26724
25439 | 413.2765 | 26724
25440 | 419.8158 | 26724
25441 | 419.0591 | 26724
25442 | 422.5959 | 26724
25443 | 408.4044 | 26724
25444 | 407.4399 | 26724
25445 | 407.8023 | 26724
25446 | 416.4297 | 26724
25447 | 407.5534 | 26724
25448 | 424.6955 | 26724
25449 | 408.7145 | 26724
25450 | 422.3932 | 26724
25451 | 408.9685 | 26724
25452 | 431.5766 | 26724
25453 | 406.4235 | 26724
25454 | 412.3605 | 26724
25455 | 413.9041 | 26724
25456 | 420.5227 | 26724
25457 | 420.932 | 26724
25458 | 417.1338 | 26724
25459 | 399.2947 | 26724
25460 | 407.2688 | 26724
25461 | 418.5515 | 26724
25462 | 410.9401 | 26724
25463 | 412.1679 | 26724
25464 | 407.1987 | 26724
25465 | 420.737 | 26724
25466 | 422.7217 | 26724
25467 | 407.4258 | 26724
25468 | 413.6115 | 26724
25469 | 404.8465 | 26724
25470 | 428.1284 | 26724
25471 | 415.3401 | 26724
25472 | 410.4959 | 26724
25473 | 412.5477 | 26724
25474 | 428.5962 | 26724
25475 | 410.8406 | 26724
25476 | 405.7897 | 26724
25477 | 425.9162 | 26724
25478 | 426.6232 | 26724
25479 | 409.7913 | 26724
25480 | 414.3161 | 26724
25481 | 419.2427 | 26724
25482 | 414.292 | 26724
25483 | 410.0419 | 26724
25484 | 412.9105 | 26724
25485 | 419.8701 | 26724
25486 | 415.9982 | 26724
25487 | 421.1157 | 26724
25488 | 411.2618 | 26724
25489 | 417.2632 | 26724
25490 | 418.198 | 26724
25491 | 406.297 | 26724
25492 | 427.3124 | 26724
25493 | 428.8349 | 26724
25494 | 418.9393 | 26724
25495 | 424.1032 | 26724
25496 | 406.9415 | 26724
25497 | 412.399 | 26724
25498 | 421.3961 | 26724
25499 | 433.3254 | 26724
25500 | 407.9416 | 26724
25501 | 427.0661 | 26724
25502 | 409.6908 | 26724
25503 | 408.5787 | 26724
25504 | 427.1978 | 26724
25505 | 414.4003 | 26724
25506 | 414.6045 | 26724
25507 | 410.3271 | 26724
25508 | 421.5978 | 26724
25509 | 407.637 | 26724
25510 | 411.789 | 26724
25511 | 419.6605 | 26724
25512 | 416.4948 | 26724
25513 | 417.7554 | 26724
25514 | 409.1369 | 26724
25515 | 423.1415 | 26724
25516 | 412.8678 | 26724
25517 | 412.7814 | 26724
25518 | 434.4777 | 26724
25519 | 399.7662 | 26724
25520 | 415.2551 | 26724
25521 | 402.8905 | 26724
25522 | 424.3462 | 26724
25523 | 409.9512 | 26724
25524 | 427.1651 | 26724
25525 | 397.1281 | 26724
25526 | 410.7118 | 26724
25527 | 425.4098 | 26724
25528 | 412.5213 | 26724
25529 | 410.9533 | 26724
25530 | 403.475 | 26724
25531 | 408.654 | 26724
25532 | 401.1854 | 26724
25533 | 405.5501 | 26724
25534 | 422.974 | 26724
25535 | 410.6607 | 26724
25536 | 417.4146 | 26724
25537 | 417.3045 | 26724
25538 | 410.9788 | 26724
25539 | 418.3432 | 26724
25540 | 410.006 | 26724
25541 | 408.5346 | 26724
25542 | 430.3443 | 26724
25543 | 419.0769 | 26724
25544 | 423.2961 | 26724
25545 | 428.0395 | 26724
25546 | 404.6951 | 26724
25547 | 408.7874 | 26724
25548 | 411.3009 | 26724
25549 | 406.301 | 26724
25550 | 410.8076 | 26724
25551 | 424.0262 | 26724
25552 | 407.4822 | 26724
25553 | 418.2765 | 26724
25554 | 406.397 | 26724
25555 | 418.4801 | 26724
25556 | 432.3669 | 26724
25557 | 419.0658 | 26724
25558 | 410.3104 | 26724
25559 | 414.0562 | 26724
25560 | 417.9164 | 26724
25561 | 425.8493 | 26724
25562 | 408.207 | 26724
25563 | 410.3688 | 26724
25564 | 427.2019 | 26724
25565 | 410.9325 | 26724
25566 | 406.5213 | 26724
25567 | 400.396 | 26724
25568 | 424.2336 | 26724
25569 | 419.5888 | 26724
25570 | 403.038 | 26724
25571 | 410.6388 | 26724
25572 | 414.0704 | 26724
25573 | 417.1657 | 26724
25574 | 404.8227 | 26724
25575 | 417.1047 | 26724
25576 | 415.9785 | 26724
25577 | 422.5696 | 26724
25578 | 414.4835 | 26724
25579 | 421.5027 | 26724
25580 | 401.9251 | 26724
25581 | 425.9981 | 26724
25582 | 414.8686 | 26724
25583 | 432.6228 | 26724
25584 | 414.8592 | 26724
25585 | 401.154 | 26724
25586 | 417.7683 | 26724
25587 | 423.6647 | 26724
25588 | 410.7341 | 26724
25589 | 417.932 | 26724
25590 | 408.2544 | 26724
25591 | 423.153 | 26724
25592 | 420.6902 | 26724
25593 | 415.6472 | 26724
25594 | 418.5901 | 26724
25595 | 421.6342 | 26724
25596 | 435.5249 | 26724
25597 | 422.3753 | 26724
25598 | 422.8696 | 26724
25599 | 406.6701 | 26724
25600 | 410.4147 | 26724
25601 | 427.0429 | 26724
25602 | 425.8993 | 26724
25603 | 413.3164 | 26724
25604 | 425.7223 | 26724
25605 | 419.7917 | 26724
25606 | 431.0159 | 26724
25607 | 423.9831 | 26724
25608 | 412.8771 | 26724
25609 | 423.1099 | 26724
25610 | 418.6654 | 26724
25611 | 398.1954 | 26724
25612 | 413.2684 | 26724
25613 | 427.9935 | 26724
25614 | 406.8323 | 26724
25615 | 429.3521 | 26724
25616 | 408.6599 | 26724
25617 | 409.7892 | 26724
25618 | 421.9429 | 26724
25619 | 417.3406 | 26724
25620 | 423.1944 | 26724
25621 | 418.8925 | 26724
25622 | 418.6442 | 26724
25623 | 402.9659 | 26724
25624 | 419.8348 | 26724
25625 | 416.4147 | 26724
25626 | 406.5899 | 26724
25627 | 427.4192 | 26724
25628 | 421.0787 | 26724
25629 | 411.9407 | 26724
25630 | 407.8643 | 26724
25631 | 418.7438 | 26724
25632 | 415.1534 | 26724
25633 | 398.2096 | 26724
25634 | 410.9561 | 26724
25635 | 417.6854 | 26724
25636 | 425.3552 | 26724
25637 | 415.2211 | 26724
25638 | 410.4648 | 26724
25639 | 416.2689 | 26724
25640 | 413.0065 | 26724
25641 | 419.6666 | 26724
25642 | 433.9266 | 26724
25643 | 416.7935 | 26724
25644 | 407.6464 | 26724
25645 | 423.8138 | 26724
25646 | 415.237 | 26724
25647 | 419.665 | 26724
25648 | 409.5064 | 26724
25649 | 424.3486 | 26724
25650 | 418.7174 | 26724
25651 | 423.2465 | 26724
25652 | 409.5986 | 26724
25653 | 418.4184 | 26724
25654 | 419.3125 | 26724
25655 | 421.9126 | 26724
25656 | 414.1638 | 26724
25657 | 418.4747 | 26724
25658 | 427.6361 | 26724
25659 | 421.1747 | 26724
25660 | 408.53 | 26724
25661 | 417.1498 | 26724
25662 | 407.6655 | 26724
25663 | 412.5625 | 26724
25664 | 423.5518 | 26724
25665 | 420.7158 | 26724
25666 | 409.7523 | 26724
25667 | 421.2868 | 26724
25668 | 415.2506 | 26724
25669 | 411.1857 | 26724
25670 | 410.5724 | 26724
25671 | 412.9717 | 26724
25672 | 413.0857 | 26724
25673 | 410.0211 | 26724
25674 | 429.7129 | 26724
25675 | 412.4979 | 26724
25676 | 425.826 | 26724
25677 | 413.284 | 26724
25678 | 409.8883 | 26724
25679 | 421.1592 | 26724
25680 | 424.6799 | 26724
25681 | 427.1353 | 26724
25682 | 410.7134 | 26724
25683 | 408.524 | 26724
25684 | 417.7359 | 26724
25685 | 408.6851 | 26724
25686 | 426.0872 | 26724
25687 | 414.1636 | 26724
25688 | 420.8853 | 26724
25689 | 428.7735 | 26724
25690 | 413.3052 | 26724
25691 | 426.8097 | 26724
25692 | 424.392 | 26724
25693 | 405.7428 | 26724
25694 | 420.3838 | 26724
25695 | 407.4979 | 26724
25696 | 406.8893 | 26724
25697 | 426.9244 | 26724
25698 | 409.7112 | 26724
25699 | 417.6303 | 26724
25700 | 413.8079 | 26724
25701 | 416.1819 | 26724
25702 | 405.0684 | 26724
25703 | 405.0799 | 26724
25704 | 414.6827 | 26724
25705 | 427.8662 | 26724
25706 | 407.5131 | 26724
25707 | 421.663 | 26724
25708 | 418.619 | 26724
25709 | 406.8536 | 26724
25710 | 423.9447 | 26724
25711 | 408.334 | 26724
25712 | 414.4754 | 26724
25713 | 413.5634 | 26724
25714 | 430.9301 | 26724
25715 | 429.7199 | 26724
25716 | 407.8663 | 26724
25717 | 417.2785 | 26724
25718 | 424.1976 | 26724
25719 | 422.2669 | 26724
25720 | 419.8117 | 26724
25721 | 422.2927 | 26724
25722 | 413.5324 | 26724
25723 | 415.6928 | 26724
25724 | 424.012 | 26724
25725 | 419.3784 | 26724
25726 | 425.0911 | 26724
25727 | 406.327 | 26724
25728 | 412.3089 | 26724
25729 | 425.0323 | 26724
25730 | 431.3377 | 26724
25731 | 426.077 | 26724
25732 | 410.0831 | 26724
25733 | 399.7276 | 26724
25734 | 412.34 | 26724
25735 | 417.0331 | 26724
25736 | 425.9084 | 26724
25737 | 417.1737 | 26724
25738 | 403.1819 | 26724
25739 | 421.2701 | 26724
25740 | 399.2496 | 26724
25741 | 420.7917 | 26724
25742 | 429.4279 | 26724
25743 | 421.6991 | 26724
25744 | 411.5789 | 26724
25745 | 415.1263 | 26724
25746 | 425.3091 | 26724
25747 | 408.7807 | 26724
25748 | 408.107 | 26724
25749 | 404.1087 | 26724
25750 | 418.3261 | 26724
25751 | 413.6131 | 26724
25752 | 420.3088 | 26724
25753 | 416.7188 | 26724
25754 | 421.1648 | 26724
25755 | 426.6398 | 26724
25756 | 411.6433 | 26724
25757 | 409.5534 | 26724
25758 | 434.1003 | 26724
25759 | 417.4471 | 26724
25760 | 413.4635 | 26724
25761 | 410.3926 | 26724
25762 | 411.739 | 26724
25763 | 414.0583 | 26724
25764 | 418.465 | 26724
25765 | 405.7562 | 26724
25766 | 410.3729 | 26724
25767 | 425.9043 | 26724
25768 | 423.2619 | 26724
25769 | 419.532 | 26724
25770 | 417.7596 | 26724
25771 | 413.8156 | 26724
25772 | 411.9209 | 26724
25773 | 416.0738 | 26724
25774 | 410.6656 | 26724
25775 | 425.6338 | 26724
25776 | 411.0149 | 26724
25777 | 410.2135 | 26724
25778 | 425.678 | 26724
25779 | 422.9121 | 26724
25780 | 402.839 | 26724
25781 | 424.4898 | 26724
25782 | 418.5436 | 26724
25783 | 413.269 | 26724
25784 | 407.8023 | 26724
25785 | 416.3997 | 26724
25786 | 413.5301 | 26724
25787 | 418.2017 | 26724
25788 | 425.8871 | 26724
25789 | 408.6807 | 26724
25790 | 405.282 | 26724
25791 | 415.4378 | 26724
25792 | 421.7602 | 26724
25793 | 415.921 | 26724
25794 | 411.5897 | 26724
25795 | 415.5744 | 26724
25796 | 405.7259 | 26724
25797 | 410.7266 | 26724
25798 | 410.1294 | 26724
25799 | 408.0365 | 26724
25800 | 418.2202 | 26724
25801 | 421.844 | 26724
25802 | 403.1701 | 26724
25803 | 422.9884 | 26724
25804 | 426.8713 | 26724
25805 | 421.703 | 26724
25806 | 404.1376 | 26724
25807 | 422.8176 | 26724
25808 | 427.8725 | 26724
25809 | 406.84 | 26724
25810 | 414.538 | 26724
25811 | 415.4818 | 26724
25812 | 424.4751 | 26724
25813 | 416.5787 | 26724
25814 | 413.2176 | 26724
25815 | 415.6573 | 26724
25816 | 419.9447 | 26724
25817 | 415.0338 | 26724
25818 | 412.6056 | 26724
25819 | 407.2358 | 26724
25820 | 417.9289 | 26724
25821 | 410.2114 | 26724
25822 | 418.2345 | 26724
25823 | 420.8989 | 26724
25824 | 405.7043 | 26724
25825 | 419.2682 | 26724
25826 | 419.5142 | 26724
25827 | 410.6522 | 26724
25828 | 425.0539 | 26724
25829 | 415.5202 | 26724
25830 | 417.9682 | 26724
25831 | 414.5911 | 26724
25832 | 420.7854 | 26724
25833 | 413.623 | 26724
25834 | 412.5204 | 26724
25835 | 422.925 | 26724
25836 | 422.71 | 26724
25837 | 417.3721 | 26724
25838 | 420.0708 | 26724
25839 | 417.2516 | 26724
25840 | 399.681 | 26724
25841 | 431.0894 | 26724
25842 | 418.5153 | 26724
25843 | 419.806 | 26724
25844 | 408.4513 | 26724
25845 | 412.273 | 26724
25846 | 410.8651 | 26724
25847 | 424.862 | 26724
25848 | 422.1757 | 26724
25849 | 421.953 | 26724
25850 | 413.3196 | 26724
25851 | 419.6759 | 26724
25852 | 422.5748 | 26724
25853 | 407.3531 | 26724
25854 | 398.9368 | 26724
25855 | 409.0511 | 26724
25856 | 428.4366 | 26724
25857 | 425.162 | 26724
25858 | 409.5914 | 26724
25859 | 408.9412 | 26724
25860 | 418.1275 | 26724
25861 | 429.5075 | 26724
25862 | 426.9056 | 26724
25863 | 411.0484 | 26724
25864 | 416.7282 | 26724
25865 | 419.7748 | 26724
25866 | 410.1231 | 26724
25867 | 414.3606 | 26724
25868 | 408.0156 | 26724
25869 | 407.4695 | 26724
25870 | 418.6144 | 26724
25871 | 408.4273 | 26724
25872 | 407.9755 | 26724
25873 | 404.4433 | 26724
25874 | 419.2087 | 26724
25875 | 403.8241 | 26724
25876 | 418.8991 | 26724
25877 | 411.6907 | 26724
25878 | 397.3607 | 26724
25879 | 408.2316 | 26724
25880 | 416.8175 | 26724
25881 | 423.1675 | 26724
25882 | 413.9815 | 26724
25883 | 416.1183 | 26724
25884 | 428.4451 | 26724
25885 | 409.1651 | 26724
25886 | 411.8076 | 26724
25887 | 422.0371 | 26724
25888 | 422.2409 | 26724
25889 | 421.311 | 26724
25890 | 411.7712 | 26724
25891 | 412.9084 | 26724
25892 | 415.0176 | 26724
25893 | 418.9506 | 26724
25894 | 423.5659 | 26724
25895 | 412.3077 | 26724
25896 | 418.4237 | 26724
25897 | 415.3585 | 26724
25898 | 427.321 | 26724
25899 | 408.8813 | 26724
25900 | 422.0316 | 26724
25901 | 415.2282 | 26724
25902 | 409.356 | 26724
25903 | 413.0071 | 26724
25904 | 402.8098 | 26724
25905 | 415.7077 | 26724
25906 | 402.4577 | 26724
25907 | 425.3572 | 26724
25908 | 420.9851 | 26724
25909 | 420.7349 | 26724
25910 | 411.113 | 26724
25911 | 425.8499 | 26724
25912 | 420.9407 | 26724
25913 | 410.3098 | 26724
25914 | 431 | 26724
25915 | 416.0996 | 26724
25916 | 426.0062 | 26724
25917 | 412.9836 | 26724
25918 | 420.8703 | 26724
25919 | 415.7712 | 26724
25920 | 415.6113 | 26724
25921 | 424.9868 | 26724
25922 | 423.5394 | 26724
25923 | 422.2534 | 26724
25924 | 400.7104 | 26724
25925 | 403.8493 | 26724
25926 | 422.1907 | 26724
25927 | 428.8204 | 26724
25928 | 413.3885 | 26724
25929 | 413.4682 | 26724
25930 | 406.6864 | 26724
25931 | 423.9997 | 26724
25932 | 418.2024 | 26724
25933 | 417.8118 | 26724
25934 | 418.1239 | 26724
25935 | 398.9168 | 26724
25936 | 418.1945 | 26724
25937 | 410.7452 | 26724
25938 | 412.2649 | 26724
25939 | 408.4636 | 26724
25940 | 423.5017 | 26724
25941 | 407.1726 | 26724
25942 | 421.3486 | 26724
25943 | 414.7151 | 26724
25944 | 407.3458 | 26724
25945 | 424.3576 | 26724
25946 | 414.8189 | 26724
25947 | 410.1613 | 26724
25948 | 412.7777 | 26724
25949 | 408.6706 | 26724
25950 | 428.3604 | 26724
25951 | 419.8117 | 26724
25952 | 428.2915 | 26724
25953 | 426.8151 | 26724
25954 | 415.9637 | 26724
25955 | 426.1264 | 26724
25956 | 408.6146 | 26724
25957 | 417.8285 | 26724
25958 | 417.4328 | 26724
25959 | 415.7119 | 26724
25960 | 421.6474 | 26724
25961 | 416.0438 | 26724
25962 | 412.7564 | 26724
25963 | 421.2273 | 26724
25964 | 406.0782 | 26724
25965 | 413.083 | 26724
25966 | 406.0049 | 26724
25967 | 395.5549 | 26724
25968 | 431.4181 | 26724
25969 | 431.348 | 26724
25970 | 422.9579 | 26724
25971 | 424.7372 | 26724
25972 | 412.8909 | 26724
25973 | 402.1426 | 26724
25974 | 422.6316 | 26724
25975 | 426.1937 | 26724
25976 | 399.051 | 26724
25977 | 432.4802 | 26724
25978 | 404.6656 | 26724
25979 | 410.8854 | 26724
25980 | 434.0046 | 26724
25981 | 434.5442 | 26724
25982 | 405.9994 | 26724
25983 | 416.2591 | 26724
25984 | 426.1974 | 26724
25985 | 410.6849 | 26724
25986 | 419.5429 | 26724
25987 | 431.9905 | 26724
25988 | 423.6404 | 26724
25989 | 416.4664 | 26724
25990 | 402.9514 | 26724
25991 | 409.7415 | 26724
25992 | 422.1762 | 26724
25993 | 416.1155 | 26724
25994 | 429.5881 | 26724
25995 | 403.4925 | 26724
25996 | 408.6761 | 26724
25997 | 413.3891 | 26724
25998 | 412.3987 | 26724
25999 | 411.4629 | 26724
26000 | 413.0627 | 26724
26001 | 416.3696 | 26724
26002 | 409.0736 | 26724
26003 | 399.6159 | 26724
26004 | 418.2934 | 26724
26005 | 423.4323 | 26724
26006 | 406.15 | 26724
26007 | 414.5991 | 26724
26008 | 416.0157 | 26724
26009 | 418.3977 | 26724
26010 | 416.1783 | 26724
26011 | 421.8515 | 26724
26012 | 415.219 | 26724
26013 | 413.3147 | 26724
26014 | 409.4069 | 26724
26015 | 417.9902 | 26724
26016 | 419.0558 | 26724
26017 | 417.3383 | 26724
26018 | 408.6377 | 26724
26019 | 416.4067 | 26724
26020 | 413.9636 | 26724
26021 | 406.8075 | 26724
26022 | 414.9188 | 26724
26023 | 418.6268 | 26724
26024 | 411.7733 | 26724
26025 | 413.8242 | 26724
26026 | 420.5507 | 26724
26027 | 412.5143 | 26724
26028 | 429.0301 | 26724
26029 | 421.5835 | 26724
26030 | 417.3738 | 26724
26031 | 425.5786 | 26724
26032 | 425.013 | 26724
26033 | 423.5317 | 26724
26034 | 415.8251 | 26724
26035 | 417.3382 | 26724
26036 | 409.1171 | 26724
26037 | 407.2079 | 26724
26038 | 407.484 | 26724
26039 | 432.9955 | 26724
26040 | 405.7251 | 26724
26041 | 416.0507 | 26724
26042 | 431.1903 | 26724
26043 | 416.4014 | 26724
26044 | 421.6708 | 26724
26045 | 412.1819 | 26724
26046 | 419.2678 | 26724
26047 | 410.9255 | 26724
26048 | 419.9382 | 26724
26049 | 422.3038 | 26724
26050 | 411.5729 | 26724
26051 | 400.712 | 26724
26052 | 419.8872 | 26724
26053 | 415.3102 | 26724
26054 | 408.0737 | 26724
26055 | 408.7669 | 26724
26056 | 424.9795 | 26724
26057 | 408.4761 | 26724
26058 | 415.4948 | 26724
26059 | 429.2558 | 26724
26060 | 408.3006 | 26724
26061 | 421.2061 | 26724
26062 | 423.3835 | 26724
26063 | 415.0075 | 26724
26064 | 417.5849 | 26724
26065 | 409.9369 | 26724
26066 | 406.2021 | 26724
26067 | 407.8733 | 26724
26068 | 404.9108 | 26724
26069 | 413.8265 | 26724
26070 | 425.6068 | 26724
26071 | 413.5442 | 26724
26072 | 413.6641 | 26724
26073 | 406.4494 | 26724
26074 | 404.0542 | 26724
26075 | 409.2216 | 26724
26076 | 402.4379 | 26724
26077 | 420.6466 | 26724
26078 | 409.1703 | 26724
26079 | 408.2299 | 26724
26080 | 417.4465 | 26724
26081 | 409.3545 | 26724
26082 | 407.6898 | 26724
26083 | 416.409 | 26724
26084 | 404.4763 | 26724
26085 | 415.9444 | 26724
26086 | 406.7348 | 26724
26087 | 418.3973 | 26724
26088 | 427.2051 | 26724
26089 | 427.3333 | 26724
26090 | 408.2756 | 26724
26091 | 411.5966 | 26724
26092 | 419.4365 | 26724
26093 | 413.81 | 26724
26094 | 419.307 | 26724
26095 | 425.6917 | 26724
26096 | 419.9518 | 26724
26097 | 420.2479 | 26724
26098 | 411.4175 | 26724
26099 | 416.1666 | 26724
26100 | 426.6218 | 26724
26101 | 406.678 | 26724
26102 | 416.0268 | 26724
26103 | 410.7144 | 26724
26104 | 423.7095 | 26724
26105 | 421.5595 | 26724
26106 | 409.1298 | 26724
26107 | 417.7555 | 26724
26108 | 416.5748 | 26724
26109 | 417.9212 | 26724
26110 | 425.1402 | 26724
26111 | 430.0057 | 26724
26112 | 422.5989 | 26724
26113 | 425.1024 | 26724
26114 | 406.9663 | 26724
26115 | 426.3042 | 26724
26116 | 419.7994 | 26724
26117 | 417.4682 | 26724
26118 | 409.0501 | 26724
26119 | 424.4663 | 26724
26120 | 407.6625 | 26724
26121 | 423.2774 | 26724
26122 | 411.7006 | 26724
26123 | 417.9128 | 26724
26124 | 406.0216 | 26724
26125 | 417.4689 | 26724
26126 | 421.5769 | 26724
26127 | 408.1326 | 26724
26128 | 426.2187 | 26724
26129 | 413.9925 | 26724
26130 | 418.7215 | 26724
26131 | 409.9545 | 26724
26132 | 414.7947 | 26724
26133 | 427.2932 | 26724
26134 | 414.0219 | 26724
26135 | 406.3983 | 26724
26136 | 431.772 | 26724
26137 | 424.521 | 26724
26138 | 409.4122 | 26724
26139 | 414.614 | 26724
26140 | 426.277 | 26724
26141 | 408.8372 | 26724
26142 | 419.7906 | 26724
26143 | 405.2237 | 26724
26144 | 420.7159 | 26724
26145 | 404.666 | 26724
26146 | 413.1677 | 26724
26147 | 415.1795 | 26724
26148 | 425.4368 | 26724
26149 | 419.3651 | 26724
26150 | 405.3135 | 26724
26151 | 426.0751 | 26724
26152 | 429.6218 | 26724
26153 | 424.5807 | 26724
26154 | 403.6023 | 26724
26155 | 413.3861 | 26724
26156 | 412.9725 | 26724
26157 | 407.7194 | 26724
26158 | 410.2608 | 26724
26159 | 424.1877 | 26724
26160 | 403.3159 | 26724
26161 | 418.2833 | 26724
26162 | 416.5087 | 26724
26163 | 425.5979 | 26724
26164 | 404.5575 | 26724
26165 | 415.9333 | 26724
26166 | 431.0464 | 26724
26167 | 409.424 | 26724
26168 | 420.113 | 26724
26169 | 410.6575 | 26724
26170 | 417.183 | 26724
26171 | 426.2281 | 26724
26172 | 410.7757 | 26724
26173 | 416.7092 | 26724
26174 | 417.1739 | 26724
26175 | 413.262 | 26724
26176 | 427.4981 | 26724
26177 | 411.3918 | 26724
26178 | 413.6577 | 26724
26179 | 417.375 | 26724
26180 | 423.0985 | 26724
26181 | 402.2585 | 26724
26182 | 415.7683 | 26724
26183 | 417.3686 | 26724
26184 | 404.9461 | 26724
26185 | 408.2142 | 26724
26186 | 422.2135 | 26724
26187 | 415.8428 | 26724
26188 | 410.0727 | 26724
26189 | 410.7995 | 26724
26190 | 402.1003 | 26724
26191 | 412.7505 | 26724
26192 | 431.3156 | 26724
26193 | 424.0673 | 26724
26194 | 414.1792 | 26724
26195 | 414.6465 | 26724
26196 | 425.601 | 26724
26197 | 413.7012 | 26724
26198 | 402.9179 | 26724
26199 | 426.059 | 26724
26200 | 422.5469 | 26724
26201 | 421.9772 | 26724
26202 | 421.2672 | 26724
26203 | 418.0123 | 26724
26204 | 420.7536 | 26724
26205 | 409.4035 | 26724
26206 | 426.6499 | 26724
26207 | 401.3767 | 26724
26208 | 415.329 | 26724
26209 | 410.0023 | 26724
26210 | 427.2491 | 26724
26211 | 414.3646 | 26724
26212 | 416.837 | 26724
26213 | 412.6158 | 26724
26214 | 419.5698 | 26724
26215 | 408.2385 | 26724
26216 | 427.6796 | 26724
26217 | 414.6885 | 26724
26218 | 410.9864 | 26724
26219 | 426.5441 | 26724
26220 | 410.4041 | 26724
26221 | 424.4112 | 26724
26222 | 416.6012 | 26724
26223 | 427.5706 | 26724
26224 | 410.388 | 26724
26225 | 418.3912 | 26724
26226 | 428.012 | 26724
26227 | 403.7395 | 26724
26228 | 408.0222 | 26724
26229 | 424.5648 | 26724
26230 | 406.1472 | 26724
26231 | 411.8197 | 26724
26232 | 425.8305 | 26724
26233 | 404.924 | 26724
26234 | 418.77 | 26724
26235 | 425.2556 | 26724
26236 | 418.9005 | 26724
26237 | 401.9052 | 26724
26238 | 412.1467 | 26724
26239 | 399.469 | 26724
26240 | 402.2076 | 26724
26241 | 414.564 | 26724
26242 | 420.238 | 26724
26243 | 412.6675 | 26724
26244 | 406.6249 | 26724
26245 | 419.0095 | 26724
26246 | 430.2691 | 26724
26247 | 418.9546 | 26724
26248 | 420.1534 | 26724
26249 | 417.1917 | 26724
26250 | 432.1508 | 26724
26251 | 407.0038 | 26724
26252 | 418.5266 | 26724
26253 | 413.5345 | 26724
26254 | 426.0748 | 26724
26255 | 412.1275 | 26724
26256 | 428.9007 | 26724
26257 | 409.9061 | 26724
26258 | 413.8873 | 26724
26259 | 416.7297 | 26724
26260 | 421.2796 | 26724
26261 | 425.7555 | 26724
26262 | 406.4785 | 26724
26263 | 417.257 | 26724
26264 | 405.087 | 26724
26265 | 407.3336 | 26724
26266 | 415.234 | 26724
26267 | 419.4649 | 26724
26268 | 418.9913 | 26724
26269 | 406.6874 | 26724
26270 | 418.3274 | 26724
26271 | 417.1756 | 26724
26272 | 419.5545 | 26724
26273 | 413.9627 | 26724
26274 | 414.6339 | 26724
26275 | 421.4984 | 26724
26276 | 412.2286 | 26724
26277 | 425.4056 | 26724
26278 | 404.3637 | 26724
26279 | 415.7357 | 26724
26280 | 417.0576 | 26724
26281 | 406.1123 | 26724
26282 | 429.8347 | 26724
26283 | 418.7614 | 26724
26284 | 411.0674 | 26724
26285 | 414.7149 | 26724
26286 | 413.7665 | 26724
26287 | 420.2975 | 26724
26288 | 422.9724 | 26724
26289 | 413.7251 | 26724
26290 | 415.6492 | 26724
26291 | 420.1548 | 26724
26292 | 428.5742 | 26724
26293 | 408.3152 | 26724
26294 | 419.3399 | 26724
26295 | 415.6059 | 26724
26296 | 403.5411 | 26724
26297 | 414.4525 | 26724
26298 | 419.1566 | 26724
26299 | 410.0348 | 26724
26300 | 420.4041 | 26724
26301 | 432.9883 | 26724
26302 | 413.8255 | 26724
26303 | 416.1027 | 26724
26304 | 410.2166 | 26724
26305 | 405.1037 | 26724
26306 | 432.3198 | 26724
26307 | 403.9868 | 26724
26308 | 426.7969 | 26724
26309 | 419.9833 | 26724
26310 | 427.0315 | 26724
26311 | 418.195 | 26724
26312 | 422.1783 | 26724
26313 | 407.8521 | 26724
26314 | 413.2183 | 26724
26315 | 404.3482 | 26724
26316 | 409.7093 | 26724
26317 | 404.4838 | 26724
26318 | 430.9995 | 26724
26319 | 411.0366 | 26724
26320 | 419.9333 | 26724
26321 | 418.8419 | 26724
26322 | 421.2634 | 26724
26323 | 413.9653 | 26724
26324 | 428.9546 | 26724
26325 | 436.3078 | 26724
26326 | 408.5879 | 26724
26327 | 430.5408 | 26724
26328 | 434.8111 | 26724
26329 | 422.9342 | 26724
26330 | 426.8377 | 26724
26331 | 425.7448 | 26724
26332 | 408.7737 | 26724
26333 | 422.7696 | 26724
26334 | 422.3651 | 26724
26335 | 412.7979 | 26724
26336 | 424.2804 | 26724
26337 | 426.9132 | 26724
26338 | 413.446 | 26724
26339 | 417.9778 | 26724
26340 | 412.6418 | 26724
26341 | 422.4039 | 26724
26342 | 407.7165 | 26724
26343 | 403.7657 | 26724
26344 | 408.9554 | 26724
26345 | 408.9906 | 26724
26346 | 403.0687 | 26724
26347 | 415.8004 | 26724
26348 | 416.3383 | 26724
26349 | 423.7531 | 26724
26350 | 410.3257 | 26724
26351 | 419.6543 | 26724
26352 | 422.1837 | 26724
26353 | 404.0296 | 26724
26354 | 437.3915 | 26724
26355 | 422.2696 | 26724
26356 | 432.6657 | 26724
26357 | 430.2 | 26724
26358 | 415.4709 | 26724
26359 | 426.4446 | 26724
26360 | 416.5006 | 26724
26361 | 422.7325 | 26724
26362 | 414.8174 | 26724
26363 | 419.02 | 26724
26364 | 429.6682 | 26724
26365 | 410.5892 | 26724
26366 | 407.7963 | 26724
26367 | 408.2783 | 26724
26368 | 429.4196 | 26724
26369 | 434.6067 | 26724
26370 | 422.6756 | 26724
26371 | 421.2178 | 26724
26372 | 415.8336 | 26724
26373 | 411.7302 | 26724
26374 | 403.9053 | 26724
26375 | 422.4994 | 26724
26376 | 416.5601 | 26724
26377 | 420.4468 | 26724
26378 | 414.1466 | 26724
26379 | 408.1433 | 26724
26380 | 404.7615 | 26724
26381 | 422.7336 | 26724
26382 | 425.3627 | 26724
26383 | 403.2572 | 26724
26384 | 413.789 | 26724
26385 | 418.8169 | 26724
26386 | 418.9201 | 26724
26387 | 415.1633 | 26724
26388 | 420.7392 | 26724
26389 | 400.4017 | 26724
26390 | 410.5745 | 26724
26391 | 403.6959 | 26724
26392 | 412.2435 | 26724
26393 | 417.1078 | 26724
26394 | 409.6467 | 26724
26395 | 422.1824 | 26724
26396 | 420.8835 | 26724
26397 | 418.9747 | 26724
26398 | 404.0029 | 26724
26399 | 418.2044 | 26724
26400 | 423.2624 | 26724
26401 | 418.2431 | 26724
26402 | 426.8144 | 26724
26403 | 410.3166 | 26724
26404 | 413.2946 | 26724
26405 | 421.6237 | 26724
26406 | 415.154 | 26724
26407 | 405.4041 | 26724
26408 | 435.4428 | 26724
26409 | 418.0492 | 26724
26410 | 425.377 | 26724
26411 | 402.3951 | 26724
26412 | 418.4551 | 26724
26413 | 422.7621 | 26724
26414 | 420.8256 | 26724
26415 | 427.7088 | 26724
26416 | 419.4955 | 26724
26417 | 419.2324 | 26724
26418 | 416.9071 | 26724
26419 | 416.0746 | 26724
26420 | 424.1502 | 26724
26421 | 437.3016 | 26724
26422 | 416.8651 | 26724
26423 | 413.5885 | 26724
26424 | 412.4189 | 26724
26425 | 408.8931 | 26724
26426 | 418.3106 | 26724
26427 | 414.8375 | 26724
26428 | 407.4995 | 26724
26429 | 403.4999 | 26724
26430 | 418.689 | 26724
26431 | 421.7211 | 26724
26432 | 416.4893 | 26724
26433 | 422.4056 | 26724
26434 | 428.4666 | 26724
26435 | 426.8053 | 26724
26436 | 416.4412 | 26724
26437 | 406.9646 | 26724
26438 | 414.855 | 26724
26439 | 413.7897 | 26724
26440 | 425.7613 | 26724
26441 | 426.1973 | 26724
26442 | 420.502 | 26724
26443 | 432.0861 | 26724
26444 | 407.6609 | 26724
26445 | 398.4421 | 26724
26446 | 413.3235 | 26724
26447 | 424.875 | 26724
26448 | 415.2983 | 26724
26449 | 414.7597 | 26724
26450 | 422.4292 | 26724
26451 | 403.7577 | 26724
26452 | 427.6824 | 26724
26453 | 417.1283 | 26724
26454 | 421.6637 | 26724
26455 | 416.5791 | 26724
26456 | 420.302 | 26724
26457 | 429.4802 | 26724
26458 | 415.5242 | 26724
26459 | 410.7975 | 26724
26460 | 406.8083 | 26724
26461 | 414.6484 | 26724
26462 | 418.4128 | 26724
26463 | 416.9886 | 26724
26464 | 398.7935 | 26724
26465 | 421.9218 | 26724
26466 | 411.9412 | 26724
26467 | 417.1693 | 26724
26468 | 409.6033 | 26724
26469 | 418.2719 | 26724
26470 | 415.7752 | 26724
26471 | 420.8221 | 26724
26472 | 427.4456 | 26724
26473 | 411.9147 | 26724
26474 | 408.2837 | 26724
26475 | 413.0455 | 26724
26476 | 414.6758 | 26724
26477 | 428.6434 | 26724
26478 | 424.5627 | 26724
26479 | 422.1496 | 26724
26480 | 410.0998 | 26724
26481 | 407.5296 | 26724
26482 | 404.3179 | 26724
26483 | 405.3852 | 26724
26484 | 423.5108 | 26724
26485 | 401.1192 | 26724
26486 | 437.3681 | 26724
26487 | 421.802 | 26724
26488 | 416.1284 | 26724
26489 | 406.4595 | 26724
26490 | 429.3731 | 26724
26491 | 417.5478 | 26724
26492 | 414.3944 | 26724
26493 | 410.8701 | 26724
26494 | 421.2962 | 26724
26495 | 406.5487 | 26724
26496 | 400.8804 | 26724
26497 | 424.8633 | 26724
26498 | 399.6954 | 26724
26499 | 419.8744 | 26724
26500 | 418.4245 | 26724
26501 | 407.8816 | 26724
26502 | 409.4719 | 26724
26503 | 421.2566 | 26724
26504 | 421.9967 | 26724
26505 | 407.4195 | 26724
26506 | 405.4233 | 26724
26507 | 405.0319 | 26724
26508 | 414.3994 | 26724
26509 | 422.041 | 26724
26510 | 422.0376 | 26724
26511 | 410.1525 | 26724
26512 | 424.5617 | 26724
26513 | 424.4434 | 26724
26514 | 424.0157 | 26724
26515 | 416.1748 | 26724
26516 | 412.831 | 26724
26517 | 422.7845 | 26724
26518 | 421.18 | 26724
26519 | 434.7277 | 26724
26520 | 418.3415 | 26724
26521 | 414.0365 | 26724
26522 | 404.3705 | 26724
26523 | 422.4373 | 26724
26524 | 419.4779 | 26724
26525 | 410.4912 | 26724
26526 | 418.8731 | 26724
26527 | 417.4806 | 26724
26528 | 410.3587 | 26724
26529 | 418.1192 | 26724
26530 | 417.1377 | 26724
26531 | 412.1361 | 26724
26532 | 433.3594 | 26724
26533 | 418.304 | 26724
26534 | 397.3926 | 26724
26535 | 407.9652 | 26724
26536 | 415.9562 | 26724
26537 | 428.0713 | 26724
26538 | 412.3296 | 26724
26539 | 420.4315 | 26724
26540 | 415.4736 | 26724
26541 | 408.7866 | 26724
26542 | 407.6956 | 26724
26543 | 423.2662 | 26724
26544 | 416.94 | 26724
26545 | 407.2314 | 26724
26546 | 413.4967 | 26724
26547 | 412.8345 | 26724
26548 | 425.3404 | 26724
26549 | 405.2208 | 26724
26550 | 416.7644 | 26724
26551 | 423.8475 | 26724
26552 | 410.0502 | 26724
26553 | 441.2978 | 26724
26554 | 402.4209 | 26724
26555 | 415.5346 | 26724
26556 | 401.5175 | 26724
26557 | 414.0647 | 26724
26558 | 408.3734 | 26724
26559 | 409.4625 | 26724
26560 | 407.1197 | 26724
26561 | 411.0079 | 26724
26562 | 417.9754 | 26724
26563 | 408.187 | 26724
26564 | 410.3351 | 26724
26565 | 416.034 | 26724
26566 | 423.1008 | 26724
26567 | 437.7724 | 26724
26568 | 413.8309 | 26724
26569 | 414.293 | 26724
26570 | 422.788 | 26724
26571 | 402.7911 | 26724
26572 | 416.2973 | 26724
26573 | 406.99 | 26724
26574 | 410.2279 | 26724
26575 | 412.7914 | 26724
26576 | 411.1275 | 26724
26577 | 418.1745 | 26724
26578 | 414.3394 | 26724
26579 | 421.1576 | 26724
26580 | 416.6757 | 26724
26581 | 421.1393 | 26724
26582 | 409.2729 | 26724
26583 | 414.0044 | 26724
26584 | 395.4814 | 26724
26585 | 418.0209 | 26724
26586 | 418.4557 | 26724
26587 | 420.9134 | 26724
26588 | 421.2487 | 26724
26589 | 416.5974 | 26724
26590 | 421.0291 | 26724
26591 | 424.6509 | 26724
26592 | 409.2331 | 26724
26593 | 424.205 | 26724
26594 | 397.2623 | 26724
26595 | 412.997 | 26724
26596 | 416.3986 | 26724
26597 | 415.7416 | 26724
26598 | 419.2316 | 26724
26599 | 409.8683 | 26724
26600 | 409.9752 | 26724
26601 | 420.2887 | 26724
26602 | 414.2925 | 26724
26603 | 429.2552 | 26724
26604 | 400.6445 | 26724
26605 | 420.0077 | 26724
26606 | 423.5391 | 26724
26607 | 415.6906 | 26724
26608 | 424.6499 | 26724
26609 | 418.8716 | 26724
26610 | 416.9695 | 26724
26611 | 419.2429 | 26724
26612 | 431.9115 | 26724
26613 | 425.3419 | 26724
26614 | 408.9623 | 26724
26615 | 424.5616 | 26724
26616 | 410.1456 | 26724
26617 | 422.3738 | 26724
26618 | 407.2561 | 26724
26619 | 410.9024 | 26724
26620 | 414.3443 | 26724
26621 | 419.3687 | 26724
26622 | 408.1943 | 26724
26623 | 419.3359 | 26724
26624 | 421.7869 | 26724
26625 | 411.5283 | 26724
26626 | 402.2165 | 26724
26627 | 422.7917 | 26724
26628 | 414.3682 | 26724
26629 | 422.7554 | 26724
26630 | 418.9001 | 26724
26631 | 414.7643 | 26724
26632 | 420.9343 | 26724
26633 | 415.9816 | 26724
26634 | 409.3068 | 26724
26635 | 428.5775 | 26724
26636 | 411.1538 | 26724
26637 | 415.1746 | 26724
26638 | 423.8995 | 26724
26639 | 422.6124 | 26724
26640 | 423.9717 | 26724
26641 | 410.0773 | 26724
26642 | 411.0672 | 26724
26643 | 404.0428 | 26724
26644 | 406.6694 | 26724
26645 | 402.4221 | 26724
26646 | 411.2872 | 26724
26647 | 402.9926 | 26724
26648 | 401.1892 | 26724
26649 | 412.5664 | 26724
26650 | 414.0785 | 26724
26651 | 431.3606 | 26724
26652 | 428.3517 | 26724
26653 | 412.8739 | 26724
26654 | 416.3972 | 26724
26655 | 400.1334 | 26724
26656 | 420.7431 | 26724
26657 | 426.3231 | 26724
26658 | 422.353 | 26724
26659 | 428.1278 | 26724
26660 | 413.1867 | 26724
26661 | 417.2541 | 26724
26662 | 412.1732 | 26724
26663 | 401.6687 | 26724
26664 | 421.0588 | 26724
26665 | 416.1097 | 26724
26666 | 417.9053 | 26724
26667 | 399.0717 | 26724
26668 | 420.3624 | 26724
26669 | 424.6014 | 26724
26670 | 431.6597 | 26724
26671 | 409.743 | 26724
26672 | 417.7752 | 26724
26673 | 428.3042 | 26724
26674 | 416.2307 | 26724
26675 | 432.1875 | 26724
26676 | 415.7433 | 26724
26677 | 415.3786 | 26724
26678 | 419.5743 | 26724
26679 | 408.988 | 26724
26680 | 418.185 | 26724
26681 | 423.9983 | 26724
26682 | 407.2781 | 26724
26683 | 423.5803 | 26724
26684 | 417.1841 | 26724
26685 | 427.217 | 26724
26686 | 418.5666 | 26724
26687 | 436.171 | 26724
26688 | 408.3548 | 26724
26689 | 418.7731 | 26724
26690 | 418.5232 | 26724
26691 | 418.7826 | 26724
26692 | 403.7918 | 26724
26693 | 426.1185 | 26724
26694 | 423.1128 | 26724
26695 | 416.537 | 26724
26696 | 409.9282 | 26724
26697 | 409.3366 | 26724
26698 | 406.0218 | 26724
26699 | 414.4135 | 26724
26700 | 408.134 | 26724
26701 | 424.2056 | 26724
26702 | 405.7318 | 26724
26703 | 420.0225 | 26724
26704 | 406.1383 | 26724
26705 | 415.5274 | 26724
26706 | 423.9767 | 26724
26707 | 406.3561 | 26724
26708 | 419.0452 | 26724
26709 | 407.3401 | 26724
26710 | 424.9116 | 26724
26711 | 409.1298 | 26724
26712 | 418.4732 | 26724
26713 | 421.8355 | 26724
26714 | 404.4537 | 26724
26715 | 417.063 | 26724
26716 | 423.2192 | 26724
26717 | 407.9532 | 26724
26718 | 408.7301 | 26724
26719 | 415.4992 | 26724
26720 | 420.4922 | 26724
26721 | 430.6727 | 26724
26722 | 406.1143 | 26724
26723 | 424.6851 | 26724
26724 | 417.2604 | 26724
26725 | 427.7445 | 26724
26726 | 426.6178 | 26724
26727 | 422.0582 | 26724
26728 | 406.7272 | 26724
26729 | 428.9695 | 26724
26730 | 407.3116 | 26724
26731 | 421.3496 | 26724
26732 | 421.1301 | 26724
26733 | 426.5921 | 26724
26734 | 399.9902 | 26724
26735 | 414.5919 | 26724
26736 | 409.8523 | 26724
26737 | 421.326 | 26724
26738 | 415.71 | 26724
26739 | 422.6592 | 26724
26740 | 410.2699 | 26724
26741 | 410.9851 | 26724
26742 | 413.107 | 26724
26743 | 421.2024 | 26724
26744 | 421.8202 | 26724
26745 | 407.478 | 26724
26746 | 417.5751 | 26724
26747 | 424.2771 | 26724
26748 | 436.7451 | 26724
26749 | 416.5467 | 26724
26750 | 417.343 | 26724
26751 | 426.2195 | 26724
26752 | 414.032 | 26724
26753 | 424.9483 | 26724
26754 | 402.8472 | 26724
26755 | 419.0924 | 26724
26756 | 424.8614 | 26724
26757 | 407.3424 | 26724
26758 | 416.2671 | 26724
26759 | 425.2143 | 26724
26760 | 411.7941 | 26724
26761 | 423.6234 | 26724
26762 | 425.9443 | 26724
26763 | 408.2712 | 26724
26764 | 404.6656 | 26724
26765 | 401.5343 | 26724
26766 | 412.2512 | 26724
26767 | 412.193 | 26724
26768 | 429.9548 | 26724
26769 | 418.8635 | 26724
26770 | 406.1725 | 26724
26771 | 400.5368 | 26724
26772 | 406.1069 | 26724
26773 | 430.2336 | 26724
26774 | 421.1423 | 26724
26775 | 416.2091 | 26724
26776 | 408.6355 | 26724
26777 | 421.8216 | 26724
26778 | 414.5351 | 26724
26779 | 423.9322 | 26724
26780 | 414.4206 | 26724
26781 | 403.9195 | 26724
26782 | 407.2637 | 26724
26783 | 429.6846 | 26724
26784 | 417.1212 | 26724
26785 | 423.0437 | 26724
26786 | 416.8 | 26724
26787 | 419.7123 | 26724
26788 | 417.2576 | 26724
26789 | 405.822 | 26724
26790 | 401.1887 | 26724
26791 | 406.4561 | 26724
26792 | 420.7262 | 26724
26793 | 411.8666 | 26724
26794 | 415.6909 | 26724
26795 | 426.6007 | 26724
26796 | 421.6766 | 26724
26797 | 429.2195 | 26724
26798 | 405.8069 | 26724
26799 | 410.3507 | 26724
26800 | 411.5833 | 26724
26801 | 416.575 | 26724
26802 | 419.326 | 26724
26803 | 416.711 | 26724
26804 | 399.1879 | 26724
26805 | 407.6907 | 26724
26806 | 418.9343 | 26724
26807 | 429.7021 | 26724
26808 | 419.3208 | 26724
26809 | 414.1047 | 26724
26810 | 415.7598 | 26724
26811 | 417.728 | 26724
26812 | 420.5806 | 26724
26813 | 414.8922 | 26724
26814 | 435.1789 | 26724
26815 | 410.8803 | 26724
26816 | 417.7136 | 26724
26817 | 417.3848 | 26724
26818 | 421.9438 | 26724
26819 | 408.048 | 26724
26820 | 409.4569 | 26724
26821 | 413.4665 | 26724
26822 | 408.4918 | 26724
26823 | 423.5127 | 26724
26824 | 415.7801 | 26724
26825 | 425.5054 | 26724
26826 | 405.4267 | 26724
26827 | 415.0127 | 26724
26828 | 424.796 | 26724
26829 | 410.0914 | 26724
26830 | 393.2736 | 26724
26831 | 413.7204 | 26724
26832 | 427.5966 | 26724
26833 | 395.6187 | 26724
26834 | 402.9036 | 26724
26835 | 421.0591 | 26724
26836 | 421.8487 | 26724
26837 | 406.8016 | 26724
26838 | 417.4289 | 26724
26839 | 420.8043 | 26724
26840 | 416.4528 | 26724
26841 | 408.8292 | 26724
26842 | 422.3047 | 26724
26843 | 423.6991 | 26724
26844 | 428.8132 | 26724
26845 | 423.5991 | 26724
26846 | 414.3035 | 26724
26847 | 413.612 | 26724
26848 | 426.4458 | 26724
26849 | 414.3906 | 26724
26850 | 414.7394 | 26724
26851 | 404.0101 | 26724
26852 | 415.6138 | 26724
26853 | 406.5201 | 26724
26854 | 426.561 | 26724
26855 | 427.5959 | 26724
26856 | 422.564 | 26724
26857 | 415.7319 | 26724
26858 | 415.7969 | 26724
26859 | 404.5848 | 26724
26860 | 422.5598 | 26724
26861 | 411.2631 | 26724
26862 | 409.9115 | 26724
26863 | 410.437 | 26724
26864 | 427.5344 | 26724
26865 | 404.4376 | 26724
26866 | 414.139 | 26724
26867 | 409.7886 | 26724
26868 | 411.1219 | 26724
26869 | 419.2216 | 26724
26870 | 424.7485 | 26724
26871 | 424.9131 | 26724
26872 | 405.7898 | 26724
26873 | 415.5135 | 26724
26874 | 436.2066 | 26724
26875 | 419.3891 | 26724
26876 | 425.0737 | 26724
26877 | 412.7544 | 26724
26878 | 417.265 | 26724
26879 | 416.3926 | 26724
26880 | 413.0727 | 26724
26881 | 433.9645 | 26724
26882 | 408.3855 | 26724
26883 | 419.3448 | 26724
26884 | 417.0226 | 26724
26885 | 425.8448 | 26724
26886 | 425.3119 | 26724
26887 | 412.6243 | 26724
26888 | 420.3029 | 26724
26889 | 405.3678 | 26724
26890 | 413.8014 | 26724
26891 | 422.2621 | 26724
26892 | 408.6837 | 26724
26893 | 413.5052 | 26724
26894 | 427.4313 | 26724
26895 | 413.0028 | 26724
26896 | 416.7624 | 26724
26897 | 408.0685 | 26724
26898 | 424.7106 | 26724
26899 | 415.0751 | 26724
26900 | 408.6967 | 26724
26901 | 421.615 | 26724
26902 | 409.538 | 26724
26903 | 416.7677 | 26724
26904 | 430.4847 | 26724
26905 | 418.9484 | 26724
26906 | 421.2821 | 26724
26907 | 418.2559 | 26724
26908 | 425.4215 | 26724
26909 | 413.1221 | 26724
26910 | 408.9763 | 26724
26911 | 418.4371 | 26724
26912 | 424.3168 | 26724
26913 | 417.2087 | 26724
26914 | 412.9402 | 26724
26915 | 408.9723 | 26724
26916 | 407.9055 | 26724
26917 | 418.6405 | 26724
26918 | 410.1322 | 26724
26919 | 413.497 | 26724
26920 | 414.0626 | 26724
26921 | 429.5006 | 26724
26922 | 429.8552 | 26724
26923 | 429.5978 | 26724
26924 | 414.2371 | 26724
26925 | 422.438 | 26724
26926 | 425.3717 | 26724
26927 | 417.331 | 26724
26928 | 415.0412 | 26724
26929 | 401.8668 | 26724
26930 | 433.6831 | 26724
26931 | 427.6895 | 26724
26932 | 408.252 | 26724
26933 | 418.9581 | 26724
26934 | 421.5113 | 26724
26935 | 416.4355 | 26724
26936 | 416.5989 | 26724
26937 | 415.3606 | 26724
26938 | 415.0937 | 26724
26939 | 420.3803 | 26724
26940 | 414.9197 | 26724
26941 | 416.0769 | 26724
26942 | 418.4825 | 26724
26943 | 413.0888 | 26724
26944 | 415.8222 | 26724
26945 | 421.0222 | 26724
26946 | 427.6964 | 26724
26947 | 416.962 | 26724
26948 | 417.5356 | 26724
26949 | 412.9292 | 26724
26950 | 412.2284 | 26724
26951 | 402.6375 | 26724
26952 | 431.2856 | 26724
26953 | 415.0596 | 26724
26954 | 418.5295 | 26724
26955 | 437.9747 | 26724
26956 | 400.8963 | 26724
26957 | 425.3099 | 26724
26958 | 414.7026 | 26724
26959 | 417.4423 | 26724
26960 | 418.9083 | 26724
26961 | 420.3547 | 26724
26962 | 426.6988 | 26724
26963 | 413.2833 | 26724
26964 | 416.2482 | 26724
26965 | 425.3242 | 26724
26966 | 400.7066 | 26724
26967 | 419.1563 | 26724
26968 | 419.3718 | 26724
26969 | 402.4723 | 26724
26970 | 410.5782 | 26724
26971 | 413.9024 | 26724
26972 | 423.8082 | 26724
26973 | 421.6295 | 26724
26974 | 395.4937 | 26724
26975 | 420.3113 | 26724
26976 | 417.8324 | 26724
26977 | 416.4268 | 26724
26978 | 428.288 | 26724
26979 | 411.0926 | 26724
26980 | 418.4796 | 26724
26981 | 430.8444 | 26724
26982 | 432.6746 | 26724
26983 | 424.39 | 26724
26984 | 415.9536 | 26724
26985 | 400.277 | 26724
26986 | 419.8324 | 26724
26987 | 409.7618 | 26724
26988 | 401.2001 | 26724
26989 | 417.6222 | 26724
26990 | 402.7008 | 26724
26991 | 410.3761 | 26724
26992 | 415.0832 | 26724
26993 | 420.1958 | 26724
26994 | 412.5337 | 26724
26995 | 423.3439 | 26724
26996 | 418.2094 | 26724
26997 | 413.0356 | 26724
26998 | 396.4008 | 26724
26999 | 400.3592 | 26724
27000 | 405.926 | 26724
27001 | 405.7834 | 26724
27002 | 425.6153 | 26724
27003 | 416.1552 | 26724
27004 | 417.7885 | 26724
27005 | 410.5149 | 26724
27006 | 405.2675 | 26724
27007 | 418.6679 | 26724
27008 | 414.1263 | 26724
27009 | 416.9513 | 26724
27010 | 417.8993 | 26724
27011 | 427.4546 | 26724
27012 | 424.3216 | 26724
27013 | 404.3539 | 26724
27014 | 428.5008 | 26724
27015 | 415.0909 | 26724
27016 | 401.6178 | 26724
27017 | 419.848 | 26724
27018 | 419 | 26724
27019 | 419.2291 | 26724
27020 | 415.9091 | 26724
27021 | 413.9245 | 26724
27022 | 424.3536 | 26724
27023 | 414.1921 | 26724
27024 | 421.4824 | 26724
27025 | 400.4562 | 26724
27026 | 405.9644 | 26724
27027 | 417.8328 | 26724
27028 | 418.6143 | 26724
27029 | 440.8624 | 26724
27030 | 425.479 | 26724
27031 | 422.6362 | 26724
27032 | 425.3368 | 26724
27033 | 398.4067 | 26724
27034 | 412.5993 | 26724
27035 | 424.7666 | 26724
27036 | 423.2125 | 26724
27037 | 418.0781 | 26724
27038 | 408.1125 | 26724
27039 | 426.081 | 26724
27040 | 407.5116 | 26724
27041 | 420.4838 | 26724
27042 | 397.8905 | 26724
27043 | 413.7878 | 26724
27044 | 423.8315 | 26724
27045 | 411.8631 | 26724
27046 | 406.0885 | 26724
27047 | 424.1034 | 26724
27048 | 411.8646 | 26724
27049 | 426.2349 | 26724
27050 | 416.1661 | 26724
27051 | 422.027 | 26724
27052 | 419.6585 | 26724
27053 | 416.9293 | 26724
27054 | 405.7374 | 26724
27055 | 410.9527 | 26724
27056 | 415.3899 | 26724
27057 | 413.2248 | 26724
27058 | 415.1132 | 26724
27059 | 426.3158 | 26724
27060 | 416.3114 | 26724
27061 | 418.875 | 26724
27062 | 421.8727 | 26724
27063 | 419.9954 | 26724
27064 | 420.3269 | 26724
27065 | 414.9742 | 26724
27066 | 410.6976 | 26724
27067 | 412.2506 | 26724
27068 | 416.391 | 26724
27069 | 412.1361 | 26724
27070 | 407.1062 | 26724
27071 | 398.089 | 26724
27072 | 423.8774 | 26724
27073 | 417.6652 | 26724
27074 | 420.7556 | 26724
27075 | 398.1457 | 26724
27076 | 417.4363 | 26724
27077 | 426.8002 | 26724
27078 | 410.7268 | 26724
27079 | 408.3323 | 26724
27080 | 417.8737 | 26724
27081 | 421.678 | 26724
27082 | 426.7017 | 26724
27083 | 419.5116 | 26724
27084 | 415.8693 | 26724
27085 | 407.5236 | 26724
27086 | 411.6599 | 26724
27087 | 425.7029 | 26724
27088 | 415.1582 | 26724
27089 | 420.2113 | 26724
27090 | 414.06 | 26724
27091 | 414.242 | 26724
27092 | 422.869 | 26724
27093 | 425.0744 | 26724
27094 | 428.4718 | 26724
27095 | 417.1913 | 26724
27096 | 421.7019 | 26724
27097 | 414.2488 | 26724
27098 | 409.608 | 26724
27099 | 422.3549 | 26724
27100 | 411.9764 | 26724
27101 | 412.8409 | 26724
27102 | 416.2556 | 26724
27103 | 408.3011 | 26724
27104 | 414.9753 | 26724
27105 | 414.996 | 26724
27106 | 416.642 | 26724
27107 | 418.5718 | 26724
27108 | 420.5244 | 26724
27109 | 420.2511 | 26724
27110 | 411.2922 | 26724
27111 | 414.1811 | 26724
27112 | 419.5208 | 26724
27113 | 412.0227 | 26724
27114 | 410.4006 | 26724
27115 | 413.4412 | 26724
27116 | 425.769 | 26724
27117 | 425.7953 | 26724
27118 | 411.7485 | 26724
27119 | 407.1635 | 26724
27120 | 418.0388 | 26724
27121 | 411.2381 | 26724
27122 | 413.1391 | 26724
27123 | 431.0805 | 26724
27124 | 413.9203 | 26724
27125 | 415.4019 | 26724
27126 | 418.3895 | 26724
27127 | 405.2464 | 26724
27128 | 442.3876 | 26724
27129 | 405.7673 | 26724
27130 | 421.6874 | 26724
27131 | 421.4463 | 26724
27132 | 401.3303 | 26724
27133 | 419.632 | 26724
27134 | 431.4358 | 26724
27135 | 410.4891 | 26724
27136 | 408.0979 | 26724
27137 | 415.7454 | 26724
27138 | 408.4473 | 26724
27139 | 413.166 | 26724
27140 | 428.682 | 26724
27141 | 419.7578 | 26724
27142 | 417.246 | 26724
27143 | 419.4585 | 26724
27144 | 423.6809 | 26724
27145 | 427.344 | 26724
27146 | 426.0201 | 26724
27147 | 410.0631 | 26724
27148 | 422.5021 | 26724
27149 | 408.1563 | 26724
27150 | 400.9166 | 26724
27151 | 409.7636 | 26724
27152 | 416.8242 | 26724
27153 | 421.5271 | 26724
27154 | 421.3376 | 26724
27155 | 418.16 | 26724
27156 | 410.6652 | 26724
27157 | 417.5647 | 26724
27158 | 419.795 | 26724
27159 | 406.0098 | 26724
27160 | 409.7886 | 26724
27161 | 402.791 | 26724
27162 | 411.7302 | 26724
27163 | 423.2947 | 26724
27164 | 416.6434 | 26724
27165 | 417.9755 | 26724
27166 | 413.0752 | 26724
27167 | 412.3565 | 26724
27168 | 421.7558 | 26724
27169 | 421.9171 | 26724
27170 | 417.368 | 26724
27171 | 410.3122 | 26724
27172 | 420.9246 | 26724
27173 | 423.5217 | 26724
27174 | 421.5273 | 26724
27175 | 425.4715 | 26724
27176 | 411.2632 | 26724
27177 | 393.8927 | 26724
27178 | 424.4035 | 26724
27179 | 419.5666 | 26724
27180 | 413.4505 | 26724
27181 | 414.187 | 26724
27182 | 413.337 | 26724
27183 | 401.6929 | 26724
27184 | 425.7677 | 26724
27185 | 422.9481 | 26724
27186 | 426.0073 | 26724
27187 | 416.428 | 26724
27188 | 425.2444 | 26724
27189 | 421.2248 | 26724
27190 | 415.3085 | 26724
27191 | 422.2845 | 26724
27192 | 411.1941 | 26724
27193 | 422.842 | 26724
27194 | 414.6306 | 26724
27195 | 418.5855 | 26724
27196 | 400.7828 | 26724
27197 | 410.6716 | 26724
27198 | 410.1962 | 26724
27199 | 413.3155 | 26724
27200 | 411.8323 | 26724
27201 | 429.078 | 26724
27202 | 414.7418 | 26724
27203 | 416.6975 | 26724
27204 | 425.8349 | 26724
27205 | 402.5855 | 26724
27206 | 404.7319 | 26724
27207 | 417.0716 | 26724
27208 | 417.9004 | 26724
27209 | 413.2951 | 26724
27210 | 425.8544 | 26724
27211 | 400.0481 | 26724
27212 | 422.1325 | 26724
27213 | 436.7612 | 26724
27214 | 419.8533 | 26724
27215 | 418.7479 | 26724
27216 | 416.5223 | 26724
27217 | 432.1182 | 26724
27218 | 398.3657 | 26724
27219 | 400.0034 | 26724
27220 | 419.7388 | 26724
27221 | 412.3776 | 26724
27222 | 421.9336 | 26724
27223 | 420.247 | 26724
27224 | 426.8458 | 26724
27225 | 418.8093 | 26724
27226 | 427.1474 | 26724
27227 | 410.2812 | 26724
27228 | 413.6189 | 26724
27229 | 424.0764 | 26724
27230 | 424.9716 | 26724
27231 | 426.8513 | 26724
27232 | 410.4357 | 26724
27233 | 425.2585 | 26724
27234 | 406.3454 | 26724
27235 | 402.8947 | 26724
27236 | 415.5878 | 26724
27237 | 409.3685 | 26724
27238 | 414.5603 | 26724
27239 | 411.5659 | 26724
27240 | 420.2382 | 26724
27241 | 418.7933 | 26724
27242 | 415.5472 | 26724
27243 | 416.1396 | 26724
27244 | 407.7957 | 26724
27245 | 406.375 | 26724
27246 | 415.8013 | 26724
27247 | 426.0917 | 26724
27248 | 416.152 | 26724
27249 | 428.4067 | 26724
27250 | 426.0345 | 26724
27251 | 417.301 | 26724
27252 | 420.2219 | 26724
27253 | 424.8299 | 26724
27254 | 415.5761 | 26724
27255 | 416.2163 | 26724
27256 | 417.3567 | 26724
27257 | 424.274 | 26724
27258 | 423.6905 | 26724
27259 | 425.9289 | 26724
27260 | 421.8961 | 26724
27261 | 418.6531 | 26724
27262 | 405.9991 | 26724
27263 | 424.9385 | 26724
27264 | 411.4266 | 26724
27265 | 426.2204 | 26724
27266 | 401.1843 | 26724
27267 | 407.2363 | 26724
27268 | 412.5298 | 26724
27269 | 424.2412 | 26724
27270 | 416.6119 | 26724
27271 | 414.0142 | 26724
27272 | 427.2749 | 26724
27273 | 405.6847 | 26724
27274 | 408.2748 | 26724
27275 | 419.5926 | 26724
27276 | 421.9752 | 26724
27277 | 419.2612 | 26724
27278 | 412.0692 | 26724
27279 | 415.7501 | 26724
27280 | 418.4386 | 26724
27281 | 419.6691 | 26724
27282 | 413.6559 | 26724
27283 | 415.2819 | 26724
27284 | 411.8912 | 26724
27285 | 411.8414 | 26724
27286 | 407.5007 | 26724
27287 | 420.0912 | 26724
27288 | 423.3985 | 26724
27289 | 417.9542 | 26724
27290 | 408.7929 | 26724
27291 | 415.3211 | 26724
27292 | 417.2279 | 26724
27293 | 410.6567 | 26724
27294 | 420.5889 | 26724
27295 | 423.56 | 26724
27296 | 420.9283 | 26724
27297 | 410.8767 | 26724
27298 | 408.4596 | 26724
27299 | 408.8191 | 26724
27300 | 415.1445 | 26724
27301 | 396.5076 | 26724
27302 | 416.4079 | 26724
27303 | 417.6143 | 26724
27304 | 414.894 | 26724
27305 | 411.8095 | 26724
27306 | 406.167 | 26724
27307 | 415.7328 | 26724
27308 | 403.8659 | 26724
27309 | 418.2161 | 26724
27310 | 417.0653 | 26724
27311 | 422.0139 | 26724
27312 | 415.3552 | 26724
27313 | 427.7057 | 26724
27314 | 433.5621 | 26724
27315 | 404.0404 | 26724
27316 | 424.3396 | 26724
27317 | 419.9302 | 26724
27318 | 420.1949 | 26724
27319 | 416.2433 | 26724
27320 | 417.7891 | 26724
27321 | 427.5268 | 26724
27322 | 424.0086 | 26724
27323 | 409.3935 | 26724
27324 | 422.9729 | 26724
27325 | 421.215 | 26724
27326 | 424.6377 | 26724
27327 | 428.2543 | 26724
27328 | 407.8517 | 26724
27329 | 412.5765 | 26724
27330 | 422.152 | 26724
27331 | 424.98 | 26724
27332 | 418.6904 | 26724
27333 | 428.6906 | 26724
27334 | 431.7554 | 26724
27335 | 423.3293 | 26724
27336 | 416.5813 | 26724
27337 | 418.5597 | 26724
27338 | 423.9779 | 26724
27339 | 416.1329 | 26724
27340 | 422.6391 | 26724
27341 | 412.0084 | 26724
27342 | 413.3212 | 26724
27343 | 421.9693 | 26724
27344 | 424.1369 | 26724
27345 | 413.446 | 26724
27346 | 418.0896 | 26724
27347 | 418.2825 | 26724
27348 | 406.5376 | 26724
27349 | 420.6093 | 26724
27350 | 402.8707 | 26724
27351 | 405.659 | 26724
27352 | 408.6805 | 26724
27353 | 424.4835 | 26724
27354 | 421.965 | 26724
27355 | 416.0473 | 26724
27356 | 415.9447 | 26724
27357 | 427.0349 | 26724
27358 | 408.4995 | 26724
27359 | 415.2596 | 26724
27360 | 410.8143 | 26724
27361 | 418.5711 | 26724
27362 | 412.3037 | 26724
27363 | 411.2621 | 26724
27364 | 410.1914 | 26724
27365 | 412.1579 | 26724
27366 | 431.366 | 26724
27367 | 414.0486 | 26724
27368 | 414.4893 | 26724
27369 | 406.8035 | 26724
27370 | 427.9843 | 26724
27371 | 423.3705 | 26724
27372 | 402.5089 | 26724
27373 | 422.7783 | 26724
27374 | 405.4349 | 26724
27375 | 416.2307 | 26724
27376 | 407.7028 | 26724
27377 | 401.309 | 26724
27378 | 423.6584 | 26724
27379 | 406.7665 | 26724
27380 | 412.0874 | 26724
27381 | 427.4903 | 26724
27382 | 424.5473 | 26724
27383 | 419.1544 | 26724
27384 | 413.8821 | 26724
27385 | 424.5341 | 26724
27386 | 416.2948 | 26724
27387 | 420.4618 | 26724
27388 | 414.1774 | 26724
27389 | 412.0861 | 26724
27390 | 420.5202 | 26724
27391 | 420.4655 | 26724
27392 | 395.3574 | 26724
27393 | 422.7172 | 26724
27394 | 420.5306 | 26724
27395 | 406.2024 | 26724
27396 | 406.8021 | 26724
27397 | 437.1592 | 26724
27398 | 408.8276 | 26724
27399 | 425.8155 | 26724
27400 | 428.32 | 26724
27401 | 413.3953 | 26724
27402 | 413.092 | 26724
27403 | 410.902 | 26724
27404 | 420.7878 | 26724
27405 | 418.5693 | 26724
27406 | 413.4291 | 26724
27407 | 413.2015 | 26724
27408 | 401.1583 | 26724
27409 | 408.048 | 26724
27410 | 422.7789 | 26724
27411 | 422.4962 | 26724
27412 | 426.1053 | 26724
27413 | 424.6877 | 26724
27414 | 422.3316 | 26724
27415 | 410.6185 | 26724
27416 | 408.7797 | 26724
27417 | 416.1699 | 26724
27418 | 432.3647 | 26724
27419 | 419.068 | 26724
27420 | 406.1691 | 26724
27421 | 426.905 | 26724
27422 | 407.6314 | 26724
27423 | 426.0759 | 26724
27424 | 410.1639 | 26724
27425 | 416.21 | 26724
27426 | 416.7141 | 26724
27427 | 406.27 | 26724
27428 | 402.2217 | 26724
27429 | 398.9857 | 26724
27430 | 425.7336 | 26724
27431 | 415.7118 | 26724
27432 | 402.0657 | 26724
27433 | 411.3499 | 26724
27434 | 411.674 | 26724
27435 | 406.1918 | 26724
27436 | 418.721 | 26724
27437 | 415.1835 | 26724
27438 | 403.8267 | 26724
27439 | 415.6708 | 26724
27440 | 414.0219 | 26724
27441 | 419.2313 | 26724
27442 | 405.1083 | 26724
27443 | 411.054 | 26724
27444 | 424.9047 | 26724
27445 | 417.5759 | 26724
27446 | 422.4418 | 26724
27447 | 419.9181 | 26724
27448 | 406.0366 | 26724
27449 | 420.8593 | 26724
27450 | 418.7617 | 26724
27451 | 410.6824 | 26724
27452 | 420.5779 | 26724
27453 | 410.8836 | 26724
27454 | 423.4678 | 26724
27455 | 421.2426 | 26724
27456 | 413.2769 | 26724
27457 | 400.6024 | 26724
27458 | 414.7903 | 26724
27459 | 430.5159 | 26724
27460 | 421.1008 | 26724
27461 | 418.5095 | 26724
27462 | 416.2375 | 26724
27463 | 417.3189 | 26724
27464 | 420.2475 | 26724
27465 | 419.269 | 26724
27466 | 403.8459 | 26724
27467 | 417.3123 | 26724
27468 | 414.5712 | 26724
27469 | 425.544 | 26724
27470 | 425.7144 | 26724
27471 | 409.419 | 26724
27472 | 410.9615 | 26724
27473 | 425.7086 | 26724
27474 | 415.5576 | 26724
27475 | 420.5315 | 26724
27476 | 414.3019 | 26724
27477 | 415.7133 | 26724
27478 | 421.8246 | 26724
27479 | 406.8552 | 26724
27480 | 412.6731 | 26724
27481 | 408.617 | 26724
27482 | 405.6189 | 26724
27483 | 406.6736 | 26724
27484 | 416.3098 | 26724
27485 | 418.2105 | 26724
27486 | 413.4121 | 26724
27487 | 408.5487 | 26724
27488 | 424.2662 | 26724
27489 | 420.339 | 26724
27490 | 404.5058 | 26724
27491 | 405.6468 | 26724
27492 | 408.3075 | 26724
27493 | 421.4472 | 26724
27494 | 417.5164 | 26724
27495 | 423.032 | 26724
27496 | 410.8508 | 26724
27497 | 416.0749 | 26724
27498 | 419.5332 | 26724
27499 | 422.8353 | 26724
27500 | 408.7798 | 26724
27501 | 430.2027 | 26724
27502 | 418.4847 | 26724
27503 | 429.3846 | 26724
27504 | 414.1612 | 26724
27505 | 406.7909 | 26724
27506 | 409.4659 | 26724
27507 | 408.7332 | 26724
27508 | 419.5217 | 26724
27509 | 402.1384 | 26724
27510 | 419.4327 | 26724
27511 | 425.5591 | 26724
27512 | 410.1657 | 26724
27513 | 408.5298 | 26724
27514 | 411.802 | 26724
27515 | 422.6033 | 26724
27516 | 405.5116 | 26724
27517 | 407.616 | 26724
27518 | 408.0126 | 26724
27519 | 414.3878 | 26724
27520 | 420.6933 | 26724
27521 | 426.1001 | 26724
27522 | 408.7939 | 26724
27523 | 416.9397 | 26724
27524 | 408.0205 | 26724
27525 | 408.9316 | 26724
27526 | 413.1493 | 26724
27527 | 416.5121 | 26724
27528 | 406.216 | 26724
27529 | 423.0916 | 26724
27530 | 406.8153 | 26724
27531 | 418.3993 | 26724
27532 | 425.5972 | 26724
27533 | 418.4984 | 26724
27534 | 419.7484 | 26724
27535 | 411.3541 | 26724
27536 | 414.2765 | 26724
27537 | 411.3689 | 26724
27538 | 406.6394 | 26724
27539 | 410.7451 | 26724
27540 | 422.9665 | 26724
27541 | 411.1596 | 26724
27542 | 422.5175 | 26724
27543 | 398.6475 | 26724
27544 | 414.9957 | 26724
27545 | 416.3495 | 26724
27546 | 416.6764 | 26724
27547 | 409.2106 | 26724
27548 | 414.9412 | 26724
27549 | 424.8614 | 26724
27550 | 402.7571 | 26724
27551 | 428.4814 | 26724
27552 | 422.2471 | 26724
27553 | 423.3812 | 26724
27554 | 418.8558 | 26724
27555 | 416.597 | 26724
27556 | 420.4972 | 26724
27557 | 408.7237 | 26724
27558 | 406.0319 | 26724
27559 | 409.9389 | 26724
27560 | 422.4684 | 26724
27561 | 407.5296 | 26724
27562 | 428.2068 | 26724
27563 | 395.193 | 26724
27564 | 426.05 | 26724
27565 | 419.2278 | 26724
27566 | 413.8055 | 26724
27567 | 403.9529 | 26724
27568 | 401.7745 | 26724
27569 | 422.7977 | 26724
27570 | 409.2031 | 26724
27571 | 430.3318 | 26724
27572 | 426.6757 | 26724
27573 | 403.1905 | 26724
27574 | 415.2083 | 26724
27575 | 410.4298 | 26724
27576 | 413.3156 | 26724
27577 | 417.3935 | 26724
27578 | 421.192 | 26724
27579 | 410.5951 | 26724
27580 | 411.3403 | 26724
27581 | 416.808 | 26724
27582 | 417.4245 | 26724
27583 | 416.9414 | 26724
27584 | 410.7602 | 26724
27585 | 408.4323 | 26724
27586 | 416.6207 | 26724
27587 | 406.1109 | 26724
27588 | 415.6173 | 26724
27589 | 407.8554 | 26724
27590 | 414.5297 | 26724
27591 | 396.8617 | 26724
27592 | 414.0075 | 26724
27593 | 425.3561 | 26724
27594 | 429.7205 | 26724
27595 | 425.2593 | 26724
27596 | 401.0299 | 26724
27597 | 416.7898 | 26724
27598 | 418.3811 | 26724
27599 | 420.1266 | 26724
27600 | 420.7403 | 26724
27601 | 409.8296 | 26724
27602 | 412.6453 | 26724
27603 | 415.3509 | 26724
27604 | 422.9361 | 26724
27605 | 414.5066 | 26724
27606 | 423.7486 | 26724
27607 | 409.3375 | 26724
27608 | 410.0487 | 26724
27609 | 409.9758 | 26724
27610 | 401.8925 | 26724
27611 | 408.3724 | 26724
27612 | 416.9267 | 26724
27613 | 422.6746 | 26724
27614 | 429.6638 | 26724
27615 | 427.6413 | 26724
27616 | 415.3922 | 26724
27617 | 404.8324 | 26724
27618 | 418.6774 | 26724
27619 | 411.4068 | 26724
27620 | 415.5493 | 26724
27621 | 402.287 | 26724
27622 | 420.0482 | 26724
27623 | 407.4476 | 26724
27624 | 416.7365 | 26724
27625 | 424.8632 | 26724
27626 | 409.4359 | 26724
27627 | 426.4412 | 26724
27628 | 420.2998 | 26724
27629 | 412.9758 | 26724
27630 | 409.0061 | 26724
27631 | 409.429 | 26724
27632 | 410.0241 | 26724
27633 | 408.3215 | 26724
27634 | 420.509 | 26724
27635 | 407.9637 | 26724
27636 | 403.2564 | 26724
27637 | 420.852 | 26724
27638 | 423.9479 | 26724
27639 | 428.3311 | 26724
27640 | 407.8783 | 26724
27641 | 412.5578 | 26724
27642 | 415.4661 | 26724
27643 | 419.4494 | 26724
27644 | 422.3378 | 26724
27645 | 400.5828 | 26724
27646 | 424.8475 | 26724
27647 | 410.9456 | 26724
27648 | 404.2393 | 26724
27649 | 412.6743 | 26724
27650 | 435.4791 | 26724
27651 | 423.8273 | 26724
27652 | 422.8911 | 26724
27653 | 432.1141 | 26724
27654 | 431.4354 | 26724
27655 | 413.4841 | 26724
27656 | 421.0322 | 26724
27657 | 415.7502 | 26724
27658 | 406.6559 | 26724
27659 | 400.3755 | 26724
27660 | 417.7157 | 26724
27661 | 427.0213 | 26724
27662 | 412.8899 | 26724
27663 | 421.1617 | 26724
27664 | 417.5882 | 26724
27665 | 423.5245 | 26724
27666 | 410.4168 | 26724
27667 | 418.0687 | 26724
27668 | 417.3406 | 26724
27669 | 421.0261 | 26724
27670 | 410.5341 | 26724
27671 | 416.5023 | 26724
27672 | 413.8346 | 26724
27673 | 422.8927 | 26724
27674 | 413.1153 | 26724
27675 | 411.3579 | 26724
27676 | 405.3161 | 26724
27677 | 423.0472 | 26724
27678 | 406.5068 | 26724
27679 | 422.0661 | 26724
27680 | 406.9201 | 26724
27681 | 429.7829 | 26724
27682 | 416.4446 | 26724
27683 | 408.9191 | 26724
27684 | 421.6129 | 26724
27685 | 425.8072 | 26724
27686 | 407.1985 | 26724
27687 | 418.6059 | 26724
27688 | 414.8804 | 26724
27689 | 401.713 | 26724
27690 | 421.2629 | 26724
27691 | 423.4868 | 26724
27692 | 415.1662 | 26724
27693 | 416.3868 | 26724
27694 | 414.0731 | 26724
27695 | 414.3981 | 26724
27696 | 407.8013 | 26724
27697 | 416.7264 | 26724
27698 | 418.4971 | 26724
27699 | 420.5962 | 26724
27700 | 414.1597 | 26724
27701 | 407.1911 | 26724
27702 | 428.1057 | 26724
27703 | 427.2367 | 26724
27704 | 430.8744 | 26724
27705 | 405.1871 | 26724
27706 | 416.1953 | 26724
27707 | 414.7991 | 26724
27708 | 413.5289 | 26724
27709 | 411.2969 | 26724
27710 | 414.7046 | 26724
27711 | 415.0134 | 26724
27712 | 411.7706 | 26724
27713 | 435.567 | 26724
27714 | 418.1384 | 26724
27715 | 424.9461 | 26724
27716 | 416.7707 | 26724
27717 | 423.5812 | 26724
27718 | 422.3875 | 26724
27719 | 416.2323 | 26724
27720 | 432.9838 | 26724
27721 | 427.2915 | 26724
27722 | 431.886 | 26724
27723 | 397.7922 | 26724
27724 | 425.6576 | 26724
27725 | 417.0499 | 26724
27726 | 412.2648 | 26724
27727 | 408.0642 | 26724
27728 | 408.6953 | 26724
27729 | 419.2845 | 26724
27730 | 402.3914 | 26724
27731 | 418.374 | 26724
27732 | 418.5716 | 26724
27733 | 431.1934 | 26724
27734 | 416.2767 | 26724
27735 | 415.9045 | 26724
27736 | 427.7089 | 26724
27737 | 402.2926 | 26724
27738 | 424.4312 | 26724
27739 | 414.0854 | 26724
27740 | 411.439 | 26724
27741 | 406.8375 | 26724
27742 | 410.3928 | 26724
27743 | 416.3303 | 26724
27744 | 431.8914 | 26724
27745 | 413.3827 | 26724
27746 | 406.705 | 26724
27747 | 411.0755 | 26724
27748 | 407.0014 | 26724
27749 | 409.3677 | 26724
27750 | 420.3457 | 26724
27751 | 431.389 | 26724
27752 | 408.4615 | 26724
27753 | 426.2912 | 26724
27754 | 431.5547 | 26724
27755 | 402.4547 | 26724
27756 | 405.0886 | 26724
27757 | 419.5669 | 26724
27758 | 417.1825 | 26724
27759 | 413.771 | 26724
27760 | 410.2155 | 26724
27761 | 407.994 | 26724
27762 | 413.5465 | 26724
27763 | 416.589 | 26724
27764 | 410.2145 | 26724
27765 | 416.4262 | 26724
27766 | 418.304 | 26724
27767 | 418.0877 | 26724
27768 | 425.2323 | 26724
27769 | 414.2341 | 26724
27770 | 405.0328 | 26724
27771 | 412.106 | 26724
27772 | 406.4346 | 26724
27773 | 418.2447 | 26724
27774 | 396.5211 | 26724
27775 | 401.254 | 26724
27776 | 408.6599 | 26724
27777 | 404.3486 | 26724
27778 | 407.0983 | 26724
27779 | 412.5312 | 26724
27780 | 397.577 | 26724
27781 | 425.534 | 26724
27782 | 422.3237 | 26724
27783 | 395.909 | 26724
27784 | 412.1624 | 26724
27785 | 400.5319 | 26724
27786 | 415.0861 | 26724
27787 | 433.9585 | 26724
27788 | 410.2833 | 26724
27789 | 428.9314 | 26724
27790 | 413.5357 | 26724
27791 | 408.7996 | 26724
27792 | 429.0196 | 26724
27793 | 403.1788 | 26724
27794 | 404.1099 | 26724
27795 | 416.1467 | 26724
27796 | 405.8176 | 26724
27797 | 413.4445 | 26724
27798 | 404.3969 | 26724
27799 | 420.7617 | 26724
27800 | 417.5907 | 26724
27801 | 419.4327 | 26724
27802 | 430.8243 | 26724
27803 | 416.0147 | 26724
27804 | 418.7137 | 26724
27805 | 426.933 | 26724
27806 | 419.2657 | 26724
27807 | 413.7217 | 26724
27808 | 420.6399 | 26724
27809 | 415.8119 | 26724
27810 | 408.491 | 26724
27811 | 419.9618 | 26724
27812 | 426.2633 | 26724
27813 | 421.5248 | 26724
27814 | 420.8613 | 26724
27815 | 399.9615 | 26724
27816 | 422.6485 | 26724
27817 | 419.3925 | 26724
27818 | 422.3925 | 26724
27819 | 405.4099 | 26724
27820 | 415.761 | 26724
27821 | 423.6498 | 26724
27822 | 413.7041 | 26724
27823 | 406.4824 | 26724
27824 | 429.0638 | 26724
27825 | 422.4803 | 26724
27826 | 408.2857 | 26724
27827 | 414.8868 | 26724
27828 | 412.7694 | 26724
27829 | 422.6466 | 26724
27830 | 424.9285 | 26724
27831 | 419.0293 | 26724
27832 | 423.5871 | 26724
27833 | 419.0493 | 26724
27834 | 422.8625 | 26724
27835 | 415.7218 | 26724
27836 | 410.1663 | 26724
27837 | 410.438 | 26724
27838 | 430.6178 | 26724
27839 | 409.468 | 26724
27840 | 413.2635 | 26724
27841 | 409.2577 | 26724
27842 | 412.7906 | 26724
27843 | 412.4967 | 26724
27844 | 418.7578 | 26724
27845 | 412.7506 | 26724
27846 | 401.3568 | 26724
27847 | 408.9945 | 26724
27848 | 420.0608 | 26724
27849 | 410.7569 | 26724
27850 | 412.2272 | 26724
27851 | 417.322 | 26724
27852 | 417.731 | 26724
27853 | 423.024 | 26724
27854 | 423.1657 | 26724
27855 | 414.2559 | 26724
27856 | 416.6601 | 26724
27857 | 413.4685 | 26724
27858 | 420.895 | 26724
27859 | 402.405 | 26724
27860 | 410.6375 | 26724
27861 | 411.9426 | 26724
27862 | 418.4898 | 26724
27863 | 420.1134 | 26724
27864 | 411.3703 | 26724
27865 | 419.2768 | 26724
27866 | 413.1944 | 26724
27867 | 424.5169 | 26724
27868 | 427.3718 | 26724
27869 | 410.2926 | 26724
27870 | 418.1499 | 26724
27871 | 417.7055 | 26724
27872 | 426.93 | 26724
27873 | 422.661 | 26724
27874 | 410.0284 | 26724
27875 | 421.1961 | 26724
27876 | 409.0168 | 26724
27877 | 406.4686 | 26724
27878 | 424.0095 | 26724
27879 | 412.62 | 26724
27880 | 427.6352 | 26724
27881 | 408.1977 | 26724
27882 | 423.8512 | 26724
27883 | 405.1255 | 26724
27884 | 395.4428 | 26724
27885 | 431.3157 | 26724
27886 | 416.7949 | 26724
27887 | 422.9404 | 26724
27888 | 418.6274 | 26724
27889 | 398.0926 | 26724
27890 | 416.6089 | 26724
27891 | 414.8487 | 26724
27892 | 403.2094 | 26724
27893 | 412.0781 | 26724
27894 | 417.2343 | 26724
27895 | 428.2649 | 26724
27896 | 414.5016 | 26724
27897 | 418.1148 | 26724
27898 | 418.1522 | 26724
27899 | 422.9582 | 26724
27900 | 418.557 | 26724
27901 | 411.2145 | 26724
27902 | 420.2452 | 26724
27903 | 430.8461 | 26724
27904 | 403.1717 | 26724
27905 | 403.238 | 26724
27906 | 409.5196 | 26724
27907 | 427.0219 | 26724
27908 | 409.1236 | 26724
27909 | 430.3108 | 26724
27910 | 413.3472 | 26724
27911 | 427.8208 | 26724
27912 | 407.1894 | 26724
27913 | 412.7692 | 26724
27914 | 416.1691 | 26724
27915 | 421.9882 | 26724
27916 | 430.4865 | 26724
27917 | 424.5379 | 26724
27918 | 426.419 | 26724
27919 | 415.6134 | 26724
27920 | 415.8952 | 26724
27921 | 429.7714 | 26724
27922 | 419.9964 | 26724
27923 | 421.6263 | 26724
27924 | 421.3168 | 26724
27925 | 406.2837 | 26724
27926 | 429.6542 | 26724
27927 | 399.3035 | 26724
27928 | 416.7523 | 26724
27929 | 434.5053 | 26724
27930 | 414.1227 | 26724
27931 | 405.9244 | 26724
27932 | 415.6925 | 26724
27933 | 406.6869 | 26724
27934 | 422.7216 | 26724
27935 | 405.4996 | 26724
27936 | 416.7201 | 26724
27937 | 405.1974 | 26724
27938 | 412.3085 | 26724
27939 | 418.0252 | 26724
27940 | 414.1514 | 26724
27941 | 408.2911 | 26724
27942 | 411.649 | 26724
27943 | 430.7657 | 26724
27944 | 397.1426 | 26724
27945 | 423.2295 | 26724
27946 | 404.5915 | 26724
27947 | 412.9748 | 26724
27948 | 401.8565 | 26724
27949 | 432.4584 | 26724
27950 | 413.3539 | 26724
27951 | 408.7206 | 26724
27952 | 427.9254 | 26724
27953 | 424.5442 | 26724
27954 | 424.988 | 26724
27955 | 405.779 | 26724
27956 | 421.5366 | 26724
27957 | 415.2814 | 26724
27958 | 406.3016 | 26724
27959 | 413.5055 | 26724
27960 | 413.2463 | 26724
27961 | 425.5712 | 26724
27962 | 413.2316 | 26724
27963 | 420.2608 | 26724
27964 | 416.3972 | 26724
27965 | 418.3916 | 26724
27966 | 413.3681 | 26724
27967 | 420.8829 | 26724
27968 | 417.3362 | 26724
27969 | 405.8856 | 26724
27970 | 410.4074 | 26724
27971 | 411.9848 | 26724
27972 | 422.4634 | 26724
27973 | 417.5255 | 26724
27974 | 425.7028 | 26724
27975 | 411.1388 | 26724
27976 | 418.1336 | 26724
27977 | 422.2739 | 26724
27978 | 417.9701 | 26724
27979 | 420.7319 | 26724
27980 | 407.2027 | 26724
27981 | 407.0391 | 26724
27982 | 411.1713 | 26724
27983 | 410.5098 | 26724
27984 | 397.6104 | 26724
27985 | 396.8448 | 26724
27986 | 423.3809 | 26724
27987 | 404.6208 | 26724
27988 | 413.3952 | 26724
27989 | 407.8039 | 26724
27990 | 404.7923 | 26724
27991 | 413.3071 | 26724
27992 | 417.8167 | 26724
27993 | 414.6188 | 26724
27994 | 407.4208 | 26724
27995 | 410.832 | 26724
27996 | 408.3545 | 26724
27997 | 424.9475 | 26724
27998 | 415.2493 | 26724
27999 | 429.7467 | 26724
28000 | 417.4298 | 26724
28001 | 420.8188 | 26724
28002 | 424.3562 | 26724
28003 | 405.1722 | 26724
28004 | 410.7243 | 26724
28005 | 415.8412 | 26724
28006 | 420.6898 | 26724
28007 | 402.1921 | 26724
28008 | 407.2498 | 26724
28009 | 415.6022 | 26724
28010 | 407.0571 | 26724
28011 | 405.2993 | 26724
28012 | 417.8107 | 26724
28013 | 428.56 | 26724
28014 | 406.3093 | 26724
28015 | 429.6525 | 26724
28016 | 417.3519 | 26724
28017 | 418.1783 | 26724
28018 | 411.9781 | 26724
28019 | 432.1619 | 26724
28020 | 423.5544 | 26724
28021 | 401.7927 | 26724
28022 | 416.8711 | 26724
28023 | 407.8798 | 26724
28024 | 414.3124 | 26724
28025 | 410.5782 | 26724
28026 | 417.486 | 26724
28027 | 412.9297 | 26724
28028 | 414.5245 | 26724
28029 | 419.3005 | 26724
28030 | 417.7752 | 26724
28031 | 410.5515 | 26724
28032 | 418.015 | 26724
28033 | 427.592 | 26724
28034 | 407.8488 | 26724
28035 | 432.9586 | 26724
28036 | 410.6303 | 26724
28037 | 434.0279 | 26724
28038 | 413.5196 | 26724
28039 | 415.0255 | 26724
28040 | 411.8117 | 26724
28041 | 418.4163 | 26724
28042 | 406.6388 | 26724
28043 | 421.8002 | 26724
28044 | 413.1684 | 26724
28045 | 417.0918 | 26724
28046 | 413.766 | 26724
28047 | 429.3342 | 26724
28048 | 412.7571 | 26724
28049 | 429.8906 | 26724
28050 | 426.9496 | 26724
28051 | 425.2532 | 26724
28052 | 404.828 | 26724
28053 | 419.6137 | 26724
28054 | 433.3345 | 26724
28055 | 417.4443 | 26724
28056 | 417.5231 | 26724
28057 | 406.8213 | 26724
28058 | 409.9057 | 26724
28059 | 413.9812 | 26724
28060 | 413.8332 | 26724
28061 | 421.4871 | 26724
28062 | 405.5608 | 26724
28063 | 406.605 | 26724
28064 | 418.3147 | 26724
28065 | 402.7188 | 26724
28066 | 421.0852 | 26724
28067 | 412.3772 | 26724
28068 | 414.6109 | 26724
28069 | 417.1592 | 26724
28070 | 422.9088 | 26724
28071 | 403.4003 | 26724
28072 | 423.6451 | 26724
28073 | 417.4196 | 26724
28074 | 414.2827 | 26724
28075 | 417.8919 | 26724
28076 | 423.319 | 26724
28077 | 417.8077 | 26724
28078 | 405.4321 | 26724
28079 | 411.9701 | 26724
28080 | 413.1309 | 26724
28081 | 415.95 | 26724
28082 | 422.8806 | 26724
28083 | 409.2449 | 26724
28084 | 432.9375 | 26724
28085 | 403.8103 | 26724
28086 | 404.7863 | 26724
28087 | 419.6983 | 26724
28088 | 409.0652 | 26724
28089 | 425.7261 | 26724
28090 | 413.8531 | 26724
28091 | 399.8623 | 26724
28092 | 411.4087 | 26724
28093 | 418.2678 | 26724
28094 | 409.2299 | 26724
28095 | 408.8229 | 26724
28096 | 415.2255 | 26724
28097 | 406.5649 | 26724
28098 | 425.8429 | 26724
28099 | 417.4658 | 26724
28100 | 405.6249 | 26724
28101 | 416.4896 | 26724
28102 | 403.7248 | 26724
28103 | 409.1016 | 26724
28104 | 412.2784 | 26724
28105 | 415.3287 | 26724
28106 | 414.6326 | 26724
28107 | 425.0964 | 26724
28108 | 419.4738 | 26724
28109 | 423.1139 | 26724
28110 | 412.2836 | 26724
28111 | 412.6761 | 26724
28112 | 414.7085 | 26724
28113 | 427.9657 | 26724
28114 | 404.1063 | 26724
28115 | 430.9959 | 26724
28116 | 424.2818 | 26724
28117 | 414.5817 | 26724
28118 | 409.3621 | 26724
28119 | 401.8102 | 26724
28120 | 400.4333 | 26724
28121 | 426.1021 | 26724
28122 | 402.7063 | 26724
28123 | 419.4178 | 26724
28124 | 412.6925 | 26724
28125 | 421.3598 | 26724
28126 | 417.2956 | 26724
28127 | 425.5134 | 26724
28128 | 418.5044 | 26724
28129 | 423.9451 | 26724
28130 | 419.754 | 26724
28131 | 418.9809 | 26724
28132 | 430.0342 | 26724
28133 | 405.7924 | 26724
28134 | 426.3916 | 26724
28135 | 422.8291 | 26724
28136 | 402.9772 | 26724
28137 | 430.6042 | 26724
28138 | 407.7138 | 26724
28139 | 409.0298 | 26724
28140 | 423.3754 | 26724
28141 | 427.4168 | 26724
28142 | 418.9725 | 26724
28143 | 414.2591 | 26724
28144 | 415.6484 | 26724
28145 | 430.4721 | 26724
28146 | 421.7946 | 26724
28147 | 424.906 | 26724
28148 | 426.4344 | 26724
28149 | 411.386 | 26724
28150 | 407.5064 | 26724
28151 | 415.4034 | 26724
28152 | 426.1878 | 26724
28153 | 410.8716 | 26724
28154 | 402.8336 | 26724
28155 | 414.629 | 26724
28156 | 407.6868 | 26724
28157 | 414.1621 | 26724
28158 | 423.7397 | 26724
28159 | 427.225 | 26724
28160 | 421.0269 | 26724
28161 | 409.5731 | 26724
28162 | 409.6922 | 26724
28163 | 415.285 | 26724
28164 | 422.4483 | 26724
28165 | 412.0616 | 26724
28166 | 432.4509 | 26724
28167 | 434.3097 | 26724
28168 | 408.8252 | 26724
28169 | 414.3058 | 26724
28170 | 427.6439 | 26724
28171 | 417.5308 | 26724
28172 | 418.371 | 26724
28173 | 401.438 | 26724
28174 | 420.7225 | 26724
28175 | 426.3598 | 26724
28176 | 400.9572 | 26724
28177 | 400.7328 | 26724
28178 | 424.6217 | 26724
28179 | 402.877 | 26724
28180 | 423.8249 | 26724
28181 | 411.5831 | 26724
28182 | 425.5827 | 26724
28183 | 409.2517 | 26724
28184 | 419.9902 | 26724
28185 | 407.6976 | 26724
28186 | 407.3492 | 26724
28187 | 418.1435 | 26724
28188 | 424.5816 | 26724
28189 | 421.4181 | 26724
28190 | 420.7033 | 26724
28191 | 402.4972 | 26724
28192 | 411.7371 | 26724
28193 | 412.0267 | 26724
28194 | 409.7831 | 26724
28195 | 425.1087 | 26724
28196 | 400.9539 | 26724
28197 | 409.8426 | 26724
28198 | 407.4045 | 26724
28199 | 414.487 | 26724
28200 | 418.8518 | 26724
28201 | 416.3775 | 26724
28202 | 414.2737 | 26724
28203 | 433.6117 | 26724
28204 | 414.7352 | 26724
28205 | 415.7488 | 26724
28206 | 420.0946 | 26724
28207 | 412.5183 | 26724
28208 | 410.047 | 26724
28209 | 400.2491 | 26724
28210 | 416.9715 | 26724
28211 | 413.1429 | 26724
28212 | 408.578 | 26724
28213 | 418.5682 | 26724
28214 | 422.0593 | 26724
28215 | 412.3581 | 26724
28216 | 421.6478 | 26724
28217 | 426.315 | 26724
28218 | 423.2704 | 26724
28219 | 420.7385 | 26724
28220 | 410.3845 | 26724
28221 | 408.2387 | 26724
28222 | 409.9935 | 26724
28223 | 408.469 | 26724
28224 | 418.1019 | 26724
28225 | 419.1184 | 26724
28226 | 418.773 | 26724
28227 | 428.7153 | 26724
28228 | 411.3193 | 26724
28229 | 424.6059 | 26724
28230 | 415.2814 | 26724
28231 | 416.6621 | 26724
28232 | 411.019 | 26724
28233 | 423.3092 | 26724
28234 | 429.6612 | 26724
28235 | 409.7169 | 26724
28236 | 427.6373 | 26724
28237 | 409.532 | 26724
28238 | 419.4329 | 26724
28239 | 424.9236 | 26724
28240 | 419.8177 | 26724
28241 | 402.6548 | 26724
28242 | 423.4109 | 26724
28243 | 405.0743 | 26724
28244 | 414.2087 | 26724
28245 | 408.2388 | 26724
28246 | 404.7731 | 26724
28247 | 422.8632 | 26724
28248 | 426.5795 | 26724
28249 | 429.7087 | 26724
28250 | 412.2451 | 26724
28251 | 402.5216 | 26724
28252 | 405.7039 | 26724
28253 | 414.3684 | 26724
28254 | 409.2917 | 26724
28255 | 416.9631 | 26724
28256 | 427.255 | 26724
28257 | 421.4364 | 26724
28258 | 413.5772 | 26724
28259 | 424.1976 | 26724
28260 | 421.7484 | 26724
28261 | 400.5598 | 26724
28262 | 425.1956 | 26724
28263 | 410.6915 | 26724
28264 | 407.5618 | 26724
28265 | 418.3757 | 26724
28266 | 426.4026 | 26724
28267 | 413.6717 | 26724
28268 | 419.1544 | 26724
28269 | 421.5374 | 26724
28270 | 410.5774 | 26724
28271 | 413.2681 | 26724
28272 | 407.9166 | 26724
28273 | 412.0235 | 26724
28274 | 425.2489 | 26724
28275 | 417.0236 | 26724
28276 | 420.7823 | 26724
28277 | 415.1798 | 26724
28278 | 411.6695 | 26724
28279 | 412.0791 | 26724
28280 | 423.5644 | 26724
28281 | 421.0516 | 26724
28282 | 414.2782 | 26724
28283 | 403.9941 | 26724
28284 | 416.3248 | 26724
28285 | 406.7841 | 26724
28286 | 415.9308 | 26724
28287 | 427.3425 | 26724
28288 | 406.4578 | 26724
28289 | 422.558 | 26724
28290 | 417.3145 | 26724
28291 | 409.7602 | 26724
28292 | 414.9845 | 26724
28293 | 419.4111 | 26724
28294 | 417.198 | 26724
28295 | 414.9759 | 26724
28296 | 420.7766 | 26724
28297 | 413.9688 | 26724
28298 | 433.2464 | 26724
28299 | 425.5694 | 26724
28300 | 417.3012 | 26724
28301 | 417.3688 | 26724
28302 | 423.6884 | 26724
28303 | 410.9846 | 26724
28304 | 420.2593 | 26724
28305 | 424.6141 | 26724
28306 | 418.2089 | 26724
28307 | 426.099 | 26724
28308 | 420.5849 | 26724
28309 | 426.7464 | 26724
28310 | 408.8896 | 26724
28311 | 424.1508 | 26724
28312 | 430.7719 | 26724
28313 | 423.7977 | 26724
28314 | 407.4985 | 26724
28315 | 408.451 | 26724
28316 | 418.1193 | 26724
28317 | 426.2413 | 26724
28318 | 421.8189 | 26724
28319 | 422.3639 | 26724
28320 | 425.3091 | 26724
28321 | 412.0257 | 26724
28322 | 410.1061 | 26724
28323 | 423.0404 | 26724
28324 | 407.022 | 26724
28325 | 421.312 | 26724
28326 | 417.0408 | 26724
28327 | 414.0047 | 26724
28328 | 416.5727 | 26724
28329 | 423.6286 | 26724
28330 | 422.9836 | 26724
28331 | 421.2006 | 26724
28332 | 411.6632 | 26724
28333 | 410.1987 | 26724
28334 | 420.8591 | 26724
28335 | 412.312 | 26724
28336 | 425.7483 | 26724
28337 | 417.1967 | 26724
28338 | 419.3171 | 26724
28339 | 410.3073 | 26724
28340 | 424.4227 | 26724
28341 | 428.4182 | 26724
28342 | 416.5305 | 26724
28343 | 432.1189 | 26724
28344 | 433.8276 | 26724
28345 | 406.1604 | 26724
28346 | 417.6793 | 26724
28347 | 419.3165 | 26724
28348 | 399.9414 | 26724
28349 | 401.9794 | 26724
28350 | 416.8137 | 26724
28351 | 402.892 | 26724
28352 | 402.6197 | 26724
28353 | 402.1896 | 26724
28354 | 407.8301 | 26724
28355 | 425.7499 | 26724
28356 | 422.8498 | 26724
28357 | 416.565 | 26724
28358 | 431.0679 | 26724
28359 | 421.6599 | 26724
28360 | 425.4073 | 26724
28361 | 422.5275 | 26724
28362 | 423.9314 | 26724
28363 | 421.3747 | 26724
28364 | 407.4137 | 26724
28365 | 398.263 | 26724
28366 | 417.8831 | 26724
28367 | 417.5199 | 26724
28368 | 425.2163 | 26724
28369 | 419.9781 | 26724
28370 | 421.1675 | 26724
28371 | 407.0139 | 26724
28372 | 418.5794 | 26724
28373 | 424.3102 | 26724
28374 | 411.4969 | 26724
28375 | 405.084 | 26724
28376 | 400.1285 | 26724
28377 | 422.4962 | 26724
28378 | 434.6774 | 26724
28379 | 410.5063 | 26724
28380 | 425.0319 | 26724
28381 | 406.1379 | 26724
28382 | 420.5441 | 26724
28383 | 415.5202 | 26724
28384 | 425.1845 | 26724
28385 | 427.4436 | 26724
28386 | 415.3398 | 26724
28387 | 424.3475 | 26724
28388 | 427.8031 | 26724
28389 | 419.0749 | 26724
28390 | 427.9676 | 26724
28391 | 418.9653 | 26724
28392 | 428.4626 | 26724
28393 | 417.8094 | 26724
28394 | 407.338 | 26724
28395 | 425.1411 | 26724
28396 | 422.71 | 26724
28397 | 419.4535 | 26724
28398 | 407.0079 | 26724
28399 | 408.8167 | 26724
28400 | 415.1607 | 26724
28401 | 421.9823 | 26724
28402 | 406.2946 | 26724
28403 | 415.8918 | 26724
28404 | 420.0593 | 26724
28405 | 427.3885 | 26724
28406 | 409.9398 | 26724
28407 | 402.8721 | 26724
28408 | 419.3286 | 26724
28409 | 408.068 | 26724
28410 | 417.8301 | 26724
28411 | 415.5596 | 26724
28412 | 430.9938 | 26724
28413 | 406.9564 | 26724
28414 | 427.1697 | 26724
28415 | 415.9582 | 26724
28416 | 413.0868 | 26724
28417 | 411.4311 | 26724
28418 | 411.2167 | 26724
28419 | 418.3055 | 26724
28420 | 415.5258 | 26724
28421 | 409.0511 | 26724
28422 | 404.3681 | 26724
28423 | 419.6839 | 26724
28424 | 397.8123 | 26724
28425 | 412.9805 | 26724
28426 | 421.5479 | 26724
28427 | 415.1071 | 26724
28428 | 424.0272 | 26724
28429 | 416.2615 | 26724
28430 | 421.7902 | 26724
28431 | 405.859 | 26724
28432 | 419.264 | 26724
28433 | 406.7399 | 26724
28434 | 414.8376 | 26724
28435 | 409.0958 | 26724
28436 | 435.9586 | 26724
28437 | 424.1979 | 26724
28438 | 423.4651 | 26724
28439 | 422.8319 | 26724
28440 | 415.1689 | 26724
28441 | 405.6892 | 26724
28442 | 429.4631 | 26724
28443 | 414.5752 | 26724
28444 | 407.3938 | 26724
28445 | 413.279 | 26724
28446 | 429.3058 | 26724
28447 | 405.8272 | 26724
28448 | 422.8336 | 26724
28449 | 419.5897 | 26724
28450 | 411.9572 | 26724
28451 | 398.5211 | 26724
28452 | 414.1857 | 26724
28453 | 407.026 | 26724
28454 | 406.0999 | 26724
28455 | 399.4704 | 26724
28456 | 426.8147 | 26724
28457 | 404.656 | 26724
28458 | 419.1943 | 26724
28459 | 421.3478 | 26724
28460 | 404.9811 | 26724
28461 | 406.8042 | 26724
28462 | 412.3676 | 26724
28463 | 402.7301 | 26724
28464 | 433.1065 | 26724
28465 | 421.2694 | 26724
28466 | 426.4915 | 26724
28467 | 407.8366 | 26724
28468 | 428.3522 | 26724
28469 | 425.8022 | 26724
28470 | 421.1399 | 26724
28471 | 423.2819 | 26724
28472 | 410.8231 | 26724
28473 | 420.1297 | 26724
28474 | 402.9647 | 26724
28475 | 421.0927 | 26724
28476 | 421.5395 | 26724
28477 | 423.9853 | 26724
28478 | 418.9263 | 26724
28479 | 403.6867 | 26724
28480 | 428.5991 | 26724
28481 | 408.4797 | 26724
28482 | 425.1811 | 26724
28483 | 421.7703 | 26724
28484 | 416.8366 | 26724
28485 | 422.1111 | 26724
28486 | 404.6272 | 26724
28487 | 420.4196 | 26724
28488 | 414.9372 | 26724
28489 | 418.9886 | 26724
28490 | 430.6936 | 26724
28491 | 415.859 | 26724
28492 | 406.9722 | 26724
28493 | 416.0427 | 26724
28494 | 423.0481 | 26724
28495 | 417.9542 | 26724
28496 | 406.538 | 26724
28497 | 426.1078 | 26724
28498 | 405.2789 | 26724
28499 | 397.1336 | 26724
28500 | 423.2044 | 26724
28501 | 421.0795 | 26724
28502 | 424.497 | 26724
28503 | 414.2516 | 26724
28504 | 434.9336 | 26724
28505 | 413.9115 | 26724
28506 | 406.0671 | 26724
28507 | 421.3358 | 26724
28508 | 422.4982 | 26724
28509 | 418.6171 | 26724
28510 | 416.9641 | 26724
28511 | 408.8696 | 26724
28512 | 411.9882 | 26724
28513 | 416.9521 | 26724
28514 | 414.0276 | 26724
28515 | 404.0662 | 26724
28516 | 417.4046 | 26724
28517 | 416.3482 | 26724
28518 | 427.8807 | 26724
28519 | 418.2439 | 26724
28520 | 412.5816 | 26724
28521 | 412.903 | 26724
28522 | 426.3337 | 26724
28523 | 401.6328 | 26724
28524 | 404.3355 | 26724
28525 | 420.0498 | 26724
28526 | 415.5283 | 26724
28527 | 416.6635 | 26724
28528 | 419.122 | 26724
28529 | 428.6869 | 26724
28530 | 411.1124 | 26724
28531 | 404.8357 | 26724
28532 | 422.3742 | 26724
28533 | 411.6052 | 26724
28534 | 429.7292 | 26724
28535 | 424.3693 | 26724
28536 | 405.2214 | 26724
28537 | 413.2675 | 26724
28538 | 424.4068 | 26724
28539 | 415.0975 | 26724
28540 | 424.5868 | 26724
28541 | 400.3957 | 26724
28542 | 422.6137 | 26724
28543 | 434.9691 | 26724
28544 | 411.8562 | 26724
28545 | 420.8178 | 26724
28546 | 423.542 | 26724
28547 | 412.7071 | 26724
28548 | 424.0813 | 26724
28549 | 407.6582 | 26724
28550 | 423.1629 | 26724
28551 | 415.7252 | 26724
28552 | 412.2215 | 26724
28553 | 417.0711 | 26724
28554 | 426.9014 | 26724
28555 | 426.2062 | 26724
28556 | 411.6883 | 26724
28557 | 414.1409 | 26724
28558 | 423.3122 | 26724
28559 | 407.8693 | 26724
28560 | 417.753 | 26724
28561 | 411.9455 | 26724
28562 | 413.2557 | 26724
28563 | 427.9236 | 26724
28564 | 434.6443 | 26724
28565 | 418.4132 | 26724
28566 | 417.556 | 26724
28567 | 400.8398 | 26724
28568 | 426.4615 | 26724
28569 | 421.3685 | 26724
28570 | 432.419 | 26724
28571 | 398.9276 | 26724
28572 | 419.9998 | 26724
28573 | 406.3214 | 26724
28574 | 438.995 | 26724
28575 | 422.1395 | 26724
28576 | 408.7087 | 26724
28577 | 417.8646 | 26724
28578 | 419.0301 | 26724
28579 | 409.4021 | 26724
28580 | 416.6425 | 26724
28581 | 415.2026 | 26724
28582 | 422.791 | 26724
28583 | 407.301 | 26724
28584 | 431.9701 | 26724
28585 | 418.3614 | 26724
28586 | 412.2554 | 26724
28587 | 413.165 | 26724
28588 | 421.1816 | 26724
28589 | 416.616 | 26724
28590 | 425.003 | 26724
28591 | 416.1324 | 26724
28592 | 402.6262 | 26724
28593 | 409.0668 | 26724
28594 | 417.4367 | 26724
28595 | 411.3897 | 26724
28596 | 417.6838 | 26724
28597 | 424.099 | 26724
28598 | 410.9097 | 26724
28599 | 413.2797 | 26724
28600 | 404.1688 | 26724
28601 | 417.3249 | 26724
28602 | 402.7006 | 26724
28603 | 421.1261 | 26724
28604 | 406.9716 | 26724
28605 | 416.2019 | 26724
28606 | 412.2422 | 26724
28607 | 415.5882 | 26724
28608 | 422.2419 | 26724
28609 | 405.837 | 26724
28610 | 406.4176 | 26724
28611 | 420.65 | 26724
28612 | 427.8441 | 26724
28613 | 397.6073 | 26724
28614 | 423.574 | 26724
28615 | 423.394 | 26724
28616 | 403.5709 | 26724
28617 | 412.5329 | 26724
28618 | 412.0046 | 26724
28619 | 413.3494 | 26724
28620 | 420.4431 | 26724
28621 | 416.2527 | 26724
28622 | 415.9081 | 26724
28623 | 404.7303 | 26724
28624 | 421.2437 | 26724
28625 | 403.6202 | 26724
28626 | 420.1107 | 26724
28627 | 414.8679 | 26724
28628 | 426.3627 | 26724
28629 | 418.3204 | 26724
28630 | 420.1632 | 26724
28631 | 420.2968 | 26724
28632 | 408.4355 | 26724
28633 | 411.3571 | 26724
28634 | 412.8209 | 26724
28635 | 413.0562 | 26724
28636 | 420.3946 | 26724
28637 | 422.0273 | 26724
28638 | 412.5696 | 26724
28639 | 404.33 | 26724
28640 | 423.9232 | 26724
28641 | 409.5937 | 26724
28642 | 432.523 | 26724
28643 | 420.5002 | 26724
28644 | 413.7212 | 26724
28645 | 435.1203 | 26724
28646 | 410.1688 | 26724
28647 | 403.999 | 26724
28648 | 426.6108 | 26724
28649 | 426.8431 | 26724
28650 | 432.75 | 26724
28651 | 417.8641 | 26724
28652 | 406.8227 | 26724
28653 | 431.9974 | 26724
28654 | 422.2284 | 26724
28655 | 411.3164 | 26724
28656 | 407.7618 | 26724
28657 | 416.3169 | 26724
28658 | 413.0449 | 26724
28659 | 427.0168 | 26724
28660 | 405.7036 | 26724
28661 | 420.217 | 26724
28662 | 428.6316 | 26724
28663 | 417.6285 | 26724
28664 | 417.9868 | 26724
28665 | 416.8627 | 26724
28666 | 430.6788 | 26724
28667 | 411.2533 | 26724
28668 | 414.3237 | 26724
28669 | 409.9852 | 26724
28670 | 415.6955 | 26724
28671 | 412.0634 | 26724
28672 | 409.8751 | 26724
28673 | 420.2001 | 26724
28674 | 425.2806 | 26724
28675 | 421.0848 | 26724
28676 | 425.4222 | 26724
28677 | 415.257 | 26724
28678 | 414.7054 | 26724
28679 | 435.0831 | 26724
28680 | 411.888 | 26724
28681 | 413.6925 | 26724
28682 | 413.2698 | 26724
28683 | 417.679 | 26724
28684 | 413.6976 | 26724
28685 | 409.2183 | 26724
28686 | 430.7624 | 26724
28687 | 435.0832 | 26724
28688 | 423.1493 | 26724
28689 | 406.1241 | 26724
28690 | 410.207 | 26724
28691 | 408.047 | 26724
28692 | 415.5959 | 26724
28693 | 423.017 | 26724
28694 | 401.7824 | 26724
28695 | 416.4083 | 26724
28696 | 417.4494 | 26724
28697 | 409.5276 | 26724
28698 | 424.8994 | 26724
28699 | 417.7596 | 26724
28700 | 411.9088 | 26724
28701 | 412.379 | 26724
28702 | 412.9007 | 26724
28703 | 421.7496 | 26724
28704 | 404.9647 | 26724
28705 | 433.9456 | 26724
28706 | 418.0966 | 26724
28707 | 406.3282 | 26724
28708 | 417.697 | 26724
28709 | 420.7561 | 26724
28710 | 426.7291 | 26724
28711 | 420.2261 | 26724
28712 | 420.2348 | 26724
28713 | 397.1245 | 26724
28714 | 411.8983 | 26724
28715 | 411.7912 | 26724
28716 | 418.0014 | 26724
28717 | 412.008 | 26724
28718 | 411.412 | 26724
28719 | 414.5905 | 26724
28720 | 427.4496 | 26724
28721 | 424.9218 | 26724
28722 | 424.1142 | 26724
28723 | 416.0861 | 26724
28724 | 406.1143 | 26724
28725 | 413.2772 | 26724
28726 | 421.4798 | 26724
28727 | 422.0839 | 26724
28728 | 420.3121 | 26724
28729 | 420.4647 | 26724
28730 | 406.0457 | 26724
28731 | 419.8161 | 26724
28732 | 423.5211 | 26724
28733 | 407.1879 | 26724
28734 | 412.3584 | 26724
28735 | 416.6058 | 26724
28736 | 411.3035 | 26724
28737 | 402.5479 | 26724
28738 | 425.926 | 26724
28739 | 419.89 | 26724
28740 | 413.5633 | 26724
28741 | 435.7663 | 26724
28742 | 412.6315 | 26724
28743 | 406.2189 | 26724
28744 | 417.8153 | 26724
28745 | 419.9078 | 26724
28746 | 408.4198 | 26724
28747 | 424.2764 | 26724
28748 | 431.3963 | 26724
28749 | 424.7698 | 26724
28750 | 418.9684 | 26724
28751 | 406.2458 | 26724
28752 | 423.8702 | 26724
28753 | 415.8529 | 26724
28754 | 423.0959 | 26724
28755 | 415.7581 | 26724
28756 | 421.6212 | 26724
28757 | 417.3896 | 26724
28758 | 405.6857 | 26724
28759 | 418.8101 | 26724
28760 | 412.3032 | 26724
28761 | 425.6932 | 26724
28762 | 414.2038 | 26724
28763 | 416.424 | 26724
28764 | 412.8453 | 26724
28765 | 414.695 | 26724
28766 | 436.4774 | 26724
28767 | 424.622 | 26724
28768 | 406.6074 | 26724
28769 | 424.2371 | 26724
28770 | 419.1194 | 26724
28771 | 415.2001 | 26724
28772 | 428.246 | 26724
28773 | 402.914 | 26724
28774 | 413.1643 | 26724
28775 | 410.6266 | 26724
28776 | 412.3424 | 26724
28777 | 412.2495 | 26724
28778 | 440.0033 | 26724
28779 | 417.6043 | 26724
28780 | 416.8496 | 26724
28781 | 414.8715 | 26724
28782 | 421.7798 | 26724
28783 | 424.2527 | 26724
28784 | 432.2356 | 26724
28785 | 416.3382 | 26724
28786 | 415.438 | 26724
28787 | 407.2795 | 26724
28788 | 410.8679 | 26724
28789 | 430.8802 | 26724
28790 | 411.3266 | 26724
28791 | 417.6201 | 26724
28792 | 419.8489 | 26724
28793 | 416.5988 | 26724
28794 | 422.4611 | 26724
28795 | 416.5978 | 26724
28796 | 422.8042 | 26724
28797 | 414.3048 | 26724
28798 | 422.1936 | 26724
28799 | 417.9204 | 26724
28800 | 404.4719 | 26724
28801 | 412.0804 | 26724
28802 | 398.9097 | 26724
28803 | 420.3052 | 26724
28804 | 420.0121 | 26724
28805 | 413.8713 | 26724
28806 | 412.5139 | 26724
28807 | 420.2624 | 26724
28808 | 421.4592 | 26724
28809 | 430.7443 | 26724
28810 | 416.145 | 26724
28811 | 414.1764 | 26724
28812 | 409.9047 | 26724
28813 | 426.125 | 26724
28814 | 407.3382 | 26724
28815 | 414.2647 | 26724
28816 | 414.7517 | 26724
28817 | 415.5753 | 26724
28818 | 428.6441 | 26724
28819 | 414.7602 | 26724
28820 | 422.7851 | 26724
28821 | 407.0963 | 26724
28822 | 422.9187 | 26724
28823 | 411.2583 | 26724
28824 | 405.7852 | 26724
28825 | 413.0429 | 26724
28826 | 424.2078 | 26724
28827 | 426.6242 | 26724
28828 | 422.3533 | 26724
28829 | 423.229 | 26724
28830 | 411.7007 | 26724
28831 | 414.7195 | 26724
28832 | 412.3596 | 26724
28833 | 420.3606 | 26724
28834 | 417.7046 | 26724
28835 | 414.8506 | 26724
28836 | 414.5182 | 26724
28837 | 420.8437 | 26724
28838 | 413.5112 | 26724
28839 | 413.9021 | 26724
28840 | 410.5285 | 26724
28841 | 417.8727 | 26724
28842 | 412.5307 | 26724
28843 | 402.9381 | 26724
28844 | 429.3586 | 26724
28845 | 407.7039 | 26724
28846 | 414.2955 | 26724
28847 | 424.4601 | 26724
28848 | 414.112 | 26724
28849 | 425.2065 | 26724
28850 | 414.0854 | 26724
28851 | 411.5771 | 26724
28852 | 407.0421 | 26724
28853 | 425.4478 | 26724
28854 | 417.7425 | 26724
28855 | 409.0686 | 26724
28856 | 425.7122 | 26724
28857 | 418.2062 | 26724
28858 | 402.4517 | 26724
28859 | 425.6475 | 26724
28860 | 402.4979 | 26724
28861 | 418.7089 | 26724
28862 | 424.1803 | 26724
28863 | 403.6836 | 26724
28864 | 414.5187 | 26724
28865 | 417.8029 | 26724
28866 | 413.1512 | 26724
28867 | 401.1633 | 26724
28868 | 413.861 | 26724
28869 | 416.0388 | 26724
28870 | 411.2198 | 26724
28871 | 429.3217 | 26724
28872 | 410.0884 | 26724
28873 | 409.5096 | 26724
28874 | 418.6605 | 26724
28875 | 412.8623 | 26724
28876 | 423.2938 | 26724
28877 | 421.1929 | 26724
28878 | 402.8958 | 26724
28879 | 416.8996 | 26724
28880 | 416.8619 | 26724
28881 | 422.0173 | 26724
28882 | 410.7821 | 26724
28883 | 416.9675 | 26724
28884 | 413.0136 | 26724
28885 | 405.2017 | 26724
28886 | 404.2335 | 26724
28887 | 428.3715 | 26724
28888 | 421.9501 | 26724
28889 | 399.7559 | 26724
28890 | 410.2943 | 26724
28891 | 418.5184 | 26724
28892 | 399.7763 | 26724
28893 | 430.9658 | 26724
28894 | 407.955 | 26724
28895 | 420.2136 | 26724
28896 | 429.2927 | 26724
28897 | 411.1002 | 26724
28898 | 424.2785 | 26724
28899 | 408.2381 | 26724
28900 | 411.9528 | 26724
28901 | 414.9544 | 26724
28902 | 398.8813 | 26724
28903 | 413.1987 | 26724
28904 | 410.5155 | 26724
28905 | 420.8914 | 26724
28906 | 411.9995 | 26724
28907 | 411.1731 | 26724
28908 | 432.181 | 26724
28909 | 423.7058 | 26724
28910 | 406.6746 | 26724
28911 | 415.7737 | 26724
28912 | 408.2855 | 26724
28913 | 423.6463 | 26724
28914 | 409.0541 | 26724
28915 | 423.0556 | 26724
28916 | 405.1195 | 26724
28917 | 420.2304 | 26724
28918 | 418.7648 | 26724
28919 | 407.5116 | 26724
28920 | 415.9577 | 26724
28921 | 411.6213 | 26724
28922 | 434.3121 | 26724
28923 | 407.8057 | 26724
28924 | 432.3122 | 26724
28925 | 421.4471 | 26724
28926 | 426.7763 | 26724
28927 | 411.7509 | 26724
28928 | 416.2337 | 26724
28929 | 422.7495 | 26724
28930 | 418.471 | 26724
28931 | 411.5798 | 26724
28932 | 418.9253 | 26724
28933 | 420.7389 | 26724
28934 | 419.3551 | 26724
28935 | 417.0931 | 26724
28936 | 421.2784 | 26724
28937 | 419.7612 | 26724
28938 | 426.0958 | 26724
28939 | 417.8232 | 26724
28940 | 408.0894 | 26724
28941 | 409.8205 | 26724
28942 | 426.2971 | 26724
28943 | 403.329 | 26724
28944 | 411.9015 | 26724
28945 | 418.9887 | 26724
28946 | 419.1569 | 26724
28947 | 412.1852 | 26724
28948 | 419.2667 | 26724
28949 | 432.9276 | 26724
28950 | 427.5249 | 26724
28951 | 414.7515 | 26724
28952 | 407.7634 | 26724
28953 | 422.0975 | 26724
28954 | 417.1342 | 26724
28955 | 413.4568 | 26724
28956 | 415.9048 | 26724
28957 | 406.6903 | 26724
28958 | 414.5028 | 26724
28959 | 432.1305 | 26724
28960 | 424.3423 | 26724
28961 | 413.5916 | 26724
28962 | 419.0961 | 26724
28963 | 406.045 | 26724
28964 | 418.5116 | 26724
28965 | 402.5813 | 26724
28966 | 422.3996 | 26724
28967 | 419.7798 | 26724
28968 | 417.663 | 26724
28969 | 404.275 | 26724
28970 | 425.5831 | 26724
28971 | 416.1938 | 26724
28972 | 412.3604 | 26724
28973 | 418.8633 | 26724
28974 | 401.5432 | 26724
28975 | 403.7197 | 26724
28976 | 407.9312 | 26724
28977 | 418.4429 | 26724
28978 | 421.7099 | 26724
28979 | 422.9787 | 26724
28980 | 416.1333 | 26724
28981 | 409.5194 | 26724
28982 | 408.7547 | 26724
28983 | 404.6013 | 26724
28984 | 408.8515 | 26724
28985 | 408.4096 | 26724
28986 | 423.676 | 26724
28987 | 411.7948 | 26724
28988 | 414.3652 | 26724
28989 | 423.5198 | 26724
28990 | 409.9506 | 26724
28991 | 424.3952 | 26724
28992 | 429.0247 | 26724
28993 | 415.6429 | 26724
28994 | 413.2502 | 26724
28995 | 410.7953 | 26724
28996 | 416.2613 | 26724
28997 | 411.7516 | 26724
28998 | 421.4014 | 26724
28999 | 409.1231 | 26724
29000 | 424.5388 | 26724
29001 | 412.587 | 26724
29002 | 431.0217 | 26724
29003 | 426.9521 | 26724
29004 | 408.3789 | 26724
29005 | 409.0267 | 26724
29006 | 426.2617 | 26724
29007 | 414.3196 | 26724
29008 | 420.9777 | 26724
29009 | 418.0502 | 26724
29010 | 408.9118 | 26724
29011 | 417.2421 | 26724
29012 | 415.3426 | 26724
29013 | 407.9065 | 26724
29014 | 421.9349 | 26724
29015 | 423.7232 | 26724
29016 | 419.7291 | 26724
29017 | 417.2434 | 26724
29018 | 432.8615 | 26724
29019 | 403.7839 | 26724
29020 | 406.1062 | 26724
29021 | 415.5709 | 26724
29022 | 404.8859 | 26724
29023 | 420.3323 | 26724
29024 | 408.2059 | 26724
29025 | 419.8414 | 26724
29026 | 414.1544 | 26724
29027 | 411.2219 | 26724
29028 | 403.1785 | 26724
29029 | 401.7198 | 26724
29030 | 415.9716 | 26724
29031 | 405.2243 | 26724
29032 | 417.8884 | 26724
29033 | 434.7862 | 26724
29034 | 418.2599 | 26724
29035 | 425.2791 | 26724
29036 | 421.1978 | 26724
29037 | 433.3201 | 26724
29038 | 411.798 | 26724
29039 | 418.4168 | 26724
29040 | 408.1203 | 26724
29041 | 406.8087 | 26724
29042 | 424.4012 | 26724
29043 | 414.9041 | 26724
29044 | 401.8872 | 26724
29045 | 414.1769 | 26724
29046 | 420.0456 | 26724
29047 | 402.4393 | 26724
29048 | 401.3526 | 26724
29049 | 409.632 | 26724
29050 | 409.283 | 26724
29051 | 403.4704 | 26724
29052 | 426.7279 | 26724
29053 | 434.9072 | 26724
29054 | 418.4864 | 26724
29055 | 407.8058 | 26724
29056 | 412.0462 | 26724
29057 | 418.1226 | 26724
29058 | 410.9585 | 26724
29059 | 411.123 | 26724
29060 | 424.625 | 26724
29061 | 424.8533 | 26724
29062 | 419.28 | 26724
29063 | 431.118 | 26724
29064 | 412.3733 | 26724
29065 | 423.2678 | 26724
29066 | 417.0418 | 26724
29067 | 424.1166 | 26724
29068 | 409.3409 | 26724
29069 | 407.3154 | 26724
29070 | 418.3628 | 26724
29071 | 396.7731 | 26724
29072 | 427.3763 | 26724
29073 | 410.1733 | 26724
29074 | 399.8859 | 26724
29075 | 415.053 | 26724
29076 | 416.0004 | 26724
29077 | 416.9075 | 26724
29078 | 413.1866 | 26724
29079 | 412.3701 | 26724
29080 | 418.1407 | 26724
29081 | 423.2768 | 26724
29082 | 413.1326 | 26724
29083 | 416.9663 | 26724
29084 | 414.322 | 26724
29085 | 407.3272 | 26724
29086 | 420.3253 | 26724
29087 | 412.6333 | 26724
29088 | 418.4666 | 26724
29089 | 411.5621 | 26724
29090 | 411.4367 | 26724
29091 | 417.7565 | 26724
29092 | 416.4416 | 26724
29093 | 404.8401 | 26724
29094 | 415.1742 | 26724
29095 | 423.0214 | 26724
29096 | 401.2592 | 26724
29097 | 405.0963 | 26724
29098 | 420.7296 | 26724
29099 | 427.8081 | 26724
29100 | 429.4171 | 26724
29101 | 419.0582 | 26724
29102 | 421.3099 | 26724
29103 | 407.2853 | 26724
29104 | 420.2788 | 26724
29105 | 422.3678 | 26724
29106 | 416.3256 | 26724
29107 | 432.8524 | 26724
29108 | 406.3587 | 26724
29109 | 418.3743 | 26724
29110 | 417.1028 | 26724
29111 | 422.5079 | 26724
29112 | 406.2023 | 26724
29113 | 422.1958 | 26724
29114 | 401.2479 | 26724
29115 | 423.752 | 26724
29116 | 423.7319 | 26724
29117 | 394.927 | 26724
29118 | 409.8058 | 26724
29119 | 417.4962 | 26724
29120 | 416.065 | 26724
29121 | 403.5653 | 26724
29122 | 414.4366 | 26724
29123 | 407.6665 | 26724
29124 | 426.1309 | 26724
29125 | 415.1494 | 26724
29126 | 410.9647 | 26724
29127 | 416.1594 | 26724
29128 | 400.2762 | 26724
29129 | 421.6092 | 26724
29130 | 405.3522 | 26724
29131 | 397.7858 | 26724
29132 | 418.9721 | 26724
29133 | 406.1159 | 26724
29134 | 406.4729 | 26724
29135 | 419.7783 | 26724
29136 | 407.4866 | 26724
29137 | 416.3333 | 26724
29138 | 429.8368 | 26724
29139 | 422.1645 | 26724
29140 | 424.4989 | 26724
29141 | 409.9316 | 26724
29142 | 425.3756 | 26724
29143 | 422.668 | 26724
29144 | 422.7276 | 26724
29145 | 425.9235 | 26724
29146 | 407.1554 | 26724
29147 | 416.9127 | 26724
29148 | 420.9577 | 26724
29149 | 416.3332 | 26724
29150 | 410.2211 | 26724
29151 | 401.1853 | 26724
29152 | 423.3075 | 26724
29153 | 397.2375 | 26724
29154 | 409.7514 | 26724
29155 | 411.6076 | 26724
29156 | 417.4937 | 26724
29157 | 409.0513 | 26724
29158 | 409.0624 | 26724
29159 | 428.6173 | 26724
29160 | 401.6054 | 26724
29161 | 422.5743 | 26724
29162 | 414.7762 | 26724
29163 | 410.0389 | 26724
29164 | 410.3957 | 26724
29165 | 410.7162 | 26724
29166 | 415.9713 | 26724
29167 | 411.5606 | 26724
29168 | 422.6336 | 26724
29169 | 413.1908 | 26724
29170 | 414.0619 | 26724
29171 | 419.5714 | 26724
29172 | 409.3305 | 26724
29173 | 400.8046 | 26724
29174 | 402.3645 | 26724
29175 | 404.3127 | 26724
29176 | 407.7094 | 26724
29177 | 432.0185 | 26724
29178 | 420.8163 | 26724
29179 | 425.0465 | 26724
29180 | 401.2759 | 26724
29181 | 395.6171 | 26724
29182 | 411.0339 | 26724
29183 | 407.6582 | 26724
29184 | 415.8767 | 26724
29185 | 407.9319 | 26724
29186 | 414.9137 | 26724
29187 | 416.8008 | 26724
29188 | 417.5178 | 26724
29189 | 424.1262 | 26724
29190 | 410.3723 | 26724
29191 | 407.2809 | 26724
29192 | 409.0965 | 26724
29193 | 417.0671 | 26724
29194 | 415.4135 | 26724
29195 | 424.2463 | 26724
29196 | 410.9058 | 26724
29197 | 407.9438 | 26724
29198 | 421.9556 | 26724
29199 | 410.8416 | 26724
29200 | 418.9394 | 26724
29201 | 423.7545 | 26724
29202 | 419.8304 | 26724
29203 | 410.7609 | 26724
29204 | 426.7247 | 26724
29205 | 423.8579 | 26724
29206 | 412.933 | 26724
29207 | 421.1336 | 26724
29208 | 404.9721 | 26724
29209 | 407.9458 | 26724
29210 | 424.4112 | 26724
29211 | 409.312 | 26724
29212 | 403.2209 | 26724
29213 | 424.5951 | 26724
29214 | 409.9347 | 26724
29215 | 421.2529 | 26724
29216 | 406.8073 | 26724
29217 | 409.3269 | 26724
29218 | 431.2801 | 26724
29219 | 416.9576 | 26724
29220 | 431.9358 | 26724
29221 | 422.6359 | 26724
29222 | 435.4128 | 26724
29223 | 419.7679 | 26724
29224 | 420.3503 | 26724
29225 | 401.5407 | 26724
29226 | 431.0607 | 26724
29227 | 422.3683 | 26724
29228 | 418.9724 | 26724
29229 | 405.601 | 26724
29230 | 418.3405 | 26724
29231 | 409.5316 | 26724
29232 | 422.2145 | 26724
29233 | 419.2922 | 26724
29234 | 424.2333 | 26724
29235 | 430.2333 | 26724
29236 | 414.5805 | 26724
29237 | 409.6832 | 26724
29238 | 417.3613 | 26724
29239 | 422.4123 | 26724
29240 | 416.1643 | 26724
29241 | 417.2496 | 26724
29242 | 421.7183 | 26724
29243 | 413.7975 | 26724
29244 | 411.7745 | 26724
29245 | 412.4855 | 26724
29246 | 422.7409 | 26724
29247 | 428.8502 | 26724
29248 | 394.488 | 26724
29249 | 417.117 | 26724
29250 | 419.664 | 26724
29251 | 413.9305 | 26724
29252 | 410.5247 | 26724
29253 | 417.533 | 26724
29254 | 411.0931 | 26724
29255 | 401.5683 | 26724
29256 | 434.6195 | 26724
29257 | 407.3969 | 26724
29258 | 428.0628 | 26724
29259 | 417.479 | 26724
29260 | 410.0803 | 26724
29261 | 431.3918 | 26724
29262 | 410.4702 | 26724
29263 | 424.7722 | 26724
29264 | 420.2647 | 26724
29265 | 413.7115 | 26724
29266 | 416.7415 | 26724
29267 | 404.5703 | 26724
29268 | 409.0194 | 26724
29269 | 427.1212 | 26724
29270 | 399.5686 | 26724
29271 | 405.2289 | 26724
29272 | 417.5997 | 26724
29273 | 416.0701 | 26724
29274 | 416.3785 | 26724
29275 | 412.3464 | 26724
29276 | 397.4892 | 26724
29277 | 417.7892 | 26724
29278 | 414.7495 | 26724
29279 | 425.656 | 26724
29280 | 425.3517 | 26724
29281 | 418.8882 | 26724
29282 | 392.5091 | 26724
29283 | 415.4523 | 26724
29284 | 414.8553 | 26724
29285 | 406.4508 | 26724
29286 | 420.2948 | 26724
29287 | 415.3883 | 26724
29288 | 409.7547 | 26724
29289 | 430.5237 | 26724
29290 | 407.6682 | 26724
29291 | 412.4101 | 26724
29292 | 417.8803 | 26724
29293 | 422.0676 | 26724
29294 | 407.0143 | 26724
29295 | 400.895 | 26724
29296 | 411.82 | 26724
29297 | 420.0768 | 26724
29298 | 415.176 | 26724
29299 | 420.5084 | 26724
29300 | 421.873 | 26724
29301 | 421.0781 | 26724
29302 | 415.9474 | 26724
29303 | 429.9641 | 26724
29304 | 422.9334 | 26724
29305 | 422.7952 | 26724
29306 | 431.0871 | 26724
29307 | 407.9204 | 26724
29308 | 419.1325 | 26724
29309 | 420.2084 | 26724
29310 | 417.1341 | 26724
29311 | 419.6337 | 26724
29312 | 408.1453 | 26724
29313 | 421.8374 | 26724
29314 | 409.2865 | 26724
29315 | 425.8008 | 26724
29316 | 416.8325 | 26724
29317 | 404.4194 | 26724
29318 | 401.7607 | 26724
29319 | 419.3071 | 26724
29320 | 423.2358 | 26724
29321 | 414.5717 | 26724
29322 | 410.0557 | 26724
29323 | 412.1047 | 26724
29324 | 418.3758 | 26724
29325 | 421.1196 | 26724
29326 | 424.4649 | 26724
29327 | 416.514 | 26724
29328 | 413.8278 | 26724
29329 | 405.8138 | 26724
29330 | 429.6859 | 26724
29331 | 417.257 | 26724
29332 | 413.4214 | 26724
29333 | 421.7095 | 26724
29334 | 409.1239 | 26724
29335 | 432.6002 | 26724
29336 | 422.7902 | 26724
29337 | 416.8594 | 26724
29338 | 421.8582 | 26724
29339 | 423.4582 | 26724
29340 | 414.3142 | 26724
29341 | 402.7287 | 26724
29342 | 426.7308 | 26724
29343 | 412.916 | 26724
29344 | 435.5713 | 26724
29345 | 432.6817 | 26724
29346 | 409.1655 | 26724
29347 | 420.4313 | 26724
29348 | 422.6228 | 26724
29349 | 412.1048 | 26724
29350 | 409.0442 | 26724
29351 | 408.0598 | 26724
29352 | 414.8251 | 26724
29353 | 420.6764 | 26724
29354 | 411.5214 | 26724
29355 | 416.6647 | 26724
29356 | 424.4569 | 26724
29357 | 430.047 | 26724
29358 | 417.8449 | 26724
29359 | 415.9025 | 26724
29360 | 426.604 | 26724
29361 | 435.1625 | 26724
29362 | 407.417 | 26724
29363 | 421.504 | 26724
29364 | 407.676 | 26724
29365 | 422.6604 | 26724
29366 | 401.5879 | 26724
29367 | 429.6619 | 26724
29368 | 409.9351 | 26724
29369 | 414.2437 | 26724
29370 | 404.8161 | 26724
29371 | 422.1896 | 26724
29372 | 420.8227 | 26724
29373 | 416.5314 | 26724
29374 | 403.9468 | 26724
29375 | 415.3009 | 26724
29376 | 411.6926 | 26724
29377 | 419.7517 | 26724
29378 | 429.393 | 26724
29379 | 412.1863 | 26724
29380 | 429.7653 | 26724
29381 | 420.1525 | 26724
29382 | 416.7662 | 26724
29383 | 417.7614 | 26724
29384 | 418.5537 | 26724
29385 | 391.9316 | 26724
29386 | 417.4563 | 26724
29387 | 405.0737 | 26724
29388 | 405.1075 | 26724
29389 | 411.0018 | 26724
29390 | 420.14 | 26724
29391 | 404.873 | 26724
29392 | 412.7457 | 26724
29393 | 411.7039 | 26724
29394 | 428.5103 | 26724
29395 | 408.3276 | 26724
29396 | 425.7634 | 26724
29397 | 409.6613 | 26724
29398 | 417.1815 | 26724
29399 | 421.9963 | 26724
29400 | 413.6351 | 26724
29401 | 416.6934 | 26724
29402 | 418.6571 | 26724
29403 | 405.2893 | 26724
29404 | 424.0761 | 26724
29405 | 413.5073 | 26724
29406 | 408.7973 | 26724
29407 | 428.7294 | 26724
29408 | 417.6458 | 26724
29409 | 429.2612 | 26724
29410 | 430.1694 | 26724
29411 | 425.5262 | 26724
29412 | 415.2492 | 26724
29413 | 403.6322 | 26724
29414 | 407.7224 | 26724
29415 | 418.4488 | 26724
29416 | 420.3626 | 26724
29417 | 414.4758 | 26724
29418 | 420.3834 | 26724
29419 | 428.8785 | 26724
29420 | 414.6452 | 26724
29421 | 415.3772 | 26724
29422 | 419.2793 | 26724
29423 | 415.5773 | 26724
29424 | 426.7863 | 26724
29425 | 412.4019 | 26724
29426 | 419.3013 | 26724
29427 | 414.7903 | 26724
29428 | 426.2355 | 26724
29429 | 400.7554 | 26724
29430 | 418.8168 | 26724
29431 | 417.4173 | 26724
29432 | 417.4557 | 26724
29433 | 413.3989 | 26724
29434 | 425.7694 | 26724
29435 | 417.5646 | 26724
29436 | 416.8495 | 26724
29437 | 425.3377 | 26724
29438 | 425.53 | 26724
29439 | 412.7813 | 26724
29440 | 420.5641 | 26724
29441 | 415.8313 | 26724
29442 | 414.9289 | 26724
29443 | 408.1978 | 26724
29444 | 421.425 | 26724
29445 | 426.8429 | 26724
29446 | 421.0355 | 26724
29447 | 405.4135 | 26724
29448 | 412.5949 | 26724
29449 | 426.2622 | 26724
29450 | 427.4712 | 26724
29451 | 408.5017 | 26724
29452 | 405.6889 | 26724
29453 | 410.8917 | 26724
29454 | 419.352 | 26724
29455 | 421.8721 | 26724
29456 | 403.3654 | 26724
29457 | 426.8494 | 26724
29458 | 418.618 | 26724
29459 | 421.578 | 26724
29460 | 421.7535 | 26724
29461 | 415.5115 | 26724
29462 | 419.1194 | 26724
29463 | 417.9886 | 26724
29464 | 415.0642 | 26724
29465 | 418.6853 | 26724
29466 | 424.2595 | 26724
29467 | 404.5327 | 26724
29468 | 411.7021 | 26724
29469 | 415.5728 | 26724
29470 | 414.1476 | 26724
29471 | 409.2203 | 26724
29472 | 415.4892 | 26724
29473 | 422.6654 | 26724
29474 | 398.3523 | 26724
29475 | 406.8519 | 26724
29476 | 412.8411 | 26724
29477 | 418.5474 | 26724
29478 | 419.2348 | 26724
29479 | 426.6428 | 26724
29480 | 413.1592 | 26724
29481 | 426.2982 | 26724
29482 | 430.6969 | 26724
29483 | 418.0524 | 26724
29484 | 416.6341 | 26724
29485 | 425.2487 | 26724
29486 | 422.0642 | 26724
29487 | 416.192 | 26724
29488 | 420.4261 | 26724
29489 | 424.7305 | 26724
29490 | 412.7011 | 26724
29491 | 416.6523 | 26724
29492 | 438.1829 | 26724
29493 | 400.8829 | 26724
29494 | 418.1283 | 26724
29495 | 429.3432 | 26724
29496 | 429.3069 | 26724
29497 | 428.7056 | 26724
29498 | 426.0044 | 26724
29499 | 420.361 | 26724
29500 | 426.7339 | 26724
29501 | 405.4128 | 26724
29502 | 409.2501 | 26724
29503 | 403.8699 | 26724
29504 | 420.1148 | 26724
29505 | 423.3268 | 26724
29506 | 406.8668 | 26724
29507 | 407.7204 | 26724
29508 | 416.9059 | 26724
29509 | 420.7887 | 26724
29510 | 431.9528 | 26724
29511 | 418.7776 | 26724
29512 | 407.9081 | 26724
29513 | 411.0235 | 26724
29514 | 433.1567 | 26724
29515 | 405.8975 | 26724
29516 | 414.956 | 26724
29517 | 415.8069 | 26724
29518 | 419.4963 | 26724
29519 | 413.4935 | 26724
29520 | 424.1535 | 26724
29521 | 414.3772 | 26724
29522 | 418.9707 | 26724
29523 | 403.5312 | 26724
29524 | 419.7107 | 26724
29525 | 421.671 | 26724
29526 | 417.5856 | 26724
29527 | 416.0534 | 26724
29528 | 413.3136 | 26724
29529 | 402.5802 | 26724
29530 | 425.2462 | 26724
29531 | 423.0042 | 26724
29532 | 413.4418 | 26724
29533 | 425.212 | 26724
29534 | 408.435 | 26724
29535 | 428.384 | 26724
29536 | 418.0587 | 26724
29537 | 410.219 | 26724
29538 | 412.9205 | 26724
29539 | 417.487 | 26724
29540 | 420.0232 | 26724
29541 | 412.7458 | 26724
29542 | 403.5832 | 26724
29543 | 420.3373 | 26724
29544 | 409.7765 | 26724
29545 | 419.8662 | 26724
29546 | 413.0847 | 26724
29547 | 433.4314 | 26724
29548 | 418.0966 | 26724
29549 | 415.3901 | 26724
29550 | 422.9089 | 26724
29551 | 425.5504 | 26724
29552 | 407.3452 | 26724
29553 | 407.9684 | 26724
29554 | 416.7042 | 26724
29555 | 416.7203 | 26724
29556 | 419.4032 | 26724
29557 | 404.0428 | 26724
29558 | 412.4045 | 26724
29559 | 417.7096 | 26724
29560 | 405.9566 | 26724
29561 | 405.8364 | 26724
29562 | 414.7758 | 26724
29563 | 404.9559 | 26724
29564 | 408.8542 | 26724
29565 | 426.7037 | 26724
29566 | 420.7648 | 26724
29567 | 405.8648 | 26724
29568 | 417.7302 | 26724
29569 | 421.2327 | 26724
29570 | 405.9077 | 26724
29571 | 410.8791 | 26724
29572 | 408.6277 | 26724
29573 | 419.8603 | 26724
29574 | 415.6677 | 26724
29575 | 405.3494 | 26724
29576 | 413.4381 | 26724
29577 | 408.0775 | 26724
29578 | 413.5548 | 26724
29579 | 400.8109 | 26724
29580 | 427.4672 | 26724
29581 | 417.3523 | 26724
29582 | 405.9842 | 26724
29583 | 422.4521 | 26724
29584 | 409.9411 | 26724
29585 | 427.0105 | 26724
29586 | 426.5187 | 26724
29587 | 414.4117 | 26724
29588 | 411.3932 | 26724
29589 | 429.3484 | 26724
29590 | 435.6179 | 26724
29591 | 414.5268 | 26724
29592 | 408.8715 | 26724
29593 | 417.4573 | 26724
29594 | 425.0207 | 26724
29595 | 418.9174 | 26724
29596 | 418.9616 | 26724
29597 | 421.4609 | 26724
29598 | 413.4561 | 26724
29599 | 416.6918 | 26724
29600 | 432.649 | 26724
29601 | 414.9079 | 26724
29602 | 424.8237 | 26724
29603 | 413.5699 | 26724
29604 | 422.8075 | 26724
29605 | 415.2248 | 26724
29606 | 414.2732 | 26724
29607 | 410.7302 | 26724
29608 | 417.4364 | 26724
29609 | 415.4501 | 26724
29610 | 412.8069 | 26724
29611 | 413.3382 | 26724
29612 | 417.0322 | 26724
29613 | 420.7831 | 26724
29614 | 421.4029 | 26724
29615 | 412.2431 | 26724
29616 | 415.3913 | 26724
29617 | 410.5324 | 26724
29618 | 416.8072 | 26724
29619 | 415.0131 | 26724
29620 | 413.6183 | 26724
29621 | 423.9795 | 26724
29622 | 425.6203 | 26724
29623 | 408.1016 | 26724
29624 | 416.6449 | 26724
29625 | 410.8328 | 26724
29626 | 405.833 | 26724
29627 | 405.6748 | 26724
29628 | 414.035 | 26724
29629 | 417.807 | 26724
29630 | 418.5594 | 26724
29631 | 407.8188 | 26724
29632 | 421.4708 | 26724
29633 | 404.5297 | 26724
29634 | 409.8222 | 26724
29635 | 426.9931 | 26724
29636 | 424.4974 | 26724
29637 | 407.9843 | 26724
29638 | 404.1811 | 26724
29639 | 410.3655 | 26724
29640 | 407.3311 | 26724
29641 | 399.8935 | 26724
29642 | 421.3305 | 26724
29643 | 397.2536 | 26724
29644 | 405.0157 | 26724
29645 | 422.7238 | 26724
29646 | 429.0773 | 26724
29647 | 426.0759 | 26724
29648 | 422.7447 | 26724
29649 | 408.9861 | 26724
29650 | 408.4883 | 26724
29651 | 432.1527 | 26724
29652 | 432.2227 | 26724
29653 | 404.4209 | 26724
29654 | 406.9511 | 26724
29655 | 413.3797 | 26724
29656 | 418.6411 | 26724
29657 | 423.9127 | 26724
29658 | 409.7326 | 26724
29659 | 420.8892 | 26724
29660 | 410.7016 | 26724
29661 | 418.2305 | 26724
29662 | 422.7216 | 26724
29663 | 409.86 | 26724
29664 | 412.6954 | 26724
29665 | 419.6238 | 26724
29666 | 413.1753 | 26724
29667 | 412.7227 | 26724
29668 | 410.9889 | 26724
29669 | 408.546 | 26724
29670 | 426.2273 | 26724
29671 | 414.4401 | 26724
29672 | 409.4851 | 26724
29673 | 405.4902 | 26724
29674 | 418.0274 | 26724
29675 | 418.3951 | 26724
29676 | 407.4743 | 26724
29677 | 412.3944 | 26724
29678 | 425.4259 | 26724
29679 | 412.5218 | 26724
29680 | 429.8199 | 26724
29681 | 412.0292 | 26724
29682 | 412.7739 | 26724
29683 | 416.2938 | 26724
29684 | 421.2856 | 26724
29685 | 429.4222 | 26724
29686 | 420.8166 | 26724
29687 | 422.2698 | 26724
29688 | 411.4352 | 26724
29689 | 406.6025 | 26724
29690 | 420.2396 | 26724
29691 | 412.7135 | 26724
29692 | 414.5696 | 26724
29693 | 421.5208 | 26724
29694 | 420.5479 | 26724
29695 | 418.0887 | 26724
29696 | 422.8165 | 26724
29697 | 423.1754 | 26724
29698 | 425.8496 | 26724
29699 | 428.6338 | 26724
29700 | 420.0896 | 26724
29701 | 418.1582 | 26724
29702 | 413.8274 | 26724
29703 | 398.9797 | 26724
29704 | 418.0059 | 26724
29705 | 424.8496 | 26724
29706 | 426.4953 | 26724
29707 | 434.764 | 26724
29708 | 417.0301 | 26724
29709 | 405.4256 | 26724
29710 | 416.9259 | 26724
29711 | 422.5129 | 26724
29712 | 406.2152 | 26724
29713 | 433.8446 | 26724
29714 | 408.9984 | 26724
29715 | 413.4798 | 26724
29716 | 427.8236 | 26724
29717 | 406.0477 | 26724
29718 | 400.363 | 26724
29719 | 400.3961 | 26724
29720 | 421.1497 | 26724
29721 | 424.4839 | 26724
29722 | 419.0303 | 26724
29723 | 422.7077 | 26724
29724 | 427.5258 | 26724
29725 | 426.6399 | 26724
29726 | 421.7016 | 26724
29727 | 422.5851 | 26724
29728 | 411.2697 | 26724
29729 | 415.5037 | 26724
29730 | 421.694 | 26724
29731 | 416.9258 | 26724
29732 | 430.4047 | 26724
29733 | 408.1656 | 26724
29734 | 403.4462 | 26724
29735 | 418.2712 | 26724
29736 | 431.8101 | 26724
29737 | 426.8541 | 26724
29738 | 405.5 | 26724
29739 | 417.7633 | 26724
29740 | 412.6831 | 26724
29741 | 418.2624 | 26724
29742 | 414.4839 | 26724
29743 | 418.885 | 26724
29744 | 405.8998 | 26724
29745 | 424.0579 | 26724
29746 | 407.8787 | 26724
29747 | 414.9961 | 26724
29748 | 414.4285 | 26724
29749 | 411.5646 | 26724
29750 | 408.3567 | 26724
29751 | 404.8248 | 26724
29752 | 410.0003 | 26724
29753 | 428.4512 | 26724
29754 | 423.9372 | 26724
29755 | 419.3807 | 26724
29756 | 424.9129 | 26724
29757 | 436.5404 | 26724
29758 | 416.321 | 26724
29759 | 415.4434 | 26724
29760 | 416.05 | 26724
29761 | 421.117 | 26724
29762 | 403.3822 | 26724
29763 | 411.6177 | 26724
29764 | 417.3718 | 26724
29765 | 408.0256 | 26724
29766 | 413.1556 | 26724
29767 | 411.5565 | 26724
29768 | 420.2492 | 26724
29769 | 419.7919 | 26724
29770 | 426.1615 | 26724
29771 | 411.5255 | 26724
29772 | 421.933 | 26724
29773 | 419.3339 | 26724
29774 | 405.6314 | 26724
29775 | 416.9083 | 26724
29776 | 430.8486 | 26724
29777 | 410.1386 | 26724
29778 | 414.7207 | 26724
29779 | 403.5278 | 26724
29780 | 422.7966 | 26724
29781 | 409.3116 | 26724
29782 | 417.3324 | 26724
29783 | 406.1017 | 26724
29784 | 405.989 | 26724
29785 | 414.2965 | 26724
29786 | 397.9283 | 26724
29787 | 415.329 | 26724
29788 | 418.2846 | 26724
29789 | 408.4037 | 26724
29790 | 423.7344 | 26724
29791 | 405.6293 | 26724
29792 | 422.837 | 26724
29793 | 412.0487 | 26724
29794 | 422.3553 | 26724
29795 | 419.7691 | 26724
29796 | 411.2431 | 26724
29797 | 421.5771 | 26724
29798 | 422.4036 | 26724
29799 | 417.3731 | 26724
29800 | 428.0041 | 26724
29801 | 411.0729 | 26724
29802 | 415.7472 | 26724
29803 | 418.8803 | 26724
29804 | 408.2541 | 26724
29805 | 405.4011 | 26724
29806 | 426.2361 | 26724
29807 | 416.1797 | 26724
29808 | 418.5091 | 26724
29809 | 428.2305 | 26724
29810 | 424.9461 | 26724
29811 | 415.6021 | 26724
29812 | 432.799 | 26724
29813 | 419.666 | 26724
29814 | 431.2019 | 26724
29815 | 418.0435 | 26724
29816 | 422.5182 | 26724
29817 | 422.0333 | 26724
29818 | 411.5419 | 26724
29819 | 427.5087 | 26724
29820 | 424.439 | 26724
29821 | 414.2539 | 26724
29822 | 423.4633 | 26724
29823 | 414.4695 | 26724
29824 | 406.1661 | 26724
29825 | 416.9613 | 26724
29826 | 405.0109 | 26724
29827 | 429.3835 | 26724
29828 | 416.7528 | 26724
29829 | 408.3642 | 26724
29830 | 421.7018 | 26724
29831 | 411.0653 | 26724
29832 | 416.4559 | 26724
29833 | 414.2567 | 26724
29834 | 418.8494 | 26724
29835 | 412.4471 | 26724
29836 | 399.8806 | 26724
29837 | 413.4039 | 26724
29838 | 411.6669 | 26724
29839 | 412.8822 | 26724
29840 | 416.3284 | 26724
29841 | 435.1885 | 26724
29842 | 409.6292 | 26724
29843 | 415.1617 | 26724
29844 | 414.161 | 26724
29845 | 418.4096 | 26724
29846 | 408.0449 | 26724
29847 | 430.0806 | 26724
29848 | 420.5815 | 26724
29849 | 416.1478 | 26724
29850 | 428.1249 | 26724
29851 | 425.715 | 26724
29852 | 410.2951 | 26724
29853 | 408.6601 | 26724
29854 | 409.9593 | 26724
29855 | 431.3528 | 26724
29856 | 420.4891 | 26724
29857 | 424.2699 | 26724
29858 | 414.1698 | 26724
29859 | 421.3891 | 26724
29860 | 423.718 | 26724
29861 | 429.6118 | 26724
29862 | 416.5452 | 26724
29863 | 428.5286 | 26724
29864 | 424.6768 | 26724
29865 | 422.4334 | 26724
29866 | 404.0406 | 26724
29867 | 408.1869 | 26724
29868 | 430.0056 | 26724
29869 | 418.0584 | 26724
29870 | 410.8657 | 26724
29871 | 422.9892 | 26724
29872 | 415.0054 | 26724
29873 | 431.0761 | 26724
29874 | 420.0724 | 26724
29875 | 426.7579 | 26724
29876 | 427.1194 | 26724
29877 | 415.717 | 26724
29878 | 423.7612 | 26724
29879 | 422.7325 | 26724
29880 | 422.0107 | 26724
29881 | 406.5903 | 26724
29882 | 432.1049 | 26724
29883 | 419.1054 | 26724
29884 | 401.2698 | 26724
29885 | 411.7834 | 26724
29886 | 415.1412 | 26724
29887 | 421.82 | 26724
29888 | 422.076 | 26724
29889 | 413.7474 | 26724
29890 | 421.4175 | 26724
29891 | 424.0053 | 26724
29892 | 411.6218 | 26724
29893 | 407.3907 | 26724
29894 | 418.3111 | 26724
29895 | 415.8875 | 26724
29896 | 394.5677 | 26724
29897 | 414.7322 | 26724
29898 | 426.3587 | 26724
29899 | 420.8945 | 26724
29900 | 417.7191 | 26724
29901 | 426.275 | 26724
29902 | 401.9588 | 26724
29903 | 415.1237 | 26724
29904 | 412.8772 | 26724
29905 | 414.8569 | 26724
29906 | 414.8032 | 26724
29907 | 412.2473 | 26724
29908 | 425.557 | 26724
29909 | 410.4828 | 26724
29910 | 414.8305 | 26724
29911 | 416.3389 | 26724
29912 | 430.9311 | 26724
29913 | 409.4412 | 26724
29914 | 410.3514 | 26724
29915 | 425.1299 | 26724
29916 | 428.9977 | 26724
29917 | 422.9831 | 26724
29918 | 423.5082 | 26724
29919 | 405.3346 | 26724
29920 | 407.7809 | 26724
29921 | 406.132 | 26724
29922 | 418.2774 | 26724
29923 | 418.1881 | 26724
29924 | 411.3736 | 26724
29925 | 408.6911 | 26724
29926 | 400.109 | 26724
29927 | 431.1512 | 26724
29928 | 429.5921 | 26724
29929 | 420.7859 | 26724
29930 | 425.9418 | 26724
29931 | 426.2168 | 26724
29932 | 417.212 | 26724
29933 | 415.9941 | 26724
29934 | 424.076 | 26724
29935 | 415.0053 | 26724
29936 | 401.3615 | 26724
29937 | 426.2249 | 26724
29938 | 426.2933 | 26724
29939 | 414.0169 | 26724
29940 | 423.0926 | 26724
29941 | 417.1837 | 26724
29942 | 406.5868 | 26724
29943 | 431.2965 | 26724
29944 | 436.9991 | 26724
29945 | 426.5166 | 26724
29946 | 430.3842 | 26724
29947 | 401.383 | 26724
29948 | 409.2529 | 26724
29949 | 412.8421 | 26724
29950 | 420.5061 | 26724
29951 | 405.5455 | 26724
29952 | 412.3754 | 26724
29953 | 422.3211 | 26724
29954 | 423.007 | 26724
29955 | 421.4844 | 26724
29956 | 424.199 | 26724
29957 | 411.2702 | 26724
29958 | 428.0191 | 26724
29959 | 418.8008 | 26724
29960 | 409.3892 | 26724
29961 | 414.7662 | 26724
29962 | 424.8413 | 26724
29963 | 427.083 | 26724
29964 | 418.9725 | 26724
29965 | 417.6494 | 26724
29966 | 414.6558 | 26724
29967 | 420.0974 | 26724
29968 | 413.5195 | 26724
29969 | 398.3442 | 26724
29970 | 414.3586 | 26724
29971 | 418.0675 | 26724
29972 | 411.6728 | 26724
29973 | 422.0655 | 26724
29974 | 414.8431 | 26724
29975 | 414.3004 | 26724
29976 | 419.725 | 26724
29977 | 424.8245 | 26724
29978 | 402.5327 | 26724
29979 | 408.5781 | 26724
29980 | 409.4193 | 26724
29981 | 399.208 | 26724
29982 | 427.9455 | 26724
29983 | 426.9149 | 26724
29984 | 425.4422 | 26724
29985 | 413.9662 | 26724
29986 | 416.0678 | 26724
29987 | 417.3707 | 26724
29988 | 410.2293 | 26724
29989 | 417.4427 | 26724
29990 | 406.5261 | 26724
29991 | 412.785 | 26724
29992 | 416.9113 | 26724
29993 | 434.4393 | 26724
29994 | 418.4891 | 26724
29995 | 418.6887 | 26724
29996 | 410.8611 | 26724
29997 | 412.4044 | 26724
29998 | 401.5377 | 26724
29999 | 423.1669 | 26724
30000 | 415.5836 | 26724
30001 | 410.9748 | 26724
30002 | 413.4728 | 26724
30003 | 418.9669 | 26724
30004 | 411.9504 | 26724
30005 | 423.9505 | 26724
30006 | 416.5989 | 26724
30007 | 408.9923 | 26724
30008 | 418.822 | 26724
30009 | 417.6435 | 26724
30010 | 422.1317 | 26724
30011 | 419.694 | 26724
30012 | 406.2388 | 26724
30013 | 413.8204 | 26724
30014 | 426.0642 | 26724
30015 | 428.9812 | 26724
30016 | 426.2264 | 26724
30017 | 418.8658 | 26724
30018 | 420.6442 | 26724
30019 | 408.8565 | 26724
30020 | 426.8708 | 26724
30021 | 428.7007 | 26724
30022 | 424.2471 | 26724
30023 | 414.738 | 26724
30024 | 423.9347 | 26724
30025 | 423.301 | 26724
30026 | 412.5168 | 26724
30027 | 423.901 | 26724
30028 | 410.4085 | 26724
30029 | 422.7008 | 26724
30030 | 401.1516 | 26724
30031 | 406.121 | 26724
30032 | 424.7998 | 26724
30033 | 411.7842 | 26724
30034 | 429.4815 | 26724
30035 | 409.78 | 26724
30036 | 422.2632 | 26724
30037 | 405.4979 | 26724
30038 | 418.7205 | 26724
30039 | 422.8698 | 26724
30040 | 437.927 | 26724
30041 | 424.2918 | 26724
30042 | 417.038 | 26724
30043 | 419.0039 | 26724
30044 | 412.4582 | 26724
30045 | 416.1122 | 26724
30046 | 427.0601 | 26724
30047 | 424.7627 | 26724
30048 | 410.0975 | 26724
30049 | 416.4719 | 26724
30050 | 412.0945 | 26724
30051 | 411.7029 | 26724
30052 | 409.3324 | 26724
30053 | 411.3751 | 26724
30054 | 410.6075 | 26724
30055 | 409.5084 | 26724
30056 | 423.9275 | 26724
30057 | 422.8996 | 26724
30058 | 417.8449 | 26724
30059 | 419.858 | 26724
30060 | 423.0549 | 26724
30061 | 426.4269 | 26724
30062 | 402.2228 | 26724
30063 | 423.6571 | 26724
30064 | 408.7722 | 26724
30065 | 414.7476 | 26724
30066 | 421.1975 | 26724
30067 | 428.0176 | 26724
30068 | 421.8675 | 26724
30069 | 421.4945 | 26724
30070 | 426.4898 | 26724
30071 | 423.8786 | 26724
30072 | 408.4445 | 26724
30073 | 406.0894 | 26724
30074 | 423.3376 | 26724
30075 | 433.87 | 26724
30076 | 421.7823 | 26724
30077 | 426.2227 | 26724
30078 | 407.437 | 26724
30079 | 414.5389 | 26724
30080 | 408.8925 | 26724
30081 | 425.6636 | 26724
30082 | 402.1384 | 26724
30083 | 420.3382 | 26724
30084 | 417.4433 | 26724
30085 | 419.8727 | 26724
30086 | 409.0219 | 26724
30087 | 417.3367 | 26724
30088 | 424.0426 | 26724
30089 | 431.9696 | 26724
30090 | 426.3733 | 26724
30091 | 403.8762 | 26724
30092 | 419.8392 | 26724
30093 | 407.7664 | 26724
30094 | 409.1216 | 26724
30095 | 416.0336 | 26724
30096 | 428.0373 | 26724
30097 | 423.0593 | 26724
30098 | 409.9062 | 26724
30099 | 414.9368 | 26724
30100 | 410.1666 | 26724
30101 | 417.9909 | 26724
30102 | 425.1437 | 26724
30103 | 416.3514 | 26724
30104 | 409.5048 | 26724
30105 | 401.8983 | 26724
30106 | 412.5887 | 26724
30107 | 411.7131 | 26724
30108 | 420.4791 | 26724
30109 | 407.2547 | 26724
30110 | 414.7613 | 26724
30111 | 410.8432 | 26724
30112 | 416.9208 | 26724
30113 | 432.204 | 26724
30114 | 419.1098 | 26724
30115 | 425.36 | 26724
30116 | 418.0884 | 26724
30117 | 423.3213 | 26724
30118 | 416.5405 | 26724
30119 | 402.066 | 26724
30120 | 425.8368 | 26724
30121 | 412.9322 | 26724
30122 | 421.7792 | 26724
30123 | 409.9718 | 26724
30124 | 417.9397 | 26724
30125 | 410.7997 | 26724
30126 | 412.4826 | 26724
30127 | 410.6325 | 26724
30128 | 414.8749 | 26724
30129 | 413.5397 | 26724
30130 | 417.1845 | 26724
30131 | 424.5686 | 26724
30132 | 420.0549 | 26724
30133 | 409.3987 | 26724
30134 | 419.1863 | 26724
30135 | 404.9622 | 26724
30136 | 411.5861 | 26724
30137 | 422.963 | 26724
30138 | 429.1096 | 26724
30139 | 417.8215 | 26724
30140 | 420.2437 | 26724
30141 | 423.4574 | 26724
30142 | 415.131 | 26724
30143 | 414.4659 | 26724
30144 | 416.953 | 26724
30145 | 422.7313 | 26724
30146 | 406.0766 | 26724
30147 | 413.9847 | 26724
30148 | 412.3325 | 26724
30149 | 414.4588 | 26724
30150 | 429.7357 | 26724
30151 | 421.7747 | 26724
30152 | 423.1365 | 26724
30153 | 422.9272 | 26724
30154 | 418.0839 | 26724
30155 | 429.7663 | 26724
30156 | 410.6585 | 26724
30157 | 418.0672 | 26724
30158 | 409.1049 | 26724
30159 | 413.1456 | 26724
30160 | 421.9197 | 26724
30161 | 415.5465 | 26724
30162 | 421.0244 | 26724
30163 | 418.0953 | 26724
30164 | 426.4287 | 26724
30165 | 426.955 | 26724
30166 | 419.1203 | 26724
30167 | 427.7709 | 26724
30168 | 427.404 | 26724
30169 | 412.3771 | 26724
30170 | 409.2167 | 26724
30171 | 417.4143 | 26724
30172 | 411.4477 | 26724
30173 | 417.4925 | 26724
30174 | 415.2885 | 26724
30175 | 412.2535 | 26724
30176 | 413.9328 | 26724
30177 | 421.7098 | 26724
30178 | 416.199 | 26724
30179 | 403.2704 | 26724
30180 | 418.9196 | 26724
30181 | 411.6431 | 26724
30182 | 411.2754 | 26724
30183 | 419.9033 | 26724
30184 | 428.1059 | 26724
30185 | 435.1149 | 26724
30186 | 409.6575 | 26724
30187 | 406.9547 | 26724
30188 | 426.2025 | 26724
30189 | 411.6599 | 26724
30190 | 428.4206 | 26724
30191 | 424.227 | 26724
30192 | 407.6651 | 26724
30193 | 416.5412 | 26724
30194 | 421.5649 | 26724
30195 | 415.401 | 26724
30196 | 414.5966 | 26724
30197 | 424.0041 | 26724
30198 | 427.0435 | 26724
30199 | 416.0775 | 26724
30200 | 413.5221 | 26724
30201 | 412.3205 | 26724
30202 | 423.9338 | 26724
30203 | 412.383 | 26724
30204 | 407.1282 | 26724
30205 | 426.1469 | 26724
30206 | 412.9484 | 26724
30207 | 432.7065 | 26724
30208 | 407.1372 | 26724
30209 | 407.1757 | 26724
30210 | 418.7589 | 26724
30211 | 424.7548 | 26724
30212 | 406.8343 | 26724
30213 | 423.8278 | 26724
30214 | 416.5835 | 26724
30215 | 421.1095 | 26724
30216 | 410.7589 | 26724
30217 | 422.9548 | 26724
30218 | 417.703 | 26724
30219 | 420.8701 | 26724
30220 | 409.1491 | 26724
30221 | 420.4609 | 26724
30222 | 410.5519 | 26724
30223 | 410.9733 | 26724
30224 | 420.3282 | 26724
30225 | 419.1839 | 26724
30226 | 418.9729 | 26724
30227 | 418.0381 | 26724
30228 | 408.3702 | 26724
30229 | 416.9495 | 26724
30230 | 423.1962 | 26724
30231 | 422.0301 | 26724
30232 | 418.9614 | 26724
30233 | 397.3132 | 26724
30234 | 407.4786 | 26724
30235 | 416.0249 | 26724
30236 | 415.23 | 26724
30237 | 406.9025 | 26724
30238 | 424.5673 | 26724
30239 | 409.9427 | 26724
30240 | 397.0659 | 26724
30241 | 421.7828 | 26724
30242 | 408.7932 | 26724
30243 | 421.6894 | 26724
30244 | 414.7032 | 26724
30245 | 409.1562 | 26724
30246 | 418.3465 | 26724
30247 | 415.8287 | 26724
30248 | 408.9803 | 26724
30249 | 430.8039 | 26724
30250 | 410.2857 | 26724
30251 | 420.9172 | 26724
30252 | 414.9634 | 26724
30253 | 413.1778 | 26724
30254 | 429.0758 | 26724
30255 | 399.8936 | 26724
30256 | 404.7071 | 26724
30257 | 412.3847 | 26724
30258 | 418.3388 | 26724
30259 | 427.0986 | 26724
30260 | 423.7675 | 26724
30261 | 412.2219 | 26724
30262 | 417.6797 | 26724
30263 | 420.5519 | 26724
30264 | 415.3767 | 26724
30265 | 410.7144 | 26724
30266 | 410.8329 | 26724
30267 | 429.271 | 26724
30268 | 424.7256 | 26724
30269 | 413.1099 | 26724
30270 | 414.6302 | 26724
30271 | 423.7123 | 26724
30272 | 413.1566 | 26724
30273 | 424.0525 | 26724
30274 | 430.1605 | 26724
30275 | 394.1168 | 26724
30276 | 421.4082 | 26724
30277 | 411.2883 | 26724
30278 | 411.4757 | 26724
30279 | 429.1491 | 26724
30280 | 425.7874 | 26724
30281 | 423.101 | 26724
30282 | 414.3794 | 26724
30283 | 424.8974 | 26724
30284 | 414.4605 | 26724
30285 | 409.7064 | 26724
30286 | 433.6591 | 26724
30287 | 414.5831 | 26724
30288 | 416.4763 | 26724
30289 | 416.4613 | 26724
30290 | 420.7968 | 26724
30291 | 428.3053 | 26724
30292 | 426.103 | 26724
30293 | 419.6869 | 26724
30294 | 408.9951 | 26724
30295 | 412.4647 | 26724
30296 | 430.9205 | 26724
30297 | 421.2667 | 26724
30298 | 423.2106 | 26724
30299 | 428.4392 | 26724
30300 | 416.7346 | 26724
30301 | 412.6994 | 26724
30302 | 416.183 | 26724
30303 | 434.9433 | 26724
30304 | 410.9588 | 26724
30305 | 418.9172 | 26724
30306 | 418.1109 | 26724
30307 | 413.372 | 26724
30308 | 398.3846 | 26724
30309 | 416.1486 | 26724
30310 | 415.6234 | 26724
30311 | 423.9171 | 26724
30312 | 406.941 | 26724
30313 | 414.8236 | 26724
30314 | 419.5061 | 26724
30315 | 430.356 | 26724
30316 | 435.634 | 26724
30317 | 432.1993 | 26724
30318 | 412.8859 | 26724
30319 | 415.6417 | 26724
30320 | 412.7407 | 26724
30321 | 404.5913 | 26724
30322 | 405.7258 | 26724
30323 | 407.8305 | 26724
30324 | 415.646 | 26724
30325 | 428.559 | 26724
30326 | 413.0138 | 26724
30327 | 431.5732 | 26724
30328 | 403.2814 | 26724
30329 | 419.5176 | 26724
30330 | 415.6446 | 26724
30331 | 413.6771 | 26724
30332 | 417.0369 | 26724
30333 | 420.8858 | 26724
30334 | 400.7355 | 26724
30335 | 408.1551 | 26724
30336 | 406.0531 | 26724
30337 | 419.0229 | 26724
30338 | 418.7547 | 26724
30339 | 424.4092 | 26724
30340 | 424.8101 | 26724
30341 | 424.8674 | 26724
30342 | 417.7075 | 26724
30343 | 397.9254 | 26724
30344 | 417.3326 | 26724
30345 | 414.9535 | 26724
30346 | 396.4052 | 26724
30347 | 408.6712 | 26724
30348 | 421.2826 | 26724
30349 | 428.4627 | 26724
30350 | 420.5391 | 26724
30351 | 398.503 | 26724
30352 | 410.9726 | 26724
30353 | 425.284 | 26724
30354 | 421.6579 | 26724
30355 | 401.2755 | 26724
30356 | 404.1001 | 26724
30357 | 421.0314 | 26724
30358 | 421.6171 | 26724
30359 | 408.5586 | 26724
30360 | 420.5085 | 26724
30361 | 434.8911 | 26724
30362 | 419.4058 | 26724
30363 | 414.7725 | 26724
30364 | 405.9012 | 26724
30365 | 413.756 | 26724
30366 | 399.2621 | 26724
30367 | 402.1634 | 26724
30368 | 423.7808 | 26724
30369 | 410.3415 | 26724
30370 | 423.6913 | 26724
30371 | 410.3365 | 26724
30372 | 414.2216 | 26724
30373 | 405.4185 | 26724
30374 | 414.2535 | 26724
30375 | 417.8009 | 26724
30376 | 431.7697 | 26724
30377 | 422.4785 | 26724
30378 | 412.7118 | 26724
30379 | 413.4745 | 26724
30380 | 394.928 | 26724
30381 | 402.4702 | 26724
30382 | 431.8039 | 26724
30383 | 425.3817 | 26724
30384 | 424.3667 | 26724
30385 | 414.5459 | 26724
30386 | 409.8764 | 26724
30387 | 425.0893 | 26724
30388 | 420.2451 | 26724
30389 | 424.7469 | 26724
30390 | 422.9053 | 26724
30391 | 418.459 | 26724
30392 | 419.4342 | 26724
30393 | 421.9287 | 26724
30394 | 404.9867 | 26724
30395 | 415.8915 | 26724
30396 | 418.0964 | 26724
30397 | 416.368 | 26724
30398 | 414.1354 | 26724
30399 | 407.3844 | 26724
30400 | 426.8929 | 26724
30401 | 427.0135 | 26724
30402 | 418.3124 | 26724
30403 | 430.4176 | 26724
30404 | 420.5003 | 26724
30405 | 423.8672 | 26724
30406 | 423.0143 | 26724
30407 | 423.5999 | 26724
30408 | 412.5915 | 26724
30409 | 414.1894 | 26724
30410 | 404.9813 | 26724
30411 | 410.8724 | 26724
30412 | 409.2956 | 26724
30413 | 404.5204 | 26724
30414 | 423.1774 | 26724
30415 | 405.4545 | 26724
30416 | 427.8583 | 26724
30417 | 422.6597 | 26724
30418 | 420.9286 | 26724
30419 | 423.3144 | 26724
30420 | 398.4344 | 26724
30421 | 403.7138 | 26724
30422 | 415.2703 | 26724
30423 | 407.837 | 26724
30424 | 414.1579 | 26724
30425 | 406.0174 | 26724
30426 | 418.2641 | 26724
30427 | 430.6328 | 26724
30428 | 413.1198 | 26724
30429 | 428.6016 | 26724
30430 | 428.0583 | 26724
30431 | 419.0089 | 26724
30432 | 421.772 | 26724
30433 | 412.1296 | 26724
30434 | 410.5795 | 26724
30435 | 428.2207 | 26724
30436 | 411.0983 | 26724
30437 | 425.9404 | 26724
30438 | 408.622 | 26724
30439 | 420.9391 | 26724
30440 | 408.1839 | 26724
30441 | 426.6141 | 26724
30442 | 411.6669 | 26724
30443 | 405.4727 | 26724
30444 | 427.5559 | 26724
30445 | 419.5713 | 26724
30446 | 421.4224 | 26724
30447 | 424.9485 | 26724
30448 | 422.8969 | 26724
30449 | 399.5819 | 26724
30450 | 430.6507 | 26724
30451 | 400.4266 | 26724
30452 | 430.6543 | 26724
30453 | 397.321 | 26724
30454 | 414.2636 | 26724
30455 | 430.3345 | 26724
30456 | 410.1397 | 26724
30457 | 415.13 | 26724
30458 | 417.878 | 26724
30459 | 409.5728 | 26724
30460 | 407.8654 | 26724
30461 | 420.6533 | 26724
30462 | 410.0711 | 26724
30463 | 398.6392 | 26724
30464 | 422.2245 | 26724
30465 | 410.8331 | 26724
30466 | 420.5234 | 26724
30467 | 430.9579 | 26724
30468 | 411.4629 | 26724
30469 | 412.0446 | 26724
30470 | 407.8702 | 26724
30471 | 401.8137 | 26724
30472 | 419.9195 | 26724
30473 | 412.318 | 26724
30474 | 412.1077 | 26724
30475 | 419.8007 | 26724
30476 | 412.6013 | 26724
30477 | 404.0841 | 26724
30478 | 404.7708 | 26724
30479 | 423.378 | 26724
30480 | 414.0386 | 26724
30481 | 411.7954 | 26724
30482 | 415.4951 | 26724
30483 | 421.5263 | 26724
30484 | 420.7259 | 26724
30485 | 417.6207 | 26724
30486 | 398.2696 | 26724
30487 | 425.6156 | 26724
30488 | 397.1221 | 26724
30489 | 401.4103 | 26724
30490 | 411.8689 | 26724
30491 | 423.5773 | 26724
30492 | 407.4312 | 26724
30493 | 427.9092 | 26724
30494 | 412.7427 | 26724
30495 | 420.5476 | 26724
30496 | 430.9421 | 26724
30497 | 400.1143 | 26724
30498 | 431.218 | 26724
30499 | 407.9547 | 26724
30500 | 407.357 | 26724
30501 | 404.5284 | 26724
30502 | 435.4193 | 26724
30503 | 420.9062 | 26724
30504 | 427.836 | 26724
30505 | 414.2004 | 26724
30506 | 416.4555 | 26724
30507 | 409.2429 | 26724
30508 | 402.6804 | 26724
30509 | 410.8222 | 26724
30510 | 426.1752 | 26724
30511 | 419.424 | 26724
30512 | 426.5822 | 26724
30513 | 422.027 | 26724
30514 | 416.9692 | 26724
30515 | 420.6134 | 26724
30516 | 430.1567 | 26724
30517 | 409.2452 | 26724
30518 | 428.9697 | 26724
30519 | 415.0218 | 26724
30520 | 416.0019 | 26724
30521 | 429.94 | 26724
30522 | 410.9511 | 26724
30523 | 415.7765 | 26724
30524 | 414.1322 | 26724
30525 | 415.2372 | 26724
30526 | 427.0266 | 26724
30527 | 422.8163 | 26724
30528 | 433.9742 | 26724
30529 | 413.01 | 26724
30530 | 411.5264 | 26724
30531 | 400.2426 | 26724
30532 | 418.3526 | 26724
30533 | 414.416 | 26724
30534 | 431.7846 | 26724
30535 | 399.8854 | 26724
30536 | 425.2865 | 26724
30537 | 412.9245 | 26724
30538 | 422.0414 | 26724
30539 | 411.4875 | 26724
30540 | 424.3528 | 26724
30541 | 419.0757 | 26724
30542 | 400.311 | 26724
30543 | 423.5485 | 26724
30544 | 415.6154 | 26724
30545 | 429.9102 | 26724
30546 | 416.6832 | 26724
30547 | 422.3901 | 26724
30548 | 404.6447 | 26724
30549 | 423.3653 | 26724
30550 | 430.5381 | 26724
30551 | 419.0254 | 26724
30552 | 411.0579 | 26724
30553 | 410.6971 | 26724
30554 | 430.8837 | 26724
30555 | 410.2548 | 26724
30556 | 411.28 | 26724
30557 | 416.8602 | 26724
30558 | 418.3457 | 26724
30559 | 424.5539 | 26724
30560 | 402.5312 | 26724
30561 | 419.712 | 26724
30562 | 415.4076 | 26724
30563 | 417.9111 | 26724
30564 | 430.4713 | 26724
30565 | 396.6903 | 26724
30566 | 426.4697 | 26724
30567 | 403.4193 | 26724
30568 | 420.7279 | 26724
30569 | 400.2413 | 26724
30570 | 408.7001 | 26724
30571 | 416.2523 | 26724
30572 | 405.2474 | 26724
30573 | 429.2917 | 26724
30574 | 411.1987 | 26724
30575 | 427.7458 | 26724
30576 | 413.7937 | 26724
30577 | 430.2014 | 26724
30578 | 408.5355 | 26724
30579 | 422.761 | 26724
30580 | 415.1288 | 26724
30581 | 412.0488 | 26724
30582 | 418.072 | 26724
30583 | 416.3347 | 26724
30584 | 430.6898 | 26724
30585 | 413.9401 | 26724
30586 | 408.6655 | 26724
30587 | 409.8582 | 26724
30588 | 415.5275 | 26724
30589 | 410.652 | 26724
30590 | 401.6999 | 26724
30591 | 426.7568 | 26724
30592 | 408.2938 | 26724
30593 | 403.3436 | 26724
30594 | 419.1141 | 26724
30595 | 419.2536 | 26724
30596 | 424.7305 | 26724
30597 | 417.7352 | 26724
30598 | 433.7606 | 26724
30599 | 427.8144 | 26724
30600 | 419.0458 | 26724
30601 | 397.2447 | 26724
30602 | 408.8036 | 26724
30603 | 432.5012 | 26724
30604 | 428.145 | 26724
30605 | 421.5576 | 26724
30606 | 414.2208 | 26724
30607 | 429.5577 | 26724
30608 | 423.263 | 26724
30609 | 406.9846 | 26724
30610 | 410.3007 | 26724
30611 | 417.2184 | 26724
30612 | 415.1992 | 26724
30613 | 414.5555 | 26724
30614 | 416.5996 | 26724
30615 | 415.6968 | 26724
30616 | 410.5831 | 26724
30617 | 408.0993 | 26724
30618 | 412.8946 | 26724
30619 | 410.4446 | 26724
30620 | 407.9086 | 26724
30621 | 416.3001 | 26724
30622 | 406.0281 | 26724
30623 | 412.3164 | 26724
30624 | 420.3455 | 26724
30625 | 419.271 | 26724
30626 | 417.8034 | 26724
30627 | 427.02 | 26724
30628 | 422.0061 | 26724
30629 | 419.1021 | 26724
30630 | 425.7773 | 26724
30631 | 423.2482 | 26724
30632 | 409.4843 | 26724
30633 | 417.6321 | 26724
30634 | 421.6248 | 26724
30635 | 420.1461 | 26724
30636 | 418.7525 | 26724
30637 | 426.63 | 26724
30638 | 403.3127 | 26724
30639 | 427.2027 | 26724
30640 | 415.7654 | 26724
30641 | 419.843 | 26724
30642 | 420.423 | 26724
30643 | 423.2343 | 26724
30644 | 412.8143 | 26724
30645 | 417.158 | 26724
30646 | 410.9315 | 26724
30647 | 430.9767 | 26724
30648 | 424.329 | 26724
30649 | 406.7269 | 26724
30650 | 410.1694 | 26724
30651 | 423.5204 | 26724
30652 | 407.2797 | 26724
30653 | 410.6969 | 26724
30654 | 408.9961 | 26724
30655 | 424.1842 | 26724
30656 | 420.1819 | 26724
30657 | 427.5689 | 26724
30658 | 407.9203 | 26724
30659 | 420.5792 | 26724
30660 | 407.2035 | 26724
30661 | 409.1803 | 26724
30662 | 423.288 | 26724
30663 | 432.426 | 26724
30664 | 412.9116 | 26724
30665 | 409.8534 | 26724
30666 | 425.8352 | 26724
30667 | 405.2063 | 26724
30668 | 413.921 | 26724
30669 | 420.0356 | 26724
30670 | 415.9063 | 26724
30671 | 427.4955 | 26724
30672 | 425.1231 | 26724
30673 | 416.6907 | 26724
30674 | 409.7952 | 26724
30675 | 415.5893 | 26724
30676 | 423.7846 | 26724
30677 | 408.4949 | 26724
30678 | 416.1158 | 26724
30679 | 407.562 | 26724
30680 | 409.5817 | 26724
30681 | 417.2701 | 26724
30682 | 414.57 | 26724
30683 | 421.8508 | 26724
30684 | 421.4268 | 26724
30685 | 418.1534 | 26724
30686 | 416.8417 | 26724
30687 | 412.2911 | 26724
30688 | 421.9037 | 26724
30689 | 417.545 | 26724
30690 | 432.5464 | 26724
30691 | 422.5234 | 26724
30692 | 433.4606 | 26724
30693 | 428.0524 | 26724
30694 | 424.5107 | 26724
30695 | 419.0825 | 26724
30696 | 410.9959 | 26724
30697 | 417.019 | 26724
30698 | 432.4015 | 26724
30699 | 420.7364 | 26724
30700 | 427.4555 | 26724
30701 | 418.3227 | 26724
30702 | 407.0613 | 26724
30703 | 424.4389 | 26724
30704 | 408.0024 | 26724
30705 | 420.0799 | 26724
30706 | 415.0449 | 26724
30707 | 420.0362 | 26724
30708 | 413.1333 | 26724
30709 | 417.6732 | 26724
30710 | 433.9322 | 26724
30711 | 409.8405 | 26724
30712 | 426.101 | 26724
30713 | 409.6389 | 26724
30714 | 415.4799 | 26724
30715 | 417.2245 | 26724
30716 | 416.0563 | 26724
30717 | 425.2596 | 26724
30718 | 419.3961 | 26724
30719 | 421.3455 | 26724
30720 | 431.8335 | 26724
30721 | 424.3044 | 26724
30722 | 402.8313 | 26724
30723 | 404.8434 | 26724
30724 | 424.6695 | 26724
30725 | 408.3246 | 26724
30726 | 419.2381 | 26724
30727 | 420.5987 | 26724
30728 | 414.1958 | 26724
30729 | 416.3085 | 26724
30730 | 419.0687 | 26724
30731 | 410.9294 | 26724
30732 | 420.1454 | 26724
30733 | 410.7081 | 26724
30734 | 414.219 | 26724
30735 | 398.22 | 26724
30736 | 412.0541 | 26724
30737 | 400.8668 | 26724
30738 | 408.6214 | 26724
30739 | 413.3989 | 26724
30740 | 417.6904 | 26724
30741 | 407.81 | 26724
30742 | 420.1252 | 26724
30743 | 402.5162 | 26724
30744 | 425.8811 | 26724
30745 | 433.4943 | 26724
30746 | 415.0452 | 26724
30747 | 424.0863 | 26724
30748 | 422.0059 | 26724
30749 | 426.7954 | 26724
30750 | 408.0339 | 26724
30751 | 414.9017 | 26724
30752 | 407.0154 | 26724
30753 | 415.5343 | 26724
30754 | 418.0469 | 26724
30755 | 413.8413 | 26724
30756 | 428.1668 | 26724
30757 | 414.2761 | 26724
30758 | 408.3056 | 26724
30759 | 420.1701 | 26724
30760 | 405.8943 | 26724
30761 | 398.3077 | 26724
30762 | 412.0833 | 26724
30763 | 416.3749 | 26724
30764 | 426.5316 | 26724
30765 | 437.7958 | 26724
30766 | 417.7067 | 26724
30767 | 414.1815 | 26724
30768 | 413.5868 | 26724
30769 | 408.1868 | 26724
30770 | 429.9163 | 26724
30771 | 415.3556 | 26724
30772 | 409.4104 | 26724
30773 | 417.3125 | 26724
30774 | 431.9118 | 26724
30775 | 400.7427 | 26724
30776 | 424.6018 | 26724
30777 | 423.435 | 26724
30778 | 405.4508 | 26724
30779 | 424.889 | 26724
30780 | 412.6546 | 26724
30781 | 420.9072 | 26724
30782 | 430.1473 | 26724
30783 | 425.0299 | 26724
30784 | 407.5152 | 26724
30785 | 404.0775 | 26724
30786 | 408.27 | 26724
30787 | 413.3911 | 26724
30788 | 426.4465 | 26724
30789 | 437.2629 | 26724
30790 | 415.8163 | 26724
30791 | 404.2625 | 26724
30792 | 414.6201 | 26724
30793 | 416.0083 | 26724
30794 | 427.2483 | 26724
30795 | 408.7042 | 26724
30796 | 421.4177 | 26724
30797 | 428.4066 | 26724
30798 | 408.6304 | 26724
30799 | 420.7243 | 26724
30800 | 421.1649 | 26724
30801 | 414.9126 | 26724
30802 | 431.3727 | 26724
30803 | 418.2109 | 26724
30804 | 423.2476 | 26724
30805 | 416.1608 | 26724
30806 | 416.2729 | 26724
30807 | 427.9015 | 26724
30808 | 414.5693 | 26724
30809 | 436.6469 | 26724
30810 | 430.6608 | 26724
30811 | 423.2356 | 26724
30812 | 420.5041 | 26724
30813 | 425.9069 | 26724
30814 | 416.8365 | 26724
30815 | 410.9059 | 26724
30816 | 411.4999 | 26724
30817 | 413.4473 | 26724
30818 | 408.5007 | 26724
30819 | 411.8517 | 26724
30820 | 418.4352 | 26724
30821 | 410.9973 | 26724
30822 | 419.2957 | 26724
30823 | 410.2634 | 26724
30824 | 418.887 | 26724
30825 | 416.9284 | 26724
30826 | 406.186 | 26724
30827 | 420.8964 | 26724
30828 | 414.0273 | 26724
30829 | 418.7741 | 26724
30830 | 422.2784 | 26724
30831 | 420.9033 | 26724
30832 | 407.9269 | 26724
30833 | 424.7564 | 26724
30834 | 410.7649 | 26724
30835 | 413.9973 | 26724
30836 | 416.2809 | 26724
30837 | 412.9572 | 26724
30838 | 408.387 | 26724
30839 | 423.069 | 26724
30840 | 413.6498 | 26724
30841 | 410.9156 | 26724
30842 | 413.0864 | 26724
30843 | 407.0299 | 26724
30844 | 407.5767 | 26724
30845 | 412.0561 | 26724
30846 | 425.4372 | 26724
30847 | 417.4372 | 26724
30848 | 428.2091 | 26724
30849 | 411.7815 | 26724
30850 | 415.2847 | 26724
30851 | 405.0457 | 26724
30852 | 420.4974 | 26724
30853 | 419.476 | 26724
30854 | 406.5129 | 26724
30855 | 406.425 | 26724
30856 | 423.0279 | 26724
30857 | 415.9622 | 26724
30858 | 407.6087 | 26724
30859 | 417.7312 | 26724
30860 | 415.5431 | 26724
30861 | 417.4291 | 26724
30862 | 422.6317 | 26724
30863 | 412.5183 | 26724
30864 | 418.7389 | 26724
30865 | 429.5063 | 26724
30866 | 394.4264 | 26724
30867 | 421.9815 | 26724
30868 | 417.395 | 26724
30869 | 414.5338 | 26724
30870 | 416.0473 | 26724
30871 | 421.0184 | 26724
30872 | 415.2184 | 26724
30873 | 415.013 | 26724
30874 | 421.9327 | 26724
30875 | 409.6311 | 26724
30876 | 414.4534 | 26724
30877 | 433.5348 | 26724
30878 | 412.4406 | 26724
30879 | 421.6523 | 26724
30880 | 421.2759 | 26724
30881 | 409.8112 | 26724
30882 | 405.9583 | 26724
30883 | 400.8197 | 26724
30884 | 412.8038 | 26724
30885 | 413.8923 | 26724
30886 | 411.6565 | 26724
30887 | 415.8409 | 26724
30888 | 424.1089 | 26724
30889 | 404.0866 | 26724
30890 | 410.7414 | 26724
30891 | 410.1753 | 26724
30892 | 424.0228 | 26724
30893 | 412.8521 | 26724
30894 | 409.9415 | 26724
30895 | 430.1991 | 26724
30896 | 410.9069 | 26724
30897 | 411.8498 | 26724
30898 | 410.6573 | 26724
30899 | 415.5551 | 26724
30900 | 428.5687 | 26724
30901 | 421.4995 | 26724
30902 | 416.6857 | 26724
30903 | 424.1151 | 26724
30904 | 426.0417 | 26724
30905 | 420.8631 | 26724
30906 | 408.7415 | 26724
30907 | 403.9126 | 26724
30908 | 410.6711 | 26724
30909 | 414.8051 | 26724
30910 | 410.5506 | 26724
30911 | 415.0282 | 26724
30912 | 414.011 | 26724
30913 | 420.8187 | 26724
30914 | 413.6616 | 26724
30915 | 431.5332 | 26724
30916 | 403.9956 | 26724
30917 | 406.9834 | 26724
30918 | 414.2953 | 26724
30919 | 407.237 | 26724
30920 | 402.15 | 26724
30921 | 419.4489 | 26724
30922 | 413.6458 | 26724
30923 | 407.0189 | 26724
30924 | 407.2889 | 26724
30925 | 408.8823 | 26724
30926 | 409.91 | 26724
30927 | 414.8659 | 26724
30928 | 412.6139 | 26724
30929 | 415.7438 | 26724
30930 | 408.7711 | 26724
30931 | 415.6121 | 26724
30932 | 410.6502 | 26724
30933 | 407.6379 | 26724
30934 | 404.8565 | 26724
30935 | 418.9588 | 26724
30936 | 425.262 | 26724
30937 | 422.4427 | 26724
30938 | 424.3579 | 26724
30939 | 423.876 | 26724
30940 | 411.8547 | 26724
30941 | 416.6135 | 26724
30942 | 432.9088 | 26724
30943 | 418.4182 | 26724
30944 | 408.5508 | 26724
30945 | 428.0262 | 26724
30946 | 407.3501 | 26724
30947 | 418.3418 | 26724
30948 | 415.2699 | 26724
30949 | 406.3906 | 26724
30950 | 399.147 | 26724
30951 | 418.0718 | 26724
30952 | 427.8281 | 26724
30953 | 429.8962 | 26724
30954 | 430.9851 | 26724
30955 | 419.4476 | 26724
30956 | 425.2738 | 26724
30957 | 409.8208 | 26724
30958 | 424.1214 | 26724
30959 | 418.2274 | 26724
30960 | 420.0312 | 26724
30961 | 415.2359 | 26724
30962 | 415.081 | 26724
30963 | 420.0444 | 26724
30964 | 419.4502 | 26724
30965 | 406.9605 | 26724
30966 | 394.0578 | 26724
30967 | 420.5805 | 26724
30968 | 426.8518 | 26724
30969 | 413.7532 | 26724
30970 | 409.8705 | 26724
30971 | 414.8216 | 26724
30972 | 412.8208 | 26724
30973 | 416.442 | 26724
30974 | 417.3247 | 26724
30975 | 403.6836 | 26724
30976 | 411.9356 | 26724
30977 | 408.249 | 26724
30978 | 410.2087 | 26724
30979 | 422.3664 | 26724
30980 | 412.4781 | 26724
30981 | 427.9077 | 26724
30982 | 417.9621 | 26724
30983 | 429.5108 | 26724
30984 | 411.3655 | 26724
30985 | 421.018 | 26724
30986 | 412.9358 | 26724
30987 | 429.597 | 26724
30988 | 415.5988 | 26724
30989 | 433.4455 | 26724
30990 | 428.2003 | 26724
30991 | 405.7276 | 26724
30992 | 418.3733 | 26724
30993 | 422.0307 | 26724
30994 | 428.5619 | 26724
30995 | 415.745 | 26724
30996 | 411.7131 | 26724
30997 | 423.8008 | 26724
30998 | 423.3491 | 26724
30999 | 406.4058 | 26724
31000 | 404.4307 | 26724
31001 | 410.5876 | 26724
31002 | 403.2213 | 26724
31003 | 411.5918 | 26724
31004 | 414.0089 | 26724
31005 | 407.4891 | 26724
31006 | 415.0676 | 26724
31007 | 426.0148 | 26724
31008 | 420.5111 | 26724
31009 | 428.6139 | 26724
31010 | 422.0499 | 26724
31011 | 402.6464 | 26724
31012 | 407.0706 | 26724
31013 | 410.8561 | 26724
31014 | 417.4702 | 26724
31015 | 413.2588 | 26724
31016 | 408.2884 | 26724
31017 | 425.1692 | 26724
31018 | 432.4085 | 26724
31019 | 435.0903 | 26724
31020 | 405.6843 | 26724
31021 | 425.3925 | 26724
31022 | 415.3607 | 26724
31023 | 416.6659 | 26724
31024 | 434.1537 | 26724
31025 | 422.9863 | 26724
31026 | 415.5038 | 26724
31027 | 421.0013 | 26724
31028 | 430.5764 | 26724
31029 | 398.4251 | 26724
31030 | 409.6088 | 26724
31031 | 417.3227 | 26724
31032 | 411.5761 | 26724
31033 | 415.509 | 26724
31034 | 409.7554 | 26724
31035 | 419.7436 | 26724
31036 | 410.5889 | 26724
31037 | 423.6436 | 26724
31038 | 419.8085 | 26724
31039 | 419.444 | 26724
31040 | 418.5672 | 26724
31041 | 426.198 | 26724
31042 | 421.228 | 26724
31043 | 416.0954 | 26724
31044 | 424.8218 | 26724
31045 | 422.5468 | 26724
31046 | 401.2805 | 26724
31047 | 412.8494 | 26724
31048 | 429.8294 | 26724
31049 | 428.7094 | 26724
31050 | 407.4305 | 26724
31051 | 416.9572 | 26724
31052 | 414.1765 | 26724
31053 | 412.3475 | 26724
31054 | 428.1308 | 26724
31055 | 413.718 | 26724
31056 | 410.4704 | 26724
31057 | 414.8882 | 26724
31058 | 413.1678 | 26724
31059 | 404.4095 | 26724
31060 | 422.5722 | 26724
31061 | 404.708 | 26724
31062 | 433.6721 | 26724
31063 | 406.973 | 26724
31064 | 413.0356 | 26724
31065 | 418.4218 | 26724
31066 | 423.9244 | 26724
31067 | 407.354 | 26724
31068 | 417.6107 | 26724
31069 | 413.5346 | 26724
31070 | 408.3436 | 26724
31071 | 421.3585 | 26724
31072 | 416.5957 | 26724
31073 | 416.9458 | 26724
31074 | 428.0047 | 26724
31075 | 426.0493 | 26724
31076 | 415.4563 | 26724
31077 | 414.5814 | 26724
31078 | 416.7426 | 26724
31079 | 434.1311 | 26724
31080 | 420.1882 | 26724
31081 | 414.7366 | 26724
31082 | 402.4001 | 26724
31083 | 411.9612 | 26724
31084 | 428.9679 | 26724
31085 | 433.6134 | 26724
31086 | 418.2235 | 26724
31087 | 417.1051 | 26724
31088 | 425.9502 | 26724
31089 | 408.3487 | 26724
31090 | 419.4567 | 26724
31091 | 415.1326 | 26724
31092 | 403.5636 | 26724
31093 | 409.6111 | 26724
31094 | 418.4534 | 26724
31095 | 404.2958 | 26724
31096 | 412.3132 | 26724
31097 | 406.2212 | 26724
31098 | 411.8875 | 26724
31099 | 412.1749 | 26724
31100 | 431.2971 | 26724
31101 | 420.7086 | 26724
31102 | 433.1168 | 26724
31103 | 419.0043 | 26724
31104 | 419.1879 | 26724
31105 | 423.5371 | 26724
31106 | 421.4822 | 26724
31107 | 426.1704 | 26724
31108 | 413.4246 | 26724
31109 | 424.4144 | 26724
31110 | 407.3213 | 26724
31111 | 407.2221 | 26724
31112 | 408.152 | 26724
31113 | 411.8285 | 26724
31114 | 419.4441 | 26724
31115 | 417.6825 | 26724
31116 | 418.0782 | 26724
31117 | 420.4936 | 26724
31118 | 428.3986 | 26724
31119 | 408.4526 | 26724
31120 | 421.1693 | 26724
31121 | 396.4876 | 26724
31122 | 428.511 | 26724
31123 | 405.4779 | 26724
31124 | 418.5085 | 26724
31125 | 417.738 | 26724
31126 | 420.6898 | 26724
31127 | 410.4832 | 26724
31128 | 434.386 | 26724
31129 | 417.2191 | 26724
31130 | 406.2555 | 26724
31131 | 418.1921 | 26724
31132 | 428.0652 | 26724
31133 | 411.8748 | 26724
31134 | 423.713 | 26724
31135 | 401.3701 | 26724
31136 | 409.3317 | 26724
31137 | 407.588 | 26724
31138 | 408.7705 | 26724
31139 | 407.8989 | 26724
31140 | 406.059 | 26724
31141 | 409.4588 | 26724
31142 | 408.3529 | 26724
31143 | 398.3352 | 26724
31144 | 414.7294 | 26724
31145 | 413.2629 | 26724
31146 | 403.1404 | 26724
31147 | 427.3153 | 26724
31148 | 413.569 | 26724
31149 | 415.7453 | 26724
31150 | 428.2163 | 26724
31151 | 414.6523 | 26724
31152 | 427.0261 | 26724
31153 | 431.2416 | 26724
31154 | 409.7045 | 26724
31155 | 413.1662 | 26724
31156 | 410.9604 | 26724
31157 | 426.8515 | 26724
31158 | 422.0134 | 26724
31159 | 415.9313 | 26724
31160 | 413.8956 | 26724
31161 | 424.131 | 26724
31162 | 409.703 | 26724
31163 | 409.1329 | 26724
31164 | 403.9821 | 26724
31165 | 416.5626 | 26724
31166 | 414.3114 | 26724
31167 | 429.2393 | 26724
31168 | 428.7591 | 26724
31169 | 430.3572 | 26724
31170 | 414.4704 | 26724
31171 | 426.7588 | 26724
31172 | 419.7894 | 26724
31173 | 425.8177 | 26724
31174 | 419.2472 | 26724
31175 | 429.29 | 26724
31176 | 413.5652 | 26724
31177 | 421.1476 | 26724
31178 | 408.3251 | 26724
31179 | 420.822 | 26724
31180 | 417.9895 | 26724
31181 | 408.0311 | 26724
31182 | 422.657 | 26724
31183 | 420.4589 | 26724
31184 | 427.0274 | 26724
31185 | 409.5219 | 26724
31186 | 408.1183 | 26724
31187 | 410.5604 | 26724
31188 | 412.2379 | 26724
31189 | 426.3147 | 26724
31190 | 411.9299 | 26724
31191 | 416.9314 | 26724
31192 | 420.8166 | 26724
31193 | 423.4159 | 26724
31194 | 404.0355 | 26724
31195 | 420.6094 | 26724
31196 | 427.3365 | 26724
31197 | 406.8852 | 26724
31198 | 419.5146 | 26724
31199 | 422.8765 | 26724
31200 | 405.952 | 26724
31201 | 413.7401 | 26724
31202 | 424.8452 | 26724
31203 | 414.326 | 26724
31204 | 410.9741 | 26724
31205 | 413.011 | 26724
31206 | 412.9362 | 26724
31207 | 426.4636 | 26724
31208 | 421.3694 | 26724
31209 | 416.2772 | 26724
31210 | 417.5217 | 26724
31211 | 425.0163 | 26724
31212 | 407.404 | 26724
31213 | 403.2108 | 26724
31214 | 418.5448 | 26724
31215 | 421.8892 | 26724
31216 | 418.9695 | 26724
31217 | 414.1744 | 26724
31218 | 416.6305 | 26724
31219 | 411.1554 | 26724
31220 | 424.6298 | 26724
31221 | 436.0132 | 26724
31222 | 420.241 | 26724
31223 | 411.9921 | 26724
31224 | 425.426 | 26724
31225 | 401.012 | 26724
31226 | 419.4479 | 26724
31227 | 417.3353 | 26724
31228 | 403.3331 | 26724
31229 | 418.7685 | 26724
31230 | 425.3193 | 26724
31231 | 409.0138 | 26724
31232 | 404.3354 | 26724
31233 | 419.8206 | 26724
31234 | 408.1836 | 26724
31235 | 419.9973 | 26724
31236 | 413.3732 | 26724
31237 | 423.9754 | 26724
31238 | 410.6805 | 26724
31239 | 405.5184 | 26724
31240 | 414.6889 | 26724
31241 | 412.1676 | 26724
31242 | 403.3408 | 26724
31243 | 424.266 | 26724
31244 | 403.9633 | 26724
31245 | 427.2456 | 26724
31246 | 421.8149 | 26724
31247 | 414.6281 | 26724
31248 | 428.7005 | 26724
31249 | 421.8333 | 26724
31250 | 418.2282 | 26724
31251 | 411.7728 | 26724
31252 | 413.2943 | 26724
31253 | 417.0147 | 26724
31254 | 422.7495 | 26724
31255 | 417.7809 | 26724
31256 | 420.4179 | 26724
31257 | 414.6707 | 26724
31258 | 408.1628 | 26724
31259 | 415.4931 | 26724
31260 | 427.8106 | 26724
31261 | 425.2548 | 26724
31262 | 419.3253 | 26724
31263 | 412.0206 | 26724
31264 | 415.2732 | 26724
31265 | 417.2219 | 26724
31266 | 407.0878 | 26724
31267 | 420.7096 | 26724
31268 | 411.4213 | 26724
31269 | 426.4117 | 26724
31270 | 409.4188 | 26724
31271 | 426.107 | 26724
31272 | 422.7654 | 26724
31273 | 436.1926 | 26724
31274 | 417.7096 | 26724
31275 | 399.3387 | 26724
31276 | 415.1838 | 26724
31277 | 404.4067 | 26724
31278 | 415.4539 | 26724
31279 | 421.4379 | 26724
31280 | 405.6466 | 26724
31281 | 416.9065 | 26724
31282 | 417.0508 | 26724
31283 | 422.5573 | 26724
31284 | 419.739 | 26724
31285 | 413.1828 | 26724
31286 | 406.9887 | 26724
31287 | 420.9595 | 26724
31288 | 406.5321 | 26724
31289 | 420.0506 | 26724
31290 | 415.2463 | 26724
31291 | 426.3897 | 26724
31292 | 424.1086 | 26724
31293 | 409.6224 | 26724
31294 | 430.8415 | 26724
31295 | 421.4549 | 26724
31296 | 405.0973 | 26724
31297 | 412.4399 | 26724
31298 | 417.3771 | 26724
31299 | 413.7566 | 26724
31300 | 408.168 | 26724
31301 | 412.3669 | 26724
31302 | 418.431 | 26724
31303 | 415.2403 | 26724
31304 | 406.2729 | 26724
31305 | 412.3117 | 26724
31306 | 418.6968 | 26724
31307 | 403.8884 | 26724
31308 | 427.7652 | 26724
31309 | 406.1333 | 26724
31310 | 414.2921 | 26724
31311 | 424.2543 | 26724
31312 | 412.7576 | 26724
31313 | 412.9462 | 26724
31314 | 408.6333 | 26724
31315 | 401.3254 | 26724
31316 | 424.7033 | 26724
31317 | 410.1607 | 26724
31318 | 404.404 | 26724
31319 | 419.2514 | 26724
31320 | 405.8694 | 26724
31321 | 409.0246 | 26724
31322 | 413.1075 | 26724
31323 | 425.203 | 26724
31324 | 414.8377 | 26724
31325 | 418.4902 | 26724
31326 | 411.3397 | 26724
31327 | 415.3256 | 26724
31328 | 406.8484 | 26724
31329 | 411.6112 | 26724
31330 | 416.2738 | 26724
31331 | 418.9192 | 26724
31332 | 412.5112 | 26724
31333 | 417.4443 | 26724
31334 | 409.8999 | 26724
31335 | 417.4511 | 26724
31336 | 426.7644 | 26724
31337 | 414.2788 | 26724
31338 | 412.1252 | 26724
31339 | 434.9367 | 26724
31340 | 432.7593 | 26724
31341 | 404.5827 | 26724
31342 | 407.8886 | 26724
31343 | 421.8706 | 26724
31344 | 429.1707 | 26724
31345 | 411.1589 | 26724
31346 | 413.7626 | 26724
31347 | 433.6082 | 26724
31348 | 409.0952 | 26724
31349 | 408.5226 | 26724
31350 | 416.595 | 26724
31351 | 403.4681 | 26724
31352 | 419.7612 | 26724
31353 | 412.8372 | 26724
31354 | 415.2096 | 26724
31355 | 413.6036 | 26724
31356 | 418.5446 | 26724
31357 | 412.865 | 26724
31358 | 412.4265 | 26724
31359 | 416.2675 | 26724
31360 | 419.1075 | 26724
31361 | 417.7004 | 26724
31362 | 420.787 | 26724
31363 | 407.1426 | 26724
31364 | 409.9539 | 26724
31365 | 429.8015 | 26724
31366 | 426.8205 | 26724
31367 | 420.3157 | 26724
31368 | 415.0692 | 26724
31369 | 413.9458 | 26724
31370 | 424.3071 | 26724
31371 | 421.4022 | 26724
31372 | 426.4773 | 26724
31373 | 421.8503 | 26724
31374 | 420.1973 | 26724
31375 | 407.6249 | 26724
31376 | 410.3326 | 26724
31377 | 414.181 | 26724
31378 | 409.3914 | 26724
31379 | 419.0552 | 26724
31380 | 406.1422 | 26724
31381 | 411.5509 | 26724
31382 | 415.5888 | 26724
31383 | 415.1853 | 26724
31384 | 405.227 | 26724
31385 | 409.3685 | 26724
31386 | 407.9333 | 26724
31387 | 416.3377 | 26724
31388 | 427.6037 | 26724
31389 | 405.8077 | 26724
31390 | 414.6921 | 26724
31391 | 423.4868 | 26724
31392 | 399.7259 | 26724
31393 | 412.5827 | 26724
31394 | 412.0995 | 26724
31395 | 425.7074 | 26724
31396 | 427.8188 | 26724
31397 | 413.6988 | 26724
31398 | 415.4 | 26724
31399 | 410.5865 | 26724
31400 | 423.0698 | 26724
31401 | 402.4522 | 26724
31402 | 404.4674 | 26724
31403 | 427.2615 | 26724
31404 | 411.2073 | 26724
31405 | 420.3407 | 26724
31406 | 426.7558 | 26724
31407 | 433.8089 | 26724
31408 | 416.9126 | 26724
31409 | 417.3778 | 26724
31410 | 418.0803 | 26724
31411 | 403.571 | 26724
31412 | 411.2325 | 26724
31413 | 418.5042 | 26724
31414 | 408.2891 | 26724
31415 | 422.6701 | 26724
31416 | 415.8864 | 26724
31417 | 405.5224 | 26724
31418 | 409.714 | 26724
31419 | 413.5273 | 26724
31420 | 416.75 | 26724
31421 | 407.1059 | 26724
31422 | 413.9079 | 26724
31423 | 417.8316 | 26724
31424 | 416.4254 | 26724
31425 | 402.288 | 26724
31426 | 418.9163 | 26724
31427 | 420.7163 | 26724
31428 | 409.0278 | 26724
31429 | 409.4067 | 26724
31430 | 420.19 | 26724
31431 | 411.2877 | 26724
31432 | 417.0198 | 26724
31433 | 401.7433 | 26724
31434 | 419.4789 | 26724
31435 | 419.0487 | 26724
31436 | 424.8372 | 26724
31437 | 414.6883 | 26724
31438 | 415.5972 | 26724
31439 | 419.8816 | 26724
31440 | 410.977 | 26724
31441 | 414.5646 | 26724
31442 | 427.6384 | 26724
31443 | 425.4457 | 26724
31444 | 422.8184 | 26724
31445 | 412.6059 | 26724
31446 | 404.7096 | 26724
31447 | 403.2195 | 26724
31448 | 422.7879 | 26724
31449 | 409.3728 | 26724
31450 | 421.9928 | 26724
31451 | 426.1914 | 26724
31452 | 422.9081 | 26724
31453 | 404.4561 | 26724
31454 | 408.767 | 26724
31455 | 426.8896 | 26724
31456 | 417.8481 | 26724
31457 | 410.3957 | 26724
31458 | 421.7206 | 26724
31459 | 423.2076 | 26724
31460 | 409.1431 | 26724
31461 | 413.6469 | 26724
31462 | 424.4696 | 26724
31463 | 412.2122 | 26724
31464 | 418.7196 | 26724
31465 | 411.6682 | 26724
31466 | 418.9271 | 26724
31467 | 414.7402 | 26724
31468 | 408.572 | 26724
31469 | 420.7729 | 26724
31470 | 424.612 | 26724
31471 | 425.7933 | 26724
31472 | 417.9925 | 26724
31473 | 403.9329 | 26724
31474 | 409.2339 | 26724
31475 | 407.6898 | 26724
31476 | 420.5914 | 26724
31477 | 422.2237 | 26724
31478 | 417.3597 | 26724
31479 | 413.0865 | 26724
31480 | 419.812 | 26724
31481 | 415.9803 | 26724
31482 | 430.5041 | 26724
31483 | 421.7872 | 26724
31484 | 417.942 | 26724
31485 | 420.7211 | 26724
31486 | 415.5903 | 26724
31487 | 426.4566 | 26724
31488 | 406.4824 | 26724
31489 | 416.4648 | 26724
31490 | 424.7724 | 26724
31491 | 416.344 | 26724
31492 | 404.3479 | 26724
31493 | 418.3101 | 26724
31494 | 405.8208 | 26724
31495 | 414.3652 | 26724
31496 | 427.0151 | 26724
31497 | 401.8809 | 26724
31498 | 416.6697 | 26724
31499 | 415.9092 | 26724
31500 | 414.6603 | 26724
31501 | 407.7131 | 26724
31502 | 412.7308 | 26724
31503 | 420.0631 | 26724
31504 | 405.2764 | 26724
31505 | 415.764 | 26724
31506 | 424.4866 | 26724
31507 | 416.7371 | 26724
31508 | 419.3132 | 26724
31509 | 418.6143 | 26724
31510 | 412.7389 | 26724
31511 | 412.3193 | 26724
31512 | 407.499 | 26724
31513 | 416.1922 | 26724
31514 | 404.0159 | 26724
31515 | 419.6835 | 26724
31516 | 419.2638 | 26724
31517 | 427.7003 | 26724
31518 | 412.6192 | 26724
31519 | 404.33 | 26724
31520 | 405.7692 | 26724
31521 | 414.6554 | 26724
31522 | 412.2967 | 26724
31523 | 430.0782 | 26724
31524 | 414.8354 | 26724
31525 | 414.6357 | 26724
31526 | 408.2007 | 26724
31527 | 402.5248 | 26724
31528 | 404.0229 | 26724
31529 | 419.344 | 26724
31530 | 406.3892 | 26724
31531 | 415.0504 | 26724
31532 | 423.0888 | 26724
31533 | 414.9216 | 26724
31534 | 424.4445 | 26724
31535 | 418.1412 | 26724
31536 | 422.1725 | 26724
31537 | 421.0865 | 26724
31538 | 430.6916 | 26724
31539 | 427.2339 | 26724
31540 | 424.6389 | 26724
31541 | 407.3912 | 26724
31542 | 413.6559 | 26724
31543 | 416.8069 | 26724
31544 | 414.3025 | 26724
31545 | 420.0185 | 26724
31546 | 406.9796 | 26724
31547 | 411.1873 | 26724
31548 | 409.1606 | 26724
31549 | 419.1876 | 26724
31550 | 420.7906 | 26724
31551 | 403.2514 | 26724
31552 | 433.6093 | 26724
31553 | 423.8299 | 26724
31554 | 414.4542 | 26724
31555 | 406.8194 | 26724
31556 | 424.4814 | 26724
31557 | 404.4235 | 26724
31558 | 420.7728 | 26724
31559 | 420.7359 | 26724
31560 | 411.0319 | 26724
31561 | 423.0079 | 26724
31562 | 432.7921 | 26724
31563 | 410.853 | 26724
31564 | 427.3335 | 26724
31565 | 411.5485 | 26724
31566 | 402.1575 | 26724
31567 | 414.7732 | 26724
31568 | 415.9325 | 26724
31569 | 422.0579 | 26724
31570 | 416.297 | 26724
31571 | 404.9448 | 26724
31572 | 403.1153 | 26724
31573 | 424.6933 | 26724
31574 | 423.3955 | 26724
31575 | 415.2 | 26724
31576 | 415.6044 | 26724
31577 | 411.0395 | 26724
31578 | 424.0975 | 26724
31579 | 416.4803 | 26724
31580 | 425.2759 | 26724
31581 | 418.4574 | 26724
31582 | 405.9751 | 26724
31583 | 424.0012 | 26724
31584 | 407.3864 | 26724
31585 | 406.996 | 26724
31586 | 404.9698 | 26724
31587 | 415.9305 | 26724
31588 | 405.8555 | 26724
31589 | 421.613 | 26724
31590 | 421.243 | 26724
31591 | 425.2502 | 26724
31592 | 422.4423 | 26724
31593 | 401.5479 | 26724
31594 | 428.0585 | 26724
31595 | 406.2159 | 26724
31596 | 406.3668 | 26724
31597 | 411.9485 | 26724
31598 | 419.4306 | 26724
31599 | 407.6275 | 26724
31600 | 422.5833 | 26724
31601 | 412.8869 | 26724
31602 | 416.9976 | 26724
31603 | 429.0049 | 26724
31604 | 424.7038 | 26724
31605 | 415.0821 | 26724
31606 | 418.6359 | 26724
31607 | 412.884 | 26724
31608 | 412.8665 | 26724
31609 | 416.8209 | 26724
31610 | 421.4214 | 26724
31611 | 420.3712 | 26724
31612 | 397.6689 | 26724
31613 | 421.7527 | 26724
31614 | 421.2472 | 26724
31615 | 403.64 | 26724
31616 | 421.8079 | 26724
31617 | 400.1613 | 26724
31618 | 409.0928 | 26724
31619 | 416.3596 | 26724
31620 | 409.3706 | 26724
31621 | 400.2621 | 26724
31622 | 406.274 | 26724
31623 | 410.4436 | 26724
31624 | 412.1853 | 26724
31625 | 422.5848 | 26724
31626 | 420.2968 | 26724
31627 | 419.6732 | 26724
31628 | 418.4481 | 26724
31629 | 417.2877 | 26724
31630 | 409.5999 | 26724
31631 | 407.8529 | 26724
31632 | 415.8286 | 26724
31633 | 414.6063 | 26724
31634 | 424.7443 | 26724
31635 | 426.7588 | 26724
31636 | 408.1971 | 26724
31637 | 406.9635 | 26724
31638 | 419.1344 | 26724
31639 | 415.9782 | 26724
31640 | 425.1873 | 26724
31641 | 433.1966 | 26724
31642 | 426.4951 | 26724
31643 | 424.9858 | 26724
31644 | 421.0722 | 26724
31645 | 414.4454 | 26724
31646 | 410.4215 | 26724
31647 | 408.2254 | 26724
31648 | 416.6659 | 26724
31649 | 409.2641 | 26724
31650 | 405.3087 | 26724
31651 | 410.7607 | 26724
31652 | 420.9996 | 26724
31653 | 408.7622 | 26724
31654 | 411.8665 | 26724
31655 | 411.7861 | 26724
31656 | 416.8232 | 26724
31657 | 406.7049 | 26724
31658 | 420.7656 | 26724
31659 | 421.6874 | 26724
31660 | 413.1547 | 26724
31661 | 409.1336 | 26724
31662 | 426.1095 | 26724
31663 | 425.0291 | 26724
31664 | 424.8593 | 26724
31665 | 410.8754 | 26724
31666 | 401.8668 | 26724
31667 | 409.8162 | 26724
31668 | 412.0107 | 26724
31669 | 430.4717 | 26724
31670 | 409.5016 | 26724
31671 | 416.8611 | 26724
31672 | 409.1796 | 26724
31673 | 411.5026 | 26724
31674 | 407.71 | 26724
31675 | 416.301 | 26724
31676 | 416.2027 | 26724
31677 | 410.1616 | 26724
31678 | 412.1624 | 26724
31679 | 405.3726 | 26724
31680 | 421.7144 | 26724
31681 | 415.011 | 26724
31682 | 422.8537 | 26724
31683 | 419.3067 | 26724
31684 | 403.1037 | 26724
31685 | 416.6367 | 26724
31686 | 409.3836 | 26724
31687 | 420.0015 | 26724
31688 | 407.174 | 26724
31689 | 429.08 | 26724
31690 | 408.366 | 26724
31691 | 404.4594 | 26724
31692 | 414.3385 | 26724
31693 | 406.8687 | 26724
31694 | 409.2619 | 26724
31695 | 424.9932 | 26724
31696 | 434.9079 | 26724
31697 | 411.4949 | 26724
31698 | 402.3846 | 26724
31699 | 425.1693 | 26724
31700 | 409.794 | 26724
31701 | 405.0362 | 26724
31702 | 437.4221 | 26724
31703 | 412.9505 | 26724
31704 | 411.224 | 26724
31705 | 416.4421 | 26724
31706 | 416.2579 | 26724
31707 | 408.255 | 26724
31708 | 423.6908 | 26724
31709 | 418.9369 | 26724
31710 | 418.202 | 26724
31711 | 414.8858 | 26724
31712 | 423.8149 | 26724
31713 | 418.8679 | 26724
31714 | 400.2777 | 26724
31715 | 421.5917 | 26724
31716 | 406.5529 | 26724
31717 | 410.9604 | 26724
31718 | 415.1532 | 26724
31719 | 409.4892 | 26724
31720 | 411.5554 | 26724
31721 | 423.6388 | 26724
31722 | 424.0138 | 26724
31723 | 405.8655 | 26724
31724 | 412.1204 | 26724
31725 | 423.0219 | 26724
31726 | 426.3127 | 26724
31727 | 406.964 | 26724
31728 | 425.7667 | 26724
31729 | 403.3599 | 26724
31730 | 417.988 | 26724
31731 | 432.3312 | 26724
31732 | 416.744 | 26724
31733 | 417.0998 | 26724
31734 | 406.5072 | 26724
31735 | 410.518 | 26724
31736 | 411.9891 | 26724
31737 | 414.5244 | 26724
31738 | 404.4843 | 26724
31739 | 431.8577 | 26724
31740 | 428.8952 | 26724
31741 | 422.934 | 26724
31742 | 406.1488 | 26724
31743 | 421.6606 | 26724
31744 | 419.2462 | 26724
31745 | 415.4695 | 26724
31746 | 410.9032 | 26724
31747 | 412.947 | 26724
31748 | 431.4312 | 26724
31749 | 419.9292 | 26724
31750 | 411.1186 | 26724
31751 | 416.6473 | 26724
31752 | 415.9708 | 26724
31753 | 432.5623 | 26724
31754 | 412.5473 | 26724
31755 | 416.6032 | 26724
31756 | 432.1645 | 26724
31757 | 428.0878 | 26724
31758 | 419.7317 | 26724
31759 | 412.7722 | 26724
31760 | 420.8453 | 26724
31761 | 415.8667 | 26724
31762 | 417.3792 | 26724
31763 | 410.14 | 26724
31764 | 412.2917 | 26724
31765 | 417.8451 | 26724
31766 | 426.316 | 26724
31767 | 421.2824 | 26724
31768 | 411.1623 | 26724
31769 | 401.9045 | 26724
31770 | 422.3618 | 26724
31771 | 421.5347 | 26724
31772 | 411.1981 | 26724
31773 | 415.0151 | 26724
31774 | 422.5116 | 26724
31775 | 416.0307 | 26724
31776 | 407.1368 | 26724
31777 | 410.6513 | 26724
31778 | 416.2671 | 26724
31779 | 410.5023 | 26724
31780 | 411.8652 | 26724
31781 | 425.1158 | 26724
31782 | 398.9206 | 26724
31783 | 412.1549 | 26724
31784 | 413.9323 | 26724
31785 | 414.0796 | 26724
31786 | 417.3139 | 26724
31787 | 421.6009 | 26724
31788 | 411.6485 | 26724
31789 | 422.6104 | 26724
31790 | 409.0546 | 26724
31791 | 431.2639 | 26724
31792 | 416.6122 | 26724
31793 | 422.1587 | 26724
31794 | 408.7047 | 26724
31795 | 418.123 | 26724
31796 | 418.9313 | 26724
31797 | 408.9861 | 26724
31798 | 417.6095 | 26724
31799 | 401.8112 | 26724
31800 | 415.256 | 26724
31801 | 417.8911 | 26724
31802 | 403.8394 | 26724
31803 | 399.9562 | 26724
31804 | 416.5249 | 26724
31805 | 418.4276 | 26724
31806 | 396.7514 | 26724
31807 | 420.6606 | 26724
31808 | 411.871 | 26724
31809 | 414.5896 | 26724
31810 | 421.6101 | 26724
31811 | 429.9701 | 26724
31812 | 416.8144 | 26724
31813 | 424.6797 | 26724
31814 | 405.6845 | 26724
31815 | 418.839 | 26724
31816 | 411.1624 | 26724
31817 | 406.0889 | 26724
31818 | 420.4391 | 26724
31819 | 404.1466 | 26724
31820 | 415.6466 | 26724
31821 | 416.7886 | 26724
31822 | 413.6696 | 26724
31823 | 425.9749 | 26724
31824 | 427.8352 | 26724
31825 | 428.4469 | 26724
31826 | 403.5816 | 26724
31827 | 409.9885 | 26724
31828 | 402.3834 | 26724
31829 | 413.2846 | 26724
31830 | 415.7203 | 26724
31831 | 425.8086 | 26724
31832 | 407.2489 | 26724
31833 | 407.8594 | 26724
31834 | 412.1987 | 26724
31835 | 402.0601 | 26724
31836 | 411.3537 | 26724
31837 | 413.4291 | 26724
31838 | 428.4482 | 26724
31839 | 416.9348 | 26724
31840 | 428.7369 | 26724
31841 | 416.5266 | 26724
31842 | 422.9656 | 26724
31843 | 418.8762 | 26724
31844 | 399.6826 | 26724
31845 | 429.9534 | 26724
31846 | 398.6592 | 26724
31847 | 415.5604 | 26724
31848 | 409.2073 | 26724
31849 | 406.4309 | 26724
31850 | 419.2094 | 26724
31851 | 421.7843 | 26724
31852 | 413.2032 | 26724
31853 | 415.8976 | 26724
31854 | 413.1767 | 26724
31855 | 408.828 | 26724
31856 | 427.9478 | 26724
31857 | 407.3898 | 26724
31858 | 427.3534 | 26724
31859 | 418.1979 | 26724
31860 | 420.0346 | 26724
31861 | 414.4572 | 26724
31862 | 412.4843 | 26724
31863 | 413.2503 | 26724
31864 | 409.1932 | 26724
31865 | 402.4806 | 26724
31866 | 421.1693 | 26724
31867 | 410.1597 | 26724
31868 | 417.6016 | 26724
31869 | 415.2898 | 26724
31870 | 426.3461 | 26724
31871 | 421.6287 | 26724
31872 | 417.916 | 26724
31873 | 414.7421 | 26724
31874 | 413.8347 | 26724
31875 | 424.5511 | 26724
31876 | 422.1172 | 26724
31877 | 420.5288 | 26724
31878 | 398.9652 | 26724
31879 | 423.4306 | 26724
31880 | 414.3787 | 26724
31881 | 404.8562 | 26724
31882 | 423.4129 | 26724
31883 | 408.8937 | 26724
31884 | 413.9829 | 26724
31885 | 402.2163 | 26724
31886 | 429.6704 | 26724
31887 | 411.733 | 26724
31888 | 413.4586 | 26724
31889 | 408.4116 | 26724
31890 | 405.0525 | 26724
31891 | 417.6431 | 26724
31892 | 420.9696 | 26724
31893 | 412.2906 | 26724
31894 | 429.464 | 26724
31895 | 408.6324 | 26724
31896 | 407.9831 | 26724
31897 | 420.6421 | 26724
31898 | 409.3914 | 26724
31899 | 427.2242 | 26724
31900 | 421.6798 | 26724
31901 | 421.693 | 26724
31902 | 412.5377 | 26724
31903 | 409.9146 | 26724
31904 | 419.9471 | 26724
31905 | 425.0325 | 26724
31906 | 396.0811 | 26724
31907 | 418.1537 | 26724
31908 | 420.7042 | 26724
31909 | 396.8589 | 26724
31910 | 420.3159 | 26724
31911 | 434.9169 | 26724
31912 | 397.2273 | 26724
31913 | 410.8682 | 26724
31914 | 410.1732 | 26724
31915 | 409.1838 | 26724
31916 | 406.4666 | 26724
31917 | 418.1801 | 26724
31918 | 420.6838 | 26724
31919 | 410.5322 | 26724
31920 | 425.2488 | 26724
31921 | 400.7809 | 26724
31922 | 422.3366 | 26724
31923 | 403.9373 | 26724
31924 | 415.9339 | 26724
31925 | 428.3222 | 26724
31926 | 402.1598 | 26724
31927 | 412.418 | 26724
31928 | 431.5042 | 26724
31929 | 428.6674 | 26724
31930 | 414.8646 | 26724
31931 | 416.205 | 26724
31932 | 418.8028 | 26724
31933 | 412.3711 | 26724
31934 | 401.5522 | 26724
31935 | 419.5639 | 26724
31936 | 422.7949 | 26724
31937 | 429.7363 | 26724
31938 | 418.1168 | 26724
31939 | 417.1852 | 26724
31940 | 423.1345 | 26724
31941 | 415.1887 | 26724
31942 | 398.7978 | 26724
31943 | 419.17 | 26724
31944 | 414.5358 | 26724
31945 | 418.0265 | 26724
31946 | 424.9198 | 26724
31947 | 415.916 | 26724
31948 | 423.3812 | 26724
31949 | 410.2686 | 26724
31950 | 422.187 | 26724
31951 | 422.4307 | 26724
31952 | 410.9818 | 26724
31953 | 407.4959 | 26724
31954 | 412.7816 | 26724
31955 | 418.3722 | 26724
31956 | 424.1653 | 26724
31957 | 425.6984 | 26724
31958 | 403.5378 | 26724
31959 | 413.3733 | 26724
31960 | 402.9598 | 26724
31961 | 408.8995 | 26724
31962 | 400.8139 | 26724
31963 | 414.6838 | 26724
31964 | 405.8261 | 26724
31965 | 416.9619 | 26724
31966 | 418.3719 | 26724
31967 | 404.527 | 26724
31968 | 408.136 | 26724
31969 | 424.7084 | 26724
31970 | 410.4571 | 26724
31971 | 433.185 | 26724
31972 | 415.932 | 26724
31973 | 416.5058 | 26724
31974 | 410.8686 | 26724
31975 | 401.8662 | 26724
31976 | 425.5176 | 26724
31977 | 416.6097 | 26724
31978 | 422.748 | 26724
31979 | 425.6703 | 26724
31980 | 409.5448 | 26724
31981 | 415.565 | 26724
31982 | 401.4988 | 26724
31983 | 425.9467 | 26724
31984 | 424.2542 | 26724
31985 | 404.3787 | 26724
31986 | 425.3436 | 26724
31987 | 421.3825 | 26724
31988 | 417.2046 | 26724
31989 | 406.5869 | 26724
31990 | 410.9142 | 26724
31991 | 426.4913 | 26724
31992 | 415.3104 | 26724
31993 | 417.0527 | 26724
31994 | 430.2394 | 26724
31995 | 431.167 | 26724
31996 | 409.5197 | 26724
31997 | 406.8378 | 26724
31998 | 421.9282 | 26724
31999 | 423.9613 | 26724
32000 | 404.0227 | 26724
32001 | 415.8306 | 26724
32002 | 412.9925 | 26724
32003 | 399.266 | 26724
32004 | 415.2698 | 26724
32005 | 407.176 | 26724
32006 | 420.1369 | 26724
32007 | 409.8486 | 26724
32008 | 408.9243 | 26724
32009 | 408.1884 | 26724
32010 | 421.1095 | 26724
32011 | 421.6533 | 26724
32012 | 433.2768 | 26724
32013 | 405.9742 | 26724
32014 | 411.8212 | 26724
32015 | 407.4132 | 26724
32016 | 412.9337 | 26724
32017 | 415.2772 | 26724
32018 | 427.5449 | 26724
32019 | 419.508 | 26724
32020 | 410.3263 | 26724
32021 | 416.2441 | 26724
32022 | 411.4475 | 26724
32023 | 420.8287 | 26724
32024 | 418.5132 | 26724
32025 | 418.1075 | 26724
32026 | 418.6245 | 26724
32027 | 408.601 | 26724
32028 | 422.0384 | 26724
32029 | 415.3938 | 26724
32030 | 413.3575 | 26724
32031 | 423.837 | 26724
32032 | 418.9069 | 26724
32033 | 415.1712 | 26724
32034 | 414.9888 | 26724
32035 | 414.7425 | 26724
32036 | 428.1007 | 26724
32037 | 429.7995 | 26724
32038 | 409.2186 | 26724
32039 | 432.4584 | 26724
32040 | 411.678 | 26724
32041 | 416.8974 | 26724
32042 | 429.1358 | 26724
32043 | 424.973 | 26724
32044 | 414.1316 | 26724
32045 | 402.819 | 26724
32046 | 420.2731 | 26724
32047 | 418.1998 | 26724
32048 | 412.7399 | 26724
32049 | 414.6525 | 26724
32050 | 423.4046 | 26724
32051 | 417.9108 | 26724
32052 | 431.3366 | 26724
32053 | 400.574 | 26724
32054 | 416.9022 | 26724
32055 | 425.39 | 26724
32056 | 411.6312 | 26724
32057 | 409.2582 | 26724
32058 | 415.1592 | 26724
32059 | 416.905 | 26724
32060 | 423.1316 | 26724
32061 | 406.8552 | 26724
32062 | 410.8525 | 26724
32063 | 413.0477 | 26724
32064 | 398.4148 | 26724
32065 | 427.9306 | 26724
32066 | 424.0513 | 26724
32067 | 409.7927 | 26724
32068 | 405.2908 | 26724
32069 | 424.1051 | 26724
32070 | 421.8529 | 26724
32071 | 408.4158 | 26724
32072 | 413.8509 | 26724
32073 | 405.7169 | 26724
32074 | 423.3801 | 26724
32075 | 424.6684 | 26724
32076 | 426.6659 | 26724
32077 | 411.5183 | 26724
32078 | 414.2916 | 26724
32079 | 410.6227 | 26724
32080 | 420.7097 | 26724
32081 | 424.836 | 26724
32082 | 410.5318 | 26724
32083 | 421.8429 | 26724
32084 | 400.9274 | 26724
32085 | 404.8433 | 26724
32086 | 414.7281 | 26724
32087 | 427.7655 | 26724
32088 | 399.4293 | 26724
32089 | 430.7683 | 26724
32090 | 418.8012 | 26724
32091 | 425.8807 | 26724
32092 | 421.5569 | 26724
32093 | 410.4353 | 26724
32094 | 433.6386 | 26724
32095 | 404.8268 | 26724
32096 | 409.8199 | 26724
32097 | 415.2051 | 26724
32098 | 409.8941 | 26724
32099 | 411.4464 | 26724
32100 | 408.0541 | 26724
32101 | 406.6233 | 26724
32102 | 422.0625 | 26724
32103 | 416.4552 | 26724
32104 | 405.6972 | 26724
32105 | 398.5732 | 26724
32106 | 423.396 | 26724
32107 | 411.4018 | 26724
32108 | 410.5689 | 26724
32109 | 418.4808 | 26724
32110 | 432.2251 | 26724
32111 | 430.7316 | 26724
32112 | 409.4592 | 26724
32113 | 413.1371 | 26724
32114 | 408.158 | 26724
32115 | 408.0172 | 26724
32116 | 430.182 | 26724
32117 | 416.9248 | 26724
32118 | 407.6376 | 26724
32119 | 402.677 | 26724
32120 | 416.3383 | 26724
32121 | 420.3499 | 26724
32122 | 419.7745 | 26724
32123 | 409.0603 | 26724
32124 | 403.6991 | 26724
32125 | 422.2983 | 26724
32126 | 412.4502 | 26724
32127 | 421.7206 | 26724
32128 | 400.0406 | 26724
32129 | 428.7771 | 26724
32130 | 415.2346 | 26724
32131 | 409.5292 | 26724
32132 | 425.9133 | 26724
32133 | 425.7809 | 26724
32134 | 409.1221 | 26724
32135 | 415.9397 | 26724
32136 | 407.3441 | 26724
32137 | 416.8758 | 26724
32138 | 432.8328 | 26724
32139 | 410.4064 | 26724
32140 | 418.826 | 26724
32141 | 423.5379 | 26724
32142 | 436.9263 | 26724
32143 | 411.7714 | 26724
32144 | 427.1811 | 26724
32145 | 419.6054 | 26724
32146 | 415.5437 | 26724
32147 | 407.6911 | 26724
32148 | 400.956 | 26724
32149 | 414.6212 | 26724
32150 | 413.0361 | 26724
32151 | 420.9118 | 26724
32152 | 421.9442 | 26724
32153 | 405.3228 | 26724
32154 | 401.4339 | 26724
32155 | 425.9916 | 26724
32156 | 422.8944 | 26724
32157 | 419.2513 | 26724
32158 | 413.8282 | 26724
32159 | 414.8942 | 26724
32160 | 420.6321 | 26724
32161 | 424.386 | 26724
32162 | 426.2079 | 26724
32163 | 408.7721 | 26724
32164 | 407.9859 | 26724
32165 | 419.1633 | 26724
32166 | 406.3578 | 26724
32167 | 420.8842 | 26724
32168 | 424.9986 | 26724
32169 | 415.7617 | 26724
32170 | 416.2377 | 26724
32171 | 419.1034 | 26724
32172 | 429.3688 | 26724
32173 | 415.6739 | 26724
32174 | 406.7774 | 26724
32175 | 411.2897 | 26724
32176 | 413.123 | 26724
32177 | 405.4625 | 26724
32178 | 413.0345 | 26724
32179 | 421.3832 | 26724
32180 | 412.7571 | 26724
32181 | 413.1697 | 26724
32182 | 404.6112 | 26724
32183 | 416.611 | 26724
32184 | 429.4528 | 26724
32185 | 418.225 | 26724
32186 | 431.0098 | 26724
32187 | 420.0795 | 26724
32188 | 414.1043 | 26724
32189 | 416.5249 | 26724
32190 | 409.3599 | 26724
32191 | 426.1254 | 26724
32192 | 425.2479 | 26724
32193 | 410.3457 | 26724
32194 | 407.0397 | 26724
32195 | 412.9195 | 26724
32196 | 436.4495 | 26724
32197 | 425.8681 | 26724
32198 | 418.0015 | 26724
32199 | 403.7973 | 26724
32200 | 405.7107 | 26724
32201 | 417.9062 | 26724
32202 | 408.7606 | 26724
32203 | 417.129 | 26724
32204 | 404.7145 | 26724
32205 | 412.7055 | 26724
32206 | 416.1475 | 26724
32207 | 414.923 | 26724
32208 | 405.1145 | 26724
32209 | 405.9965 | 26724
32210 | 423.5534 | 26724
32211 | 407.9996 | 26724
32212 | 439.1486 | 26724
32213 | 417.846 | 26724
32214 | 409.1829 | 26724
32215 | 419.6969 | 26724
32216 | 418.2808 | 26724
32217 | 408.329 | 26724
32218 | 420.2821 | 26724
32219 | 430.0207 | 26724
32220 | 410.7892 | 26724
32221 | 426.7774 | 26724
32222 | 408.6586 | 26724
32223 | 429.1667 | 26724
32224 | 411.7728 | 26724
32225 | 412.4603 | 26724
32226 | 416.6105 | 26724
32227 | 408.3561 | 26724
32228 | 422.7814 | 26724
32229 | 424.4131 | 26724
32230 | 410.1281 | 26724
32231 | 419.4292 | 26724
32232 | 400.7245 | 26724
32233 | 431.5566 | 26724
32234 | 426.0953 | 26724
32235 | 420.4084 | 26724
32236 | 412.0499 | 26724
32237 | 422.1576 | 26724
32238 | 415.1907 | 26724
32239 | 425.4864 | 26724
32240 | 430.4968 | 26724
32241 | 417.3727 | 26724
32242 | 410.7121 | 26724
32243 | 424.8067 | 26724
32244 | 430.8742 | 26724
32245 | 411.0097 | 26724
32246 | 422.8548 | 26724
32247 | 420.5602 | 26724
32248 | 425.1882 | 26724
32249 | 416.4597 | 26724
32250 | 409.8454 | 26724
32251 | 430.3735 | 26724
32252 | 418.4829 | 26724
32253 | 416.5989 | 26724
32254 | 409.002 | 26724
32255 | 423.4331 | 26724
32256 | 404.4603 | 26724
32257 | 413.5263 | 26724
32258 | 417.6535 | 26724
32259 | 417.4073 | 26724
32260 | 424.1242 | 26724
32261 | 420.014 | 26724
32262 | 414.2716 | 26724
32263 | 414.8965 | 26724
32264 | 405.8653 | 26724
32265 | 424.27 | 26724
32266 | 409.3535 | 26724
32267 | 420.7208 | 26724
32268 | 407.9524 | 26724
32269 | 413.1913 | 26724
32270 | 418.2047 | 26724
32271 | 413.4236 | 26724
32272 | 412.8064 | 26724
32273 | 411.0835 | 26724
32274 | 412.6068 | 26724
32275 | 428.3519 | 26724
32276 | 431.0622 | 26724
32277 | 415.7661 | 26724
32278 | 413.9915 | 26724
32279 | 414.9075 | 26724
32280 | 411.7602 | 26724
32281 | 411.8854 | 26724
32282 | 422.7943 | 26724
32283 | 404.4465 | 26724
32284 | 415.6437 | 26724
32285 | 415.815 | 26724
32286 | 411.2633 | 26724
32287 | 419.3006 | 26724
32288 | 407.4333 | 26724
32289 | 399.5654 | 26724
32290 | 413.6058 | 26724
32291 | 418.5712 | 26724
32292 | 425.6059 | 26724
32293 | 436.0551 | 26724
32294 | 408.0664 | 26724
32295 | 411.4356 | 26724
32296 | 416.8097 | 26724
32297 | 427.0912 | 26724
32298 | 417.8962 | 26724
32299 | 429.5166 | 26724
32300 | 413.9201 | 26724
32301 | 410.4839 | 26724
32302 | 402.9952 | 26724
32303 | 416.8988 | 26724
32304 | 409.4463 | 26724
32305 | 419.2759 | 26724
32306 | 420.5867 | 26724
32307 | 412.5768 | 26724
32308 | 410.204 | 26724
32309 | 412.1902 | 26724
32310 | 416.6946 | 26724
32311 | 414.8821 | 26724
32312 | 421.3706 | 26724
32313 | 414.2174 | 26724
32314 | 425.0547 | 26724
32315 | 410.1854 | 26724
32316 | 416.2765 | 26724
32317 | 425.4556 | 26724
32318 | 419.457 | 26724
32319 | 408.1376 | 26724
32320 | 413.7683 | 26724
32321 | 428.8768 | 26724
32322 | 415.5301 | 26724
32323 | 420.4318 | 26724
32324 | 404.898 | 26724
32325 | 409.5201 | 26724
32326 | 409.4374 | 26724
32327 | 426.5494 | 26724
32328 | 415.1585 | 26724
32329 | 420.1835 | 26724
32330 | 401.8453 | 26724
32331 | 424.0103 | 26724
32332 | 424.94 | 26724
32333 | 421.207 | 26724
32334 | 420.9444 | 26724
32335 | 426.7935 | 26724
32336 | 418.2878 | 26724
32337 | 407.3774 | 26724
32338 | 415.0628 | 26724
32339 | 411.1849 | 26724
32340 | 426.2454 | 26724
32341 | 417.6846 | 26724
32342 | 425.5045 | 26724
32343 | 420.4751 | 26724
32344 | 418.4018 | 26724
32345 | 406.4209 | 26724
32346 | 422.3511 | 26724
32347 | 414.548 | 26724
32348 | 424.9435 | 26724
32349 | 406.248 | 26724
32350 | 428.7269 | 26724
32351 | 424.9096 | 26724
32352 | 408.971 | 26724
32353 | 421.0728 | 26724
32354 | 421.1916 | 26724
32355 | 428.3626 | 26724
32356 | 413.2265 | 26724
32357 | 415.3907 | 26724
32358 | 426.3197 | 26724
32359 | 418.8007 | 26724
32360 | 411.4577 | 26724
32361 | 418.1076 | 26724
32362 | 424.0289 | 26724
32363 | 410.8508 | 26724
32364 | 420.6107 | 26724
32365 | 421.2998 | 26724
32366 | 434.1322 | 26724
32367 | 416.7675 | 26724
32368 | 408.8621 | 26724
32369 | 411.2393 | 26724
32370 | 428.2303 | 26724
32371 | 413.7485 | 26724
32372 | 412.6953 | 26724
32373 | 425.9404 | 26724
32374 | 410.0789 | 26724
32375 | 428.705 | 26724
32376 | 410.7122 | 26724
32377 | 417.0551 | 26724
32378 | 422.6554 | 26724
32379 | 431.3734 | 26724
32380 | 414.2982 | 26724
32381 | 423.9794 | 26724
32382 | 406.909 | 26724
32383 | 414.7297 | 26724
32384 | 421.1203 | 26724
32385 | 399.9573 | 26724
32386 | 429.4243 | 26724
32387 | 412.6349 | 26724
32388 | 430.731 | 26724
32389 | 411.0499 | 26724
32390 | 423.7362 | 26724
32391 | 412.3101 | 26724
32392 | 422.6202 | 26724
32393 | 406.8611 | 26724
32394 | 409.5148 | 26724
32395 | 406.7064 | 26724
32396 | 406.9915 | 26724
32397 | 409.6682 | 26724
32398 | 410.8882 | 26724
32399 | 418.5907 | 26724
32400 | 413.1459 | 26724
32401 | 423.8064 | 26724
32402 | 427.1518 | 26724
32403 | 409.2567 | 26724
32404 | 423.3509 | 26724
32405 | 426.8712 | 26724
32406 | 420.0476 | 26724
32407 | 417.4884 | 26724
32408 | 414.101 | 26724
32409 | 413.0895 | 26724
32410 | 418.173 | 26724
32411 | 404.0649 | 26724
32412 | 414.8422 | 26724
32413 | 413.0438 | 26724
32414 | 406.67 | 26724
32415 | 413.6116 | 26724
32416 | 417.5015 | 26724
32417 | 410.8375 | 26724
32418 | 405.8295 | 26724
32419 | 419.3209 | 26724
32420 | 403.1873 | 26724
32421 | 421.7139 | 26724
32422 | 420.6138 | 26724
32423 | 420.5367 | 26724
32424 | 420.2087 | 26724
32425 | 411.7932 | 26724
32426 | 410.7343 | 26724
32427 | 401.188 | 26724
32428 | 420.0595 | 26724
32429 | 423.0784 | 26724
32430 | 420.6088 | 26724
32431 | 417.8816 | 26724
32432 | 416.9714 | 26724
32433 | 419.3565 | 26724
32434 | 429.0833 | 26724
32435 | 431.5856 | 26724
32436 | 419.485 | 26724
32437 | 417.6497 | 26724
32438 | 414.5959 | 26724
32439 | 410.4028 | 26724
32440 | 411.3526 | 26724
32441 | 411.7127 | 26724
32442 | 404.3287 | 26724
32443 | 420.709 | 26724
32444 | 427.2704 | 26724
32445 | 435.3371 | 26724
32446 | 415.5296 | 26724
32447 | 420.6954 | 26724
32448 | 429.2682 | 26724
32449 | 419.7593 | 26724
32450 | 415.6589 | 26724
32451 | 418.1092 | 26724
32452 | 408.4513 | 26724
32453 | 412.188 | 26724
32454 | 435.9424 | 26724
32455 | 415.6852 | 26724
32456 | 418.7334 | 26724
32457 | 417.5704 | 26724
32458 | 416.2794 | 26724
32459 | 432.6925 | 26724
32460 | 423.4622 | 26724
32461 | 422.1976 | 26724
32462 | 414.6361 | 26724
32463 | 422.1351 | 26724
32464 | 398.8303 | 26724
32465 | 426.5554 | 26724
32466 | 413.1176 | 26724
32467 | 424.0858 | 26724
32468 | 406.8416 | 26724
32469 | 406.4809 | 26724
32470 | 421.9853 | 26724
32471 | 434.437 | 26724
32472 | 414.047 | 26724
32473 | 418.0336 | 26724
32474 | 400.6078 | 26724
32475 | 412.6473 | 26724
32476 | 423.1417 | 26724
32477 | 429.5597 | 26724
32478 | 423.4608 | 26724
32479 | 412.0619 | 26724
32480 | 416.1297 | 26724
32481 | 423.0501 | 26724
32482 | 417.584 | 26724
32483 | 432.3536 | 26724
32484 | 411.522 | 26724
32485 | 414.4683 | 26724
32486 | 423.7853 | 26724
32487 | 419.1712 | 26724
32488 | 414.1016 | 26724
32489 | 420.7912 | 26724
32490 | 413.8393 | 26724
32491 | 416.4131 | 26724
32492 | 433.8182 | 26724
32493 | 418.3884 | 26724
32494 | 418.5997 | 26724
32495 | 424.0098 | 26724
32496 | 431.2577 | 26724
32497 | 413.9568 | 26724
32498 | 419.681 | 26724
32499 | 426.8491 | 26724
32500 | 410.9258 | 26724
32501 | 424.0026 | 26724
32502 | 415.1256 | 26724
32503 | 404.1173 | 26724
32504 | 428.8355 | 26724
32505 | 435.0915 | 26724
32506 | 412.1519 | 26724
32507 | 409.189 | 26724
32508 | 409.644 | 26724
32509 | 425.7809 | 26724
32510 | 422.574 | 26724
32511 | 426.2427 | 26724
32512 | 422.1655 | 26724
32513 | 425.2657 | 26724
32514 | 410.2369 | 26724
32515 | 414.6757 | 26724
32516 | 420.9669 | 26724
32517 | 424.1491 | 26724
32518 | 399.4035 | 26724
32519 | 416.5491 | 26724
32520 | 408.2761 | 26724
32521 | 427.4379 | 26724
32522 | 414.7071 | 26724
32523 | 417.2593 | 26724
32524 | 429.6263 | 26724
32525 | 402.9514 | 26724
32526 | 424.9112 | 26724
32527 | 417.0403 | 26724
32528 | 422.5383 | 26724
32529 | 402.642 | 26724
32530 | 417.6595 | 26724
32531 | 418.2966 | 26724
32532 | 421.2102 | 26724
32533 | 423.6395 | 26724
32534 | 423.5636 | 26724
32535 | 414.0733 | 26724
32536 | 413.4987 | 26724
32537 | 413.5032 | 26724
32538 | 430.1346 | 26724
32539 | 425.4927 | 26724
32540 | 406.8142 | 26724
32541 | 413.8291 | 26724
32542 | 426.4576 | 26724
32543 | 411.2037 | 26724
32544 | 410.1288 | 26724
32545 | 427.0397 | 26724
32546 | 407.6127 | 26724
32547 | 427.28 | 26724
32548 | 428.3407 | 26724
32549 | 414.5696 | 26724
32550 | 420.3522 | 26724
32551 | 415.8971 | 26724
32552 | 416.8729 | 26724
32553 | 415.124 | 26724
32554 | 406.5467 | 26724
32555 | 410.4686 | 26724
32556 | 418.871 | 26724
32557 | 412.3783 | 26724
32558 | 430.5005 | 26724
32559 | 418.1836 | 26724
32560 | 405.8688 | 26724
32561 | 424.3865 | 26724
32562 | 419.3307 | 26724
32563 | 403.0636 | 26724
32564 | 417.5943 | 26724
32565 | 417.4967 | 26724
32566 | 426.0328 | 26724
32567 | 423.098 | 26724
32568 | 413.121 | 26724
32569 | 423.5485 | 26724
32570 | 422.7709 | 26724
32571 | 418.634 | 26724
32572 | 424.163 | 26724
32573 | 424.798 | 26724
32574 | 404.52 | 26724
32575 | 410.0986 | 26724
32576 | 397.2585 | 26724
32577 | 404.4696 | 26724
32578 | 418.973 | 26724
32579 | 414.253 | 26724
32580 | 425.2074 | 26724
32581 | 417.9717 | 26724
32582 | 431.6929 | 26724
32583 | 421.114 | 26724
32584 | 425.195 | 26724
32585 | 415.0049 | 26724
32586 | 409.3154 | 26724
32587 | 417.4444 | 26724
32588 | 429.5076 | 26724
32589 | 421.9439 | 26724
32590 | 411.6979 | 26724
32591 | 434.1298 | 26724
32592 | 415.3834 | 26724
32593 | 426.0058 | 26724
32594 | 432.7973 | 26724
32595 | 410.3671 | 26724
32596 | 407.0091 | 26724
32597 | 419.5477 | 26724
32598 | 425.6835 | 26724
32599 | 398.0338 | 26724
32600 | 403.5911 | 26724
32601 | 409.2147 | 26724
32602 | 415.8977 | 26724
32603 | 410.0928 | 26724
32604 | 410.4137 | 26724
32605 | 420.7938 | 26724
32606 | 411.3889 | 26724
32607 | 409.0151 | 26724
32608 | 412.9558 | 26724
32609 | 426.1569 | 26724
32610 | 428.4971 | 26724
32611 | 423.5124 | 26724
32612 | 398.1987 | 26724
32613 | 412.5695 | 26724
32614 | 419.9161 | 26724
32615 | 414.4925 | 26724
32616 | 409.2964 | 26724
32617 | 402.9631 | 26724
32618 | 428.588 | 26724
32619 | 423.6274 | 26724
32620 | 417.2919 | 26724
32621 | 423.8491 | 26724
32622 | 411.0669 | 26724
32623 | 419.2938 | 26724
32624 | 415.237 | 26724
32625 | 428.6921 | 26724
32626 | 426.1655 | 26724
32627 | 412.534 | 26724
32628 | 428.7033 | 26724
32629 | 410.3944 | 26724
32630 | 424.6416 | 26724
32631 | 421.0999 | 26724
32632 | 419.7021 | 26724
32633 | 414.9291 | 26724
32634 | 428.0207 | 26724
32635 | 418.1914 | 26724
32636 | 415.7563 | 26724
32637 | 410.3727 | 26724
32638 | 406.9174 | 26724
32639 | 410.5127 | 26724
32640 | 419.4181 | 26724
32641 | 410.4732 | 26724
32642 | 408.9384 | 26724
32643 | 414.8162 | 26724
32644 | 409.0124 | 26724
32645 | 416.6072 | 26724
32646 | 421.7077 | 26724
32647 | 414.161 | 26724
32648 | 406.5083 | 26724
32649 | 421.6875 | 26724
32650 | 428.308 | 26724
32651 | 419.6117 | 26724
32652 | 421.3849 | 26724
32653 | 401.1941 | 26724
32654 | 398.671 | 26724
32655 | 415.8819 | 26724
32656 | 404.3915 | 26724
32657 | 412.1015 | 26724
32658 | 421.622 | 26724
32659 | 416.0426 | 26724
32660 | 418.2669 | 26724
32661 | 418.6676 | 26724
32662 | 421.2612 | 26724
32663 | 410.5263 | 26724
32664 | 407.1917 | 26724
32665 | 428.8161 | 26724
32666 | 416.6809 | 26724
32667 | 401.6401 | 26724
32668 | 427.3186 | 26724
32669 | 423.147 | 26724
32670 | 422.1221 | 26724
32671 | 429.2372 | 26724
32672 | 414.2369 | 26724
32673 | 412.0252 | 26724
32674 | 398.112 | 26724
32675 | 415.0967 | 26724
32676 | 408.6392 | 26724
32677 | 421.3134 | 26724
32678 | 409.9916 | 26724
32679 | 412.2617 | 26724
32680 | 432.0424 | 26724
32681 | 421.2473 | 26724
32682 | 423.9309 | 26724
32683 | 428.0869 | 26724
32684 | 407.3721 | 26724
32685 | 413.7375 | 26724
32686 | 419.8553 | 26724
32687 | 412.2411 | 26724
32688 | 420.8773 | 26724
32689 | 424.3078 | 26724
32690 | 424.0182 | 26724
32691 | 419.0136 | 26724
32692 | 413.365 | 26724
32693 | 414.6134 | 26724
32694 | 422.913 | 26724
32695 | 415.7387 | 26724
32696 | 420.7941 | 26724
32697 | 426.563 | 26724
32698 | 420.1887 | 26724
32699 | 432.3875 | 26724
32700 | 412.1905 | 26724
32701 | 417.7957 | 26724
32702 | 414.5431 | 26724
32703 | 402.4087 | 26724
32704 | 410.9255 | 26724
32705 | 421.4319 | 26724
32706 | 411.3869 | 26724
32707 | 419.9949 | 26724
32708 | 431.8879 | 26724
32709 | 421.4269 | 26724
32710 | 402.8296 | 26724
32711 | 412.7889 | 26724
32712 | 414.4614 | 26724
32713 | 422.3397 | 26724
32714 | 413.5142 | 26724
32715 | 432.7076 | 26724
32716 | 417.4867 | 26724
32717 | 427.3604 | 26724
32718 | 430.8127 | 26724
32719 | 403.8199 | 26724
32720 | 420.0021 | 26724
32721 | 408.2239 | 26724
32722 | 417.2054 | 26724
32723 | 403.3812 | 26724
32724 | 423.216 | 26724
32725 | 423.164 | 26724
32726 | 427.4148 | 26724
32727 | 426.0184 | 26724
32728 | 424.6608 | 26724
32729 | 407.5558 | 26724
32730 | 408.611 | 26724
32731 | 424.1958 | 26724
32732 | 425.1666 | 26724
32733 | 416.7263 | 26724
32734 | 410.8866 | 26724
32735 | 396.7422 | 26724
32736 | 417.4197 | 26724
32737 | 423.5939 | 26724
32738 | 416.1845 | 26724
32739 | 432.1537 | 26724
32740 | 406.0739 | 26724
32741 | 425.5389 | 26724
32742 | 414.1695 | 26724
32743 | 413.0801 | 26724
32744 | 407.8837 | 26724
32745 | 419.1874 | 26724
32746 | 427.5395 | 26724
32747 | 432.4168 | 26724
32748 | 428.7765 | 26724
32749 | 410.8611 | 26724
32750 | 416.707 | 26724
32751 | 424.6715 | 26724
32752 | 430.1082 | 26724
32753 | 429.0796 | 26724
32754 | 425.9514 | 26724
32755 | 426.2771 | 26724
32756 | 411.8536 | 26724
32757 | 410.0166 | 26724
32758 | 430.5174 | 26724
32759 | 419.3189 | 26724
32760 | 412.0278 | 26724
32761 | 414.4034 | 26724
32762 | 414.461 | 26724
32763 | 417.5214 | 26724
32764 | 416.9106 | 26724
32765 | 419.0634 | 26724
32766 | 438.9381 | 26724
32767 | 422.5914 | 26724
32768 | 432.9103 | 26724
32769 | 400.1062 | 26724
32770 | 423.8095 | 26724
32771 | 412.2543 | 26724
32772 | 400.929 | 26724
32773 | 427.3748 | 26724
32774 | 412.5511 | 26724
32775 | 418.9032 | 26724
32776 | 414.3098 | 26724
32777 | 400.7083 | 26724
32778 | 409.6591 | 26724
32779 | 420.2507 | 26724
32780 | 408.7771 | 26724
32781 | 414.4219 | 26724
32782 | 416.2211 | 26724
32783 | 410.7676 | 26724
32784 | 423.0841 | 26724
32785 | 408.9931 | 26724
32786 | 415.2887 | 26724
32787 | 417.8893 | 26724
32788 | 420.6974 | 26724
32789 | 414.0445 | 26724
32790 | 424.7711 | 26724
32791 | 421.7912 | 26724
32792 | 423.3338 | 26724
32793 | 419.1487 | 26724
32794 | 427.4421 | 26724
32795 | 399.7709 | 26724
32796 | 420.9495 | 26724
32797 | 407.7077 | 26724
32798 | 415.119 | 26724
32799 | 402.3802 | 26724
32800 | 400.7832 | 26724
32801 | 418.2685 | 26724
32802 | 432.341 | 26724
32803 | 420.8142 | 26724
32804 | 411.6479 | 26724
32805 | 421.4398 | 26724
32806 | 420.3689 | 26724
32807 | 419.1342 | 26724
32808 | 407.8899 | 26724
32809 | 405.8005 | 26724
32810 | 416.2867 | 26724
32811 | 400.4434 | 26724
32812 | 423.9691 | 26724
32813 | 419.0325 | 26724
32814 | 421.9161 | 26724
32815 | 415.5251 | 26724
32816 | 415.0523 | 26724
32817 | 415.9322 | 26724
32818 | 423.8117 | 26724
32819 | 430.3545 | 26724
32820 | 423.3128 | 26724
32821 | 426.4949 | 26724
32822 | 430.3683 | 26724
32823 | 422.919 | 26724
32824 | 405.6863 | 26724
32825 | 429.2938 | 26724
32826 | 435.9076 | 26724
32827 | 428.4684 | 26724
32828 | 415.6276 | 26724
32829 | 400.1493 | 26724
32830 | 413.7875 | 26724
32831 | 418.4869 | 26724
32832 | 408.0726 | 26724
32833 | 412.8298 | 26724
32834 | 428.3439 | 26724
32835 | 409.253 | 26724
32836 | 414.4236 | 26724
32837 | 433.1313 | 26724
32838 | 410.3826 | 26724
32839 | 417.86 | 26724
32840 | 417.501 | 26724
32841 | 411.0004 | 26724
32842 | 404.8575 | 26724
32843 | 411.0228 | 26724
32844 | 415.588 | 26724
32845 | 408.1099 | 26724
32846 | 410.5839 | 26724
32847 | 406.935 | 26724
32848 | 411.7072 | 26724
32849 | 410.6377 | 26724
32850 | 417.13 | 26724
32851 | 426.9309 | 26724
32852 | 412.3128 | 26724
32853 | 424.7927 | 26724
32854 | 420.591 | 26724
32855 | 422.6183 | 26724
32856 | 416.8084 | 26724
32857 | 424.5053 | 26724
32858 | 425.2722 | 26724
32859 | 409.5847 | 26724
32860 | 423.9366 | 26724
32861 | 410.0342 | 26724
32862 | 404.0636 | 26724
32863 | 420.8361 | 26724
32864 | 416.9917 | 26724
32865 | 410.9404 | 26724
32866 | 415.1564 | 26724
32867 | 406.4793 | 26724
32868 | 422.96 | 26724
32869 | 414.8929 | 26724
32870 | 423.526 | 26724
32871 | 416.3717 | 26724
32872 | 419.1878 | 26724
32873 | 416.0753 | 26724
32874 | 418.6179 | 26724
32875 | 421.6978 | 26724
32876 | 417.3083 | 26724
32877 | 406.0542 | 26724
32878 | 421.4142 | 26724
32879 | 423.9499 | 26724
32880 | 404.3027 | 26724
32881 | 407.9255 | 26724
32882 | 422.856 | 26724
32883 | 415.6904 | 26724
32884 | 424.7205 | 26724
32885 | 416.2367 | 26724
32886 | 408.0429 | 26724
32887 | 423.7507 | 26724
32888 | 422.8781 | 26724
32889 | 415.0693 | 26724
32890 | 416.0421 | 26724
32891 | 420.977 | 26724
32892 | 414.7377 | 26724
32893 | 416.5674 | 26724
32894 | 412.0609 | 26724
32895 | 405.8834 | 26724
32896 | 407.0953 | 26724
32897 | 433.9596 | 26724
32898 | 424.5934 | 26724
32899 | 414.255 | 26724
32900 | 409.1982 | 26724
32901 | 423.7691 | 26724
32902 | 409.2326 | 26724
32903 | 403.9444 | 26724
32904 | 417.895 | 26724
32905 | 398.9622 | 26724
32906 | 423.3534 | 26724
32907 | 415.8061 | 26724
32908 | 419.8635 | 26724
32909 | 413.317 | 26724
32910 | 415.9864 | 26724
32911 | 415.3804 | 26724
32912 | 422.7669 | 26724
32913 | 413.4071 | 26724
32914 | 423.1297 | 26724
32915 | 414.6432 | 26724
32916 | 427.6688 | 26724
32917 | 417.4816 | 26724
32918 | 412.1122 | 26724
32919 | 419.3179 | 26724
32920 | 430.6987 | 26724
32921 | 399.5163 | 26724
32922 | 419.7466 | 26724
32923 | 412.8732 | 26724
32924 | 422.7967 | 26724
32925 | 415.6143 | 26724
32926 | 413.8508 | 26724
32927 | 410.9902 | 26724
32928 | 422.8182 | 26724
32929 | 425.0618 | 26724
32930 | 419.8215 | 26724
32931 | 423.2703 | 26724
32932 | 419.3083 | 26724
32933 | 424.9502 | 26724
32934 | 422.3009 | 26724
32935 | 425.9978 | 26724
32936 | 425.2245 | 26724
32937 | 428.43 | 26724
32938 | 421.03 | 26724
32939 | 407.7463 | 26724
32940 | 413.3583 | 26724
32941 | 414.8675 | 26724
32942 | 419.1809 | 26724
32943 | 410.1263 | 26724
32944 | 422.7107 | 26724
32945 | 416.7376 | 26724
32946 | 434.6892 | 26724
32947 | 418.9298 | 26724
32948 | 433.8462 | 26724
32949 | 394.9282 | 26724
32950 | 422.228 | 26724
32951 | 404.5799 | 26724
32952 | 404.2918 | 26724
32953 | 431.0372 | 26724
32954 | 426.1201 | 26724
32955 | 407.0659 | 26724
32956 | 406.2181 | 26724
32957 | 430.4778 | 26724
32958 | 422.3465 | 26724
32959 | 407.4901 | 26724
32960 | 416.8293 | 26724
32961 | 417.4836 | 26724
32962 | 426.7285 | 26724
32963 | 420.5685 | 26724
32964 | 416.9208 | 26724
32965 | 420.845 | 26724
32966 | 423.1166 | 26724
32967 | 409.5178 | 26724
32968 | 419.3366 | 26724
32969 | 406.3216 | 26724
32970 | 410.7709 | 26724
32971 | 412.4014 | 26724
32972 | 425.7504 | 26724
32973 | 408.9845 | 26724
32974 | 407.6224 | 26724
32975 | 425.2519 | 26724
32976 | 418.5568 | 26724
32977 | 406.9834 | 26724
32978 | 415.0257 | 26724
32979 | 421.3294 | 26724
32980 | 428.0133 | 26724
32981 | 412.5136 | 26724
32982 | 410.3842 | 26724
32983 | 409.6786 | 26724
32984 | 410.3823 | 26724
32985 | 417.6626 | 26724
32986 | 428.257 | 26724
32987 | 405.1905 | 26724
32988 | 409.0767 | 26724
32989 | 406.4791 | 26724
32990 | 408.9517 | 26724
32991 | 417.8134 | 26724
32992 | 425.1317 | 26724
32993 | 413.3958 | 26724
32994 | 429.1296 | 26724
32995 | 417.7963 | 26724
32996 | 429.028 | 26724
32997 | 412.204 | 26724
32998 | 409.6975 | 26724
32999 | 414.2552 | 26724
33000 | 408.6788 | 26724
33001 | 415.6012 | 26724
33002 | 408.8087 | 26724
33003 | 398.7129 | 26724
33004 | 413.848 | 26724
33005 | 418.4408 | 26724
33006 | 409.2742 | 26724
33007 | 407.1101 | 26724
33008 | 424.8403 | 26724
33009 | 426.7759 | 26724
33010 | 404.1985 | 26724
33011 | 406.281 | 26724
33012 | 424.7969 | 26724
33013 | 412.8787 | 26724
33014 | 414.3113 | 26724
33015 | 419.2859 | 26724
33016 | 428.8251 | 26724
33017 | 420.2508 | 26724
33018 | 414.2018 | 26724
33019 | 410.4386 | 26724
33020 | 406.4252 | 26724
33021 | 427.2331 | 26724
33022 | 419.5928 | 26724
33023 | 422.6991 | 26724
33024 | 425.838 | 26724
33025 | 424.1307 | 26724
33026 | 405.7519 | 26724
33027 | 397.8829 | 26724
33028 | 412.7151 | 26724
33029 | 421.2494 | 26724
33030 | 415.854 | 26724
33031 | 407.317 | 26724
33032 | 422.3921 | 26724
33033 | 415.9423 | 26724
33034 | 404.9306 | 26724
33035 | 423.2338 | 26724
33036 | 423.4748 | 26724
33037 | 418.4059 | 26724
33038 | 415.8546 | 26724
33039 | 397.359 | 26724
33040 | 404.3371 | 26724
33041 | 434.6927 | 26724
33042 | 419.522 | 26724
33043 | 420.9731 | 26724
33044 | 419.6948 | 26724
33045 | 422.6248 | 26724
33046 | 420.9854 | 26724
33047 | 413.958 | 26724
33048 | 411.5931 | 26724
33049 | 418.9218 | 26724
33050 | 421.1628 | 26724
33051 | 419.6893 | 26724
33052 | 406.213 | 26724
33053 | 412.4874 | 26724
33054 | 419.9754 | 26724
33055 | 413.577 | 26724
33056 | 405.516 | 26724
33057 | 419.7197 | 26724
33058 | 399.342 | 26724
33059 | 429.576 | 26724
33060 | 425.2895 | 26724
33061 | 410.5552 | 26724
33062 | 420.8172 | 26724
33063 | 418.255 | 26724
33064 | 427.1111 | 26724
33065 | 409.6931 | 26724
33066 | 404.2447 | 26724
33067 | 428.5927 | 26724
33068 | 424.8601 | 26724
33069 | 407.1972 | 26724
33070 | 411.8382 | 26724
33071 | 435.6281 | 26724
33072 | 409.2959 | 26724
33073 | 432.5928 | 26724
33074 | 417.2303 | 26724
33075 | 412.9929 | 26724
33076 | 426.4572 | 26724
33077 | 424.6188 | 26724
33078 | 421.2227 | 26724
33079 | 429.1299 | 26724
33080 | 421.1652 | 26724
33081 | 425.8018 | 26724
33082 | 426.4176 | 26724
33083 | 412.5743 | 26724
33084 | 426.1193 | 26724
33085 | 415.2126 | 26724
33086 | 407.1385 | 26724
33087 | 414.4296 | 26724
33088 | 407.1419 | 26724
33089 | 415.3263 | 26724
33090 | 429.1415 | 26724
33091 | 421.6238 | 26724
33092 | 420.5124 | 26724
33093 | 421.6791 | 26724
33094 | 416.1644 | 26724
33095 | 430.9379 | 26724
33096 | 408.5193 | 26724
33097 | 411.3851 | 26724
33098 | 417.3432 | 26724
33099 | 424.3988 | 26724
33100 | 406.3391 | 26724
33101 | 420.7521 | 26724
33102 | 417.6006 | 26724
33103 | 410.3573 | 26724
33104 | 413.6426 | 26724
33105 | 401.4015 | 26724
33106 | 422.05 | 26724
33107 | 409.952 | 26724
33108 | 407.959 | 26724
33109 | 411.5723 | 26724
33110 | 408.8953 | 26724
33111 | 420.9645 | 26724
33112 | 408.2407 | 26724
33113 | 422.2652 | 26724
33114 | 415.7739 | 26724
33115 | 417.6311 | 26724
33116 | 412.4061 | 26724
33117 | 411.3708 | 26724
33118 | 419.238 | 26724
33119 | 418.6557 | 26724
33120 | 409.5266 | 26724
33121 | 423.2223 | 26724
33122 | 413.9546 | 26724
33123 | 408.9194 | 26724
33124 | 420.1885 | 26724
33125 | 425.4677 | 26724
33126 | 422.399 | 26724
33127 | 409.4184 | 26724
33128 | 416.1392 | 26724
33129 | 415.081 | 26724
33130 | 411.2485 | 26724
33131 | 417.171 | 26724
33132 | 425.1165 | 26724
33133 | 411.4684 | 26724
33134 | 425.5568 | 26724
33135 | 406.683 | 26724
33136 | 414.6999 | 26724
33137 | 413.493 | 26724
33138 | 424.2157 | 26724
33139 | 422.4839 | 26724
33140 | 432.0859 | 26724
33141 | 418.2183 | 26724
33142 | 422.0003 | 26724
33143 | 420.2957 | 26724
33144 | 411.0328 | 26724
33145 | 437.7368 | 26724
33146 | 415.3921 | 26724
33147 | 425.0374 | 26724
33148 | 403.5229 | 26724
33149 | 415.161 | 26724
33150 | 417.3134 | 26724
33151 | 405.5666 | 26724
33152 | 420.4293 | 26724
33153 | 411.0739 | 26724
33154 | 413.475 | 26724
33155 | 429.3051 | 26724
33156 | 418.048 | 26724
33157 | 409.2715 | 26724
33158 | 424.2285 | 26724
33159 | 423.2407 | 26724
33160 | 408.8766 | 26724
33161 | 418.8426 | 26724
33162 | 405.0962 | 26724
33163 | 421.4003 | 26724
33164 | 429.1649 | 26724
33165 | 421.7144 | 26724
33166 | 421.1037 | 26724
33167 | 402.5688 | 26724
33168 | 420.6656 | 26724
33169 | 414.8249 | 26724
33170 | 412.508 | 26724
33171 | 417.7117 | 26724
33172 | 422.7972 | 26724
33173 | 416.7639 | 26724
33174 | 411.5343 | 26724
33175 | 413.9429 | 26724
33176 | 406.6887 | 26724
33177 | 431.9654 | 26724
33178 | 419.9084 | 26724
33179 | 423.5429 | 26724
33180 | 418.0977 | 26724
33181 | 408.6724 | 26724
33182 | 400.5089 | 26724
33183 | 399.8152 | 26724
33184 | 423.967 | 26724
33185 | 429.4322 | 26724
33186 | 412.5685 | 26724
33187 | 421.7984 | 26724
33188 | 417.519 | 26724
33189 | 427.4139 | 26724
33190 | 423.4801 | 26724
33191 | 412.7658 | 26724
33192 | 415.7421 | 26724
33193 | 416.1969 | 26724
33194 | 421.088 | 26724
33195 | 415.8483 | 26724
33196 | 424.5244 | 26724
33197 | 417.7516 | 26724
33198 | 420.3393 | 26724
33199 | 420.3361 | 26724
33200 | 412.5367 | 26724
33201 | 409.35 | 26724
33202 | 416.7604 | 26724
33203 | 414.3248 | 26724
33204 | 410.5733 | 26724
33205 | 429.1536 | 26724
33206 | 423.7206 | 26724
33207 | 402.2615 | 26724
33208 | 432.9676 | 26724
33209 | 408.9979 | 26724
33210 | 411.1972 | 26724
33211 | 439.9354 | 26724
33212 | 407.5703 | 26724
33213 | 408.2792 | 26724
33214 | 410.3082 | 26724
33215 | 420.5175 | 26724
33216 | 412.0297 | 26724
33217 | 430.5877 | 26724
33218 | 430.566 | 26724
33219 | 424.7553 | 26724
33220 | 422.0422 | 26724
33221 | 417.1177 | 26724
33222 | 414.8147 | 26724
33223 | 417.2451 | 26724
33224 | 412.867 | 26724
33225 | 410.0472 | 26724
33226 | 416.4055 | 26724
33227 | 424.9892 | 26724
33228 | 431.0118 | 26724
33229 | 414.9593 | 26724
33230 | 404.8618 | 26724
33231 | 410.798 | 26724
33232 | 419.4114 | 26724
33233 | 420.6124 | 26724
33234 | 407.0021 | 26724
33235 | 418.5895 | 26724
33236 | 416.5168 | 26724
33237 | 417.4352 | 26724
33238 | 416.2089 | 26724
33239 | 416.477 | 26724
33240 | 398.5566 | 26724
33241 | 420.3254 | 26724
33242 | 427.3623 | 26724
33243 | 412.6777 | 26724
33244 | 416.4681 | 26724
33245 | 426.8646 | 26724
33246 | 404.503 | 26724
33247 | 416.4608 | 26724
33248 | 414.1162 | 26724
33249 | 419.6809 | 26724
33250 | 433.2131 | 26724
33251 | 432.9293 | 26724
33252 | 418.2129 | 26724
33253 | 407.3674 | 26724
33254 | 427.0952 | 26724
33255 | 406.4736 | 26724
33256 | 410.1229 | 26724
33257 | 422.9025 | 26724
33258 | 421.1864 | 26724
33259 | 425.571 | 26724
33260 | 411.1823 | 26724
33261 | 423.4239 | 26724
33262 | 419.6339 | 26724
33263 | 430.9514 | 26724
33264 | 410.6406 | 26724
33265 | 409.2713 | 26724
33266 | 408.7902 | 26724
33267 | 415.9697 | 26724
33268 | 405.3638 | 26724
33269 | 413.08 | 26724
33270 | 423.9611 | 26724
33271 | 407.064 | 26724
33272 | 403.2059 | 26724
33273 | 409.071 | 26724
33274 | 416.6832 | 26724
33275 | 409.5443 | 26724
33276 | 423.5862 | 26724
33277 | 420.9112 | 26724
33278 | 411.8844 | 26724
33279 | 421.2602 | 26724
33280 | 413.2172 | 26724
33281 | 416.7406 | 26724
33282 | 403.8445 | 26724
33283 | 409.2562 | 26724
33284 | 418.6703 | 26724
33285 | 406.8744 | 26724
33286 | 407.0185 | 26724
33287 | 429.803 | 26724
33288 | 410.737 | 26724
33289 | 419.2077 | 26724
33290 | 418.2861 | 26724
33291 | 413.9383 | 26724
33292 | 416.9363 | 26724
33293 | 412.0061 | 26724
33294 | 422.2801 | 26724
33295 | 414.6963 | 26724
33296 | 423.7625 | 26724
33297 | 411.7792 | 26724
33298 | 425.1932 | 26724
33299 | 428.1411 | 26724
33300 | 427.4005 | 26724
33301 | 403.5377 | 26724
33302 | 411.7991 | 26724
33303 | 406.9943 | 26724
33304 | 419.9437 | 26724
33305 | 423.5532 | 26724
33306 | 423.7322 | 26724
33307 | 424.8469 | 26724
33308 | 421.5057 | 26724
33309 | 404.8676 | 26724
33310 | 423.8536 | 26724
33311 | 418.2044 | 26724
33312 | 409.5113 | 26724
33313 | 415.1957 | 26724
33314 | 421.2253 | 26724
33315 | 398.4815 | 26724
33316 | 429.0405 | 26724
33317 | 401.6663 | 26724
33318 | 417.2342 | 26724
33319 | 425.2983 | 26724
33320 | 404.4948 | 26724
33321 | 424.9971 | 26724
33322 | 423.995 | 26724
33323 | 418.4647 | 26724
33324 | 410.979 | 26724
33325 | 429.2105 | 26724
33326 | 429.1686 | 26724
33327 | 413.3423 | 26724
33328 | 412.5282 | 26724
33329 | 428.6338 | 26724
33330 | 410.0455 | 26724
33331 | 411.5588 | 26724
33332 | 417.4429 | 26724
33333 | 405.1375 | 26724
33334 | 414.9121 | 26724
33335 | 419.2051 | 26724
33336 | 416.6348 | 26724
33337 | 413.2048 | 26724
33338 | 417.6496 | 26724
33339 | 424.2129 | 26724
33340 | 417.0016 | 26724
33341 | 424.0739 | 26724
33342 | 421.2446 | 26724
33343 | 423.0739 | 26724
33344 | 410.2899 | 26724
33345 | 402.0632 | 26724
33346 | 420.9823 | 26724
33347 | 415.4735 | 26724
33348 | 414.0995 | 26724
33349 | 411.7781 | 26724
33350 | 427.977 | 26724
33351 | 425.443 | 26724
33352 | 415.8214 | 26724
33353 | 403.8963 | 26724
33354 | 411.8714 | 26724
33355 | 419.4088 | 26724
33356 | 410.8253 | 26724
33357 | 417.9268 | 26724
33358 | 403.1254 | 26724
33359 | 417.8975 | 26724
33360 | 414.1706 | 26724
33361 | 417.3059 | 26724
33362 | 414.4009 | 26724
33363 | 407.6856 | 26724
33364 | 418.9168 | 26724
33365 | 408.584 | 26724
33366 | 420.1921 | 26724
33367 | 406.4987 | 26724
33368 | 408.9488 | 26724
33369 | 415.0849 | 26724
33370 | 408.7871 | 26724
33371 | 425.453 | 26724
33372 | 413.3 | 26724
33373 | 435.3231 | 26724
33374 | 426.1789 | 26724
33375 | 420.8744 | 26724
33376 | 419.4966 | 26724
33377 | 408.9661 | 26724
33378 | 411.5708 | 26724
33379 | 419.6047 | 26724
33380 | 426.2255 | 26724
33381 | 430.5211 | 26724
33382 | 396.2822 | 26724
33383 | 424.7594 | 26724
33384 | 418.5182 | 26724
33385 | 422.9141 | 26724
33386 | 406.0576 | 26724
33387 | 408.1144 | 26724
33388 | 420.9507 | 26724
33389 | 425.3648 | 26724
33390 | 416.7367 | 26724
33391 | 414.1367 | 26724
33392 | 430.7719 | 26724
33393 | 422.5329 | 26724
33394 | 410.1871 | 26724
33395 | 407.7964 | 26724
33396 | 407.8895 | 26724
33397 | 414.6076 | 26724
33398 | 404.211 | 26724
33399 | 422.2667 | 26724
33400 | 421.8041 | 26724
33401 | 425.7398 | 26724
33402 | 421.9687 | 26724
33403 | 418.9936 | 26724
33404 | 401.3274 | 26724
33405 | 400.5567 | 26724
33406 | 421.4608 | 26724
33407 | 414.4676 | 26724
33408 | 414.3441 | 26724
33409 | 408.8877 | 26724
33410 | 403.5918 | 26724
33411 | 408.2216 | 26724
33412 | 415.4807 | 26724
33413 | 410.6389 | 26724
33414 | 418.0225 | 26724
33415 | 419.2971 | 26724
33416 | 421.5093 | 26724
33417 | 396.5898 | 26724
33418 | 416.7946 | 26724
33419 | 407.2356 | 26724
33420 | 415.9715 | 26724
33421 | 424.6204 | 26724
33422 | 416.9598 | 26724
33423 | 416.7302 | 26724
33424 | 416.3834 | 26724
33425 | 415.0241 | 26724
33426 | 418.2293 | 26724
33427 | 418.8261 | 26724
33428 | 414.7338 | 26724
33429 | 412.1415 | 26724
33430 | 420.8649 | 26724
33431 | 422.1785 | 26724
33432 | 413.1894 | 26724
33433 | 408.7176 | 26724
33434 | 419.8514 | 26724
33435 | 402.9344 | 26724
33436 | 415.3742 | 26724
33437 | 410.4819 | 26724
33438 | 428.9432 | 26724
33439 | 420.2772 | 26724
33440 | 400.829 | 26724
33441 | 408.8726 | 26724
33442 | 428.9786 | 26724
33443 | 430.2629 | 26724
33444 | 417.3066 | 26724
33445 | 419.808 | 26724
33446 | 413.6229 | 26724
33447 | 409.8688 | 26724
33448 | 427.7881 | 26724
33449 | 401.745 | 26724
33450 | 425.4164 | 26724
33451 | 409.8216 | 26724
33452 | 423.4611 | 26724
33453 | 410.2847 | 26724
33454 | 427.7664 | 26724
33455 | 406.0659 | 26724
33456 | 435.9242 | 26724
33457 | 409.5341 | 26724
33458 | 413.4691 | 26724
33459 | 410.3412 | 26724
33460 | 418.0904 | 26724
33461 | 407.1599 | 26724
33462 | 423.387 | 26724
33463 | 410.6976 | 26724
33464 | 421.7876 | 26724
33465 | 405.7083 | 26724
33466 | 424.0687 | 26724
33467 | 408.6794 | 26724
33468 | 410.107 | 26724
33469 | 425.8721 | 26724
33470 | 419.7633 | 26724
33471 | 427.4529 | 26724
33472 | 430.6741 | 26724
33473 | 413.0055 | 26724
33474 | 425.7919 | 26724
33475 | 424.6716 | 26724
33476 | 419.9913 | 26724
33477 | 399.9213 | 26724
33478 | 411.0469 | 26724
33479 | 406.3232 | 26724
33480 | 423.696 | 26724
33481 | 419.6569 | 26724
33482 | 406.47 | 26724
33483 | 423.048 | 26724
33484 | 410.5812 | 26724
33485 | 418.997 | 26724
33486 | 420.3429 | 26724
33487 | 419.662 | 26724
33488 | 408.8631 | 26724
33489 | 425.0504 | 26724
33490 | 406.6384 | 26724
33491 | 427.5077 | 26724
33492 | 417.4691 | 26724
33493 | 432.3667 | 26724
33494 | 409.081 | 26724
33495 | 433.8235 | 26724
33496 | 402.7584 | 26724
33497 | 412.975 | 26724
33498 | 419.3901 | 26724
33499 | 410.0442 | 26724
33500 | 421.9898 | 26724
33501 | 419.5879 | 26724
33502 | 426.5598 | 26724
33503 | 408.0812 | 26724
33504 | 418.8584 | 26724
33505 | 416.4268 | 26724
33506 | 413.3656 | 26724
33507 | 417.6033 | 26724
33508 | 417.6931 | 26724
33509 | 414.8376 | 26724
33510 | 412.9685 | 26724
33511 | 408.5616 | 26724
33512 | 405.4369 | 26724
33513 | 413.5454 | 26724
33514 | 431.6334 | 26724
33515 | 407.0305 | 26724
33516 | 418.134 | 26724
33517 | 406.4947 | 26724
33518 | 416.9717 | 26724
33519 | 409.616 | 26724
33520 | 414.56 | 26724
33521 | 415.0419 | 26724
33522 | 407.6354 | 26724
33523 | 410.9332 | 26724
33524 | 418.4527 | 26724
33525 | 412.5003 | 26724
33526 | 414.9272 | 26724
33527 | 419.7361 | 26724
33528 | 401.2561 | 26724
33529 | 418.6097 | 26724
33530 | 412.9506 | 26724
33531 | 411.2662 | 26724
33532 | 412.335 | 26724
33533 | 425.5143 | 26724
33534 | 424.2349 | 26724
33535 | 428.0995 | 26724
33536 | 420.5692 | 26724
33537 | 415.0042 | 26724
33538 | 418.0179 | 26724
33539 | 413.6603 | 26724
33540 | 406.4098 | 26724
33541 | 416.0814 | 26724
33542 | 428.408 | 26724
33543 | 425.7069 | 26724
33544 | 408.9068 | 26724
33545 | 416.6072 | 26724
33546 | 428.9958 | 26724
33547 | 401.96 | 26724
33548 | 420.3942 | 26724
33549 | 421.017 | 26724
33550 | 422.0086 | 26724
33551 | 422.3384 | 26724
33552 | 404.7342 | 26724
33553 | 427.1867 | 26724
33554 | 413.5995 | 26724
33555 | 422.2149 | 26724
33556 | 411.8093 | 26724
33557 | 399.3063 | 26724
33558 | 426.9926 | 26724
33559 | 406.4422 | 26724
33560 | 411.7926 | 26724
33561 | 394.9785 | 26724
33562 | 401.473 | 26724
33563 | 421.6258 | 26724
33564 | 423.8112 | 26724
33565 | 414.6209 | 26724
33566 | 430.366 | 26724
33567 | 422.1273 | 26724
33568 | 398.1427 | 26724
33569 | 398.4017 | 26724
33570 | 428.8888 | 26724
33571 | 414.0599 | 26724
33572 | 405.6237 | 26724
33573 | 421.5662 | 26724
33574 | 423.5837 | 26724
33575 | 422.8785 | 26724
33576 | 396.9888 | 26724
33577 | 421.7757 | 26724
33578 | 405.1221 | 26724
33579 | 409.2967 | 26724
33580 | 415.9614 | 26724
33581 | 425.0014 | 26724
33582 | 425.0101 | 26724
33583 | 426.0617 | 26724
33584 | 414.1352 | 26724
33585 | 412.1108 | 26724
33586 | 430.6107 | 26724
33587 | 420.7758 | 26724
33588 | 413.8413 | 26724
33589 | 410.2341 | 26724
33590 | 416.9515 | 26724
33591 | 418.4719 | 26724
33592 | 416.1249 | 26724
33593 | 402.5212 | 26724
33594 | 422.4442 | 26724
33595 | 419.0786 | 26724
33596 | 430.7737 | 26724
33597 | 426.3244 | 26724
33598 | 409.8305 | 26724
33599 | 419.8912 | 26724
33600 | 412.6292 | 26724
33601 | 429.1611 | 26724
33602 | 421.4022 | 26724
33603 | 401.9906 | 26724
33604 | 425.9175 | 26724
33605 | 418.2357 | 26724
33606 | 414.3277 | 26724
33607 | 416.2944 | 26724
33608 | 416.3798 | 26724
33609 | 413.2281 | 26724
33610 | 419.2668 | 26724
33611 | 406.4446 | 26724
33612 | 434.1943 | 26724
33613 | 407.0049 | 26724
33614 | 414.6812 | 26724
33615 | 411.4273 | 26724
33616 | 421.6362 | 26724
33617 | 418.5751 | 26724
33618 | 413.743 | 26724
33619 | 426.5593 | 26724
33620 | 409.7251 | 26724
33621 | 409.6929 | 26724
33622 | 414.8472 | 26724
33623 | 409.5954 | 26724
33624 | 416.4022 | 26724
33625 | 412.967 | 26724
33626 | 407.6987 | 26724
33627 | 410.1931 | 26724
33628 | 409.3292 | 26724
33629 | 414.9644 | 26724
33630 | 414.5612 | 26724
33631 | 430.0965 | 26724
33632 | 420.7724 | 26724
33633 | 403.6088 | 26724
33634 | 409.1153 | 26724
33635 | 414.0402 | 26724
33636 | 420.0621 | 26724
33637 | 408.2864 | 26724
33638 | 429.6645 | 26724
33639 | 407.8579 | 26724
33640 | 410.1206 | 26724
33641 | 412.0856 | 26724
33642 | 409.9442 | 26724
33643 | 423.4266 | 26724
33644 | 417.2683 | 26724
33645 | 411.8088 | 26724
33646 | 426.3268 | 26724
33647 | 425.184 | 26724
33648 | 428.4609 | 26724
33649 | 424.2869 | 26724
33650 | 429.7418 | 26724
33651 | 411.9984 | 26724
33652 | 416.1858 | 26724
33653 | 417.5284 | 26724
33654 | 415.4639 | 26724
33655 | 422.2991 | 26724
33656 | 430.858 | 26724
33657 | 434.2622 | 26724
33658 | 413.7716 | 26724
33659 | 424.9041 | 26724
33660 | 419.3125 | 26724
33661 | 419.5077 | 26724
33662 | 418.8905 | 26724
33663 | 414.3286 | 26724
33664 | 411.6219 | 26724
33665 | 402.2288 | 26724
33666 | 410.3746 | 26724
33667 | 418.8833 | 26724
33668 | 409.5933 | 26724
33669 | 418.6181 | 26724
33670 | 415.991 | 26724
33671 | 411.1576 | 26724
33672 | 419.3143 | 26724
33673 | 413.1389 | 26724
33674 | 422.9547 | 26724
33675 | 417.0047 | 26724
33676 | 412.9566 | 26724
33677 | 411.236 | 26724
33678 | 425.9252 | 26724
33679 | 423.7202 | 26724
33680 | 415.999 | 26724
33681 | 397.3333 | 26724
33682 | 421.0117 | 26724
33683 | 428.7245 | 26724
33684 | 420.6255 | 26724
33685 | 415.3707 | 26724
33686 | 427.5372 | 26724
33687 | 406.7394 | 26724
33688 | 429.6322 | 26724
33689 | 414.4249 | 26724
33690 | 400.4827 | 26724
33691 | 424.1194 | 26724
33692 | 422.0324 | 26724
33693 | 409.7963 | 26724
33694 | 419.8698 | 26724
33695 | 426.2479 | 26724
33696 | 407.2309 | 26724
33697 | 420.7628 | 26724
33698 | 419.1042 | 26724
33699 | 404.9826 | 26724
33700 | 419.8078 | 26724
33701 | 408.1395 | 26724
33702 | 412.8584 | 26724
33703 | 424.9314 | 26724
33704 | 423.025 | 26724
33705 | 406.2908 | 26724
33706 | 416.911 | 26724
33707 | 416.2289 | 26724
33708 | 414.8537 | 26724
33709 | 412.8684 | 26724
33710 | 404.4608 | 26724
33711 | 405.1849 | 26724
33712 | 425.7511 | 26724
33713 | 431.1593 | 26724
33714 | 423.7711 | 26724
33715 | 421.087 | 26724
33716 | 430.8252 | 26724
33717 | 419.2352 | 26724
33718 | 404.1948 | 26724
33719 | 409.788 | 26724
33720 | 411.9539 | 26724
33721 | 410.0698 | 26724
33722 | 412.4327 | 26724
33723 | 407.9395 | 26724
33724 | 418.7609 | 26724
33725 | 429.6246 | 26724
33726 | 408.6439 | 26724
33727 | 423.0429 | 26724
33728 | 430.104 | 26724
33729 | 429.0389 | 26724
33730 | 411.6486 | 26724
33731 | 423.2498 | 26724
33732 | 406.3083 | 26724
33733 | 411.0994 | 26724
33734 | 411.4921 | 26724
33735 | 425.1117 | 26724
33736 | 406.4854 | 26724
33737 | 427.2973 | 26724
33738 | 426.0433 | 26724
33739 | 423.3975 | 26724
33740 | 423.0962 | 26724
33741 | 406.1525 | 26724
33742 | 413.13 | 26724
33743 | 405.156 | 26724
33744 | 399.9201 | 26724
33745 | 411.5529 | 26724
33746 | 405.0795 | 26724
33747 | 413.7291 | 26724
33748 | 420.3543 | 26724
33749 | 424.5305 | 26724
33750 | 423.8014 | 26724
33751 | 413.2652 | 26724
33752 | 419.9435 | 26724
33753 | 420.4615 | 26724
33754 | 400.3339 | 26724
33755 | 408.1704 | 26724
33756 | 427.2526 | 26724
33757 | 420.4901 | 26724
33758 | 410.7226 | 26724
33759 | 424.0716 | 26724
33760 | 412.5546 | 26724
33761 | 412.9251 | 26724
33762 | 430.6657 | 26724
33763 | 402.3663 | 26724
33764 | 417.5739 | 26724
33765 | 415.7154 | 26724
33766 | 417.503 | 26724
33767 | 414.8847 | 26724
33768 | 419.3035 | 26724
33769 | 411.0186 | 26724
33770 | 420.2739 | 26724
33771 | 435.9447 | 26724
33772 | 409.5651 | 26724
33773 | 408.5954 | 26724
33774 | 416.508 | 26724
33775 | 425.3689 | 26724
33776 | 420.1121 | 26724
33777 | 409.7593 | 26724
33778 | 418.2952 | 26724
33779 | 413.4977 | 26724
33780 | 437.7726 | 26724
33781 | 421.1817 | 26724
33782 | 396.8457 | 26724
33783 | 419.8136 | 26724
33784 | 404.6273 | 26724
33785 | 428.855 | 26724
33786 | 428.4191 | 26724
33787 | 413.1705 | 26724
33788 | 421.8478 | 26724
33789 | 412.8379 | 26724
33790 | 414.0171 | 26724
33791 | 428.8229 | 26724
33792 | 425.6014 | 26724
33793 | 415.4782 | 26724
33794 | 415.0712 | 26724
33795 | 408.9678 | 26724
33796 | 422.4487 | 26724
33797 | 410.1814 | 26724
33798 | 419.0399 | 26724
33799 | 421.1589 | 26724
33800 | 400.401 | 26724
33801 | 417.4081 | 26724
33802 | 409.8449 | 26724
33803 | 418.46 | 26724
33804 | 412.5084 | 26724
33805 | 419.0048 | 26724
33806 | 411.2172 | 26724
33807 | 422.4206 | 26724
33808 | 421.7371 | 26724
33809 | 415.2671 | 26724
33810 | 416.5329 | 26724
33811 | 423.064 | 26724
33812 | 428.8228 | 26724
33813 | 417.7898 | 26724
33814 | 418.4281 | 26724
33815 | 419.7877 | 26724
33816 | 416.4934 | 26724
33817 | 420.2237 | 26724
33818 | 413.9134 | 26724
33819 | 427.3326 | 26724
33820 | 418.5966 | 26724
33821 | 405.9227 | 26724
33822 | 412.8892 | 26724
33823 | 414.6096 | 26724
33824 | 423.2587 | 26724
33825 | 427.5881 | 26724
33826 | 402.7845 | 26724
33827 | 417.9156 | 26724
33828 | 421.4298 | 26724
33829 | 419.7821 | 26724
33830 | 410.6232 | 26724
33831 | 425.893 | 26724
33832 | 426.2476 | 26724
33833 | 404.3715 | 26724
33834 | 414.1326 | 26724
33835 | 418.3454 | 26724
33836 | 407.3179 | 26724
33837 | 420.1139 | 26724
33838 | 398.8493 | 26724
33839 | 411.5484 | 26724
33840 | 421.6232 | 26724
33841 | 407.0674 | 26724
33842 | 408.106 | 26724
33843 | 414.0311 | 26724
33844 | 420.679 | 26724
33845 | 416.0455 | 26724
33846 | 426.2669 | 26724
33847 | 420.76 | 26724
33848 | 414.7404 | 26724
33849 | 413.7677 | 26724
33850 | 415.068 | 26724
33851 | 409.1105 | 26724
33852 | 407.0542 | 26724
33853 | 433.083 | 26724
33854 | 419.7986 | 26724
33855 | 421.5491 | 26724
33856 | 405.3033 | 26724
33857 | 401.7541 | 26724
33858 | 415.8705 | 26724
33859 | 424.926 | 26724
33860 | 419.1551 | 26724
33861 | 422.8052 | 26724
33862 | 427.3695 | 26724
33863 | 409.6155 | 26724
33864 | 415.6875 | 26724
33865 | 409.4062 | 26724
33866 | 416.955 | 26724
33867 | 410.1702 | 26724
33868 | 426.4256 | 26724
33869 | 411.83 | 26724
33870 | 415.1594 | 26724
33871 | 409.585 | 26724
33872 | 425.3427 | 26724
33873 | 435.6941 | 26724
33874 | 417.651 | 26724
33875 | 400.1298 | 26724
33876 | 426.0075 | 26724
33877 | 414.1279 | 26724
33878 | 427.6798 | 26724
33879 | 404.488 | 26724
33880 | 402.4107 | 26724
33881 | 416.3197 | 26724
33882 | 421.1712 | 26724
33883 | 409.7989 | 26724
33884 | 412.8793 | 26724
33885 | 416.7141 | 26724
33886 | 415.8061 | 26724
33887 | 406.7921 | 26724
33888 | 405.1622 | 26724
33889 | 429.1354 | 26724
33890 | 423.046 | 26724
33891 | 418.1023 | 26724
33892 | 411.9959 | 26724
33893 | 402.9418 | 26724
33894 | 422.3373 | 26724
33895 | 417.9624 | 26724
33896 | 428.3449 | 26724
33897 | 421.4433 | 26724
33898 | 406.9064 | 26724
33899 | 427.2946 | 26724
33900 | 404.7007 | 26724
33901 | 422.0009 | 26724
33902 | 412.6169 | 26724
33903 | 415.3266 | 26724
33904 | 426.6856 | 26724
33905 | 408.206 | 26724
33906 | 418.2805 | 26724
33907 | 408.5515 | 26724
33908 | 408.2801 | 26724
33909 | 423.8201 | 26724
33910 | 406.8706 | 26724
33911 | 416.2829 | 26724
33912 | 418.9713 | 26724
33913 | 423.6509 | 26724
33914 | 420.2882 | 26724
33915 | 407.1938 | 26724
33916 | 427.4093 | 26724
33917 | 409.4751 | 26724
33918 | 412.5552 | 26724
33919 | 421.7699 | 26724
33920 | 410.5414 | 26724
33921 | 404.827 | 26724
33922 | 426.6878 | 26724
33923 | 423.0312 | 26724
33924 | 423.4003 | 26724
33925 | 425.6742 | 26724
33926 | 422.7413 | 26724
33927 | 411.8042 | 26724
33928 | 424.1905 | 26724
33929 | 407.5342 | 26724
33930 | 410.1701 | 26724
33931 | 413.1498 | 26724
33932 | 412.2684 | 26724
33933 | 410.2669 | 26724
33934 | 417.0889 | 26724
33935 | 424.2261 | 26724
33936 | 411.1396 | 26724
33937 | 402.2581 | 26724
33938 | 415.3845 | 26724
33939 | 417.4714 | 26724
33940 | 401.7996 | 26724
33941 | 411.6368 | 26724
33942 | 429.013 | 26724
33943 | 421.0089 | 26724
33944 | 427.2595 | 26724
33945 | 426.029 | 26724
33946 | 409.582 | 26724
33947 | 412.3564 | 26724
33948 | 423.468 | 26724
33949 | 425.8173 | 26724
33950 | 406.9965 | 26724
33951 | 420.7961 | 26724
33952 | 410.0491 | 26724
33953 | 405.2296 | 26724
33954 | 413.9383 | 26724
33955 | 438.0197 | 26724
33956 | 400.7913 | 26724
33957 | 423.1163 | 26724
33958 | 416.8628 | 26724
33959 | 417.3116 | 26724
33960 | 420.134 | 26724
33961 | 418.5941 | 26724
33962 | 416.2087 | 26724
33963 | 409.1148 | 26724
33964 | 399.4242 | 26724
33965 | 422.3801 | 26724
33966 | 423.8658 | 26724
33967 | 422.0081 | 26724
33968 | 412.1956 | 26724
33969 | 426.8838 | 26724
33970 | 409.6879 | 26724
33971 | 414.5692 | 26724
33972 | 416.0307 | 26724
33973 | 418.6111 | 26724
33974 | 423.6842 | 26724
33975 | 419.6439 | 26724
33976 | 421.6162 | 26724
33977 | 411.4643 | 26724
33978 | 409.7299 | 26724
33979 | 411.2063 | 26724
33980 | 423.6654 | 26724
33981 | 430.3924 | 26724
33982 | 412.9781 | 26724
33983 | 406.0657 | 26724
33984 | 410.9517 | 26724
33985 | 413.5204 | 26724
33986 | 420.0721 | 26724
33987 | 418.2155 | 26724
33988 | 405.2626 | 26724
33989 | 422.7262 | 26724
33990 | 410.6862 | 26724
33991 | 422.627 | 26724
33992 | 411.7749 | 26724
33993 | 426.3009 | 26724
33994 | 416.7125 | 26724
33995 | 419.5656 | 26724
33996 | 424.7726 | 26724
33997 | 415.8291 | 26724
33998 | 410.6646 | 26724
33999 | 424.2333 | 26724
34000 | 416.1145 | 26724
34001 | 426.6012 | 26724
34002 | 423.8915 | 26724
34003 | 422.2641 | 26724
34004 | 410.5082 | 26724
34005 | 410.1901 | 26724
34006 | 423.1102 | 26724
34007 | 417.7901 | 26724
34008 | 405.1184 | 26724
34009 | 408.7024 | 26724
34010 | 420.3044 | 26724
34011 | 421.3249 | 26724
34012 | 414.5304 | 26724
34013 | 431.7972 | 26724
34014 | 414.8434 | 26724
34015 | 423.3659 | 26724
34016 | 430.3429 | 26724
34017 | 418.8165 | 26724
34018 | 419.4463 | 26724
34019 | 417.9052 | 26724
34020 | 422.015 | 26724
34021 | 421.949 | 26724
34022 | 410.6632 | 26724
34023 | 429.5075 | 26724
34024 | 414.4988 | 26724
34025 | 416.6583 | 26724
34026 | 418.6917 | 26724
34027 | 429.8238 | 26724
34028 | 422.4746 | 26724
34029 | 432.9259 | 26724
34030 | 413.7837 | 26724
34031 | 421.0351 | 26724
34032 | 411.0758 | 26724
34033 | 411.9847 | 26724
34034 | 421.9336 | 26724
34035 | 401.7241 | 26724
34036 | 409.7575 | 26724
34037 | 404.9072 | 26724
34038 | 421.9983 | 26724
34039 | 417.5922 | 26724
34040 | 413.9505 | 26724
34041 | 408.3396 | 26724
34042 | 423.7519 | 26724
34043 | 414.0208 | 26724
34044 | 419.1894 | 26724
34045 | 414.3398 | 26724
34046 | 415.0908 | 26724
34047 | 425.1422 | 26724
34048 | 427.0628 | 26724
34049 | 415.5356 | 26724
34050 | 408.2127 | 26724
34051 | 409.2699 | 26724
34052 | 405.3842 | 26724
34053 | 418.2189 | 26724
34054 | 431.0967 | 26724
34055 | 418.7038 | 26724
34056 | 395.5009 | 26724
34057 | 407.8627 | 26724
34058 | 421.7812 | 26724
34059 | 416.7758 | 26724
34060 | 420.9451 | 26724
34061 | 428.1178 | 26724
34062 | 411.706 | 26724
34063 | 424.5615 | 26724
34064 | 419.6105 | 26724
34065 | 428.3504 | 26724
34066 | 418.0917 | 26724
34067 | 417.5367 | 26724
34068 | 427.8785 | 26724
34069 | 420.3912 | 26724
34070 | 419.9989 | 26724
34071 | 414.1844 | 26724
34072 | 412.343 | 26724
34073 | 409.121 | 26724
34074 | 419.5294 | 26724
34075 | 405.2085 | 26724
34076 | 427.6128 | 26724
34077 | 427.7862 | 26724
34078 | 413.3517 | 26724
34079 | 407.8714 | 26724
34080 | 419.3665 | 26724
34081 | 428.5428 | 26724
34082 | 412.0857 | 26724
34083 | 423.494 | 26724
34084 | 409.7507 | 26724
34085 | 407.5032 | 26724
34086 | 426.0075 | 26724
34087 | 425.5954 | 26724
34088 | 415.8384 | 26724
34089 | 428.7199 | 26724
34090 | 415.4313 | 26724
34091 | 411.3912 | 26724
34092 | 412.6303 | 26724
34093 | 425.5374 | 26724
34094 | 396.3243 | 26724
34095 | 417.17 | 26724
34096 | 423.5582 | 26724
34097 | 420.9325 | 26724
34098 | 428.4343 | 26724
34099 | 416.3874 | 26724
34100 | 423.161 | 26724
34101 | 410.9735 | 26724
34102 | 411.1006 | 26724
34103 | 415.2884 | 26724
34104 | 415.1916 | 26724
34105 | 406.1543 | 26724
34106 | 418.8764 | 26724
34107 | 415.2493 | 26724
34108 | 419.4867 | 26724
34109 | 419.8342 | 26724
34110 | 423.7423 | 26724
34111 | 426.8202 | 26724
34112 | 427.1701 | 26724
34113 | 414.6321 | 26724
34114 | 408.8508 | 26724
34115 | 413.1671 | 26724
34116 | 411.7507 | 26724
34117 | 413.502 | 26724
34118 | 402.4556 | 26724
34119 | 413.2849 | 26724
34120 | 413.7156 | 26724
34121 | 435.9326 | 26724
34122 | 410.0792 | 26724
34123 | 431.3399 | 26724
34124 | 415.7077 | 26724
34125 | 419.6427 | 26724
34126 | 412.6938 | 26724
34127 | 420.1331 | 26724
34128 | 406.5525 | 26724
34129 | 413.1622 | 26724
34130 | 417.4059 | 26724
34131 | 407.5362 | 26724
34132 | 409.2783 | 26724
34133 | 420.0442 | 26724
34134 | 403.6479 | 26724
34135 | 411.8894 | 26724
34136 | 401.3073 | 26724
34137 | 423.1191 | 26724
34138 | 440.1457 | 26724
34139 | 425.4528 | 26724
34140 | 430.0594 | 26724
34141 | 426.2027 | 26724
34142 | 404.6944 | 26724
34143 | 412.7617 | 26724
34144 | 410.7818 | 26724
34145 | 403.433 | 26724
34146 | 423.7437 | 26724
34147 | 411.9292 | 26724
34148 | 410.0869 | 26724
34149 | 397.0913 | 26724
34150 | 413.7834 | 26724
34151 | 406.0886 | 26724
34152 | 423.6193 | 26724
34153 | 414.2554 | 26724
34154 | 425.6938 | 26724
34155 | 407.0155 | 26724
34156 | 412.3299 | 26724
34157 | 420.2182 | 26724
34158 | 419.2037 | 26724
34159 | 434.8149 | 26724
34160 | 416.2375 | 26724
34161 | 412.8783 | 26724
34162 | 412.5164 | 26724
34163 | 423.9742 | 26724
34164 | 410.8453 | 26724
34165 | 403.8739 | 26724
34166 | 419.293 | 26724
34167 | 415.1178 | 26724
34168 | 419.0007 | 26724
34169 | 415.6559 | 26724
34170 | 422.5325 | 26724
34171 | 411.2986 | 26724
34172 | 419.6799 | 26724
34173 | 422.5663 | 26724
34174 | 422.5089 | 26724
34175 | 400.5437 | 26724
34176 | 407.4792 | 26724
34177 | 419.2505 | 26724
34178 | 409.2668 | 26724
34179 | 410.7022 | 26724
34180 | 420.9612 | 26724
34181 | 416.1163 | 26724
34182 | 407.2564 | 26724
34183 | 412.2938 | 26724
34184 | 419.2777 | 26724
34185 | 411.2122 | 26724
34186 | 401.6158 | 26724
34187 | 425.6203 | 26724
34188 | 419.9247 | 26724
34189 | 420.953 | 26724
34190 | 418.0005 | 26724
34191 | 417.0782 | 26724
34192 | 425.2069 | 26724
34193 | 424.3385 | 26724
34194 | 419.2598 | 26724
34195 | 423.1161 | 26724
34196 | 418.663 | 26724
34197 | 414.5466 | 26724
34198 | 420.5848 | 26724
34199 | 410.3937 | 26724
34200 | 421.3707 | 26724
34201 | 426.2672 | 26724
34202 | 418.1247 | 26724
34203 | 419.9452 | 26724
34204 | 418.1569 | 26724
34205 | 425.2778 | 26724
34206 | 412.9657 | 26724
34207 | 413.8613 | 26724
34208 | 421.0213 | 26724
34209 | 432.8051 | 26724
34210 | 428.646 | 26724
34211 | 410.0593 | 26724
34212 | 406.1296 | 26724
34213 | 406.4993 | 26724
34214 | 409.6929 | 26724
34215 | 433.6405 | 26724
34216 | 402.7784 | 26724
34217 | 414.841 | 26724
34218 | 406.9206 | 26724
34219 | 421.4994 | 26724
34220 | 412.4915 | 26724
34221 | 405.8957 | 26724
34222 | 405.3956 | 26724
34223 | 411.4693 | 26724
34224 | 412.5105 | 26724
34225 | 412.7003 | 26724
34226 | 422.5414 | 26724
34227 | 402.8044 | 26724
34228 | 417.2937 | 26724
34229 | 407.7981 | 26724
34230 | 414.8136 | 26724
34231 | 422.0036 | 26724
34232 | 404.6023 | 26724
34233 | 412.3424 | 26724
34234 | 415.4811 | 26724
34235 | 420.8448 | 26724
34236 | 428.1817 | 26724
34237 | 430.0971 | 26724
34238 | 410.3944 | 26724
34239 | 414.3292 | 26724
34240 | 422.7753 | 26724
34241 | 416.2693 | 26724
34242 | 399.005 | 26724
34243 | 430.4261 | 26724
34244 | 420.7053 | 26724
34245 | 415.3945 | 26724
34246 | 423.7114 | 26724
34247 | 413.1001 | 26724
34248 | 410.0215 | 26724
34249 | 415.2981 | 26724
34250 | 418.1167 | 26724
34251 | 436.1751 | 26724
34252 | 407.4974 | 26724
34253 | 425.6624 | 26724
34254 | 408.123 | 26724
34255 | 405.0345 | 26724
34256 | 418.9017 | 26724
34257 | 426.8752 | 26724
34258 | 404.1485 | 26724
34259 | 429.4136 | 26724
34260 | 416.7062 | 26724
34261 | 413.0208 | 26724
34262 | 414.7164 | 26724
34263 | 410.8795 | 26724
34264 | 406.1017 | 26724
34265 | 413.0856 | 26724
34266 | 420.0038 | 26724
34267 | 411.7125 | 26724
34268 | 426.6588 | 26724
34269 | 424.28 | 26724
34270 | 418.3395 | 26724
34271 | 404.5363 | 26724
34272 | 424.9021 | 26724
34273 | 418.2097 | 26724
34274 | 414.9388 | 26724
34275 | 409.897 | 26724
34276 | 412.2648 | 26724
34277 | 408.7949 | 26724
34278 | 413.8022 | 26724
34279 | 400.1477 | 26724
34280 | 418.6007 | 26724
34281 | 413.1347 | 26724
34282 | 412.0124 | 26724
34283 | 410.0538 | 26724
34284 | 413.1862 | 26724
34285 | 434.74 | 26724
34286 | 410.7103 | 26724
34287 | 432.5718 | 26724
34288 | 413.9859 | 26724
34289 | 418.268 | 26724
34290 | 421.5987 | 26724
34291 | 404.6403 | 26724
34292 | 422.397 | 26724
34293 | 421.5679 | 26724
34294 | 433.6898 | 26724
34295 | 408.7084 | 26724
34296 | 425.7429 | 26724
34297 | 413.785 | 26724
34298 | 404.3458 | 26724
34299 | 405.463 | 26724
34300 | 416.2856 | 26724
34301 | 407.5651 | 26724
34302 | 428.7664 | 26724
34303 | 411.1585 | 26724
34304 | 401.773 | 26724
34305 | 412.3205 | 26724
34306 | 410.2054 | 26724
34307 | 403.0163 | 26724
34308 | 416.2072 | 26724
34309 | 423.1335 | 26724
34310 | 412.0355 | 26724
34311 | 421.9323 | 26724
34312 | 412.1534 | 26724
34313 | 418.6865 | 26724
34314 | 415.3245 | 26724
34315 | 425.2205 | 26724
34316 | 404.6542 | 26724
34317 | 432.4916 | 26724
34318 | 413.037 | 26724
34319 | 420.4953 | 26724
34320 | 438.8766 | 26724
34321 | 414.4389 | 26724
34322 | 424.7406 | 26724
34323 | 407.7318 | 26724
34324 | 426.4388 | 26724
34325 | 407.8368 | 26724
34326 | 412.1633 | 26724
34327 | 417.027 | 26724
34328 | 410.5456 | 26724
34329 | 422.6934 | 26724
34330 | 406.3525 | 26724
34331 | 423.0779 | 26724
34332 | 413.6721 | 26724
34333 | 415.0798 | 26724
34334 | 404.7418 | 26724
34335 | 410.5272 | 26724
34336 | 402.163 | 26724
34337 | 407.8911 | 26724
34338 | 420.2224 | 26724
34339 | 421.3175 | 26724
34340 | 422.3265 | 26724
34341 | 419.3531 | 26724
34342 | 414.839 | 26724
34343 | 413.2925 | 26724
34344 | 416.5785 | 26724
34345 | 424.0623 | 26724
34346 | 422.6053 | 26724
34347 | 405.6548 | 26724
34348 | 421.259 | 26724
34349 | 406.5101 | 26724
34350 | 418.3527 | 26724
34351 | 421.0943 | 26724
34352 | 407.4333 | 26724
34353 | 427.3957 | 26724
34354 | 410.5798 | 26724
34355 | 422.9798 | 26724
34356 | 422.1695 | 26724
34357 | 419.9029 | 26724
34358 | 429.3218 | 26724
34359 | 397.9596 | 26724
34360 | 410.6125 | 26724
34361 | 409.2906 | 26724
34362 | 425.6883 | 26724
34363 | 400.0192 | 26724
34364 | 422.4652 | 26724
34365 | 423.6626 | 26724
34366 | 420.3431 | 26724
34367 | 420.1574 | 26724
34368 | 416.317 | 26724
34369 | 412.3207 | 26724
34370 | 402.8015 | 26724
34371 | 410.354 | 26724
34372 | 419.1526 | 26724
34373 | 413.5217 | 26724
34374 | 405.146 | 26724
34375 | 409.0771 | 26724
34376 | 412.0477 | 26724
34377 | 407.9942 | 26724
34378 | 419.7107 | 26724
34379 | 409.2237 | 26724
34380 | 424.4889 | 26724
34381 | 416.5522 | 26724
34382 | 403.8516 | 26724
34383 | 414.4997 | 26724
34384 | 415.8831 | 26724
34385 | 400.2851 | 26724
34386 | 417.1791 | 26724
34387 | 428.3312 | 26724
34388 | 424.3655 | 26724
34389 | 416.5339 | 26724
34390 | 407.0784 | 26724
34391 | 427.694 | 26724
34392 | 418.2559 | 26724
34393 | 423.9722 | 26724
34394 | 418.1026 | 26724
34395 | 437.4418 | 26724
34396 | 416.9174 | 26724
34397 | 413.043 | 26724
34398 | 422.204 | 26724
34399 | 423.6016 | 26724
34400 | 409.4305 | 26724
34401 | 402.6614 | 26724
34402 | 395.8901 | 26724
34403 | 415.9587 | 26724
34404 | 413.7137 | 26724
34405 | 411.8124 | 26724
34406 | 420.4613 | 26724
34407 | 400.8776 | 26724
34408 | 403.636 | 26724
34409 | 405.3118 | 26724
34410 | 413.8152 | 26724
34411 | 411.0921 | 26724
34412 | 408.0593 | 26724
34413 | 424.4862 | 26724
34414 | 420.1914 | 26724
34415 | 422.6049 | 26724
34416 | 409.5755 | 26724
34417 | 410.8113 | 26724
34418 | 416.709 | 26724
34419 | 422.0625 | 26724
34420 | 418.4607 | 26724
34421 | 413.6728 | 26724
34422 | 418.2936 | 26724
34423 | 422.3608 | 26724
34424 | 413.832 | 26724
34425 | 422.1974 | 26724
34426 | 413.0923 | 26724
34427 | 407.8008 | 26724
34428 | 411.6674 | 26724
34429 | 420.6565 | 26724
34430 | 418.841 | 26724
34431 | 415.4734 | 26724
34432 | 411.255 | 26724
34433 | 420.931 | 26724
34434 | 415.5194 | 26724
34435 | 405.5576 | 26724
34436 | 413.3874 | 26724
34437 | 418.1719 | 26724
34438 | 417.6666 | 26724
34439 | 415.7805 | 26724
34440 | 424.3048 | 26724
34441 | 423.2487 | 26724
34442 | 421.1245 | 26724
34443 | 410.4725 | 26724
34444 | 413.0073 | 26724
34445 | 415.3145 | 26724
34446 | 421.7234 | 26724
34447 | 414.4802 | 26724
34448 | 419.6239 | 26724
34449 | 420.1697 | 26724
34450 | 398.306 | 26724
34451 | 399.9327 | 26724
34452 | 404.9098 | 26724
34453 | 407.8224 | 26724
34454 | 411.3356 | 26724
34455 | 409.3379 | 26724
34456 | 415.2518 | 26724
34457 | 426.6563 | 26724
34458 | 397.2325 | 26724
34459 | 415.4071 | 26724
34460 | 399.386 | 26724
34461 | 397.804 | 26724
34462 | 423.1031 | 26724
34463 | 406.6668 | 26724
34464 | 415.7717 | 26724
34465 | 416.6511 | 26724
34466 | 424.7223 | 26724
34467 | 424.7044 | 26724
34468 | 412.4058 | 26724
34469 | 423.2207 | 26724
34470 | 413.5207 | 26724
34471 | 427.4253 | 26724
34472 | 414.6421 | 26724
34473 | 422.9043 | 26724
34474 | 414.9323 | 26724
34475 | 418.0818 | 26724
34476 | 420.78 | 26724
34477 | 435.1802 | 26724
34478 | 419.2772 | 26724
34479 | 405.2891 | 26724
34480 | 411.953 | 26724
34481 | 423.9653 | 26724
34482 | 407.8155 | 26724
34483 | 400.9804 | 26724
34484 | 421.652 | 26724
34485 | 413.6277 | 26724
34486 | 429.559 | 26724
34487 | 405.9919 | 26724
34488 | 420.7475 | 26724
34489 | 412.5207 | 26724
34490 | 421.0076 | 26724
34491 | 414.7705 | 26724
34492 | 403.8338 | 26724
34493 | 400.8473 | 26724
34494 | 414.7714 | 26724
34495 | 425.3741 | 26724
34496 | 414.8761 | 26724
34497 | 428.332 | 26724
34498 | 416.2058 | 26724
34499 | 414.6527 | 26724
34500 | 416.3644 | 26724
34501 | 417.909 | 26724
34502 | 425.0799 | 26724
34503 | 425.3872 | 26724
34504 | 413.0429 | 26724
34505 | 412.1582 | 26724
34506 | 423.6414 | 26724
34507 | 419.5199 | 26724
34508 | 418.0311 | 26724
34509 | 415.1758 | 26724
34510 | 415.9517 | 26724
34511 | 412.9142 | 26724
34512 | 423.1096 | 26724
34513 | 413.2331 | 26724
34514 | 406.5132 | 26724
34515 | 413.2503 | 26724
34516 | 410.9244 | 26724
34517 | 423.8192 | 26724
34518 | 420.0655 | 26724
34519 | 407.9043 | 26724
34520 | 416.8924 | 26724
34521 | 412.6521 | 26724
34522 | 412.866 | 26724
34523 | 401.55 | 26724
34524 | 409.6838 | 26724
34525 | 424.0186 | 26724
34526 | 421.4487 | 26724
34527 | 421.6203 | 26724
34528 | 399.5692 | 26724
34529 | 405.5895 | 26724
34530 | 410.9986 | 26724
34531 | 421.3047 | 26724
34532 | 416.5492 | 26724
34533 | 410.8323 | 26724
34534 | 399.5176 | 26724
34535 | 406.2326 | 26724
34536 | 421.2253 | 26724
34537 | 406.9416 | 26724
34538 | 415.5954 | 26724
34539 | 400.8806 | 26724
34540 | 407.7327 | 26724
34541 | 415.5197 | 26724
34542 | 403.078 | 26724
34543 | 420.7939 | 26724
34544 | 429.5062 | 26724
34545 | 418.0948 | 26724
34546 | 417.2117 | 26724
34547 | 423.0452 | 26724
34548 | 426.374 | 26724
34549 | 415.4039 | 26724
34550 | 435.4864 | 26724
34551 | 420.999 | 26724
34552 | 413.8969 | 26724
34553 | 427.495 | 26724
34554 | 420.1198 | 26724
34555 | 411.5549 | 26724
34556 | 419.701 | 26724
34557 | 420.0779 | 26724
34558 | 407.2722 | 26724
34559 | 406.6741 | 26724
34560 | 407.6944 | 26724
34561 | 412.6137 | 26724
34562 | 423.3382 | 26724
34563 | 419.1872 | 26724
34564 | 409.9942 | 26724
34565 | 413.4838 | 26724
34566 | 399.9497 | 26724
34567 | 414.852 | 26724
34568 | 414.5953 | 26724
34569 | 415.9965 | 26724
34570 | 434.2483 | 26724
34571 | 414.5704 | 26724
34572 | 419.9339 | 26724
34573 | 412.6812 | 26724
34574 | 409.4245 | 26724
34575 | 411.2445 | 26724
34576 | 409.542 | 26724
34577 | 419.4789 | 26724
34578 | 402.274 | 26724
34579 | 415.5266 | 26724
34580 | 419.9196 | 26724
34581 | 425.8245 | 26724
34582 | 421.3901 | 26724
34583 | 408.0459 | 26724
34584 | 407.1001 | 26724
34585 | 433.6491 | 26724
34586 | 428.3672 | 26724
34587 | 427.2138 | 26724
34588 | 420.5779 | 26724
34589 | 413.1545 | 26724
34590 | 418.3409 | 26724
34591 | 412.9037 | 26724
34592 | 424.6487 | 26724
34593 | 418.046 | 26724
34594 | 398.5394 | 26724
34595 | 421.3744 | 26724
34596 | 422.7682 | 26724
34597 | 421.049 | 26724
34598 | 407.0553 | 26724
34599 | 402.2548 | 26724
34600 | 402.692 | 26724
34601 | 408.6252 | 26724
34602 | 417.1369 | 26724
34603 | 414.2081 | 26724
34604 | 409.9394 | 26724
34605 | 418.3985 | 26724
34606 | 410.6317 | 26724
34607 | 409.7555 | 26724
34608 | 417.7117 | 26724
34609 | 427.3908 | 26724
34610 | 415.3658 | 26724
34611 | 413.2745 | 26724
34612 | 406.6371 | 26724
34613 | 421.1009 | 26724
34614 | 419.9185 | 26724
34615 | 413.0005 | 26724
34616 | 421.5443 | 26724
34617 | 415.1831 | 26724
34618 | 418.2169 | 26724
34619 | 410.1514 | 26724
34620 | 408.6657 | 26724
34621 | 425.0247 | 26724
34622 | 420.705 | 26724
34623 | 421.7433 | 26724
34624 | 407.7539 | 26724
34625 | 403.3935 | 26724
34626 | 411.8188 | 26724
34627 | 398.668 | 26724
34628 | 408.4758 | 26724
34629 | 400.0063 | 26724
34630 | 411.6069 | 26724
34631 | 427.3801 | 26724
34632 | 415.7515 | 26724
34633 | 412.9689 | 26724
34634 | 421.2463 | 26724
34635 | 416.7513 | 26724
34636 | 423.3874 | 26724
34637 | 417.561 | 26724
34638 | 402.2758 | 26724
34639 | 418.5265 | 26724
34640 | 412.1049 | 26724
34641 | 407.5775 | 26724
34642 | 415.7472 | 26724
34643 | 405.9538 | 26724
34644 | 416.3578 | 26724
34645 | 418.4066 | 26724
34646 | 410.324 | 26724
34647 | 413.027 | 26724
34648 | 414.3538 | 26724
34649 | 424.9224 | 26724
34650 | 405.134 | 26724
34651 | 408.2441 | 26724
34652 | 434.4848 | 26724
34653 | 422.8902 | 26724
34654 | 431.0296 | 26724
34655 | 419.5241 | 26724
34656 | 422.5662 | 26724
34657 | 435.3031 | 26724
34658 | 403.6835 | 26724
34659 | 430.1031 | 26724
34660 | 393.8341 | 26724
34661 | 402.5589 | 26724
34662 | 408.0867 | 26724
34663 | 412.8094 | 26724
34664 | 434.0973 | 26724
34665 | 409.4691 | 26724
34666 | 409.8795 | 26724
34667 | 417.0151 | 26724
34668 | 420.6189 | 26724
34669 | 410.0793 | 26724
34670 | 426.2111 | 26724
34671 | 403.6237 | 26724
34672 | 401.57 | 26724
34673 | 413.0333 | 26724
34674 | 410.1278 | 26724
34675 | 419.1221 | 26724
34676 | 410.4945 | 26724
34677 | 415.9332 | 26724
34678 | 437.4336 | 26724
34679 | 412.084 | 26724
34680 | 425.5064 | 26724
34681 | 409.3026 | 26724
34682 | 419.5252 | 26724
34683 | 423.5263 | 26724
34684 | 401.2028 | 26724
34685 | 416.8346 | 26724
34686 | 428.8423 | 26724
34687 | 413.8395 | 26724
34688 | 422.5238 | 26724
34689 | 419.0534 | 26724
34690 | 427.8624 | 26724
34691 | 422.1524 | 26724
34692 | 427.8573 | 26724
34693 | 408.6984 | 26724
34694 | 409.7157 | 26724
34695 | 403.9625 | 26724
34696 | 412.065 | 26724
34697 | 399.622 | 26724
34698 | 413.23 | 26724
34699 | 412.7963 | 26724
34700 | 422.2499 | 26724
34701 | 410.1219 | 26724
34702 | 409.9002 | 26724
34703 | 416.0651 | 26724
34704 | 430.1854 | 26724
34705 | 418.2955 | 26724
34706 | 413.9685 | 26724
34707 | 425.2108 | 26724
34708 | 424.0293 | 26724
34709 | 427.1463 | 26724
34710 | 410.837 | 26724
34711 | 415.7919 | 26724
34712 | 399.63 | 26724
34713 | 420.1276 | 26724
34714 | 416.6827 | 26724
34715 | 417.6368 | 26724
34716 | 413.8316 | 26724
34717 | 412.0064 | 26724
34718 | 435.1803 | 26724
34719 | 423.8741 | 26724
34720 | 411.9513 | 26724
34721 | 413.848 | 26724
34722 | 413.8753 | 26724
34723 | 404.4603 | 26724
34724 | 430.6676 | 26724
34725 | 420.1027 | 26724
34726 | 436.4315 | 26724
34727 | 408.0067 | 26724
34728 | 411.4736 | 26724
34729 | 422.6377 | 26724
34730 | 421.3671 | 26724
34731 | 411.3768 | 26724
34732 | 422.0718 | 26724
34733 | 417.3066 | 26724
34734 | 417.0624 | 26724
34735 | 431.3086 | 26724
34736 | 405.0684 | 26724
34737 | 428.4153 | 26724
34738 | 413.317 | 26724
34739 | 420.7413 | 26724
34740 | 432.436 | 26724
34741 | 410.2403 | 26724
34742 | 418.2192 | 26724
34743 | 431.3153 | 26724
34744 | 420.2629 | 26724
34745 | 414.4517 | 26724
34746 | 424.9569 | 26724
34747 | 424.766 | 26724
34748 | 427.3903 | 26724
34749 | 420.4858 | 26724
34750 | 417.3841 | 26724
34751 | 416.4846 | 26724
34752 | 420.3784 | 26724
34753 | 427.0279 | 26724
34754 | 421.4862 | 26724
34755 | 414.8742 | 26724
34756 | 419.269 | 26724
34757 | 408.8862 | 26724
34758 | 415.784 | 26724
34759 | 424.3982 | 26724
34760 | 410.9425 | 26724
34761 | 416.9722 | 26724
34762 | 404.5997 | 26724
34763 | 423.2997 | 26724
34764 | 424.2721 | 26724
34765 | 415.4284 | 26724
34766 | 406.7326 | 26724
34767 | 404.4249 | 26724
34768 | 411.4509 | 26724
34769 | 418.3748 | 26724
34770 | 416.4268 | 26724
34771 | 423.676 | 26724
34772 | 426.5953 | 26724
34773 | 408.9045 | 26724
34774 | 416.8671 | 26724
34775 | 424.808 | 26724
34776 | 423.4398 | 26724
34777 | 401.3359 | 26724
34778 | 416.4253 | 26724
34779 | 411.9806 | 26724
34780 | 406.6344 | 26724
34781 | 417.0145 | 26724
34782 | 410.0305 | 26724
34783 | 411.5812 | 26724
34784 | 410.2747 | 26724
34785 | 402.0506 | 26724
34786 | 408.7607 | 26724
34787 | 410.6054 | 26724
34788 | 419.3192 | 26724
34789 | 414.8288 | 26724
34790 | 418.8941 | 26724
34791 | 422.4337 | 26724
34792 | 426.0694 | 26724
34793 | 407.5365 | 26724
34794 | 411.8775 | 26724
34795 | 426.3683 | 26724
34796 | 421.807 | 26724
34797 | 421.0116 | 26724
34798 | 403.0501 | 26724
34799 | 425.4719 | 26724
34800 | 409.8022 | 26724
34801 | 414.9516 | 26724
34802 | 420.5936 | 26724
34803 | 417.9961 | 26724
34804 | 414.0668 | 26724
34805 | 423.673 | 26724
34806 | 414.2539 | 26724
34807 | 425.4172 | 26724
34808 | 432.5894 | 26724
34809 | 405.625 | 26724
34810 | 408.8008 | 26724
34811 | 415.5255 | 26724
34812 | 406.8107 | 26724
34813 | 417.9293 | 26724
34814 | 417.4549 | 26724
34815 | 412.15 | 26724
34816 | 428.7322 | 26724
34817 | 422.7714 | 26724
34818 | 430.7342 | 26724
34819 | 404.9855 | 26724
34820 | 418.4596 | 26724
34821 | 414.0217 | 26724
34822 | 425.9829 | 26724
34823 | 405.4406 | 26724
34824 | 413.7408 | 26724
34825 | 414.2678 | 26724
34826 | 422.3225 | 26724
34827 | 414.0057 | 26724
34828 | 408.9626 | 26724
34829 | 397.5908 | 26724
34830 | 418.0126 | 26724
34831 | 421.9653 | 26724
34832 | 415.2914 | 26724
34833 | 422.9452 | 26724
34834 | 418.3326 | 26724
34835 | 419.7617 | 26724
34836 | 419.3404 | 26724
34837 | 413.2345 | 26724
34838 | 414.2889 | 26724
34839 | 414.8649 | 26724
34840 | 416.1527 | 26724
34841 | 420.2417 | 26724
34842 | 414.3507 | 26724
34843 | 413.1349 | 26724
34844 | 406.6424 | 26724
34845 | 432.9372 | 26724
34846 | 427.6617 | 26724
34847 | 408.1167 | 26724
34848 | 405.3739 | 26724
34849 | 413.0029 | 26724
34850 | 427.4797 | 26724
34851 | 436.2611 | 26724
34852 | 412.9912 | 26724
34853 | 417.4301 | 26724
34854 | 416.4822 | 26724
34855 | 413.1731 | 26724
34856 | 406.9466 | 26724
34857 | 406.9856 | 26724
34858 | 419.1851 | 26724
34859 | 419.5704 | 26724
34860 | 402.6623 | 26724
34861 | 404.4968 | 26724
34862 | 424.9881 | 26724
34863 | 420.6809 | 26724
34864 | 431.1178 | 26724
34865 | 424.1512 | 26724
34866 | 411.1164 | 26724
34867 | 423.936 | 26724
34868 | 424.0247 | 26724
34869 | 402.8334 | 26724
34870 | 420.8515 | 26724
34871 | 418.1228 | 26724
34872 | 406.7718 | 26724
34873 | 430.8135 | 26724
34874 | 410.5571 | 26724
34875 | 422.4641 | 26724
34876 | 412.5399 | 26724
34877 | 422.7909 | 26724
34878 | 418.025 | 26724
34879 | 418.67 | 26724
34880 | 409.4888 | 26724
34881 | 411.9959 | 26724
34882 | 412.6125 | 26724
34883 | 408.1267 | 26724
34884 | 420.4124 | 26724
34885 | 421.9211 | 26724
34886 | 411.0887 | 26724
34887 | 421.5433 | 26724
34888 | 429.0122 | 26724
34889 | 418.7952 | 26724
34890 | 422.4367 | 26724
34891 | 404.028 | 26724
34892 | 418.8982 | 26724
34893 | 420.3573 | 26724
34894 | 404.3139 | 26724
34895 | 408.6029 | 26724
34896 | 419.0239 | 26724
34897 | 414.0169 | 26724
34898 | 405.8727 | 26724
34899 | 416.8597 | 26724
34900 | 413.9704 | 26724
34901 | 418.143 | 26724
34902 | 411.5403 | 26724
34903 | 423.0229 | 26724
34904 | 412.8042 | 26724
34905 | 415.5356 | 26724
34906 | 402.395 | 26724
34907 | 417.4403 | 26724
34908 | 402.9484 | 26724
34909 | 415.9176 | 26724
34910 | 403.9348 | 26724
34911 | 415.2293 | 26724
34912 | 412.0641 | 26724
34913 | 407.2598 | 26724
34914 | 420.1635 | 26724
34915 | 424.7547 | 26724
34916 | 430.1279 | 26724
34917 | 427.5714 | 26724
34918 | 415.4536 | 26724
34919 | 421.3518 | 26724
34920 | 398.6898 | 26724
34921 | 410.7158 | 26724
34922 | 421.2586 | 26724
34923 | 427.8892 | 26724
34924 | 413.8847 | 26724
34925 | 429.3258 | 26724
34926 | 420.5362 | 26724
34927 | 410.7291 | 26724
34928 | 405.7562 | 26724
34929 | 411.7613 | 26724
34930 | 419.3161 | 26724
34931 | 421.419 | 26724
34932 | 424.7588 | 26724
34933 | 414.363 | 26724
34934 | 411.1375 | 26724
34935 | 407.6924 | 26724
34936 | 409.5326 | 26724
34937 | 405.4953 | 26724
34938 | 421.7917 | 26724
34939 | 424.1313 | 26724
34940 | 411.8204 | 26724
34941 | 405.4859 | 26724
34942 | 407.2113 | 26724
34943 | 417.6163 | 26724
34944 | 421.8849 | 26724
34945 | 412.6395 | 26724
34946 | 421.2369 | 26724
34947 | 411.8714 | 26724
34948 | 408.74 | 26724
34949 | 409.0504 | 26724
34950 | 421.4521 | 26724
34951 | 400.1926 | 26724
34952 | 411.4474 | 26724
34953 | 407.3748 | 26724
34954 | 432.3428 | 26724
34955 | 412.901 | 26724
34956 | 420.829 | 26724
34957 | 417.795 | 26724
34958 | 413.3927 | 26724
34959 | 412.1054 | 26724
34960 | 419.0728 | 26724
34961 | 418.6539 | 26724
34962 | 432.5269 | 26724
34963 | 420.568 | 26724
34964 | 415.1138 | 26724
34965 | 431.5355 | 26724
34966 | 422.4615 | 26724
34967 | 422.917 | 26724
34968 | 415.9331 | 26724
34969 | 422.8802 | 26724
34970 | 421.245 | 26724
34971 | 417.6017 | 26724
34972 | 406.2134 | 26724
34973 | 413.9371 | 26724
34974 | 419.5447 | 26724
34975 | 421.541 | 26724
34976 | 408.0479 | 26724
34977 | 423.4371 | 26724
34978 | 423.2591 | 26724
34979 | 418.2203 | 26724
34980 | 415.6366 | 26724
34981 | 428.0364 | 26724
34982 | 405.2201 | 26724
34983 | 410.4636 | 26724
34984 | 419.5774 | 26724
34985 | 422.2403 | 26724
34986 | 430.7023 | 26724
34987 | 410.8946 | 26724
34988 | 397.8379 | 26724
34989 | 426.5218 | 26724
34990 | 426.839 | 26724
34991 | 406.7115 | 26724
34992 | 427.4774 | 26724
34993 | 407.1392 | 26724
34994 | 412.0856 | 26724
34995 | 430.2225 | 26724
34996 | 420.1852 | 26724
34997 | 414.4977 | 26724
34998 | 418.7263 | 26724
34999 | 410.7982 | 26724
35000 | 409.5239 | 26724
35001 | 410.3042 | 26724
35002 | 405.853 | 26724
35003 | 422.7954 | 26724
35004 | 412.7175 | 26724
35005 | 410.7882 | 26724
35006 | 425.9623 | 26724
35007 | 409.9621 | 26724
35008 | 422.0853 | 26724
35009 | 407.0579 | 26724
35010 | 424.1741 | 26724
35011 | 423.0422 | 26724
35012 | 426.0952 | 26724
35013 | 408.384 | 26724
35014 | 418.8494 | 26724
35015 | 421.3295 | 26724
35016 | 413.9099 | 26724
35017 | 411.4841 | 26724
35018 | 422.54 | 26724
35019 | 426.9162 | 26724
35020 | 425.3095 | 26724
35021 | 433.6196 | 26724
35022 | 413.8832 | 26724
35023 | 414.5344 | 26724
35024 | 421.1663 | 26724
35025 | 405.738 | 26724
35026 | 414.2251 | 26724
35027 | 418.8078 | 26724
35028 | 403.1294 | 26724
35029 | 409.736 | 26724
35030 | 408.7503 | 26724
35031 | 419.9257 | 26724
35032 | 425.7636 | 26724
35033 | 402.0764 | 26724
35034 | 412.0557 | 26724
35035 | 416.5541 | 26724
35036 | 405.0727 | 26724
35037 | 432.1632 | 26724
35038 | 405.3215 | 26724
35039 | 422.8097 | 26724
35040 | 416.2605 | 26724
35041 | 413.2885 | 26724
35042 | 415.8847 | 26724
35043 | 425.4304 | 26724
35044 | 415.2107 | 26724
35045 | 421.5856 | 26724
35046 | 430.5349 | 26724
35047 | 416.6733 | 26724
35048 | 417.5943 | 26724
35049 | 409.9674 | 26724
35050 | 414.8646 | 26724
35051 | 412.0209 | 26724
35052 | 416.7076 | 26724
35053 | 408.4431 | 26724
35054 | 428.4012 | 26724
35055 | 411.8444 | 26724
35056 | 414.6782 | 26724
35057 | 414.6089 | 26724
35058 | 423.9503 | 26724
35059 | 421.1059 | 26724
35060 | 426.8776 | 26724
35061 | 417.4754 | 26724
35062 | 406.9922 | 26724
35063 | 418.9133 | 26724
35064 | 415.3573 | 26724
35065 | 408.0852 | 26724
35066 | 423.4526 | 26724
35067 | 404.4916 | 26724
35068 | 409.0233 | 26724
35069 | 409.3093 | 26724
35070 | 424.2643 | 26724
35071 | 415.4805 | 26724
35072 | 422.6505 | 26724
35073 | 414.6769 | 26724
35074 | 416.5716 | 26724
35075 | 410.892 | 26724
35076 | 409.9355 | 26724
35077 | 416.8975 | 26724
35078 | 413.3838 | 26724
35079 | 414.8213 | 26724
35080 | 415.735 | 26724
35081 | 418.5193 | 26724
35082 | 425.1327 | 26724
35083 | 418.3209 | 26724
35084 | 421.5675 | 26724
35085 | 402.6522 | 26724
35086 | 413.8867 | 26724
35087 | 409.6848 | 26724
35088 | 422.5989 | 26724
35089 | 433.0906 | 26724
35090 | 404.983 | 26724
35091 | 426.7204 | 26724
35092 | 398.6901 | 26724
35093 | 414.7611 | 26724
35094 | 416.8207 | 26724
35095 | 411.2165 | 26724
35096 | 425.7746 | 26724
35097 | 413.3694 | 26724
35098 | 402.5435 | 26724
35099 | 415.349 | 26724
35100 | 411.3975 | 26724
35101 | 418.5272 | 26724
35102 | 411.0321 | 26724
35103 | 406.0126 | 26724
35104 | 416.6557 | 26724
35105 | 427.546 | 26724
35106 | 427.813 | 26724
35107 | 435.5064 | 26724
35108 | 426.7214 | 26724
35109 | 421.4889 | 26724
35110 | 414.4521 | 26724
35111 | 412.6805 | 26724
35112 | 414.525 | 26724
35113 | 406.1778 | 26724
35114 | 413.647 | 26724
35115 | 426.7572 | 26724
35116 | 419.9919 | 26724
35117 | 408.2957 | 26724
35118 | 433.6601 | 26724
35119 | 418.0522 | 26724
35120 | 417.3333 | 26724
35121 | 413.5076 | 26724
35122 | 426.8938 | 26724
35123 | 400.2948 | 26724
35124 | 423.8057 | 26724
35125 | 422.205 | 26724
35126 | 420.4361 | 26724
35127 | 418.9011 | 26724
35128 | 422.3712 | 26724
35129 | 418.5219 | 26724
35130 | 411.849 | 26724
35131 | 414.0275 | 26724
35132 | 421.074 | 26724
35133 | 416.5477 | 26724
35134 | 421.4674 | 26724
35135 | 411.3974 | 26724
35136 | 416.2387 | 26724
35137 | 409.1685 | 26724
35138 | 417.0539 | 26724
35139 | 414.3736 | 26724
35140 | 418.2933 | 26724
35141 | 431.8558 | 26724
35142 | 414.6781 | 26724
35143 | 419.1885 | 26724
35144 | 402.9664 | 26724
35145 | 423.7002 | 26724
35146 | 421.9498 | 26724
35147 | 428.9242 | 26724
35148 | 413.9239 | 26724
35149 | 406.4309 | 26724
35150 | 407.6554 | 26724
35151 | 425.7597 | 26724
35152 | 408.9862 | 26724
35153 | 420.2451 | 26724
35154 | 417.7996 | 26724
35155 | 422.1026 | 26724
35156 | 407.4359 | 26724
35157 | 424.5687 | 26724
35158 | 423.3364 | 26724
35159 | 422.0541 | 26724
35160 | 401.1856 | 26724
35161 | 414.7191 | 26724
35162 | 414.9056 | 26724
35163 | 420.0123 | 26724
35164 | 418.6838 | 26724
35165 | 398.2727 | 26724
35166 | 413.8921 | 26724
35167 | 422.101 | 26724
35168 | 416.3862 | 26724
35169 | 412.505 | 26724
35170 | 408.8674 | 26724
35171 | 421.5639 | 26724
35172 | 419.537 | 26724
35173 | 414.2897 | 26724
35174 | 424.4935 | 26724
35175 | 414.1073 | 26724
35176 | 436.3066 | 26724
35177 | 427.5621 | 26724
35178 | 415.2485 | 26724
35179 | 423.8862 | 26724
35180 | 433.1155 | 26724
35181 | 416.3478 | 26724
35182 | 407.1075 | 26724
35183 | 420.486 | 26724
35184 | 434.8299 | 26724
35185 | 413.6418 | 26724
35186 | 419.2687 | 26724
35187 | 411.236 | 26724
35188 | 417.8797 | 26724
35189 | 420.6527 | 26724
35190 | 425.9046 | 26724
35191 | 422.8571 | 26724
35192 | 422.9162 | 26724
35193 | 431.5325 | 26724
35194 | 421.1446 | 26724
35195 | 406.856 | 26724
35196 | 398.8566 | 26724
35197 | 423.8807 | 26724
35198 | 409.9654 | 26724
35199 | 405.4637 | 26724
35200 | 419.2849 | 26724
35201 | 415.6006 | 26724
35202 | 413.8645 | 26724
35203 | 410.4041 | 26724
35204 | 422.6489 | 26724
35205 | 418.4963 | 26724
35206 | 411.9219 | 26724
35207 | 423.992 | 26724
35208 | 411.3351 | 26724
35209 | 426.171 | 26724
35210 | 414.4353 | 26724
35211 | 417.35 | 26724
35212 | 422.6706 | 26724
35213 | 411.6999 | 26724
35214 | 416.3846 | 26724
35215 | 416.7795 | 26724
35216 | 413.7915 | 26724
35217 | 422.7058 | 26724
35218 | 411.4733 | 26724
35219 | 419.4931 | 26724
35220 | 407.3571 | 26724
35221 | 411.469 | 26724
35222 | 421.4997 | 26724
35223 | 425.9197 | 26724
35224 | 403.6035 | 26724
35225 | 420.1114 | 26724
35226 | 412.9209 | 26724
35227 | 435.3921 | 26724
35228 | 423.8614 | 26724
35229 | 422.843 | 26724
35230 | 430.7838 | 26724
35231 | 416.96 | 26724
35232 | 415.6692 | 26724
35233 | 415.861 | 26724
35234 | 427.0945 | 26724
35235 | 406.3275 | 26724
35236 | 412.0094 | 26724
35237 | 415.2693 | 26724
35238 | 413.0773 | 26724
35239 | 413.5951 | 26724
35240 | 412.1695 | 26724
35241 | 412.2635 | 26724
35242 | 420.101 | 26724
35243 | 414.6061 | 26724
35244 | 413.5021 | 26724
35245 | 412.0612 | 26724
35246 | 418.9443 | 26724
35247 | 421.8762 | 26724
35248 | 409.6524 | 26724
35249 | 413.0109 | 26724
35250 | 420.3625 | 26724
35251 | 411.4552 | 26724
35252 | 417.3466 | 26724
35253 | 413.8975 | 26724
35254 | 408.0866 | 26724
35255 | 412.9878 | 26724
35256 | 403.97 | 26724
35257 | 411.3372 | 26724
35258 | 405.3667 | 26724
35259 | 420.3112 | 26724
35260 | 423.0259 | 26724
35261 | 411.2076 | 26724
35262 | 415.1643 | 26724
35263 | 420.3948 | 26724
35264 | 415.6309 | 26724
35265 | 418.3752 | 26724
35266 | 428.4589 | 26724
35267 | 412.6384 | 26724
35268 | 402.0983 | 26724
35269 | 406.5719 | 26724
35270 | 414.1069 | 26724
35271 | 419.1015 | 26724
35272 | 411.1774 | 26724
35273 | 428.6663 | 26724
35274 | 424.0779 | 26724
35275 | 412.929 | 26724
35276 | 407.7748 | 26724
35277 | 427.3211 | 26724
35278 | 410.043 | 26724
35279 | 427.1899 | 26724
35280 | 430.0663 | 26724
35281 | 413.1621 | 26724
35282 | 415.8869 | 26724
35283 | 406.1661 | 26724
35284 | 429.1301 | 26724
35285 | 418.2036 | 26724
35286 | 417.4554 | 26724
35287 | 419.1936 | 26724
35288 | 412.2234 | 26724
35289 | 412.9756 | 26724
35290 | 419.1185 | 26724
35291 | 427.771 | 26724
35292 | 420.4748 | 26724
35293 | 401.5807 | 26724
35294 | 427.5511 | 26724
35295 | 420.8929 | 26724
35296 | 416.4317 | 26724
35297 | 428.4008 | 26724
35298 | 403.2435 | 26724
35299 | 410.953 | 26724
35300 | 414.5213 | 26724
35301 | 425.3606 | 26724
35302 | 415.8536 | 26724
35303 | 404.1704 | 26724
35304 | 406.2732 | 26724
35305 | 416.6298 | 26724
35306 | 408.9886 | 26724
35307 | 414.7634 | 26724
35308 | 413.0234 | 26724
35309 | 422.4449 | 26724
35310 | 424.4161 | 26724
35311 | 421.5459 | 26724
35312 | 415.2031 | 26724
35313 | 420.6369 | 26724
35314 | 410.6674 | 26724
35315 | 418.3405 | 26724
35316 | 413.4178 | 26724
35317 | 397.6756 | 26724
35318 | 421.2128 | 26724
35319 | 416.6903 | 26724
35320 | 416.8395 | 26724
35321 | 415.5325 | 26724
35322 | 413.0387 | 26724
35323 | 423.2175 | 26724
35324 | 414.1224 | 26724
35325 | 417.1926 | 26724
35326 | 424.4527 | 26724
35327 | 432.5063 | 26724
35328 | 431.4664 | 26724
35329 | 415.3883 | 26724
35330 | 413.056 | 26724
35331 | 412.6981 | 26724
35332 | 419.3875 | 26724
35333 | 431.1205 | 26724
35334 | 417.4603 | 26724
35335 | 426.5563 | 26724
35336 | 424.7936 | 26724
35337 | 424.0569 | 26724
35338 | 410.8111 | 26724
35339 | 418.1032 | 26724
35340 | 417.2277 | 26724
35341 | 422.287 | 26724
35342 | 421.9275 | 26724
35343 | 417.0837 | 26724
35344 | 418.8401 | 26724
35345 | 419.8225 | 26724
35346 | 428.5637 | 26724
35347 | 420.882 | 26724
35348 | 414.7465 | 26724
35349 | 410.9551 | 26724
35350 | 410.404 | 26724
35351 | 409.8413 | 26724
35352 | 428.6834 | 26724
35353 | 409.891 | 26724
35354 | 411.3955 | 26724
35355 | 397.6911 | 26724
35356 | 428.3712 | 26724
35357 | 415.7993 | 26724
35358 | 420.2972 | 26724
35359 | 417.9109 | 26724
35360 | 432.6502 | 26724
35361 | 408.0632 | 26724
35362 | 407.7303 | 26724
35363 | 408.7412 | 26724
35364 | 417.8407 | 26724
35365 | 410.1537 | 26724
35366 | 420.5697 | 26724
35367 | 406.553 | 26724
35368 | 416.8739 | 26724
35369 | 408.3036 | 26724
35370 | 420.4436 | 26724
35371 | 412.2969 | 26724
35372 | 418.5788 | 26724
35373 | 420.3323 | 26724
35374 | 402.3692 | 26724
35375 | 416.2849 | 26724
35376 | 399.83 | 26724
35377 | 398.3357 | 26724
35378 | 435.1766 | 26724
35379 | 392.1294 | 26724
35380 | 429.6691 | 26724
35381 | 419.5608 | 26724
35382 | 402.9584 | 26724
35383 | 402.9358 | 26724
35384 | 415.2022 | 26724
35385 | 426.8645 | 26724
35386 | 413.414 | 26724
35387 | 430.2987 | 26724
35388 | 411.5011 | 26724
35389 | 405.9632 | 26724
35390 | 397.2476 | 26724
35391 | 422.966 | 26724
35392 | 422.9395 | 26724
35393 | 423.8569 | 26724
35394 | 420.9604 | 26724
35395 | 419.8289 | 26724
35396 | 408.8677 | 26724
35397 | 409.603 | 26724
35398 | 404.3454 | 26724
35399 | 422.5998 | 26724
35400 | 425.8502 | 26724
35401 | 415.4679 | 26724
35402 | 409.698 | 26724
35403 | 411.6481 | 26724
35404 | 405.1679 | 26724
35405 | 417.2812 | 26724
35406 | 413.8113 | 26724
35407 | 419.9635 | 26724
35408 | 412.1166 | 26724
35409 | 411.2916 | 26724
35410 | 409.9068 | 26724
35411 | 414.6747 | 26724
35412 | 410.4513 | 26724
35413 | 422.5548 | 26724
35414 | 416.2848 | 26724
35415 | 431.0926 | 26724
35416 | 406.7609 | 26724
35417 | 402.8129 | 26724
35418 | 417.2683 | 26724
35419 | 420.9093 | 26724
35420 | 409.1065 | 26724
35421 | 398.5054 | 26724
35422 | 409.9199 | 26724
35423 | 421.5363 | 26724
35424 | 408.8995 | 26724
35425 | 415.1869 | 26724
35426 | 420.3669 | 26724
35427 | 425.1853 | 26724
35428 | 415.2231 | 26724
35429 | 411.1005 | 26724
35430 | 410.8828 | 26724
35431 | 403.7727 | 26724
35432 | 428.5495 | 26724
35433 | 429.0083 | 26724
35434 | 417.8487 | 26724
35435 | 402.1305 | 26724
35436 | 414.6184 | 26724
35437 | 418.6104 | 26724
35438 | 403.8552 | 26724
35439 | 419.3383 | 26724
35440 | 422.5235 | 26724
35441 | 410.4692 | 26724
35442 | 412.3135 | 26724
35443 | 403.108 | 26724
35444 | 409.4592 | 26724
35445 | 416.2383 | 26724
35446 | 414.3012 | 26724
35447 | 408.1388 | 26724
35448 | 428.4786 | 26724
35449 | 411.9764 | 26724
35450 | 411.8679 | 26724
35451 | 413.3146 | 26724
35452 | 416.602 | 26724
35453 | 421.8194 | 26724
35454 | 412.3227 | 26724
35455 | 403.977 | 26724
35456 | 411.5735 | 26724
35457 | 420.0864 | 26724
35458 | 406.344 | 26724
35459 | 399.2328 | 26724
35460 | 407.4147 | 26724
35461 | 413.5505 | 26724
35462 | 406.2113 | 26724
35463 | 424.5619 | 26724
35464 | 422.8184 | 26724
35465 | 417.0125 | 26724
35466 | 413.2119 | 26724
35467 | 405.827 | 26724
35468 | 420.4294 | 26724
35469 | 421.8379 | 26724
35470 | 439.6503 | 26724
35471 | 394.6991 | 26724
35472 | 425.6169 | 26724
35473 | 429.5204 | 26724
35474 | 414.5687 | 26724
35475 | 409.2002 | 26724
35476 | 401.7368 | 26724
35477 | 428.5829 | 26724
35478 | 416.5726 | 26724
35479 | 425.146 | 26724
35480 | 431.2204 | 26724
35481 | 413.445 | 26724
35482 | 423.5038 | 26724
35483 | 427.2635 | 26724
35484 | 406.8184 | 26724
35485 | 419.3932 | 26724
35486 | 407.9584 | 26724
35487 | 424.6876 | 26724
35488 | 419.2508 | 26724
35489 | 396.452 | 26724
35490 | 425.9299 | 26724
35491 | 413.3486 | 26724
35492 | 428.0896 | 26724
35493 | 422.033 | 26724
35494 | 408.3361 | 26724
35495 | 400.5461 | 26724
35496 | 419.1088 | 26724
35497 | 414.1413 | 26724
35498 | 428.7958 | 26724
35499 | 412.9634 | 26724
35500 | 414.1893 | 26724
35501 | 412.2195 | 26724
35502 | 405.9586 | 26724
35503 | 411.9056 | 26724
35504 | 435.9558 | 26724
35505 | 419.108 | 26724
35506 | 418.8242 | 26724
35507 | 416.5756 | 26724
35508 | 403.6734 | 26724
35509 | 423.8691 | 26724
35510 | 418.8351 | 26724
35511 | 426.987 | 26724
35512 | 410.505 | 26724
35513 | 407.0088 | 26724
35514 | 415.4592 | 26724
35515 | 413.3591 | 26724
35516 | 412.7679 | 26724
35517 | 439.5457 | 26724
35518 | 418.0955 | 26724
35519 | 415.2539 | 26724
35520 | 428.9592 | 26724
35521 | 413.3098 | 26724
35522 | 421.0519 | 26724
35523 | 407.0594 | 26724
35524 | 422.8686 | 26724
35525 | 414.2458 | 26724
35526 | 418.9844 | 26724
35527 | 419.7576 | 26724
35528 | 401.575 | 26724
35529 | 418.9618 | 26724
35530 | 418.1008 | 26724
35531 | 406.9456 | 26724
35532 | 403.4447 | 26724
35533 | 405.3228 | 26724
35534 | 411.3013 | 26724
35535 | 415.8556 | 26724
35536 | 417.5934 | 26724
35537 | 405.0297 | 26724
35538 | 403.2137 | 26724
35539 | 411.8551 | 26724
35540 | 416.0719 | 26724
35541 | 416.4169 | 26724
35542 | 425.3072 | 26724
35543 | 421.943 | 26724
35544 | 418.5809 | 26724
35545 | 423.4021 | 26724
35546 | 400.9734 | 26724
35547 | 415.229 | 26724
35548 | 407.0907 | 26724
35549 | 417.7497 | 26724
35550 | 414.9335 | 26724
35551 | 412.9402 | 26724
35552 | 433.1797 | 26724
35553 | 401.4518 | 26724
35554 | 416.1615 | 26724
35555 | 390.9356 | 26724
35556 | 427.948 | 26724
35557 | 407.9039 | 26724
35558 | 419.037 | 26724
35559 | 424.7993 | 26724
35560 | 435.4078 | 26724
35561 | 416.4542 | 26724
35562 | 433.5179 | 26724
35563 | 423.9767 | 26724
35564 | 417.3749 | 26724
35565 | 421.6156 | 26724
35566 | 413.9789 | 26724
35567 | 411.3691 | 26724
35568 | 426.7127 | 26724
35569 | 419.8111 | 26724
35570 | 422.9897 | 26724
35571 | 406.3712 | 26724
35572 | 407.5166 | 26724
35573 | 418.6518 | 26724
35574 | 412.834 | 26724
35575 | 428.1526 | 26724
35576 | 427.0638 | 26724
35577 | 406.5754 | 26724
35578 | 422.5423 | 26724
35579 | 419.5913 | 26724
35580 | 417.5717 | 26724
35581 | 423.9401 | 26724
35582 | 415.8609 | 26724
35583 | 412.9599 | 26724
35584 | 419.445 | 26724
35585 | 403.5404 | 26724
35586 | 414.9158 | 26724
35587 | 414.7423 | 26724
35588 | 419.6023 | 26724
35589 | 417.4006 | 26724
35590 | 428.1412 | 26724
35591 | 428.986 | 26724
35592 | 414.6615 | 26724
35593 | 426.4883 | 26724
35594 | 407.1816 | 26724
35595 | 417.5651 | 26724
35596 | 410.6847 | 26724
35597 | 406.4242 | 26724
35598 | 402.0441 | 26724
35599 | 422.6199 | 26724
35600 | 420.6862 | 26724
35601 | 411.2874 | 26724
35602 | 405.4287 | 26724
35603 | 414.0311 | 26724
35604 | 428.2465 | 26724
35605 | 423.5574 | 26724
35606 | 421.9834 | 26724
35607 | 426.819 | 26724
35608 | 419.634 | 26724
35609 | 423.8395 | 26724
35610 | 433.6439 | 26724
35611 | 424.5867 | 26724
35612 | 404.1592 | 26724
35613 | 413.537 | 26724
35614 | 425.5028 | 26724
35615 | 416.4566 | 26724
35616 | 415.6814 | 26724
35617 | 418.772 | 26724
35618 | 399.4119 | 26724
35619 | 417.9234 | 26724
35620 | 419.3039 | 26724
35621 | 432.6771 | 26724
35622 | 431.5105 | 26724
35623 | 423.2503 | 26724
35624 | 409.3052 | 26724
35625 | 415.5245 | 26724
35626 | 400.2462 | 26724
35627 | 410.9464 | 26724
35628 | 406.4797 | 26724
35629 | 416.5991 | 26724
35630 | 409.399 | 26724
35631 | 423.5062 | 26724
35632 | 414.1604 | 26724
35633 | 418.7536 | 26724
35634 | 413.575 | 26724
35635 | 414.8092 | 26724
35636 | 419.9567 | 26724
35637 | 416.4888 | 26724
35638 | 417.2693 | 26724
35639 | 429.0049 | 26724
35640 | 410.0093 | 26724
35641 | 416.0571 | 26724
35642 | 404.3993 | 26724
35643 | 405.3878 | 26724
35644 | 400.1947 | 26724
35645 | 415.7943 | 26724
35646 | 424.4936 | 26724
35647 | 412.1609 | 26724
35648 | 424.8362 | 26724
35649 | 404.3326 | 26724
35650 | 408.1512 | 26724
35651 | 426.2616 | 26724
35652 | 416.5974 | 26724
35653 | 422.599 | 26724
35654 | 410.9313 | 26724
35655 | 410.0812 | 26724
35656 | 412.7441 | 26724
35657 | 412.2076 | 26724
35658 | 416.1494 | 26724
35659 | 422.5732 | 26724
35660 | 410.4264 | 26724
35661 | 404.6907 | 26724
35662 | 414.2453 | 26724
35663 | 407.0446 | 26724
35664 | 419.3187 | 26724
35665 | 425.1284 | 26724
35666 | 408.403 | 26724
35667 | 417.7114 | 26724
35668 | 426.3928 | 26724
35669 | 421.4144 | 26724
35670 | 407.1381 | 26724
35671 | 412.7501 | 26724
35672 | 415.6735 | 26724
35673 | 408.0448 | 26724
35674 | 424.5587 | 26724
35675 | 404.2677 | 26724
35676 | 406.259 | 26724
35677 | 429.1108 | 26724
35678 | 408.4776 | 26724
35679 | 425.1764 | 26724
35680 | 412.7817 | 26724
35681 | 419.0155 | 26724
35682 | 419.2298 | 26724
35683 | 413.4876 | 26724
35684 | 392.4385 | 26724
35685 | 411.1641 | 26724
35686 | 425.7713 | 26724
35687 | 412.9346 | 26724
35688 | 411.0249 | 26724
35689 | 433.9517 | 26724
35690 | 408.5448 | 26724
35691 | 410.8017 | 26724
35692 | 428.172 | 26724
35693 | 415.3182 | 26724
35694 | 408.8617 | 26724
35695 | 423.0864 | 26724
35696 | 407.4472 | 26724
35697 | 395.5617 | 26724
35698 | 427.8858 | 26724
35699 | 419.4701 | 26724
35700 | 409.3487 | 26724
35701 | 410.5452 | 26724
35702 | 420.1189 | 26724
35703 | 410.4382 | 26724
35704 | 424.1453 | 26724
35705 | 416.4523 | 26724
35706 | 414.7273 | 26724
35707 | 418.1487 | 26724
35708 | 406.0677 | 26724
35709 | 426.8272 | 26724
35710 | 426.3811 | 26724
35711 | 425.3324 | 26724
35712 | 419.3967 | 26724
35713 | 410.0048 | 26724
35714 | 427.5191 | 26724
35715 | 424.6195 | 26724
35716 | 425.3084 | 26724
35717 | 429.428 | 26724
35718 | 412.6271 | 26724
35719 | 413.8664 | 26724
35720 | 414.2744 | 26724
35721 | 415.023 | 26724
35722 | 418.0196 | 26724
35723 | 412.742 | 26724
35724 | 414.0459 | 26724
35725 | 421.7482 | 26724
35726 | 421.2546 | 26724
35727 | 419.9031 | 26724
35728 | 425.9337 | 26724
35729 | 405.712 | 26724
35730 | 418.9983 | 26724
35731 | 415.402 | 26724
35732 | 414.4564 | 26724
35733 | 424.0645 | 26724
35734 | 424.4638 | 26724
35735 | 419.2322 | 26724
35736 | 428.0679 | 26724
35737 | 417.8867 | 26724
35738 | 422.3298 | 26724
35739 | 403.9154 | 26724
35740 | 421.3419 | 26724
35741 | 413.078 | 26724
35742 | 421.5257 | 26724
35743 | 413.0968 | 26724
35744 | 400.21 | 26724
35745 | 417.8922 | 26724
35746 | 406.8377 | 26724
35747 | 420.7786 | 26724
35748 | 419.2005 | 26724
35749 | 428.7104 | 26724
35750 | 415.2587 | 26724
35751 | 408.2043 | 26724
35752 | 419.158 | 26724
35753 | 429.9436 | 26724
35754 | 413.7576 | 26724
35755 | 427.7513 | 26724
35756 | 412.2522 | 26724
35757 | 415.5756 | 26724
35758 | 412.5399 | 26724
35759 | 425.5016 | 26724
35760 | 428.6967 | 26724
35761 | 428.8461 | 26724
35762 | 424.5697 | 26724
35763 | 408.6788 | 26724
35764 | 411.2167 | 26724
35765 | 412.387 | 26724
35766 | 409.6675 | 26724
35767 | 418.5946 | 26724
35768 | 415.0011 | 26724
35769 | 417.5543 | 26724
35770 | 413.4841 | 26724
35771 | 429.8735 | 26724
35772 | 419.2405 | 26724
35773 | 426.2459 | 26724
35774 | 413.6153 | 26724
35775 | 423.0124 | 26724
35776 | 410.6639 | 26724
35777 | 423.1944 | 26724
35778 | 411.1243 | 26724
35779 | 416.3203 | 26724
35780 | 410.1948 | 26724
35781 | 422.6698 | 26724
35782 | 409.1077 | 26724
35783 | 423.8414 | 26724
35784 | 423.6817 | 26724
35785 | 434.4147 | 26724
35786 | 408.3778 | 26724
35787 | 402.5385 | 26724
35788 | 406.0735 | 26724
35789 | 426.649 | 26724
35790 | 416.4713 | 26724
35791 | 421.8102 | 26724
35792 | 415.7901 | 26724
35793 | 412.6563 | 26724
35794 | 418.9799 | 26724
35795 | 416.5553 | 26724
35796 | 432.723 | 26724
35797 | 413.6291 | 26724
35798 | 432.1781 | 26724
35799 | 407.1523 | 26724
35800 | 411.7291 | 26724
35801 | 406.2166 | 26724
35802 | 409.8174 | 26724
35803 | 402.8527 | 26724
35804 | 413.6422 | 26724
35805 | 403.5594 | 26724
35806 | 413.7358 | 26724
35807 | 413.0909 | 26724
35808 | 422.9869 | 26724
35809 | 430.0662 | 26724
35810 | 417.7879 | 26724
35811 | 416.9825 | 26724
35812 | 417.4626 | 26724
35813 | 425.6856 | 26724
35814 | 431.5043 | 26724
35815 | 404.7909 | 26724
35816 | 408.213 | 26724
35817 | 427.541 | 26724
35818 | 412.0908 | 26724
35819 | 416.5478 | 26724
35820 | 419.2337 | 26724
35821 | 423.1197 | 26724
35822 | 414.4359 | 26724
35823 | 411.8432 | 26724
35824 | 404.4375 | 26724
35825 | 404.2594 | 26724
35826 | 405.2886 | 26724
35827 | 410.1868 | 26724
35828 | 423.3498 | 26724
35829 | 427.775 | 26724
35830 | 396.5849 | 26724
35831 | 417.2964 | 26724
35832 | 421.4214 | 26724
35833 | 429.5732 | 26724
35834 | 417.7726 | 26724
35835 | 404.474 | 26724
35836 | 417.841 | 26724
35837 | 411.106 | 26724
35838 | 420.9827 | 26724
35839 | 420.7334 | 26724
35840 | 421.5754 | 26724
35841 | 409.1551 | 26724
35842 | 412.7417 | 26724
35843 | 419.4146 | 26724
35844 | 420.9498 | 26724
35845 | 423.8058 | 26724
35846 | 408.8666 | 26724
35847 | 424.3175 | 26724
35848 | 414.7259 | 26724
35849 | 425.5668 | 26724
35850 | 408.5755 | 26724
35851 | 426.6989 | 26724
35852 | 415.8359 | 26724
35853 | 412.1989 | 26724
35854 | 420.3854 | 26724
35855 | 412.5772 | 26724
35856 | 416.1564 | 26724
35857 | 407.1807 | 26724
35858 | 427.4254 | 26724
35859 | 419.3003 | 26724
35860 | 407.9138 | 26724
35861 | 437.9209 | 26724
35862 | 414.8324 | 26724
35863 | 420.2938 | 26724
35864 | 393.5684 | 26724
35865 | 406.4216 | 26724
35866 | 429.8816 | 26724
35867 | 413.1791 | 26724
35868 | 422.2099 | 26724
35869 | 425.2326 | 26724
35870 | 429.4485 | 26724
35871 | 422.9186 | 26724
35872 | 422.143 | 26724
35873 | 412.8442 | 26724
35874 | 426.8632 | 26724
35875 | 436.752 | 26724
35876 | 424.2741 | 26724
35877 | 408.6017 | 26724
35878 | 413.1375 | 26724
35879 | 412.997 | 26724
35880 | 411.038 | 26724
35881 | 425.1326 | 26724
35882 | 403.3778 | 26724
35883 | 409.1913 | 26724
35884 | 407.3206 | 26724
35885 | 419.1493 | 26724
35886 | 399.287 | 26724
35887 | 417.7621 | 26724
35888 | 413.9881 | 26724
35889 | 411.5285 | 26724
35890 | 411.8888 | 26724
35891 | 417.7253 | 26724
35892 | 412.1377 | 26724
35893 | 409.451 | 26724
35894 | 411.7344 | 26724
35895 | 407.938 | 26724
35896 | 431.9634 | 26724
35897 | 409.601 | 26724
35898 | 429.6854 | 26724
35899 | 418.582 | 26724
35900 | 416.0728 | 26724
35901 | 428.4901 | 26724
35902 | 416.5035 | 26724
35903 | 424.7407 | 26724
35904 | 424.4748 | 26724
35905 | 409.6233 | 26724
35906 | 434.5122 | 26724
35907 | 414.147 | 26724
35908 | 422.7568 | 26724
35909 | 414.4625 | 26724
35910 | 414.7566 | 26724
35911 | 418.6078 | 26724
35912 | 410.1217 | 26724
35913 | 399.016 | 26724
35914 | 411.6769 | 26724
35915 | 423.8217 | 26724
35916 | 414.4441 | 26724
35917 | 420.3673 | 26724
35918 | 423.0028 | 26724
35919 | 411.1921 | 26724
35920 | 400.7782 | 26724
35921 | 420.738 | 26724
35922 | 424.9639 | 26724
35923 | 406.5694 | 26724
35924 | 416.7636 | 26724
35925 | 414.8441 | 26724
35926 | 417.2272 | 26724
35927 | 429.9173 | 26724
35928 | 421.8483 | 26724
35929 | 413.3172 | 26724
35930 | 432.2094 | 26724
35931 | 424.4266 | 26724
35932 | 415.6419 | 26724
35933 | 405.0152 | 26724
35934 | 412.5821 | 26724
35935 | 417.2558 | 26724
35936 | 418.0431 | 26724
35937 | 417.325 | 26724
35938 | 422.2491 | 26724
35939 | 421.9382 | 26724
35940 | 436.9457 | 26724
35941 | 415.9022 | 26724
35942 | 407.4707 | 26724
35943 | 419.8832 | 26724
35944 | 419.1324 | 26724
35945 | 413.0122 | 26724
35946 | 419.4944 | 26724
35947 | 403.3127 | 26724
35948 | 424.518 | 26724
35949 | 417.8765 | 26724
35950 | 407.2768 | 26724
35951 | 411.4836 | 26724
35952 | 419.6441 | 26724
35953 | 432.043 | 26724
35954 | 420.7933 | 26724
35955 | 411.3684 | 26724
35956 | 415.9239 | 26724
35957 | 425.8264 | 26724
35958 | 416.8543 | 26724
35959 | 414.2002 | 26724
35960 | 428.9378 | 26724
35961 | 407.1252 | 26724
35962 | 405.9307 | 26724
35963 | 407.1707 | 26724
35964 | 412.9025 | 26724
35965 | 419.9004 | 26724
35966 | 411.7043 | 26724
35967 | 415.7097 | 26724
35968 | 406.5871 | 26724
35969 | 410.5465 | 26724
35970 | 431.4376 | 26724
35971 | 411.6147 | 26724
35972 | 415.4306 | 26724
35973 | 425.4628 | 26724
35974 | 406.0713 | 26724
35975 | 421.5099 | 26724
35976 | 416.9933 | 26724
35977 | 420.763 | 26724
35978 | 421.6897 | 26724
35979 | 417.5434 | 26724
35980 | 413.7349 | 26724
35981 | 397.892 | 26724
35982 | 413.3009 | 26724
35983 | 428.4128 | 26724
35984 | 415.4698 | 26724
35985 | 422.978 | 26724
35986 | 414.2712 | 26724
35987 | 413.3072 | 26724
35988 | 424.5073 | 26724
35989 | 415.507 | 26724
35990 | 411.8523 | 26724
35991 | 416.8126 | 26724
35992 | 407.7026 | 26724
35993 | 429.0849 | 26724
35994 | 403.9402 | 26724
35995 | 427.2998 | 26724
35996 | 421.0928 | 26724
35997 | 413.6471 | 26724
35998 | 406.4127 | 26724
35999 | 429.1663 | 26724
36000 | 420.3021 | 26724
36001 | 404.4363 | 26724
36002 | 403.1681 | 26724
36003 | 413.3644 | 26724
36004 | 411.3199 | 26724
36005 | 410.3728 | 26724
36006 | 408.5115 | 26724
36007 | 419.016 | 26724
36008 | 422.51 | 26724
36009 | 403.3118 | 26724
36010 | 414.0699 | 26724
36011 | 413.3012 | 26724
36012 | 413.072 | 26724
36013 | 425.1023 | 26724
36014 | 414.2273 | 26724
36015 | 420.5995 | 26724
36016 | 416.0699 | 26724
36017 | 411.1711 | 26724
36018 | 424.6382 | 26724
36019 | 414.4405 | 26724
36020 | 406.1378 | 26724
36021 | 421.3417 | 26724
36022 | 424.218 | 26724
36023 | 413.9448 | 26724
36024 | 414.096 | 26724
36025 | 434.3354 | 26724
36026 | 418.4857 | 26724
36027 | 429.3 | 26724
36028 | 417.8466 | 26724
36029 | 420.2487 | 26724
36030 | 426.3116 | 26724
36031 | 415.048 | 26724
36032 | 429.1753 | 26724
36033 | 401.1431 | 26724
36034 | 412.907 | 26724
36035 | 410.3642 | 26724
36036 | 432.0228 | 26724
36037 | 412.9808 | 26724
36038 | 407.5084 | 26724
36039 | 413.5459 | 26724
36040 | 413.9093 | 26724
36041 | 411.2607 | 26724
36042 | 416.5467 | 26724
36043 | 412.9733 | 26724
36044 | 398.5209 | 26724
36045 | 408.0179 | 26724
36046 | 415.5359 | 26724
36047 | 413.9592 | 26724
36048 | 434.3938 | 26724
36049 | 400.8993 | 26724
36050 | 424.5914 | 26724
36051 | 414.8656 | 26724
36052 | 426.118 | 26724
36053 | 419.9234 | 26724
36054 | 412.563 | 26724
36055 | 409.5041 | 26724
36056 | 418.7762 | 26724
36057 | 413.3998 | 26724
36058 | 425.6423 | 26724
36059 | 410.9197 | 26724
36060 | 420.8646 | 26724
36061 | 417.1626 | 26724
36062 | 415.8194 | 26724
36063 | 420.4763 | 26724
36064 | 422.8823 | 26724
36065 | 411.984 | 26724
36066 | 397.883 | 26724
36067 | 419.1873 | 26724
36068 | 398.7772 | 26724
36069 | 412.8636 | 26724
36070 | 417.335 | 26724
36071 | 436.3422 | 26724
36072 | 430.6213 | 26724
36073 | 410.3478 | 26724
36074 | 428.0687 | 26724
36075 | 421.4228 | 26724
36076 | 405.0785 | 26724
36077 | 422.0093 | 26724
36078 | 407.9759 | 26724
36079 | 413.6698 | 26724
36080 | 413.3934 | 26724
36081 | 414.163 | 26724
36082 | 404.4536 | 26724
36083 | 413.1136 | 26724
36084 | 422.5434 | 26724
36085 | 418.0613 | 26724
36086 | 424.1668 | 26724
36087 | 408.8043 | 26724
36088 | 422.2824 | 26724
36089 | 408.1869 | 26724
36090 | 426.0247 | 26724
36091 | 435.4304 | 26724
36092 | 414.6163 | 26724
36093 | 415.1604 | 26724
36094 | 427.9097 | 26724
36095 | 405.3875 | 26724
36096 | 417.9102 | 26724
36097 | 411.569 | 26724
36098 | 406.008 | 26724
36099 | 424.1447 | 26724
36100 | 406.5364 | 26724
36101 | 408.3098 | 26724
36102 | 427.5437 | 26724
36103 | 415.7457 | 26724
36104 | 420.9391 | 26724
36105 | 403.82 | 26724
36106 | 423.3773 | 26724
36107 | 427.3652 | 26724
36108 | 412.4501 | 26724
36109 | 412.5574 | 26724
36110 | 404.9493 | 26724
36111 | 413.5678 | 26724
36112 | 415.5837 | 26724
36113 | 422.0783 | 26724
36114 | 416.807 | 26724
36115 | 419.2662 | 26724
36116 | 431.6905 | 26724
36117 | 411.2638 | 26724
36118 | 419.2111 | 26724
36119 | 413.8679 | 26724
36120 | 415.1602 | 26724
36121 | 418.0039 | 26724
36122 | 401.3652 | 26724
36123 | 403.4076 | 26724
36124 | 404.1714 | 26724
36125 | 427.7517 | 26724
36126 | 407.608 | 26724
36127 | 413.3992 | 26724
36128 | 417.3286 | 26724
36129 | 416.2472 | 26724
36130 | 408.3503 | 26724
36131 | 417.0382 | 26724
36132 | 407.0406 | 26724
36133 | 421.0235 | 26724
36134 | 421.5785 | 26724
36135 | 429.5812 | 26724
36136 | 420.1428 | 26724
36137 | 421.7485 | 26724
36138 | 405.3726 | 26724
36139 | 418.6763 | 26724
36140 | 419.8152 | 26724
36141 | 427.4495 | 26724
36142 | 409.0323 | 26724
36143 | 427.0309 | 26724
36144 | 420.0921 | 26724
36145 | 419.7296 | 26724
36146 | 414.4286 | 26724
36147 | 426.8394 | 26724
36148 | 415.7408 | 26724
36149 | 406.6942 | 26724
36150 | 409.4405 | 26724
36151 | 422.9817 | 26724
36152 | 425.6339 | 26724
36153 | 421.7883 | 26724
36154 | 416.7382 | 26724
36155 | 422.288 | 26724
36156 | 412.783 | 26724
36157 | 415.1249 | 26724
36158 | 407.8848 | 26724
36159 | 433.7347 | 26724
36160 | 414.2944 | 26724
36161 | 408.013 | 26724
36162 | 422.4433 | 26724
36163 | 407.0753 | 26724
36164 | 420.7805 | 26724
36165 | 419.2264 | 26724
36166 | 398.8701 | 26724
36167 | 419.8307 | 26724
36168 | 413.8295 | 26724
36169 | 424.5531 | 26724
36170 | 423.218 | 26724
36171 | 421.1401 | 26724
36172 | 399.367 | 26724
36173 | 409.0921 | 26724
36174 | 426.8742 | 26724
36175 | 410.8449 | 26724
36176 | 421.7194 | 26724
36177 | 424.4947 | 26724
36178 | 412.5476 | 26724
36179 | 415.0773 | 26724
36180 | 420.5439 | 26724
36181 | 422.2265 | 26724
36182 | 416.4748 | 26724
36183 | 419.4823 | 26724
36184 | 435.8437 | 26724
36185 | 413.1124 | 26724
36186 | 421.5513 | 26724
36187 | 410.5884 | 26724
36188 | 435.7815 | 26724
36189 | 407.7178 | 26724
36190 | 418.1622 | 26724
36191 | 416.5581 | 26724
36192 | 418.3849 | 26724
36193 | 406.3672 | 26724
36194 | 420.6044 | 26724
36195 | 419.1054 | 26724
36196 | 403.4641 | 26724
36197 | 426.5769 | 26724
36198 | 427.3348 | 26724
36199 | 413.3926 | 26724
36200 | 411.1558 | 26724
36201 | 417.2821 | 26724
36202 | 414.7643 | 26724
36203 | 412.9713 | 26724
36204 | 419.4451 | 26724
36205 | 413.6164 | 26724
36206 | 418.4133 | 26724
36207 | 410.296 | 26724
36208 | 408.8484 | 26724
36209 | 418.7074 | 26724
36210 | 423.0464 | 26724
36211 | 422.5974 | 26724
36212 | 426.3623 | 26724
36213 | 422.6577 | 26724
36214 | 416.9192 | 26724
36215 | 411.4328 | 26724
36216 | 428.3884 | 26724
36217 | 404.7801 | 26724
36218 | 418.382 | 26724
36219 | 415.3343 | 26724
36220 | 409.5488 | 26724
36221 | 426.0659 | 26724
36222 | 413.8874 | 26724
36223 | 417.0065 | 26724
36224 | 419.4576 | 26724
36225 | 417.689 | 26724
36226 | 426 | 26724
36227 | 427.2885 | 26724
36228 | 421.6484 | 26724
36229 | 415.2372 | 26724
36230 | 429.1397 | 26724
36231 | 421.1845 | 26724
36232 | 417.8548 | 26724
36233 | 414.8727 | 26724
36234 | 414.572 | 26724
36235 | 416.0734 | 26724
36236 | 427.6337 | 26724
36237 | 428.7661 | 26724
36238 | 410.3496 | 26724
36239 | 413.9289 | 26724
36240 | 416.7312 | 26724
36241 | 418.5223 | 26724
36242 | 410.4761 | 26724
36243 | 427.3857 | 26724
36244 | 405.4701 | 26724
36245 | 412.3612 | 26724
36246 | 431.1771 | 26724
36247 | 422.7661 | 26724
36248 | 414.3905 | 26724
36249 | 408.8843 | 26724
36250 | 420.9117 | 26724
36251 | 403.8957 | 26724
36252 | 412.1579 | 26724
36253 | 433.6444 | 26724
36254 | 408.4067 | 26724
36255 | 397.9537 | 26724
36256 | 419.8355 | 26724
36257 | 418.2731 | 26724
36258 | 419.9173 | 26724
36259 | 417.1072 | 26724
36260 | 414.8414 | 26724
36261 | 410.3672 | 26724
36262 | 419.3158 | 26724
36263 | 432.1762 | 26724
36264 | 416.4743 | 26724
36265 | 420.0137 | 26724
36266 | 399.6334 | 26724
36267 | 419.6278 | 26724
36268 | 424.3532 | 26724
36269 | 423.7333 | 26724
36270 | 416.2482 | 26724
36271 | 420.0777 | 26724
36272 | 398.6813 | 26724
36273 | 418.6769 | 26724
36274 | 411.5339 | 26724
36275 | 409.5015 | 26724
36276 | 411.5205 | 26724
36277 | 417.0179 | 26724
36278 | 413.6172 | 26724
36279 | 416.2748 | 26724
36280 | 412.3729 | 26724
36281 | 411.3708 | 26724
36282 | 416.4106 | 26724
36283 | 405.7524 | 26724
36284 | 415.4479 | 26724
36285 | 415.8504 | 26724
36286 | 401.5672 | 26724
36287 | 402.7786 | 26724
36288 | 406.8557 | 26724
36289 | 409.7362 | 26724
36290 | 402.2291 | 26724
36291 | 434.6143 | 26724
36292 | 409.3781 | 26724
36293 | 422.1117 | 26724
36294 | 408.3318 | 26724
36295 | 397.0013 | 26724
36296 | 418.7668 | 26724
36297 | 418.8803 | 26724
36298 | 417.148 | 26724
36299 | 394.9104 | 26724
36300 | 437.1926 | 26724
36301 | 416.7802 | 26724
36302 | 394.9814 | 26724
36303 | 414.2095 | 26724
36304 | 433.5918 | 26724
36305 | 427.7824 | 26724
36306 | 412.9956 | 26724
36307 | 411.9267 | 26724
36308 | 410.0832 | 26724
36309 | 403.2892 | 26724
36310 | 424.7327 | 26724
36311 | 409.6781 | 26724
36312 | 418.4636 | 26724
36313 | 435.5507 | 26724
36314 | 416.6164 | 26724
36315 | 420.3348 | 26724
36316 | 406.9078 | 26724
36317 | 413.1949 | 26724
36318 | 425.406 | 26724
36319 | 416.1538 | 26724
36320 | 417.4484 | 26724
36321 | 406.4932 | 26724
36322 | 429.6008 | 26724
36323 | 414.7316 | 26724
36324 | 413.552 | 26724
36325 | 422.2258 | 26724
36326 | 420.3679 | 26724
36327 | 421.6618 | 26724
36328 | 413.7234 | 26724
36329 | 426.5006 | 26724
36330 | 410.2108 | 26724
36331 | 419.2929 | 26724
36332 | 412.6208 | 26724
36333 | 419.095 | 26724
36334 | 412.0503 | 26724
36335 | 431.2711 | 26724
36336 | 423.4909 | 26724
36337 | 406.1165 | 26724
36338 | 417.3949 | 26724
36339 | 408.1363 | 26724
36340 | 416.245 | 26724
36341 | 411.1755 | 26724
36342 | 409.0575 | 26724
36343 | 402.5897 | 26724
36344 | 428.5606 | 26724
36345 | 416.9792 | 26724
36346 | 420.4113 | 26724
36347 | 417.2052 | 26724
36348 | 424.7313 | 26724
36349 | 415.2222 | 26724
36350 | 407.0211 | 26724
36351 | 413.3537 | 26724
36352 | 423.1293 | 26724
36353 | 417.8267 | 26724
36354 | 423.8179 | 26724
36355 | 422.6044 | 26724
36356 | 414.6718 | 26724
36357 | 404.941 | 26724
36358 | 418.536 | 26724
36359 | 428.1698 | 26724
36360 | 404.4237 | 26724
36361 | 423.3276 | 26724
36362 | 406.066 | 26724
36363 | 428.8941 | 26724
36364 | 419.4839 | 26724
36365 | 411.7164 | 26724
36366 | 413.2093 | 26724
36367 | 427.2767 | 26724
36368 | 420.6629 | 26724
36369 | 429.3883 | 26724
36370 | 419.2478 | 26724
36371 | 413.1322 | 26724
36372 | 420.8808 | 26724
36373 | 418.3269 | 26724
36374 | 413.4606 | 26724
36375 | 404.5221 | 26724
36376 | 420.701 | 26724
36377 | 433.7376 | 26724
36378 | 410.4758 | 26724
36379 | 419.2951 | 26724
36380 | 414.9141 | 26724
36381 | 426.727 | 26724
36382 | 405.9214 | 26724
36383 | 412.6542 | 26724
36384 | 412.293 | 26724
36385 | 415.651 | 26724
36386 | 430.664 | 26724
36387 | 414.1939 | 26724
36388 | 431.4772 | 26724
36389 | 420.0384 | 26724
36390 | 426.9997 | 26724
36391 | 417.0941 | 26724
36392 | 407.5958 | 26724
36393 | 410.7059 | 26724
36394 | 417.6245 | 26724
36395 | 413.4341 | 26724
36396 | 416.2805 | 26724
36397 | 415.0621 | 26724
36398 | 411.6157 | 26724
36399 | 415.1369 | 26724
36400 | 415.1879 | 26724
36401 | 422.5782 | 26724
36402 | 407.8492 | 26724
36403 | 408.0546 | 26724
36404 | 413.4249 | 26724
36405 | 423.177 | 26724
36406 | 413.2967 | 26724
36407 | 425.7703 | 26724
36408 | 410.9737 | 26724
36409 | 425.1988 | 26724
36410 | 423.213 | 26724
36411 | 420.1915 | 26724
36412 | 424.3108 | 26724
36413 | 413.39 | 26724
36414 | 409.2554 | 26724
36415 | 429.3898 | 26724
36416 | 415.3218 | 26724
36417 | 429.3396 | 26724
36418 | 409.7847 | 26724
36419 | 410.7718 | 26724
36420 | 421.8637 | 26724
36421 | 429.6986 | 26724
36422 | 398.0196 | 26724
36423 | 426.6915 | 26724
36424 | 403.8873 | 26724
36425 | 406.7177 | 26724
36426 | 411.7206 | 26724
36427 | 425.4249 | 26724
36428 | 413.7624 | 26724
36429 | 419.0208 | 26724
36430 | 426.5593 | 26724
36431 | 425.8793 | 26724
36432 | 422.7138 | 26724
36433 | 406.5416 | 26724
36434 | 425.1718 | 26724
36435 | 411.3299 | 26724
36436 | 414.1025 | 26724
36437 | 421.7265 | 26724
36438 | 429.8413 | 26724
36439 | 428.7511 | 26724
36440 | 422.5557 | 26724
36441 | 418.2066 | 26724
36442 | 401.5049 | 26724
36443 | 421.956 | 26724
36444 | 409.6687 | 26724
36445 | 407.2039 | 26724
36446 | 414.5329 | 26724
36447 | 396.7064 | 26724
36448 | 415.1007 | 26724
36449 | 405.674 | 26724
36450 | 398.953 | 26724
36451 | 425.2401 | 26724
36452 | 422.3428 | 26724
36453 | 406.2391 | 26724
36454 | 410.0104 | 26724
36455 | 422.353 | 26724
36456 | 412.857 | 26724
36457 | 402.508 | 26724
36458 | 420.9475 | 26724
36459 | 417.5049 | 26724
36460 | 413.7288 | 26724
36461 | 408.3546 | 26724
36462 | 428.0825 | 26724
36463 | 401.9319 | 26724
36464 | 420.448 | 26724
36465 | 425.5109 | 26724
36466 | 403.22 | 26724
36467 | 420.9498 | 26724
36468 | 424.1049 | 26724
36469 | 423.5236 | 26724
36470 | 403.8894 | 26724
36471 | 417.799 | 26724
36472 | 430.8985 | 26724
36473 | 401.3739 | 26724
36474 | 420.9284 | 26724
36475 | 419.0805 | 26724
36476 | 419.5026 | 26724
36477 | 419.308 | 26724
36478 | 416.6231 | 26724
36479 | 418.2581 | 26724
36480 | 408.444 | 26724
36481 | 421.0226 | 26724
36482 | 423.0899 | 26724
36483 | 428.8612 | 26724
36484 | 427.5348 | 26724
36485 | 424.1358 | 26724
36486 | 415.7967 | 26724
36487 | 420.4832 | 26724
36488 | 426.4766 | 26724
36489 | 424.4654 | 26724
36490 | 410.6583 | 26724
36491 | 407.7627 | 26724
36492 | 426.8506 | 26724
36493 | 421.5742 | 26724
36494 | 422.7282 | 26724
36495 | 405.8654 | 26724
36496 | 425.7511 | 26724
36497 | 421.0337 | 26724
36498 | 420.1495 | 26724
36499 | 405.6038 | 26724
36500 | 409.6923 | 26724
36501 | 423.6586 | 26724
36502 | 411.6558 | 26724
36503 | 426.2027 | 26724
36504 | 420.6625 | 26724
36505 | 408.7065 | 26724
36506 | 415.5756 | 26724
36507 | 419.9743 | 26724
36508 | 425.261 | 26724
36509 | 434.4909 | 26724
36510 | 417.4679 | 26724
36511 | 413.4578 | 26724
36512 | 425.7587 | 26724
36513 | 428.5541 | 26724
36514 | 428.743 | 26724
36515 | 419.2943 | 26724
36516 | 407.5444 | 26724
36517 | 425.3653 | 26724
36518 | 426.1018 | 26724
36519 | 419.6297 | 26724
36520 | 409.3114 | 26724
36521 | 428.2842 | 26724
36522 | 412.1326 | 26724
36523 | 417.8548 | 26724
36524 | 416.1094 | 26724
36525 | 418.1598 | 26724
36526 | 415.9146 | 26724
36527 | 402.8126 | 26724
36528 | 412.6155 | 26724
36529 | 415.5108 | 26724
36530 | 434.3961 | 26724
36531 | 417.4829 | 26724
36532 | 422.0579 | 26724
36533 | 410.8619 | 26724
36534 | 413.5701 | 26724
36535 | 414.1821 | 26724
36536 | 420.2142 | 26724
36537 | 430.4657 | 26724
36538 | 411.9511 | 26724
36539 | 424.4294 | 26724
36540 | 406.7694 | 26724
36541 | 414.3412 | 26724
36542 | 409.3477 | 26724
36543 | 402.2687 | 26724
36544 | 414.0688 | 26724
36545 | 411.6955 | 26724
36546 | 397.4302 | 26724
36547 | 426.1212 | 26724
36548 | 410.4619 | 26724
36549 | 433.7599 | 26724
36550 | 426.5692 | 26724
36551 | 413.6348 | 26724
36552 | 419.3269 | 26724
36553 | 416.5197 | 26724
36554 | 415.9883 | 26724
36555 | 416.9189 | 26724
36556 | 422.1281 | 26724
36557 | 431.739 | 26724
36558 | 413.1336 | 26724
36559 | 406.0558 | 26724
36560 | 419.9988 | 26724
36561 | 425.7049 | 26724
36562 | 437.7142 | 26724
36563 | 430.0824 | 26724
36564 | 405.2521 | 26724
36565 | 420.5323 | 26724
36566 | 411.6065 | 26724
36567 | 417.056 | 26724
36568 | 420.7151 | 26724
36569 | 424.3723 | 26724
36570 | 408.0459 | 26724
36571 | 422.7412 | 26724
36572 | 409.9353 | 26724
36573 | 426.3685 | 26724
36574 | 418.9163 | 26724
36575 | 404.961 | 26724
36576 | 400.1779 | 26724
36577 | 425.965 | 26724
36578 | 424.2232 | 26724
36579 | 421.9635 | 26724
36580 | 420.4439 | 26724
36581 | 426.8284 | 26724
36582 | 399.9768 | 26724
36583 | 423.367 | 26724
36584 | 424.2287 | 26724
36585 | 418.2308 | 26724
36586 | 419.0523 | 26724
36587 | 414.3617 | 26724
36588 | 418.4637 | 26724
36589 | 421.7348 | 26724
36590 | 419.5106 | 26724
36591 | 414.5995 | 26724
36592 | 424.1567 | 26724
36593 | 423.1591 | 26724
36594 | 411.3941 | 26724
36595 | 422.1977 | 26724
36596 | 413.4017 | 26724
36597 | 409.0071 | 26724
36598 | 421.5647 | 26724
36599 | 414.2052 | 26724
36600 | 421.3325 | 26724
36601 | 417.0327 | 26724
36602 | 414.8684 | 26724
36603 | 397.833 | 26724
36604 | 411.5843 | 26724
36605 | 407.1885 | 26724
36606 | 433.0376 | 26724
36607 | 422.7895 | 26724
36608 | 410.8382 | 26724
36609 | 408.4756 | 26724
36610 | 413.1666 | 26724
36611 | 418.5755 | 26724
36612 | 402.0899 | 26724
36613 | 413.7894 | 26724
36614 | 409.4006 | 26724
36615 | 419.6533 | 26724
36616 | 426.688 | 26724
36617 | 413.5799 | 26724
36618 | 416.8966 | 26724
36619 | 424.6855 | 26724
36620 | 427.8164 | 26724
36621 | 413.0039 | 26724
36622 | 413.2422 | 26724
36623 | 411.9318 | 26724
36624 | 419.5178 | 26724
36625 | 412.0221 | 26724
36626 | 420.9179 | 26724
36627 | 405.154 | 26724
36628 | 404.8215 | 26724
36629 | 421.5709 | 26724
36630 | 410.4604 | 26724
36631 | 407.3765 | 26724
36632 | 423.7206 | 26724
36633 | 426.5797 | 26724
36634 | 412.9963 | 26724
36635 | 406.7331 | 26724
36636 | 429.2526 | 26724
36637 | 423.8106 | 26724
36638 | 414.9696 | 26724
36639 | 414.2831 | 26724
36640 | 403.5071 | 26724
36641 | 416.5587 | 26724
36642 | 411.6733 | 26724
36643 | 407.7772 | 26724
36644 | 410.7967 | 26724
36645 | 409.1631 | 26724
36646 | 421.0738 | 26724
36647 | 417.1774 | 26724
36648 | 413.3535 | 26724
36649 | 428.9276 | 26724
36650 | 413.7809 | 26724
36651 | 422.8419 | 26724
36652 | 414.0053 | 26724
36653 | 420.5151 | 26724
36654 | 413.5428 | 26724
36655 | 421.9956 | 26724
36656 | 394.8525 | 26724
36657 | 398.9771 | 26724
36658 | 406.3585 | 26724
36659 | 415.7643 | 26724
36660 | 418.2685 | 26724
36661 | 427.9542 | 26724
36662 | 420.5317 | 26724
36663 | 426.3005 | 26724
36664 | 407.5229 | 26724
36665 | 413.8309 | 26724
36666 | 413.5567 | 26724
36667 | 422.2694 | 26724
36668 | 404.2864 | 26724
36669 | 412.1618 | 26724
36670 | 423.1931 | 26724
36671 | 407.5917 | 26724
36672 | 422.0937 | 26724
36673 | 423.6137 | 26724
36674 | 411.6642 | 26724
36675 | 416.7466 | 26724
36676 | 417.756 | 26724
36677 | 405.2206 | 26724
36678 | 410.9087 | 26724
36679 | 412.408 | 26724
36680 | 421.4794 | 26724
36681 | 424.0449 | 26724
36682 | 403.4944 | 26724
36683 | 416.1891 | 26724
36684 | 421.897 | 26724
36685 | 420.6162 | 26724
36686 | 431.7711 | 26724
36687 | 409.1066 | 26724
36688 | 420.0424 | 26724
36689 | 425.0209 | 26724
36690 | 416.556 | 26724
36691 | 419.9037 | 26724
36692 | 413.4698 | 26724
36693 | 417.8996 | 26724
36694 | 408.5957 | 26724
36695 | 418.4725 | 26724
36696 | 412.5276 | 26724
36697 | 404.7186 | 26724
36698 | 419.3578 | 26724
36699 | 430.4314 | 26724
36700 | 425.825 | 26724
36701 | 409.7664 | 26724
36702 | 416.9941 | 26724
36703 | 416.3384 | 26724
36704 | 416.0311 | 26724
36705 | 418.5339 | 26724
36706 | 421.8194 | 26724
36707 | 421.0205 | 26724
36708 | 419.5601 | 26724
36709 | 418.8133 | 26724
36710 | 411.5566 | 26724
36711 | 409.1829 | 26724
36712 | 408.5444 | 26724
36713 | 412.436 | 26724
36714 | 408.5312 | 26724
36715 | 421.7611 | 26724
36716 | 408.0968 | 26724
36717 | 421.2414 | 26724
36718 | 408.3927 | 26724
36719 | 401.6133 | 26724
36720 | 425.422 | 26724
36721 | 426.9471 | 26724
36722 | 409.7242 | 26724
36723 | 401.2659 | 26724
36724 | 422.8122 | 26724
36725 | 403.525 | 26724
36726 | 414.5197 | 26724
36727 | 409.8385 | 26724
36728 | 418.2492 | 26724
36729 | 421.5804 | 26724
36730 | 406.0273 | 26724
36731 | 409.3092 | 26724
36732 | 433.4853 | 26724
36733 | 413.9166 | 26724
36734 | 432.4368 | 26724
36735 | 415.5047 | 26724
36736 | 406.7207 | 26724
36737 | 431.2718 | 26724
36738 | 425.4827 | 26724
36739 | 424.9339 | 26724
36740 | 429.0366 | 26724
36741 | 410.8807 | 26724
36742 | 420.9911 | 26724
36743 | 413.5036 | 26724
36744 | 407.9275 | 26724
36745 | 424.6014 | 26724
36746 | 408.563 | 26724
36747 | 426.078 | 26724
36748 | 418.2967 | 26724
36749 | 409.3279 | 26724
36750 | 405.8487 | 26724
36751 | 434.798 | 26724
36752 | 416.6731 | 26724
36753 | 413.698 | 26724
36754 | 424.1021 | 26724
36755 | 414.1743 | 26724
36756 | 418.9666 | 26724
36757 | 417.6234 | 26724
36758 | 419.91 | 26724
36759 | 401.0952 | 26724
36760 | 413.6655 | 26724
36761 | 406.0911 | 26724
36762 | 409.6445 | 26724
36763 | 414.0429 | 26724
36764 | 408.4547 | 26724
36765 | 427.0827 | 26724
36766 | 420.6127 | 26724
36767 | 422.7151 | 26724
36768 | 428.2148 | 26724
36769 | 412.6862 | 26724
36770 | 416.2788 | 26724
36771 | 414.3591 | 26724
36772 | 419.9931 | 26724
36773 | 427.0488 | 26724
36774 | 411.6421 | 26724
36775 | 416.0256 | 26724
36776 | 421.1259 | 26724
36777 | 420.3688 | 26724
36778 | 421.2449 | 26724
36779 | 416.1468 | 26724
36780 | 421.7564 | 26724
36781 | 423.4782 | 26724
36782 | 414.5245 | 26724
36783 | 406.2961 | 26724
36784 | 412.7708 | 26724
36785 | 423.6514 | 26724
36786 | 418.5007 | 26724
36787 | 414.606 | 26724
36788 | 416.4648 | 26724
36789 | 426.3006 | 26724
36790 | 410.0262 | 26724
36791 | 422.4366 | 26724
36792 | 427.7285 | 26724
36793 | 410.6819 | 26724
36794 | 403.8995 | 26724
36795 | 409.7254 | 26724
36796 | 415.3096 | 26724
36797 | 433.3876 | 26724
36798 | 423.8012 | 26724
36799 | 410.1301 | 26724
36800 | 413.1997 | 26724
36801 | 425.3265 | 26724
36802 | 422.3291 | 26724
36803 | 413.3862 | 26724
36804 | 422.2681 | 26724
36805 | 423.8651 | 26724
36806 | 431.9652 | 26724
36807 | 423.9516 | 26724
36808 | 417.0408 | 26724
36809 | 424.1659 | 26724
36810 | 417.6584 | 26724
36811 | 419.356 | 26724
36812 | 416.4341 | 26724
36813 | 417.39 | 26724
36814 | 431.3377 | 26724
36815 | 429.5454 | 26724
36816 | 418.644 | 26724
36817 | 425.5325 | 26724
36818 | 421.6989 | 26724
36819 | 416.573 | 26724
36820 | 412.4563 | 26724
36821 | 407.6606 | 26724
36822 | 413.8624 | 26724
36823 | 424.0185 | 26724
36824 | 419.8416 | 26724
36825 | 408.7568 | 26724
36826 | 411.6353 | 26724
36827 | 437.203 | 26724
36828 | 405.3199 | 26724
36829 | 413.2939 | 26724
36830 | 420.1535 | 26724
36831 | 422.6841 | 26724
36832 | 411.2326 | 26724
36833 | 417.6954 | 26724
36834 | 421.1263 | 26724
36835 | 405.5201 | 26724
36836 | 419.3072 | 26724
36837 | 401.803 | 26724
36838 | 407.6108 | 26724
36839 | 406.0753 | 26724
36840 | 425.4309 | 26724
36841 | 415.7663 | 26724
36842 | 415.3052 | 26724
36843 | 406.8837 | 26724
36844 | 419.8301 | 26724
36845 | 407.1029 | 26724
36846 | 409.2946 | 26724
36847 | 413.5686 | 26724
36848 | 416.3765 | 26724
36849 | 424.7 | 26724
36850 | 426.8301 | 26724
36851 | 416.7915 | 26724
36852 | 408.3206 | 26724
36853 | 409.1472 | 26724
36854 | 409.4893 | 26724
36855 | 425.5291 | 26724
36856 | 408.3666 | 26724
36857 | 419.3334 | 26724
36858 | 418.7127 | 26724
36859 | 424.5398 | 26724
36860 | 400.151 | 26724
36861 | 420.1645 | 26724
36862 | 430.8448 | 26724
36863 | 426.0619 | 26724
36864 | 412.3859 | 26724
36865 | 410.2317 | 26724
36866 | 402.0273 | 26724
36867 | 420.2349 | 26724
36868 | 421.1349 | 26724
36869 | 425.5994 | 26724
36870 | 417.1088 | 26724
36871 | 414.0621 | 26724
36872 | 403.8861 | 26724
36873 | 432.1646 | 26724
36874 | 416.188 | 26724
36875 | 430.382 | 26724
36876 | 423.6306 | 26724
36877 | 419.8489 | 26724
36878 | 416.9573 | 26724
36879 | 417.0606 | 26724
36880 | 430.5923 | 26724
36881 | 417.2959 | 26724
36882 | 433.0431 | 26724
36883 | 420.9717 | 26724
36884 | 416.1828 | 26724
36885 | 425.1981 | 26724
36886 | 416.4735 | 26724
36887 | 411.8827 | 26724
36888 | 418.2034 | 26724
36889 | 412.7581 | 26724
36890 | 403.202 | 26724
36891 | 421.1954 | 26724
36892 | 410.3405 | 26724
36893 | 406.308 | 26724
36894 | 426.7627 | 26724
36895 | 412.1488 | 26724
36896 | 421.2145 | 26724
36897 | 416.1741 | 26724
36898 | 422.524 | 26724
36899 | 428.8179 | 26724
36900 | 421.3514 | 26724
36901 | 406.5357 | 26724
36902 | 415.2372 | 26724
36903 | 418.5139 | 26724
36904 | 418.3368 | 26724
36905 | 428.9474 | 26724
36906 | 421.8616 | 26724
36907 | 433.7253 | 26724
36908 | 413.2781 | 26724
36909 | 411.1376 | 26724
36910 | 425.7987 | 26724
36911 | 426.3026 | 26724
36912 | 425.224 | 26724
36913 | 410.0275 | 26724
36914 | 418.1546 | 26724
36915 | 425.9856 | 26724
36916 | 405.5278 | 26724
36917 | 419.9666 | 26724
36918 | 406.1764 | 26724
36919 | 402.9245 | 26724
36920 | 404.3446 | 26724
36921 | 402.5294 | 26724
36922 | 431.5869 | 26724
36923 | 425.0732 | 26724
36924 | 440.0054 | 26724
36925 | 422.6349 | 26724
36926 | 411.2213 | 26724
36927 | 418.9693 | 26724
36928 | 419.7824 | 26724
36929 | 404.5248 | 26724
36930 | 425.0934 | 26724
36931 | 421.3434 | 26724
36932 | 417.3467 | 26724
36933 | 413.946 | 26724
36934 | 419.7174 | 26724
36935 | 419.2009 | 26724
36936 | 411.8271 | 26724
36937 | 415.6965 | 26724
36938 | 419.6817 | 26724
36939 | 423.8083 | 26724
36940 | 418.6667 | 26724
36941 | 412.7473 | 26724
36942 | 435.2124 | 26724
36943 | 410.2006 | 26724
36944 | 428.3047 | 26724
36945 | 406.0154 | 26724
36946 | 416.4212 | 26724
36947 | 423.8602 | 26724
36948 | 413.8089 | 26724
36949 | 411.4303 | 26724
36950 | 421.337 | 26724
36951 | 413.6876 | 26724
36952 | 432.657 | 26724
36953 | 410.8094 | 26724
36954 | 416.1317 | 26724
36955 | 403.4754 | 26724
36956 | 424.293 | 26724
36957 | 425.142 | 26724
36958 | 407.2603 | 26724
36959 | 419.2715 | 26724
36960 | 406.8598 | 26724
36961 | 422.256 | 26724
36962 | 424.9166 | 26724
36963 | 417.2265 | 26724
36964 | 429.4237 | 26724
36965 | 413.745 | 26724
36966 | 424.4363 | 26724
36967 | 408.6456 | 26724
36968 | 404.8449 | 26724
36969 | 411.4556 | 26724
36970 | 418.3019 | 26724
36971 | 415.4714 | 26724
36972 | 422.0598 | 26724
36973 | 415.4111 | 26724
36974 | 406.7402 | 26724
36975 | 401.2955 | 26724
36976 | 413.6808 | 26724
36977 | 412.1562 | 26724
36978 | 422.6064 | 26724
36979 | 435.4197 | 26724
36980 | 423.6399 | 26724
36981 | 399.5077 | 26724
36982 | 416.2322 | 26724
36983 | 412.5806 | 26724
36984 | 416.0044 | 26724
36985 | 419.4228 | 26724
36986 | 415.4424 | 26724
36987 | 406.9387 | 26724
36988 | 413.8128 | 26724
36989 | 431.3893 | 26724
36990 | 415.2462 | 26724
36991 | 402.8838 | 26724
36992 | 414.332 | 26724
36993 | 417.8449 | 26724
36994 | 414.1956 | 26724
36995 | 419.6533 | 26724
36996 | 411.1237 | 26724
36997 | 407.7709 | 26724
36998 | 407.5857 | 26724
36999 | 399.1999 | 26724
37000 | 427.6148 | 26724
37001 | 418.1443 | 26724
37002 | 415.4261 | 26724
37003 | 413.8697 | 26724
37004 | 402.3181 | 26724
37005 | 421.0402 | 26724
37006 | 429.6616 | 26724
37007 | 424.1476 | 26724
37008 | 408.2895 | 26724
37009 | 411.3331 | 26724
37010 | 419.7732 | 26724
37011 | 428.4634 | 26724
37012 | 429.918 | 26724
37013 | 414.2558 | 26724
37014 | 404.5222 | 26724
37015 | 424.7626 | 26724
37016 | 412.0331 | 26724
37017 | 414.9151 | 26724
37018 | 415.5597 | 26724
37019 | 427.1286 | 26724
37020 | 405.8086 | 26724
37021 | 417.9149 | 26724
37022 | 403.2649 | 26724
37023 | 425.4023 | 26724
37024 | 405.2381 | 26724
37025 | 425.0803 | 26724
37026 | 424.402 | 26724
37027 | 413.0904 | 26724
37028 | 411.1853 | 26724
37029 | 425.131 | 26724
37030 | 415.2811 | 26724
37031 | 414.871 | 26724
37032 | 421.7011 | 26724
37033 | 423.9618 | 26724
37034 | 414.164 | 26724
37035 | 423.0395 | 26724
37036 | 421.1648 | 26724
37037 | 401.7969 | 26724
37038 | 420.5953 | 26724
37039 | 416.1762 | 26724
37040 | 416.5227 | 26724
37041 | 415.372 | 26724
37042 | 414.0655 | 26724
37043 | 421.3583 | 26724
37044 | 405.2192 | 26724
37045 | 418.0359 | 26724
37046 | 417.0611 | 26724
37047 | 420.3465 | 26724
37048 | 416.074 | 26724
37049 | 424.0695 | 26724
37050 | 411.8999 | 26724
37051 | 414.6107 | 26724
37052 | 421.4717 | 26724
37053 | 417.3578 | 26724
37054 | 414.9709 | 26724
37055 | 407.8968 | 26724
37056 | 412.0383 | 26724
37057 | 425.8512 | 26724
37058 | 416.1871 | 26724
37059 | 432.7222 | 26724
37060 | 406.5195 | 26724
37061 | 419.4594 | 26724
37062 | 412.1773 | 26724
37063 | 417.3836 | 26724
37064 | 422.4088 | 26724
37065 | 410.4678 | 26724
37066 | 419.7823 | 26724
37067 | 419.6682 | 26724
37068 | 415.6825 | 26724
37069 | 425.8013 | 26724
37070 | 418.6424 | 26724
37071 | 421.8233 | 26724
37072 | 413.9074 | 26724
37073 | 418.0824 | 26724
37074 | 418.0433 | 26724
37075 | 424.409 | 26724
37076 | 400.6551 | 26724
37077 | 406.6307 | 26724
37078 | 413.1371 | 26724
37079 | 408.8731 | 26724
37080 | 407.3884 | 26724
37081 | 412.33 | 26724
37082 | 414.3377 | 26724
37083 | 401.484 | 26724
37084 | 433.2687 | 26724
37085 | 411.9673 | 26724
37086 | 417.3972 | 26724
37087 | 411.6602 | 26724
37088 | 408.1779 | 26724
37089 | 415.7666 | 26724
37090 | 416.8985 | 26724
37091 | 425.4528 | 26724
37092 | 410.5141 | 26724
37093 | 422.1432 | 26724
37094 | 398.9589 | 26724
37095 | 424.31 | 26724
37096 | 424.6896 | 26724
37097 | 406.0871 | 26724
37098 | 413.1441 | 26724
37099 | 416.738 | 26724
37100 | 432.1567 | 26724
37101 | 416.866 | 26724
37102 | 418.5364 | 26724
37103 | 419.9497 | 26724
37104 | 410.5727 | 26724
37105 | 421.8562 | 26724
37106 | 417.0351 | 26724
37107 | 407.4148 | 26724
37108 | 417.4877 | 26724
37109 | 421.7101 | 26724
37110 | 402.9489 | 26724
37111 | 406.6475 | 26724
37112 | 419.8969 | 26724
37113 | 404.9496 | 26724
37114 | 405.9248 | 26724
37115 | 415.1221 | 26724
37116 | 409.8047 | 26724
37117 | 424.4501 | 26724
37118 | 433.879 | 26724
37119 | 416.078 | 26724
37120 | 424.0365 | 26724
37121 | 427.732 | 26724
37122 | 416.4866 | 26724
37123 | 412.9881 | 26724
37124 | 416.2243 | 26724
37125 | 403.7588 | 26724
37126 | 413.7081 | 26724
37127 | 413.4578 | 26724
37128 | 413.3428 | 26724
37129 | 411.5004 | 26724
37130 | 407.3214 | 26724
37131 | 421.0846 | 26724
37132 | 421.8887 | 26724
37133 | 423.951 | 26724
37134 | 407.0524 | 26724
37135 | 407.1143 | 26724
37136 | 423.2027 | 26724
37137 | 417.404 | 26724
37138 | 405.5058 | 26724
37139 | 426.6082 | 26724
37140 | 425.6649 | 26724
37141 | 415.8279 | 26724
37142 | 419.7753 | 26724
37143 | 421.1286 | 26724
37144 | 417.5719 | 26724
37145 | 414.135 | 26724
37146 | 418.2248 | 26724
37147 | 412.086 | 26724
37148 | 409.9344 | 26724
37149 | 406.6313 | 26724
37150 | 422.2024 | 26724
37151 | 415.6143 | 26724
37152 | 399.7355 | 26724
37153 | 427.1936 | 26724
37154 | 427.596 | 26724
37155 | 409.7212 | 26724
37156 | 417.6411 | 26724
37157 | 408.5055 | 26724
37158 | 424.2383 | 26724
37159 | 416.2788 | 26724
37160 | 416.2546 | 26724
37161 | 416.3182 | 26724
37162 | 419.1416 | 26724
37163 | 415.1289 | 26724
37164 | 402.9546 | 26724
37165 | 402.2316 | 26724
37166 | 423.6227 | 26724
37167 | 409.2589 | 26724
37168 | 412.9963 | 26724
37169 | 417.0069 | 26724
37170 | 410.5783 | 26724
37171 | 412.8143 | 26724
37172 | 417.5397 | 26724
37173 | 408.9681 | 26724
37174 | 416.962 | 26724
37175 | 396.2647 | 26724
37176 | 430.6419 | 26724
37177 | 397.3758 | 26724
37178 | 426.2678 | 26724
37179 | 416.6499 | 26724
37180 | 419.479 | 26724
37181 | 420.0519 | 26724
37182 | 425.1715 | 26724
37183 | 419.5262 | 26724
37184 | 403.8964 | 26724
37185 | 423.4182 | 26724
37186 | 408.8067 | 26724
37187 | 415.4587 | 26724
37188 | 415.2208 | 26724
37189 | 418.067 | 26724
37190 | 416.6372 | 26724
37191 | 413.607 | 26724
37192 | 420.3691 | 26724
37193 | 418.5007 | 26724
37194 | 427.9137 | 26724
37195 | 420.7873 | 26724
37196 | 409.5786 | 26724
37197 | 409.9382 | 26724
37198 | 406.5734 | 26724
37199 | 422.5052 | 26724
37200 | 417.1936 | 26724
37201 | 414.2065 | 26724
37202 | 416.2337 | 26724
37203 | 416.321 | 26724
37204 | 424.8954 | 26724
37205 | 413.7929 | 26724
37206 | 413.32 | 26724
37207 | 427.6388 | 26724
37208 | 419.5583 | 26724
37209 | 407.8892 | 26724
37210 | 430.4277 | 26724
37211 | 412.2255 | 26724
37212 | 408.0408 | 26724
37213 | 404.4114 | 26724
37214 | 408.0397 | 26724
37215 | 406.2809 | 26724
37216 | 408.2491 | 26724
37217 | 427.6813 | 26724
37218 | 407.5417 | 26724
37219 | 413.7927 | 26724
37220 | 426.2407 | 26724
37221 | 415.0235 | 26724
37222 | 420.1315 | 26724
37223 | 421.7091 | 26724
37224 | 418.4545 | 26724
37225 | 418.0452 | 26724
37226 | 421.8829 | 26724
37227 | 419.0225 | 26724
37228 | 415.4949 | 26724
37229 | 415.3001 | 26724
37230 | 426.3973 | 26724
37231 | 423.2454 | 26724
37232 | 419.5983 | 26724
37233 | 422.2006 | 26724
37234 | 407.9949 | 26724
37235 | 414.8702 | 26724
37236 | 408.083 | 26724
37237 | 426.4046 | 26724
37238 | 420.7376 | 26724
37239 | 400.4275 | 26724
37240 | 422.0427 | 26724
37241 | 418.9775 | 26724
37242 | 402.4798 | 26724
37243 | 407.9144 | 26724
37244 | 421.8858 | 26724
37245 | 423.2166 | 26724
37246 | 413.8732 | 26724
37247 | 421.893 | 26724
37248 | 416.1103 | 26724
37249 | 428.2091 | 26724
37250 | 418.4901 | 26724
37251 | 399.4835 | 26724
37252 | 419.0385 | 26724
37253 | 434.6342 | 26724
37254 | 427.9806 | 26724
37255 | 418.2844 | 26724
37256 | 415.2404 | 26724
37257 | 405.8378 | 26724
37258 | 403.042 | 26724
37259 | 418.0004 | 26724
37260 | 437.3224 | 26724
37261 | 414.0768 | 26724
37262 | 420.6998 | 26724
37263 | 412.265 | 26724
37264 | 427.5759 | 26724
37265 | 418.407 | 26724
37266 | 415.072 | 26724
37267 | 397.0115 | 26724
37268 | 412.4937 | 26724
37269 | 422.484 | 26724
37270 | 420.8365 | 26724
37271 | 416.5096 | 26724
37272 | 403.4112 | 26724
37273 | 411.8448 | 26724
37274 | 421.4644 | 26724
37275 | 423.2095 | 26724
37276 | 415.7103 | 26724
37277 | 420.7778 | 26724
37278 | 411.8838 | 26724
37279 | 420.2061 | 26724
37280 | 416.8269 | 26724
37281 | 413.1072 | 26724
37282 | 422.3552 | 26724
37283 | 418.4603 | 26724
37284 | 405.3848 | 26724
37285 | 410.0884 | 26724
37286 | 420.5814 | 26724
37287 | 427.4828 | 26724
37288 | 407.9182 | 26724
37289 | 419.9037 | 26724
37290 | 418.5036 | 26724
37291 | 402.5488 | 26724
37292 | 417.4568 | 26724
37293 | 411.0489 | 26724
37294 | 406.1065 | 26724
37295 | 428.5289 | 26724
37296 | 414.4366 | 26724
37297 | 421.1012 | 26724
37298 | 413.2231 | 26724
37299 | 430.8447 | 26724
37300 | 415.2255 | 26724
37301 | 411.9774 | 26724
37302 | 421.8093 | 26724
37303 | 415.558 | 26724
37304 | 415.6183 | 26724
37305 | 434.901 | 26724
37306 | 425.6762 | 26724
37307 | 433.5078 | 26724
37308 | 421.8216 | 26724
37309 | 419.5237 | 26724
37310 | 407.6902 | 26724
37311 | 420.0486 | 26724
37312 | 410.9125 | 26724
37313 | 403.462 | 26724
37314 | 410.4865 | 26724
37315 | 424.5619 | 26724
37316 | 429.4197 | 26724
37317 | 395.3199 | 26724
37318 | 418.9151 | 26724
37319 | 421.1622 | 26724
37320 | 425.5606 | 26724
37321 | 418.9014 | 26724
37322 | 418.4603 | 26724
37323 | 417.1454 | 26724
37324 | 436.4531 | 26724
37325 | 420.281 | 26724
37326 | 413.6947 | 26724
37327 | 410.4193 | 26724
37328 | 423.8342 | 26724
37329 | 423.2617 | 26724
37330 | 409.8799 | 26724
37331 | 398.0075 | 26724
37332 | 409.8741 | 26724
37333 | 422.6345 | 26724
37334 | 417.6138 | 26724
37335 | 412.8598 | 26724
37336 | 412.2791 | 26724
37337 | 426.8402 | 26724
37338 | 419.3818 | 26724
37339 | 417.7838 | 26724
37340 | 419.9315 | 26724
37341 | 424.2991 | 26724
37342 | 421.8028 | 26724
37343 | 416.4827 | 26724
37344 | 411.237 | 26724
37345 | 410.8514 | 26724
37346 | 426.8444 | 26724
37347 | 424.9661 | 26724
37348 | 425.5699 | 26724
37349 | 414.9561 | 26724
37350 | 411.539 | 26724
37351 | 421.8992 | 26724
37352 | 425.1618 | 26724
37353 | 404.7347 | 26724
37354 | 428.5314 | 26724
37355 | 410.8875 | 26724
37356 | 423.8284 | 26724
37357 | 422.1364 | 26724
37358 | 426.3064 | 26724
37359 | 421.0665 | 26724
37360 | 418.7087 | 26724
37361 | 420.3944 | 26724
37362 | 419.8958 | 26724
37363 | 417.7675 | 26724
37364 | 413.034 | 26724
37365 | 423.4771 | 26724
37366 | 400.6073 | 26724
37367 | 403.7898 | 26724
37368 | 407.3083 | 26724
37369 | 425.462 | 26724
37370 | 419.0768 | 26724
37371 | 428.6083 | 26724
37372 | 413.0452 | 26724
37373 | 426.5317 | 26724
37374 | 415.5114 | 26724
37375 | 413.7645 | 26724
37376 | 417.3595 | 26724
37377 | 420.0495 | 26724
37378 | 422.8613 | 26724
37379 | 421.9361 | 26724
37380 | 424.1255 | 26724
37381 | 422.3732 | 26724
37382 | 408.4433 | 26724
37383 | 422.651 | 26724
37384 | 422.4347 | 26724
37385 | 409.2251 | 26724
37386 | 411.0719 | 26724
37387 | 412.3918 | 26724
37388 | 407.8444 | 26724
37389 | 416.761 | 26724
37390 | 427.0961 | 26724
37391 | 418.7435 | 26724
37392 | 420.081 | 26724
37393 | 413.7063 | 26724
37394 | 421.4806 | 26724
37395 | 411.4267 | 26724
37396 | 407.8307 | 26724
37397 | 413.9573 | 26724
37398 | 418.6494 | 26724
37399 | 429.98 | 26724
37400 | 407.8207 | 26724
37401 | 411.8844 | 26724
37402 | 426.8841 | 26724
37403 | 411.0657 | 26724
37404 | 415.1632 | 26724
37405 | 403.5819 | 26724
37406 | 423.7684 | 26724
37407 | 403.4927 | 26724
37408 | 405.8243 | 26724
37409 | 413.8115 | 26724
37410 | 405.8496 | 26724
37411 | 422.2932 | 26724
37412 | 421.3525 | 26724
37413 | 411.8284 | 26724
37414 | 422.5669 | 26724
37415 | 411.909 | 26724
37416 | 426.2977 | 26724
37417 | 433.069 | 26724
37418 | 418.8747 | 26724
37419 | 427.5493 | 26724
37420 | 416.5574 | 26724
37421 | 426.9158 | 26724
37422 | 432.8438 | 26724
37423 | 433.6563 | 26724
37424 | 413.5277 | 26724
37425 | 405.7165 | 26724
37426 | 421.9604 | 26724
37427 | 414.1006 | 26724
37428 | 411.4117 | 26724
37429 | 421.0387 | 26724
37430 | 406.1104 | 26724
37431 | 414.5599 | 26724
37432 | 415.1472 | 26724
37433 | 405.4945 | 26724
37434 | 406.4378 | 26724
37435 | 425.1631 | 26724
37436 | 419.21 | 26724
37437 | 417.3447 | 26724
37438 | 411.0306 | 26724
37439 | 433.0412 | 26724
37440 | 417.0698 | 26724
37441 | 426.4101 | 26724
37442 | 415.3966 | 26724
37443 | 411.5124 | 26724
37444 | 408.7285 | 26724
37445 | 411.4346 | 26724
37446 | 412.6952 | 26724
37447 | 413.1194 | 26724
37448 | 416.6 | 26724
37449 | 413.4899 | 26724
37450 | 417.6212 | 26724
37451 | 413.2781 | 26724
37452 | 406.2232 | 26724
37453 | 429.1968 | 26724
37454 | 408.6851 | 26724
37455 | 399.7434 | 26724
37456 | 424.6596 | 26724
37457 | 406.6504 | 26724
37458 | 418.5537 | 26724
37459 | 430.3308 | 26724
37460 | 410.5163 | 26724
37461 | 426.8135 | 26724
37462 | 407.5956 | 26724
37463 | 426.5702 | 26724
37464 | 416.3258 | 26724
37465 | 420.8748 | 26724
37466 | 419.1676 | 26724
37467 | 421.603 | 26724
37468 | 406.8414 | 26724
37469 | 420.8486 | 26724
37470 | 409.888 | 26724
37471 | 413.8468 | 26724
37472 | 406.5402 | 26724
37473 | 406.1183 | 26724
37474 | 412.5936 | 26724
37475 | 418.9231 | 26724
37476 | 424.8408 | 26724
37477 | 417.5169 | 26724
37478 | 423.0435 | 26724
37479 | 404.3919 | 26724
37480 | 422.5892 | 26724
37481 | 419.1653 | 26724
37482 | 412.6501 | 26724
37483 | 409.5391 | 26724
37484 | 421.0448 | 26724
37485 | 412.5447 | 26724
37486 | 421.1035 | 26724
37487 | 412.755 | 26724
37488 | 407.5871 | 26724
37489 | 419.6842 | 26724
37490 | 407.8515 | 26724
37491 | 404.7832 | 26724
37492 | 427.2786 | 26724
37493 | 426.7764 | 26724
37494 | 410.6332 | 26724
37495 | 414.8637 | 26724
37496 | 406.4482 | 26724
37497 | 408.0837 | 26724
37498 | 426.0298 | 26724
37499 | 416.6691 | 26724
37500 | 419.9602 | 26724
37501 | 407.4199 | 26724
37502 | 407.907 | 26724
37503 | 425.0914 | 26724
37504 | 417.7562 | 26724
37505 | 420.9107 | 26724
37506 | 413.5729 | 26724
37507 | 428.479 | 26724
37508 | 423.3965 | 26724
37509 | 413.6315 | 26724
37510 | 407.0469 | 26724
37511 | 410.923 | 26724
37512 | 415.0277 | 26724
37513 | 409.0487 | 26724
37514 | 418.9623 | 26724
37515 | 414.1131 | 26724
37516 | 409.4221 | 26724
37517 | 417.1788 | 26724
37518 | 409.3646 | 26724
37519 | 417.6525 | 26724
37520 | 419.6899 | 26724
37521 | 422.4151 | 26724
37522 | 406.6997 | 26724
37523 | 407.6507 | 26724
37524 | 419.944 | 26724
37525 | 420.4262 | 26724
37526 | 407.5514 | 26724
37527 | 425.7985 | 26724
37528 | 408.8013 | 26724
37529 | 415.2194 | 26724
37530 | 428.1542 | 26724
37531 | 411.815 | 26724
37532 | 419.6735 | 26724
37533 | 428.9457 | 26724
37534 | 416.8311 | 26724
37535 | 395.9709 | 26724
37536 | 425.7865 | 26724
37537 | 421.3046 | 26724
37538 | 414.8573 | 26724
37539 | 411.4313 | 26724
37540 | 421.7811 | 26724
37541 | 419.589 | 26724
37542 | 427.04 | 26724
37543 | 420.0613 | 26724
37544 | 412.1152 | 26724
37545 | 423.7577 | 26724
37546 | 420.8341 | 26724
37547 | 412.6237 | 26724
37548 | 407.5708 | 26724
37549 | 413.1385 | 26724
37550 | 414.9095 | 26724
37551 | 415.4249 | 26724
37552 | 412.3938 | 26724
37553 | 413.7929 | 26724
37554 | 419.8473 | 26724
37555 | 421.423 | 26724
37556 | 415.5072 | 26724
37557 | 405.9465 | 26724
37558 | 418.9858 | 26724
37559 | 413.1618 | 26724
37560 | 420.134 | 26724
37561 | 412.3107 | 26724
37562 | 420.9516 | 26724
37563 | 416.8941 | 26724
37564 | 405.9156 | 26724
37565 | 415.2482 | 26724
37566 | 414.9267 | 26724
37567 | 402.3216 | 26724
37568 | 427.8999 | 26724
37569 | 415.9989 | 26724
37570 | 403.6185 | 26724
37571 | 422.6471 | 26724
37572 | 426.0565 | 26724
37573 | 417.214 | 26724
37574 | 408.8135 | 26724
37575 | 412.6974 | 26724
37576 | 421.6383 | 26724
37577 | 430.7399 | 26724
37578 | 419.029 | 26724
37579 | 408.4418 | 26724
37580 | 422.6427 | 26724
37581 | 416.9058 | 26724
37582 | 423.6471 | 26724
37583 | 421.8183 | 26724
37584 | 397.5105 | 26724
37585 | 416.7943 | 26724
37586 | 406.2257 | 26724
37587 | 415.2779 | 26724
37588 | 429.7923 | 26724
37589 | 420.8245 | 26724
37590 | 423.3079 | 26724
37591 | 408.1197 | 26724
37592 | 400.9904 | 26724
37593 | 424.181 | 26724
37594 | 414.7578 | 26724
37595 | 419.943 | 26724
37596 | 425.5801 | 26724
37597 | 422.375 | 26724
37598 | 438.4593 | 26724
37599 | 416.5606 | 26724
37600 | 413.5153 | 26724
37601 | 415.1055 | 26724
37602 | 412.2295 | 26724
37603 | 423.6633 | 26724
37604 | 413.1647 | 26724
37605 | 413.8205 | 26724
37606 | 410.2043 | 26724
37607 | 408.1927 | 26724
37608 | 406.5997 | 26724
37609 | 410.6799 | 26724
37610 | 408.8072 | 26724
37611 | 411.9584 | 26724
37612 | 415.6144 | 26724
37613 | 421.6954 | 26724
37614 | 411.2992 | 26724
37615 | 419.9862 | 26724
37616 | 426.4413 | 26724
37617 | 431.4689 | 26724
37618 | 409.0802 | 26724
37619 | 426.0267 | 26724
37620 | 405.3672 | 26724
37621 | 419.0751 | 26724
37622 | 427.1177 | 26724
37623 | 416.1093 | 26724
37624 | 430.1354 | 26724
37625 | 429.1625 | 26724
37626 | 424.9806 | 26724
37627 | 409.5349 | 26724
37628 | 409.913 | 26724
37629 | 436.2753 | 26724
37630 | 412.9487 | 26724
37631 | 402.7222 | 26724
37632 | 425.5555 | 26724
37633 | 420.3485 | 26724
37634 | 415.7375 | 26724
37635 | 422.1403 | 26724
37636 | 411.6189 | 26724
37637 | 416.3956 | 26724
37638 | 413.8776 | 26724
37639 | 425.5974 | 26724
37640 | 416.9899 | 26724
37641 | 437.4317 | 26724
37642 | 419.1558 | 26724
37643 | 417.2008 | 26724
37644 | 415.0985 | 26724
37645 | 407.5527 | 26724
37646 | 411.4554 | 26724
37647 | 413.9191 | 26724
37648 | 422.5081 | 26724
37649 | 415.2195 | 26724
37650 | 427.7442 | 26724
37651 | 407.0202 | 26724
37652 | 417.3305 | 26724
37653 | 426.0323 | 26724
37654 | 416.3254 | 26724
37655 | 413.4237 | 26724
37656 | 422.596 | 26724
37657 | 420.5639 | 26724
37658 | 423.9913 | 26724
37659 | 406.0798 | 26724
37660 | 399.212 | 26724
37661 | 409.6503 | 26724
37662 | 412.5039 | 26724
37663 | 410.9195 | 26724
37664 | 417.7287 | 26724
37665 | 413.3332 | 26724
37666 | 425.3327 | 26724
37667 | 414.4476 | 26724
37668 | 419.5621 | 26724
37669 | 411.6115 | 26724
37670 | 420.3497 | 26724
37671 | 407.9772 | 26724
37672 | 415.491 | 26724
37673 | 423.4035 | 26724
37674 | 405.5581 | 26724
37675 | 411.6028 | 26724
37676 | 423.0894 | 26724
37677 | 420.2827 | 26724
37678 | 429.2068 | 26724
37679 | 415.1821 | 26724
37680 | 416.9101 | 26724
37681 | 433.633 | 26724
37682 | 426.0209 | 26724
37683 | 407.9239 | 26724
37684 | 410.0409 | 26724
37685 | 410.6051 | 26724
37686 | 412.0364 | 26724
37687 | 402.0353 | 26724
37688 | 420.7866 | 26724
37689 | 419.6 | 26724
37690 | 409.3051 | 26724
37691 | 406.8097 | 26724
37692 | 415.1217 | 26724
37693 | 401.756 | 26724
37694 | 422.4527 | 26724
37695 | 414.1342 | 26724
37696 | 420.9355 | 26724
37697 | 408.0615 | 26724
37698 | 419.2705 | 26724
37699 | 423.441 | 26724
37700 | 404.8668 | 26724
37701 | 420.6106 | 26724
37702 | 409.5126 | 26724
37703 | 415.3117 | 26724
37704 | 412.9768 | 26724
37705 | 425.5554 | 26724
37706 | 434.1508 | 26724
37707 | 409.1298 | 26724
37708 | 409.834 | 26724
37709 | 410.0279 | 26724
37710 | 408.5468 | 26724
37711 | 418.9053 | 26724
37712 | 418.8487 | 26724
37713 | 408.5702 | 26724
37714 | 416.3717 | 26724
37715 | 421.8992 | 26724
37716 | 402.546 | 26724
37717 | 429.2828 | 26724
37718 | 404.3096 | 26724
37719 | 404.5645 | 26724
37720 | 405.7641 | 26724
37721 | 418.725 | 26724
37722 | 412.0484 | 26724
37723 | 419.421 | 26724
37724 | 416.5847 | 26724
37725 | 434.8976 | 26724
37726 | 422.2183 | 26724
37727 | 396.0408 | 26724
37728 | 415.0513 | 26724
37729 | 417.9321 | 26724
37730 | 410.7569 | 26724
37731 | 413.1172 | 26724
37732 | 410.2803 | 26724
37733 | 410.8012 | 26724
37734 | 422.6148 | 26724
37735 | 425.5958 | 26724
37736 | 422.2797 | 26724
37737 | 415.2058 | 26724
37738 | 418.8986 | 26724
37739 | 410.7041 | 26724
37740 | 409.9864 | 26724
37741 | 421.7325 | 26724
37742 | 415.7852 | 26724
37743 | 423.0303 | 26724
37744 | 417.6145 | 26724
37745 | 420.5887 | 26724
37746 | 425.0367 | 26724
37747 | 418.7031 | 26724
37748 | 408.4097 | 26724
37749 | 424.1779 | 26724
37750 | 425.6163 | 26724
37751 | 412.173 | 26724
37752 | 417.7978 | 26724
37753 | 425.4442 | 26724
37754 | 430.8567 | 26724
37755 | 407.1194 | 26724
37756 | 411.2289 | 26724
37757 | 418.7293 | 26724
37758 | 421.0765 | 26724
37759 | 425.2449 | 26724
37760 | 428.1021 | 26724
37761 | 419.1896 | 26724
37762 | 415.9171 | 26724
37763 | 427.2468 | 26724
37764 | 411.7646 | 26724
37765 | 425.1402 | 26724
37766 | 413.3944 | 26724
37767 | 426.2374 | 26724
37768 | 409.0315 | 26724
37769 | 422.2809 | 26724
37770 | 410.0152 | 26724
37771 | 407.0389 | 26724
37772 | 420.5647 | 26724
37773 | 410.3089 | 26724
37774 | 417.4304 | 26724
37775 | 406.2148 | 26724
37776 | 427.2055 | 26724
37777 | 415.7297 | 26724
37778 | 415.4251 | 26724
37779 | 428.5057 | 26724
37780 | 409.0579 | 26724
37781 | 419.9081 | 26724
37782 | 412.1135 | 26724
37783 | 414.9812 | 26724
37784 | 413.1098 | 26724
37785 | 414.5132 | 26724
37786 | 401.1077 | 26724
37787 | 407.7135 | 26724
37788 | 428.2893 | 26724
37789 | 422.7364 | 26724
37790 | 413.4209 | 26724
37791 | 398.1199 | 26724
37792 | 396.4776 | 26724
37793 | 413.7955 | 26724
37794 | 405.7432 | 26724
37795 | 417.4448 | 26724
37796 | 406.9114 | 26724
37797 | 415.1044 | 26724
37798 | 431.2063 | 26724
37799 | 424.2413 | 26724
37800 | 420.9138 | 26724
37801 | 411.6433 | 26724
37802 | 427.0673 | 26724
37803 | 408.6435 | 26724
37804 | 409.852 | 26724
37805 | 424.6417 | 26724
37806 | 413.6821 | 26724
37807 | 419.2087 | 26724
37808 | 417.0804 | 26724
37809 | 434.0582 | 26724
37810 | 419.3919 | 26724
37811 | 421.1487 | 26724
37812 | 419.6573 | 26724
37813 | 414.4919 | 26724
37814 | 415.7923 | 26724
37815 | 428.2623 | 26724
37816 | 434.7172 | 26724
37817 | 424.7069 | 26724
37818 | 412.467 | 26724
37819 | 414.5359 | 26724
37820 | 423.7254 | 26724
37821 | 412.8825 | 26724
37822 | 408.3386 | 26724
37823 | 424.4742 | 26724
37824 | 417.5627 | 26724
37825 | 432.6246 | 26724
37826 | 402.9841 | 26724
37827 | 409.3194 | 26724
37828 | 414.1602 | 26724
37829 | 420.4717 | 26724
37830 | 411.3461 | 26724
37831 | 430.249 | 26724
37832 | 405.8228 | 26724
37833 | 417.944 | 26724
37834 | 431.6727 | 26724
37835 | 431.2812 | 26724
37836 | 405.4246 | 26724
37837 | 415.1817 | 26724
37838 | 425.4638 | 26724
37839 | 422.6888 | 26724
37840 | 421.7524 | 26724
37841 | 406.9916 | 26724
37842 | 421.2952 | 26724
37843 | 424.5012 | 26724
37844 | 419.9952 | 26724
37845 | 422.3348 | 26724
37846 | 412.5432 | 26724
37847 | 420.2009 | 26724
37848 | 413.4428 | 26724
37849 | 426.283 | 26724
37850 | 424.8207 | 26724
37851 | 411.4501 | 26724
37852 | 411.6343 | 26724
37853 | 409.8913 | 26724
37854 | 420.1029 | 26724
37855 | 415.7927 | 26724
37856 | 414.5345 | 26724
37857 | 403.5669 | 26724
37858 | 423.6017 | 26724
37859 | 414.8956 | 26724
37860 | 400.9337 | 26724
37861 | 424.273 | 26724
37862 | 414.5311 | 26724
37863 | 402.5408 | 26724
37864 | 411.1546 | 26724
37865 | 399.5351 | 26724
37866 | 422.3329 | 26724
37867 | 430.5613 | 26724
37868 | 433.8259 | 26724
37869 | 425.238 | 26724
37870 | 416.5856 | 26724
37871 | 420.2436 | 26724
37872 | 413.4841 | 26724
37873 | 409.2812 | 26724
37874 | 423.9599 | 26724
37875 | 416.3973 | 26724
37876 | 418.9923 | 26724
37877 | 431.7436 | 26724
37878 | 411.7735 | 26724
37879 | 410.7731 | 26724
37880 | 419.8403 | 26724
37881 | 405.3653 | 26724
37882 | 412.3296 | 26724
37883 | 421.7842 | 26724
37884 | 411.978 | 26724
37885 | 404.3317 | 26724
37886 | 411.7718 | 26724
37887 | 414.3756 | 26724
37888 | 414.4353 | 26724
37889 | 414.7193 | 26724
37890 | 406.9289 | 26724
37891 | 415.6318 | 26724
37892 | 417.9333 | 26724
37893 | 430.2982 | 26724
37894 | 410.8394 | 26724
37895 | 406.0072 | 26724
37896 | 421.0556 | 26724
37897 | 421.2982 | 26724
37898 | 409.2847 | 26724
37899 | 406.7965 | 26724
37900 | 408.8001 | 26724
37901 | 414.4141 | 26724
37902 | 426.6742 | 26724
37903 | 416.6843 | 26724
37904 | 408.9247 | 26724
37905 | 420.1661 | 26724
37906 | 418.8807 | 26724
37907 | 402.77 | 26724
37908 | 398.3973 | 26724
37909 | 408.7471 | 26724
37910 | 414.2757 | 26724
37911 | 419.9473 | 26724
37912 | 410.8735 | 26724
37913 | 406.6285 | 26724
37914 | 421.9372 | 26724
37915 | 421.2196 | 26724
37916 | 411.3905 | 26724
37917 | 425.3872 | 26724
37918 | 414.2149 | 26724
37919 | 410.4274 | 26724
37920 | 422.4102 | 26724
37921 | 414.6106 | 26724
37922 | 404.7674 | 26724
37923 | 425.963 | 26724
37924 | 410.7019 | 26724
37925 | 406.7983 | 26724
37926 | 414.3711 | 26724
37927 | 406.5928 | 26724
37928 | 407.2052 | 26724
37929 | 406.4723 | 26724
37930 | 414.9962 | 26724
37931 | 409.324 | 26724
37932 | 401.8304 | 26724
37933 | 419.819 | 26724
37934 | 413.9108 | 26724
37935 | 425.2696 | 26724
37936 | 423.123 | 26724
37937 | 424.3789 | 26724
37938 | 411.8232 | 26724
37939 | 419.2805 | 26724
37940 | 417.5921 | 26724
37941 | 404.0993 | 26724
37942 | 412.3153 | 26724
37943 | 421.4282 | 26724
37944 | 415.6923 | 26724
37945 | 413.8704 | 26724
37946 | 420.5669 | 26724
37947 | 419.2893 | 26724
37948 | 406.4639 | 26724
37949 | 413.3423 | 26724
37950 | 408.0893 | 26724
37951 | 408.3425 | 26724
37952 | 413.1639 | 26724
37953 | 418.5313 | 26724
37954 | 427.8072 | 26724
37955 | 424.8071 | 26724
37956 | 414.5725 | 26724
37957 | 402.1433 | 26724
37958 | 412.4266 | 26724
37959 | 412.8853 | 26724
37960 | 407.6311 | 26724
37961 | 412.1907 | 26724
37962 | 420.2021 | 26724
37963 | 414.42 | 26724
37964 | 403.0851 | 26724
37965 | 418.0147 | 26724
37966 | 420.4093 | 26724
37967 | 419.7517 | 26724
37968 | 411.3768 | 26724
37969 | 407.5983 | 26724
37970 | 424.6297 | 26724
37971 | 412.511 | 26724
37972 | 417.1715 | 26724
37973 | 417.6973 | 26724
37974 | 415.4576 | 26724
37975 | 430.3106 | 26724
37976 | 394.1747 | 26724
37977 | 415.8907 | 26724
37978 | 411.9309 | 26724
37979 | 407.2214 | 26724
37980 | 417.4319 | 26724
37981 | 410.5803 | 26724
37982 | 421.0051 | 26724
37983 | 408.2494 | 26724
37984 | 399.1175 | 26724
37985 | 411.4507 | 26724
37986 | 416.9134 | 26724
37987 | 408.0251 | 26724
37988 | 424.1089 | 26724
37989 | 413.6297 | 26724
37990 | 405.1499 | 26724
37991 | 409.7666 | 26724
37992 | 412.0713 | 26724
37993 | 411.4988 | 26724
37994 | 419.1396 | 26724
37995 | 407.3626 | 26724
37996 | 417.3687 | 26724
37997 | 410.9411 | 26724
37998 | 411.9925 | 26724
37999 | 413.4004 | 26724
38000 | 400.5159 | 26724
38001 | 408.1897 | 26724
38002 | 421.4007 | 26724
38003 | 424.1789 | 26724
38004 | 425.6022 | 26724
38005 | 418.9976 | 26724
38006 | 417.0043 | 26724
38007 | 420.6608 | 26724
38008 | 422.4579 | 26724
38009 | 413.2281 | 26724
38010 | 425.5182 | 26724
38011 | 415.0696 | 26724
38012 | 408.1825 | 26724
38013 | 415.0296 | 26724
38014 | 405.1636 | 26724
38015 | 406.4841 | 26724
38016 | 418.509 | 26724
38017 | 408.4895 | 26724
38018 | 413.4286 | 26724
38019 | 417.2153 | 26724
38020 | 408.3912 | 26724
38021 | 420.227 | 26724
38022 | 417.5469 | 26724
38023 | 409.1964 | 26724
38024 | 413.389 | 26724
38025 | 413.2897 | 26724
38026 | 403.8891 | 26724
38027 | 411.5462 | 26724
38028 | 406.2447 | 26724
38029 | 420.4735 | 26724
38030 | 420.8921 | 26724
38031 | 421.2581 | 26724
38032 | 415.6711 | 26724
38033 | 421.1808 | 26724
38034 | 413.0225 | 26724
38035 | 424.9375 | 26724
38036 | 419.0032 | 26724
38037 | 419.9036 | 26724
38038 | 413.4911 | 26724
38039 | 397.9096 | 26724
38040 | 421.6646 | 26724
38041 | 410.9268 | 26724
38042 | 400.5884 | 26724
38043 | 419.3928 | 26724
38044 | 420.1122 | 26724
38045 | 418.9555 | 26724
38046 | 413.447 | 26724
38047 | 418.6518 | 26724
38048 | 407.766 | 26724
38049 | 419.9823 | 26724
38050 | 420.7822 | 26724
38051 | 425.3428 | 26724
38052 | 412.2408 | 26724
38053 | 420.0146 | 26724
38054 | 419.4141 | 26724
38055 | 413.3635 | 26724
38056 | 419.8514 | 26724
38057 | 425.3562 | 26724
38058 | 417.2038 | 26724
38059 | 427.3475 | 26724
38060 | 430.2386 | 26724
38061 | 404.5368 | 26724
38062 | 414.2471 | 26724
38063 | 414.6049 | 26724
38064 | 424.4969 | 26724
38065 | 417.4874 | 26724
38066 | 419.0162 | 26724
38067 | 413.2216 | 26724
38068 | 430.5116 | 26724
38069 | 412.6331 | 26724
38070 | 413.5805 | 26724
38071 | 421.3319 | 26724
38072 | 418.2621 | 26724
38073 | 420.5988 | 26724
38074 | 403.439 | 26724
38075 | 411.759 | 26724
38076 | 409.4829 | 26724
38077 | 411.3519 | 26724
38078 | 415.792 | 26724
38079 | 419.4485 | 26724
38080 | 408.4904 | 26724
38081 | 419.5158 | 26724
38082 | 408.5675 | 26724
38083 | 405.413 | 26724
38084 | 418.9352 | 26724
38085 | 411.8721 | 26724
38086 | 432.7704 | 26724
38087 | 406.4327 | 26724
38088 | 419.7191 | 26724
38089 | 431.0486 | 26724
38090 | 424.6801 | 26724
38091 | 408.3898 | 26724
38092 | 427.5389 | 26724
38093 | 416.0009 | 26724
38094 | 407.0174 | 26724
38095 | 421.8932 | 26724
38096 | 423.1155 | 26724
38097 | 418.709 | 26724
38098 | 414.9661 | 26724
38099 | 425.4695 | 26724
38100 | 430.9875 | 26724
38101 | 419.285 | 26724
38102 | 429.4353 | 26724
38103 | 401.6083 | 26724
38104 | 420.5758 | 26724
38105 | 424.1532 | 26724
38106 | 421.1482 | 26724
38107 | 419.6665 | 26724
38108 | 412.0339 | 26724
38109 | 416.1024 | 26724
38110 | 408.201 | 26724
38111 | 408.9731 | 26724
38112 | 416.8431 | 26724
38113 | 404.6363 | 26724
38114 | 429.7649 | 26724
38115 | 412.374 | 26724
38116 | 416.6894 | 26724
38117 | 415.641 | 26724
38118 | 404.7079 | 26724
38119 | 416.5677 | 26724
38120 | 401.5424 | 26724
38121 | 421.5327 | 26724
38122 | 422.3129 | 26724
38123 | 424.0332 | 26724
38124 | 417.9815 | 26724
38125 | 411.744 | 26724
38126 | 395.2675 | 26724
38127 | 413.046 | 26724
38128 | 429.105 | 26724
38129 | 409.3687 | 26724
38130 | 429.1516 | 26724
38131 | 418.4433 | 26724
38132 | 409.6253 | 26724
38133 | 415.9674 | 26724
38134 | 416.4359 | 26724
38135 | 420.534 | 26724
38136 | 409.5028 | 26724
38137 | 429.6176 | 26724
38138 | 425.4127 | 26724
38139 | 414.2899 | 26724
38140 | 413.2569 | 26724
38141 | 426.7029 | 26724
38142 | 416.9509 | 26724
38143 | 420.5843 | 26724
38144 | 418.2841 | 26724
38145 | 401.3113 | 26724
38146 | 420.6809 | 26724
38147 | 423.8498 | 26724
38148 | 419.4223 | 26724
38149 | 411.4456 | 26724
38150 | 408.4742 | 26724
38151 | 419.4924 | 26724
38152 | 419.6105 | 26724
38153 | 420.0149 | 26724
38154 | 426.331 | 26724
38155 | 405.9908 | 26724
38156 | 425.1549 | 26724
38157 | 415.5346 | 26724
38158 | 417.5758 | 26724
38159 | 414.2701 | 26724
38160 | 424.5609 | 26724
38161 | 419.4526 | 26724
38162 | 414.68 | 26724
38163 | 410.232 | 26724
38164 | 414.1822 | 26724
38165 | 423.2846 | 26724
38166 | 405.4755 | 26724
38167 | 414.675 | 26724
38168 | 424.1014 | 26724
38169 | 411.2652 | 26724
38170 | 413.9424 | 26724
38171 | 419.5903 | 26724
38172 | 416.1339 | 26724
38173 | 406.0807 | 26724
38174 | 413.0625 | 26724
38175 | 407.4638 | 26724
38176 | 420.0459 | 26724
38177 | 417.2255 | 26724
38178 | 427.5355 | 26724
38179 | 425.8054 | 26724
38180 | 408.08 | 26724
38181 | 412.3085 | 26724
38182 | 416.518 | 26724
38183 | 412.7978 | 26724
38184 | 409.845 | 26724
38185 | 403.765 | 26724
38186 | 425.9103 | 26724
38187 | 424.8721 | 26724
38188 | 434.5715 | 26724
38189 | 423.9946 | 26724
38190 | 409.0085 | 26724
38191 | 414.8931 | 26724
38192 | 407.9937 | 26724
38193 | 426.9343 | 26724
38194 | 403.6038 | 26724
38195 | 406.558 | 26724
38196 | 419.1339 | 26724
38197 | 418.8349 | 26724
38198 | 425.4046 | 26724
38199 | 421.9199 | 26724
38200 | 407.7018 | 26724
38201 | 417.8572 | 26724
38202 | 413.1343 | 26724
38203 | 416.4586 | 26724
38204 | 414.6569 | 26724
38205 | 413.8785 | 26724
38206 | 409.6932 | 26724
38207 | 411.1685 | 26724
38208 | 416.3875 | 26724
38209 | 418.1133 | 26724
38210 | 425.5648 | 26724
38211 | 429.3499 | 26724
38212 | 434.6754 | 26724
38213 | 410.6146 | 26724
38214 | 420.4546 | 26724
38215 | 420.0846 | 26724
38216 | 405.5592 | 26724
38217 | 405.7155 | 26724
38218 | 425.9777 | 26724
38219 | 412.7792 | 26724
38220 | 409.1272 | 26724
38221 | 421.0322 | 26724
38222 | 419.4062 | 26724
38223 | 415.2354 | 26724
38224 | 413.8262 | 26724
38225 | 423.8031 | 26724
38226 | 429.3902 | 26724
38227 | 418.7905 | 26724
38228 | 419.6016 | 26724
38229 | 406.5045 | 26724
38230 | 422.6733 | 26724
38231 | 425.5282 | 26724
38232 | 420.1194 | 26724
38233 | 419.4797 | 26724
38234 | 428.1643 | 26724
38235 | 413.7845 | 26724
38236 | 420.4416 | 26724
38237 | 427.6 | 26724
38238 | 410.0158 | 26724
38239 | 392.8773 | 26724
38240 | 404.3161 | 26724
38241 | 422.0914 | 26724
38242 | 414.3589 | 26724
38243 | 428.8461 | 26724
38244 | 419.7706 | 26724
38245 | 422.1062 | 26724
38246 | 412.686 | 26724
38247 | 407.9416 | 26724
38248 | 430.0762 | 26724
38249 | 414.8246 | 26724
38250 | 409.0144 | 26724
38251 | 406.7537 | 26724
38252 | 414.3783 | 26724
38253 | 412.4041 | 26724
38254 | 422.9117 | 26724
38255 | 426.1733 | 26724
38256 | 423.4335 | 26724
38257 | 433.1776 | 26724
38258 | 420.1002 | 26724
38259 | 419.5311 | 26724
38260 | 406.5472 | 26724
38261 | 411.5248 | 26724
38262 | 402.7106 | 26724
38263 | 409.0303 | 26724
38264 | 406.2664 | 26724
38265 | 419.1861 | 26724
38266 | 419.7011 | 26724
38267 | 421.9353 | 26724
38268 | 413.0976 | 26724
38269 | 421.2315 | 26724
38270 | 413.4943 | 26724
38271 | 410.5672 | 26724
38272 | 401.3856 | 26724
38273 | 424.7145 | 26724
38274 | 413.7947 | 26724
38275 | 404.6069 | 26724
38276 | 415.5557 | 26724
38277 | 435.1648 | 26724
38278 | 419.4905 | 26724
38279 | 416.9862 | 26724
38280 | 404.2826 | 26724
38281 | 426.3616 | 26724
38282 | 413.8573 | 26724
38283 | 410.3871 | 26724
38284 | 407.3417 | 26724
38285 | 421.7704 | 26724
38286 | 414.5587 | 26724
38287 | 426.5014 | 26724
38288 | 400.8423 | 26724
38289 | 420.0732 | 26724
38290 | 419.826 | 26724
38291 | 420.9885 | 26724
38292 | 420.6422 | 26724
38293 | 423.2957 | 26724
38294 | 424.5742 | 26724
38295 | 425.4417 | 26724
38296 | 414.1838 | 26724
38297 | 423.2824 | 26724
38298 | 420.6651 | 26724
38299 | 407.0344 | 26724
38300 | 417.1787 | 26724
38301 | 414.603 | 26724
38302 | 428.3654 | 26724
38303 | 411.0251 | 26724
38304 | 420.8133 | 26724
38305 | 419.8394 | 26724
38306 | 422.7816 | 26724
38307 | 400.6412 | 26724
38308 | 429.5552 | 26724
38309 | 412.3567 | 26724
38310 | 411.2813 | 26724
38311 | 416.5458 | 26724
38312 | 399.478 | 26724
38313 | 410.8679 | 26724
38314 | 403.2342 | 26724
38315 | 431.7366 | 26724
38316 | 400.2837 | 26724
38317 | 430.6641 | 26724
38318 | 419.4207 | 26724
38319 | 418.5926 | 26724
38320 | 419.1948 | 26724
38321 | 417.2433 | 26724
38322 | 410.5486 | 26724
38323 | 425.4174 | 26724
38324 | 409.8305 | 26724
38325 | 415.5577 | 26724
38326 | 398.0297 | 26724
38327 | 431.3661 | 26724
38328 | 412.0949 | 26724
38329 | 424.6463 | 26724
38330 | 422.9787 | 26724
38331 | 416.2408 | 26724
38332 | 419.3538 | 26724
38333 | 418.8755 | 26724
38334 | 414.5811 | 26724
38335 | 397.9599 | 26724
38336 | 416.1723 | 26724
38337 | 414.2182 | 26724
38338 | 403.1878 | 26724
38339 | 427.5667 | 26724
38340 | 427.5461 | 26724
38341 | 423.19 | 26724
38342 | 425.6392 | 26724
38343 | 423.4168 | 26724
38344 | 424.9693 | 26724
38345 | 419.5317 | 26724
38346 | 421.483 | 26724
38347 | 419.1836 | 26724
38348 | 426.2553 | 26724
38349 | 417.453 | 26724
38350 | 416.7948 | 26724
38351 | 414.2761 | 26724
38352 | 425.7987 | 26724
38353 | 414.3627 | 26724
38354 | 414.918 | 26724
38355 | 415.4808 | 26724
38356 | 410.9539 | 26724
38357 | 411.059 | 26724
38358 | 417.6326 | 26724
38359 | 417.7604 | 26724
38360 | 417.5436 | 26724
38361 | 422.3074 | 26724
38362 | 420.196 | 26724
38363 | 420.1939 | 26724
38364 | 422.8423 | 26724
38365 | 412.8232 | 26724
38366 | 429.2062 | 26724
38367 | 418.0854 | 26724
38368 | 416.5964 | 26724
38369 | 415.1745 | 26724
38370 | 411.5667 | 26724
38371 | 426.024 | 26724
38372 | 426.8795 | 26724
38373 | 422.7145 | 26724
38374 | 406.7668 | 26724
38375 | 399.9987 | 26724
38376 | 413.6364 | 26724
38377 | 408.4427 | 26724
38378 | 416.2878 | 26724
38379 | 425.1504 | 26724
38380 | 421.6517 | 26724
38381 | 429.2023 | 26724
38382 | 423.7982 | 26724
38383 | 422.2844 | 26724
38384 | 423.9899 | 26724
38385 | 428.9421 | 26724
38386 | 421.2659 | 26724
38387 | 427.5529 | 26724
38388 | 407.6382 | 26724
38389 | 427.3104 | 26724
38390 | 412.6956 | 26724
38391 | 406.6453 | 26724
38392 | 413.6852 | 26724
38393 | 427.8114 | 26724
38394 | 419.1061 | 26724
38395 | 417.3815 | 26724
38396 | 417.4883 | 26724
38397 | 411.889 | 26724
38398 | 407.6504 | 26724
38399 | 419.4157 | 26724
38400 | 435.787 | 26724
38401 | 412.6859 | 26724
38402 | 413.8612 | 26724
38403 | 413.6216 | 26724
38404 | 420.7358 | 26724
38405 | 422.9707 | 26724
38406 | 414.8542 | 26724
38407 | 424.8708 | 26724
38408 | 413.2739 | 26724
38409 | 418.7029 | 26724
38410 | 415.287 | 26724
38411 | 429.4389 | 26724
38412 | 405.9025 | 26724
38413 | 418.3015 | 26724
38414 | 421.2528 | 26724
38415 | 409.3113 | 26724
38416 | 416.7708 | 26724
38417 | 405.8054 | 26724
38418 | 418.3687 | 26724
38419 | 428.9715 | 26724
38420 | 421.0808 | 26724
38421 | 424.7607 | 26724
38422 | 416.0039 | 26724
38423 | 405.9372 | 26724
38424 | 406.5944 | 26724
38425 | 427.9164 | 26724
38426 | 427.461 | 26724
38427 | 409.2218 | 26724
38428 | 411.9063 | 26724
38429 | 428.0165 | 26724
38430 | 429.13 | 26724
38431 | 408.4085 | 26724
38432 | 417.7106 | 26724
38433 | 423.5232 | 26724
38434 | 425.31 | 26724
38435 | 429.2399 | 26724
38436 | 414.8202 | 26724
38437 | 409.8715 | 26724
38438 | 417.4936 | 26724
38439 | 418.6968 | 26724
38440 | 414.9728 | 26724
38441 | 411.6082 | 26724
38442 | 424.908 | 26724
38443 | 402.939 | 26724
38444 | 403.1187 | 26724
38445 | 416.0705 | 26724
38446 | 421.4851 | 26724
38447 | 430.4243 | 26724
38448 | 410.8334 | 26724
38449 | 415.9258 | 26724
38450 | 410.1581 | 26724
38451 | 403.2837 | 26724
38452 | 416.7621 | 26724
38453 | 410.5034 | 26724
38454 | 429.7933 | 26724
38455 | 412.5785 | 26724
38456 | 411.6629 | 26724
38457 | 414.0977 | 26724
38458 | 412.6149 | 26724
38459 | 411.0563 | 26724
38460 | 425.3156 | 26724
38461 | 419.3006 | 26724
38462 | 417.0405 | 26724
38463 | 418.7028 | 26724
38464 | 407.1211 | 26724
38465 | 424.695 | 26724
38466 | 422.4487 | 26724
38467 | 404.935 | 26724
38468 | 418.4789 | 26724
38469 | 413.753 | 26724
38470 | 431.1294 | 26724
38471 | 410.1167 | 26724
38472 | 424.4591 | 26724
38473 | 412.1936 | 26724
38474 | 424.281 | 26724
38475 | 422.0293 | 26724
38476 | 407.432 | 26724
38477 | 401.8618 | 26724
38478 | 412.3985 | 26724
38479 | 402.9586 | 26724
38480 | 410.235 | 26724
38481 | 422.8647 | 26724
38482 | 426.4875 | 26724
38483 | 423.1907 | 26724
38484 | 412.5414 | 26724
38485 | 419.576 | 26724
38486 | 417.7751 | 26724
38487 | 406.7383 | 26724
38488 | 413.9231 | 26724
38489 | 415.3993 | 26724
38490 | 418.4113 | 26724
38491 | 410.031 | 26724
38492 | 415.0949 | 26724
38493 | 425.4389 | 26724
38494 | 407.9726 | 26724
38495 | 408.9643 | 26724
38496 | 417.0939 | 26724
38497 | 434.789 | 26724
38498 | 423.5138 | 26724
38499 | 410.0923 | 26724
38500 | 412.224 | 26724
38501 | 418.6227 | 26724
38502 | 416.1972 | 26724
38503 | 421.6829 | 26724
38504 | 404.9551 | 26724
38505 | 404.8622 | 26724
38506 | 420.7107 | 26724
38507 | 415.1304 | 26724
38508 | 422.6272 | 26724
38509 | 420.2521 | 26724
38510 | 416.9172 | 26724
38511 | 410.215 | 26724
38512 | 408.6355 | 26724
38513 | 410.2161 | 26724
38514 | 420.0909 | 26724
38515 | 414.151 | 26724
38516 | 416.6226 | 26724
38517 | 424.4358 | 26724
38518 | 416.8122 | 26724
38519 | 412.5689 | 26724
38520 | 405.304 | 26724
38521 | 419.7464 | 26724
38522 | 422.3079 | 26724
38523 | 413.8179 | 26724
38524 | 412.0388 | 26724
38525 | 422.8952 | 26724
38526 | 433.3421 | 26724
38527 | 417.1902 | 26724
38528 | 416.1536 | 26724
38529 | 414.2908 | 26724
38530 | 429.1941 | 26724
38531 | 428.7604 | 26724
38532 | 422.2742 | 26724
38533 | 424.7397 | 26724
38534 | 405.8326 | 26724
38535 | 416.596 | 26724
38536 | 414.814 | 26724
38537 | 413.2786 | 26724
38538 | 407.9012 | 26724
38539 | 418.7505 | 26724
38540 | 404.0538 | 26724
38541 | 414.1138 | 26724
38542 | 420.2676 | 26724
38543 | 404.1352 | 26724
38544 | 413.7015 | 26724
38545 | 426.8455 | 26724
38546 | 416.4669 | 26724
38547 | 419.4753 | 26724
38548 | 398.8159 | 26724
38549 | 410.7317 | 26724
38550 | 415.3369 | 26724
38551 | 429.5689 | 26724
38552 | 411.1662 | 26724
38553 | 419.6612 | 26724
38554 | 419.679 | 26724
38555 | 406.3465 | 26724
38556 | 411.6784 | 26724
38557 | 422.0768 | 26724
38558 | 417.7252 | 26724
38559 | 406.3677 | 26724
38560 | 424.8548 | 26724
38561 | 409.363 | 26724
38562 | 398.826 | 26724
38563 | 424.4642 | 26724
38564 | 422.7874 | 26724
38565 | 414.2629 | 26724
38566 | 405.9434 | 26724
38567 | 412.0181 | 26724
38568 | 419.0831 | 26724
38569 | 428.4597 | 26724
38570 | 419.6468 | 26724
38571 | 412.8311 | 26724
38572 | 407.8854 | 26724
38573 | 404.6122 | 26724
38574 | 429.6775 | 26724
38575 | 421.9476 | 26724
38576 | 411.913 | 26724
38577 | 405.4208 | 26724
38578 | 403.6467 | 26724
38579 | 426.8721 | 26724
38580 | 427.5843 | 26724
38581 | 418.8661 | 26724
38582 | 408.707 | 26724
38583 | 413.8963 | 26724
38584 | 395.8082 | 26724
38585 | 427.4073 | 26724
38586 | 414.1954 | 26724
38587 | 419.6363 | 26724
38588 | 411.3115 | 26724
38589 | 421.5427 | 26724
38590 | 413.728 | 26724
38591 | 413.9729 | 26724
38592 | 396.4845 | 26724
38593 | 419.2165 | 26724
38594 | 427.6512 | 26724
38595 | 413.5237 | 26724
38596 | 411.7045 | 26724
38597 | 413.1002 | 26724
38598 | 419.7951 | 26724
38599 | 413.1513 | 26724
38600 | 408.2547 | 26724
38601 | 408.8801 | 26724
38602 | 406.2287 | 26724
38603 | 419.6844 | 26724
38604 | 415.2255 | 26724
38605 | 407.7867 | 26724
38606 | 431.8861 | 26724
38607 | 416.4622 | 26724
38608 | 403.8936 | 26724
38609 | 409.1153 | 26724
38610 | 403.223 | 26724
38611 | 424.7155 | 26724
38612 | 418.6606 | 26724
38613 | 409.4361 | 26724
38614 | 417.5463 | 26724
38615 | 427.5944 | 26724
38616 | 414.8756 | 26724
38617 | 413.6889 | 26724
38618 | 420.6625 | 26724
38619 | 425.6719 | 26724
38620 | 418.6124 | 26724
38621 | 415.7528 | 26724
38622 | 417.8193 | 26724
38623 | 420.9811 | 26724
38624 | 402.6325 | 26724
38625 | 411.0159 | 26724
38626 | 415.6507 | 26724
38627 | 418.0146 | 26724
38628 | 409.6141 | 26724
38629 | 413.9211 | 26724
38630 | 403.7325 | 26724
38631 | 421.7483 | 26724
38632 | 409.6381 | 26724
38633 | 405.7108 | 26724
38634 | 405.3208 | 26724
38635 | 428.2645 | 26724
38636 | 410.7067 | 26724
38637 | 416.6955 | 26724
38638 | 413.3339 | 26724
38639 | 419.9929 | 26724
38640 | 416.1249 | 26724
38641 | 421.438 | 26724
38642 | 427.4462 | 26724
38643 | 405.9421 | 26724
38644 | 412.4723 | 26724
38645 | 410.4953 | 26724
38646 | 409.0322 | 26724
38647 | 411.8403 | 26724
38648 | 414.3092 | 26724
38649 | 410.6892 | 26724
38650 | 413.1571 | 26724
38651 | 427.896 | 26724
38652 | 422.0358 | 26724
38653 | 415.3941 | 26724
38654 | 421.1765 | 26724
38655 | 405.8832 | 26724
38656 | 425.9577 | 26724
38657 | 422.0964 | 26724
38658 | 408.2725 | 26724
38659 | 417.9493 | 26724
38660 | 416.4358 | 26724
38661 | 411.0524 | 26724
38662 | 406.977 | 26724
38663 | 416.9406 | 26724
38664 | 414.8253 | 26724
38665 | 411.4386 | 26724
38666 | 421.6544 | 26724
38667 | 433.3371 | 26724
38668 | 414.8668 | 26724
38669 | 409.077 | 26724
38670 | 423.1294 | 26724
38671 | 419.7318 | 26724
38672 | 408.6971 | 26724
38673 | 419.9514 | 26724
38674 | 418.892 | 26724
38675 | 425.9004 | 26724
38676 | 405.3608 | 26724
38677 | 420.2646 | 26724
38678 | 429.9737 | 26724
38679 | 414.0101 | 26724
38680 | 425.64 | 26724
38681 | 417.462 | 26724
38682 | 412.7741 | 26724
38683 | 408.0797 | 26724
38684 | 433.9141 | 26724
38685 | 414.4418 | 26724
38686 | 424.1588 | 26724
38687 | 397.4108 | 26724
38688 | 415.0742 | 26724
38689 | 411.9907 | 26724
38690 | 419.3832 | 26724
38691 | 420.2657 | 26724
38692 | 418.5397 | 26724
38693 | 409.5589 | 26724
38694 | 419.4103 | 26724
38695 | 414.7367 | 26724
38696 | 422.5209 | 26724
38697 | 420.917 | 26724
38698 | 426.8444 | 26724
38699 | 424.8689 | 26724
38700 | 420.9144 | 26724
38701 | 433.4438 | 26724
38702 | 416.2233 | 26724
38703 | 410.4833 | 26724
38704 | 417.2447 | 26724
38705 | 422.8871 | 26724
38706 | 422.7781 | 26724
38707 | 422.9149 | 26724
38708 | 420.6488 | 26724
38709 | 418.6575 | 26724
38710 | 411.5974 | 26724
38711 | 413.7306 | 26724
38712 | 423.2893 | 26724
38713 | 422.5928 | 26724
38714 | 410.4638 | 26724
38715 | 417.8204 | 26724
38716 | 409.6152 | 26724
38717 | 413.5079 | 26724
38718 | 419.9299 | 26724
38719 | 425.8665 | 26724
38720 | 403.0754 | 26724
38721 | 410.806 | 26724
38722 | 420.8067 | 26724
38723 | 424.4953 | 26724
38724 | 412.3403 | 26724
38725 | 404.0112 | 26724
38726 | 418.535 | 26724
38727 | 410.4043 | 26724
38728 | 417.4784 | 26724
38729 | 408.6113 | 26724
38730 | 403.4756 | 26724
38731 | 417.1038 | 26724
38732 | 417.4176 | 26724
38733 | 420.9658 | 26724
38734 | 419.1489 | 26724
38735 | 421.8372 | 26724
38736 | 420.7532 | 26724
38737 | 422.9141 | 26724
38738 | 409.4715 | 26724
38739 | 427.9496 | 26724
38740 | 416.866 | 26724
38741 | 406.6142 | 26724
38742 | 407.1608 | 26724
38743 | 426.2453 | 26724
38744 | 409.2384 | 26724
38745 | 417.7154 | 26724
38746 | 407.3253 | 26724
38747 | 424.9961 | 26724
38748 | 423.3963 | 26724
38749 | 414.7989 | 26724
38750 | 404.767 | 26724
38751 | 414.9786 | 26724
38752 | 410.6004 | 26724
38753 | 414.6105 | 26724
38754 | 408.1999 | 26724
38755 | 419.667 | 26724
38756 | 414.4946 | 26724
38757 | 421.4664 | 26724
38758 | 419.2171 | 26724
38759 | 410.999 | 26724
38760 | 417.8653 | 26724
38761 | 406.2318 | 26724
38762 | 427.5172 | 26724
38763 | 413.0779 | 26724
38764 | 407.6558 | 26724
38765 | 419.2107 | 26724
38766 | 430.2556 | 26724
38767 | 432.0522 | 26724
38768 | 411.8752 | 26724
38769 | 407.1886 | 26724
38770 | 422.5195 | 26724
38771 | 434.0618 | 26724
38772 | 415.3054 | 26724
38773 | 429.1456 | 26724
38774 | 414.0993 | 26724
38775 | 415.2686 | 26724
38776 | 410.7401 | 26724
38777 | 400.599 | 26724
38778 | 420.9254 | 26724
38779 | 419.2237 | 26724
38780 | 419.6939 | 26724
38781 | 411.3449 | 26724
38782 | 405.4308 | 26724
38783 | 412.3797 | 26724
38784 | 403.5962 | 26724
38785 | 418.45 | 26724
38786 | 420.7742 | 26724
38787 | 428.2604 | 26724
38788 | 414.91 | 26724
38789 | 404.706 | 26724
38790 | 421.9073 | 26724
38791 | 423.2362 | 26724
38792 | 425.2329 | 26724
38793 | 416.0721 | 26724
38794 | 415.3128 | 26724
38795 | 412.6442 | 26724
38796 | 399.5499 | 26724
38797 | 425.2126 | 26724
38798 | 402.7055 | 26724
38799 | 416.7873 | 26724
38800 | 415.7294 | 26724
38801 | 413.1681 | 26724
38802 | 403.7448 | 26724
38803 | 412.5369 | 26724
38804 | 415.7937 | 26724
38805 | 429.2486 | 26724
38806 | 425.9231 | 26724
38807 | 408.3973 | 26724
38808 | 407.2667 | 26724
38809 | 406.3629 | 26724
38810 | 426.3039 | 26724
38811 | 413.0518 | 26724
38812 | 403.6703 | 26724
38813 | 413.6408 | 26724
38814 | 409.0899 | 26724
38815 | 411.1909 | 26724
38816 | 417.5978 | 26724
38817 | 421.2683 | 26724
38818 | 431.3708 | 26724
38819 | 419.591 | 26724
38820 | 419.4821 | 26724
38821 | 424.5814 | 26724
38822 | 425.1374 | 26724
38823 | 416.1123 | 26724
38824 | 412.7545 | 26724
38825 | 406.9017 | 26724
38826 | 432.213 | 26724
38827 | 423.3094 | 26724
38828 | 425.9265 | 26724
38829 | 427.9648 | 26724
38830 | 420.7882 | 26724
38831 | 403.9453 | 26724
38832 | 408.4933 | 26724
38833 | 415.0526 | 26724
38834 | 430.9834 | 26724
38835 | 411.7524 | 26724
38836 | 404.6485 | 26724
38837 | 420.5751 | 26724
38838 | 411.6779 | 26724
38839 | 409.6665 | 26724
38840 | 426.6265 | 26724
38841 | 405.9106 | 26724
38842 | 407.6703 | 26724
38843 | 408.4587 | 26724
38844 | 413.2575 | 26724
38845 | 413.3011 | 26724
38846 | 405.7745 | 26724
38847 | 429.7686 | 26724
38848 | 429.1164 | 26724
38849 | 426.9859 | 26724
38850 | 427.1185 | 26724
38851 | 417.1975 | 26724
38852 | 418.0966 | 26724
38853 | 423.1073 | 26724
38854 | 409.3415 | 26724
38855 | 425.1799 | 26724
38856 | 409.7912 | 26724
38857 | 404.4508 | 26724
38858 | 405.4839 | 26724
38859 | 415.2188 | 26724
38860 | 409.4897 | 26724
38861 | 400.0275 | 26724
38862 | 425.7245 | 26724
38863 | 418.6074 | 26724
38864 | 410.8434 | 26724
38865 | 426.8595 | 26724
38866 | 438.9079 | 26724
38867 | 429.1561 | 26724
38868 | 397.6431 | 26724
38869 | 413.1975 | 26724
38870 | 408.6777 | 26724
38871 | 402.4815 | 26724
38872 | 427.5412 | 26724
38873 | 431.486 | 26724
38874 | 398.1435 | 26724
38875 | 424.572 | 26724
38876 | 416.123 | 26724
38877 | 411.0505 | 26724
38878 | 419.5101 | 26724
38879 | 415.5333 | 26724
38880 | 413.0632 | 26724
38881 | 426.6564 | 26724
38882 | 410.8059 | 26724
38883 | 404.779 | 26724
38884 | 416.1853 | 26724
38885 | 411.496 | 26724
38886 | 431.7149 | 26724
38887 | 425.7457 | 26724
38888 | 408.3172 | 26724
38889 | 413.1955 | 26724
38890 | 424.9568 | 26724
38891 | 420.7972 | 26724
38892 | 409.5156 | 26724
38893 | 416.1637 | 26724
38894 | 407.6838 | 26724
38895 | 408.1009 | 26724
38896 | 418.1058 | 26724
38897 | 398.5829 | 26724
38898 | 422.3601 | 26724
38899 | 420.1845 | 26724
38900 | 423.7514 | 26724
38901 | 428.9658 | 26724
38902 | 412.5797 | 26724
38903 | 407.3718 | 26724
38904 | 427.361 | 26724
38905 | 416.1837 | 26724
38906 | 418.9353 | 26724
38907 | 422.7539 | 26724
38908 | 418.3897 | 26724
38909 | 425.1216 | 26724
38910 | 413.447 | 26724
38911 | 411.3897 | 26724
38912 | 414.8081 | 26724
38913 | 417.7561 | 26724
38914 | 407.7913 | 26724
38915 | 410.728 | 26724
38916 | 425.3542 | 26724
38917 | 416.402 | 26724
38918 | 409.4024 | 26724
38919 | 413.0546 | 26724
38920 | 417.8768 | 26724
38921 | 429.8901 | 26724
38922 | 421.0201 | 26724
38923 | 429.448 | 26724
38924 | 408.6192 | 26724
38925 | 414.1755 | 26724
38926 | 417.2773 | 26724
38927 | 409.6546 | 26724
38928 | 420.6068 | 26724
38929 | 423.3115 | 26724
38930 | 426.286 | 26724
38931 | 431.7655 | 26724
38932 | 421.7563 | 26724
38933 | 404.9434 | 26724
38934 | 404.9957 | 26724
38935 | 415.9183 | 26724
38936 | 417.8072 | 26724
38937 | 424.0975 | 26724
38938 | 415.9563 | 26724
38939 | 415.9157 | 26724
38940 | 419.7713 | 26724
38941 | 417.344 | 26724
38942 | 415.8795 | 26724
38943 | 411.3048 | 26724
38944 | 419.5116 | 26724
38945 | 412.4154 | 26724
38946 | 401.7378 | 26724
38947 | 416.8304 | 26724
38948 | 414.6619 | 26724
38949 | 403.694 | 26724
38950 | 416.581 | 26724
38951 | 417.388 | 26724
38952 | 396.2211 | 26724
38953 | 421.8472 | 26724
38954 | 425.4276 | 26724
38955 | 425.0656 | 26724
38956 | 405.0805 | 26724
38957 | 409.5341 | 26724
38958 | 417.8019 | 26724
38959 | 419.7431 | 26724
38960 | 426.5906 | 26724
38961 | 415.7017 | 26724
38962 | 419.5203 | 26724
38963 | 425.2654 | 26724
38964 | 420.7457 | 26724
38965 | 405.4168 | 26724
38966 | 416.5689 | 26724
38967 | 424.9462 | 26724
38968 | 427.5775 | 26724
38969 | 402.3695 | 26724
38970 | 413.2904 | 26724
38971 | 433.2638 | 26724
38972 | 420.9779 | 26724
38973 | 410.2959 | 26724
38974 | 423.4477 | 26724
38975 | 427.3723 | 26724
38976 | 406.5485 | 26724
38977 | 412.8604 | 26724
38978 | 422.8437 | 26724
38979 | 424.5039 | 26724
38980 | 405.6612 | 26724
38981 | 415.8029 | 26724
38982 | 420.8296 | 26724
38983 | 429.7328 | 26724
38984 | 408.1877 | 26724
38985 | 422.3033 | 26724
38986 | 397.7112 | 26724
38987 | 423.3225 | 26724
38988 | 418.6142 | 26724
38989 | 429.3514 | 26724
38990 | 410.5478 | 26724
38991 | 412.2997 | 26724
38992 | 410.3569 | 26724
38993 | 421.4613 | 26724
38994 | 423.5621 | 26724
38995 | 414.3514 | 26724
38996 | 422.4806 | 26724
38997 | 413.1731 | 26724
38998 | 406.7973 | 26724
38999 | 425.4344 | 26724
39000 | 416.0691 | 26724
39001 | 401.3969 | 26724
39002 | 408.6239 | 26724
39003 | 406.3788 | 26724
39004 | 414.9101 | 26724
39005 | 406.9491 | 26724
39006 | 410.5505 | 26724
39007 | 404.5815 | 26724
39008 | 418.745 | 26724
39009 | 431.671 | 26724
39010 | 432.3023 | 26724
39011 | 425.6551 | 26724
39012 | 407.6813 | 26724
39013 | 418.475 | 26724
39014 | 420.116 | 26724
39015 | 423.0155 | 26724
39016 | 410.0564 | 26724
39017 | 405.8035 | 26724
39018 | 428.5608 | 26724
39019 | 419.0071 | 26724
39020 | 424.7284 | 26724
39021 | 409.9831 | 26724
39022 | 402.1434 | 26724
39023 | 430.0494 | 26724
39024 | 419.1578 | 26724
39025 | 417.8731 | 26724
39026 | 420.0797 | 26724
39027 | 411.2746 | 26724
39028 | 406.5532 | 26724
39029 | 421.0719 | 26724
39030 | 417.1101 | 26724
39031 | 436.3112 | 26724
39032 | 415.6703 | 26724
39033 | 424.9903 | 26724
39034 | 429.1401 | 26724
39035 | 419.6683 | 26724
39036 | 427.1339 | 26724
39037 | 414.1348 | 26724
39038 | 427.8598 | 26724
39039 | 416.0433 | 26724
39040 | 423.6955 | 26724
39041 | 407.0164 | 26724
39042 | 421.2078 | 26724
39043 | 415.1894 | 26724
39044 | 417.0891 | 26724
39045 | 406.596 | 26724
39046 | 414.9841 | 26724
39047 | 414.3397 | 26724
39048 | 417.1772 | 26724
39049 | 393.9355 | 26724
39050 | 427.2409 | 26724
39051 | 413.5286 | 26724
39052 | 405.8701 | 26724
39053 | 418.3538 | 26724
39054 | 415.9959 | 26724
39055 | 416.5322 | 26724
39056 | 419.4406 | 26724
39057 | 422.0237 | 26724
39058 | 409.2134 | 26724
39059 | 413.866 | 26724
39060 | 422.1592 | 26724
39061 | 432.4132 | 26724
39062 | 412.6045 | 26724
39063 | 411.3265 | 26724
39064 | 411.1751 | 26724
39065 | 429.0009 | 26724
39066 | 404.879 | 26724
39067 | 413.1863 | 26724
39068 | 421.9666 | 26724
39069 | 414.5733 | 26724
39070 | 416.9171 | 26724
39071 | 413.7777 | 26724
39072 | 413.8019 | 26724
39073 | 409.7925 | 26724
39074 | 415.0236 | 26724
39075 | 409.8612 | 26724
39076 | 413.6617 | 26724
39077 | 408.1489 | 26724
39078 | 411.673 | 26724
39079 | 414.2266 | 26724
39080 | 421.26 | 26724
39081 | 416.1392 | 26724
39082 | 421.4949 | 26724
39083 | 406.8353 | 26724
39084 | 420.5843 | 26724
39085 | 429.7796 | 26724
39086 | 396.7794 | 26724
39087 | 409.9487 | 26724
39088 | 414.8277 | 26724
39089 | 408.3628 | 26724
39090 | 409.4582 | 26724
39091 | 400.0797 | 26724
39092 | 419.207 | 26724
39093 | 409.0292 | 26724
39094 | 414.6522 | 26724
39095 | 435.7891 | 26724
39096 | 420.4742 | 26724
39097 | 418.3273 | 26724
39098 | 413.671 | 26724
39099 | 423.5571 | 26724
39100 | 421.9786 | 26724
39101 | 410.4991 | 26724
39102 | 422.3658 | 26724
39103 | 418.2511 | 26724
39104 | 424.2659 | 26724
39105 | 408.8913 | 26724
39106 | 419.5808 | 26724
39107 | 413.9682 | 26724
39108 | 409.3524 | 26724
39109 | 418.938 | 26724
39110 | 408.0911 | 26724
39111 | 419.5363 | 26724
39112 | 404.8743 | 26724
39113 | 402.3945 | 26724
39114 | 423.0798 | 26724
39115 | 406.2734 | 26724
39116 | 425.4274 | 26724
39117 | 413.0557 | 26724
39118 | 423.1942 | 26724
39119 | 407.3001 | 26724
39120 | 412.6122 | 26724
39121 | 431.6594 | 26724
39122 | 425.451 | 26724
39123 | 418.3772 | 26724
39124 | 423.5621 | 26724
39125 | 407.4632 | 26724
39126 | 412.659 | 26724
39127 | 409.9777 | 26724
39128 | 412.9022 | 26724
39129 | 428.4307 | 26724
39130 | 422.02 | 26724
39131 | 406.5927 | 26724
39132 | 419.3079 | 26724
39133 | 405.1871 | 26724
39134 | 400.874 | 26724
39135 | 416.3456 | 26724
39136 | 428.4414 | 26724
39137 | 420.8816 | 26724
39138 | 396.7197 | 26724
39139 | 421.4183 | 26724
39140 | 424.0545 | 26724
39141 | 418.9051 | 26724
39142 | 419.3638 | 26724
39143 | 407.241 | 26724
39144 | 433.0788 | 26724
39145 | 420.9125 | 26724
39146 | 422.6164 | 26724
39147 | 416.7247 | 26724
39148 | 417.086 | 26724
39149 | 416.5553 | 26724
39150 | 416.8807 | 26724
39151 | 423.0943 | 26724
39152 | 417.0124 | 26724
39153 | 418.0973 | 26724
39154 | 411.6596 | 26724
39155 | 425.7285 | 26724
39156 | 422.0506 | 26724
39157 | 406.0316 | 26724
39158 | 412.9908 | 26724
39159 | 428.6782 | 26724
39160 | 424.4824 | 26724
39161 | 414.2034 | 26724
39162 | 439.0873 | 26724
39163 | 414.433 | 26724
39164 | 418.1346 | 26724
39165 | 432.0516 | 26724
39166 | 420.7746 | 26724
39167 | 423.0939 | 26724
39168 | 407.7982 | 26724
39169 | 415.1172 | 26724
39170 | 403.1205 | 26724
39171 | 431.0371 | 26724
39172 | 395.0482 | 26724
39173 | 415.9169 | 26724
39174 | 412.0557 | 26724
39175 | 411.7647 | 26724
39176 | 406.0585 | 26724
39177 | 412.2206 | 26724
39178 | 414.9423 | 26724
39179 | 413.4382 | 26724
39180 | 402.0139 | 26724
39181 | 413.3922 | 26724
39182 | 418.3483 | 26724
39183 | 409.845 | 26724
39184 | 416.3714 | 26724
39185 | 417.2481 | 26724
39186 | 422.4442 | 26724
39187 | 423.5987 | 26724
39188 | 419.3497 | 26724
39189 | 409.5829 | 26724
39190 | 420.8812 | 26724
39191 | 433.1092 | 26724
39192 | 414.3459 | 26724
39193 | 418.4421 | 26724
39194 | 419.8135 | 26724
39195 | 402.2178 | 26724
39196 | 411.1706 | 26724
39197 | 405.1035 | 26724
39198 | 413.9529 | 26724
39199 | 403.0299 | 26724
39200 | 409.9468 | 26724
39201 | 422.9355 | 26724
39202 | 425.1922 | 26724
39203 | 415.5954 | 26724
39204 | 421.4228 | 26724
39205 | 422.388 | 26724
39206 | 401.2745 | 26724
39207 | 419.0728 | 26724
39208 | 422.7201 | 26724
39209 | 427.2534 | 26724
39210 | 407.6009 | 26724
39211 | 416.7985 | 26724
39212 | 408.703 | 26724
39213 | 415.5396 | 26724
39214 | 425.8598 | 26724
39215 | 412.4851 | 26724
39216 | 417.7613 | 26724
39217 | 414.1681 | 26724
39218 | 405.859 | 26724
39219 | 406.7207 | 26724
39220 | 413.9489 | 26724
39221 | 410.0171 | 26724
39222 | 402.3588 | 26724
39223 | 423.8608 | 26724
39224 | 424.5018 | 26724
39225 | 410.1378 | 26724
39226 | 417.4457 | 26724
39227 | 418.4071 | 26724
39228 | 405.0784 | 26724
39229 | 436.2648 | 26724
39230 | 418.7874 | 26724
39231 | 416.7781 | 26724
39232 | 406.0979 | 26724
39233 | 417.615 | 26724
39234 | 422.0565 | 26724
39235 | 409.5909 | 26724
39236 | 423.7259 | 26724
39237 | 421.3168 | 26724
39238 | 420.1445 | 26724
39239 | 412.5094 | 26724
39240 | 410.7897 | 26724
39241 | 408.1501 | 26724
39242 | 422.9237 | 26724
39243 | 407.7448 | 26724
39244 | 420.0797 | 26724
39245 | 423.8701 | 26724
39246 | 410.7995 | 26724
39247 | 419.7395 | 26724
39248 | 415.9304 | 26724
39249 | 428.6463 | 26724
39250 | 404.1468 | 26724
39251 | 400.1514 | 26724
39252 | 420.861 | 26724
39253 | 418.8213 | 26724
39254 | 418.5573 | 26724
39255 | 418.9148 | 26724
39256 | 416.5469 | 26724
39257 | 400.6076 | 26724
39258 | 416.2261 | 26724
39259 | 422.5796 | 26724
39260 | 418.3877 | 26724
39261 | 424.1076 | 26724
39262 | 419.2421 | 26724
39263 | 424.5127 | 26724
39264 | 427.9516 | 26724
39265 | 417.0157 | 26724
39266 | 418.6414 | 26724
39267 | 421.3588 | 26724
39268 | 406.7932 | 26724
39269 | 405.4494 | 26724
39270 | 415.5049 | 26724
39271 | 419.7275 | 26724
39272 | 409.6828 | 26724
39273 | 422.1671 | 26724
39274 | 421.2948 | 26724
39275 | 418.1945 | 26724
39276 | 413.0696 | 26724
39277 | 405.2181 | 26724
39278 | 434.4266 | 26724
39279 | 410.3798 | 26724
39280 | 415.6779 | 26724
39281 | 416.7256 | 26724
39282 | 429.0658 | 26724
39283 | 426.6519 | 26724
39284 | 419.9731 | 26724
39285 | 425.4803 | 26724
39286 | 420.2587 | 26724
39287 | 408.6104 | 26724
39288 | 411.5614 | 26724
39289 | 414.598 | 26724
39290 | 420.2275 | 26724
39291 | 410.4359 | 26724
39292 | 412.5283 | 26724
39293 | 414.6987 | 26724
39294 | 418.0126 | 26724
39295 | 401.4595 | 26724
39296 | 419.2489 | 26724
39297 | 404.1488 | 26724
39298 | 410.7158 | 26724
39299 | 406.3155 | 26724
39300 | 407.8647 | 26724
39301 | 414.0726 | 26724
39302 | 422.5407 | 26724
39303 | 429.9622 | 26724
39304 | 417.9996 | 26724
39305 | 430.3025 | 26724
39306 | 410.4878 | 26724
39307 | 426.6138 | 26724
39308 | 413.5133 | 26724
39309 | 422.2762 | 26724
39310 | 414.9766 | 26724
39311 | 409.4373 | 26724
39312 | 420.1724 | 26724
39313 | 410.1297 | 26724
39314 | 412.4653 | 26724
39315 | 425.4802 | 26724
39316 | 424.7444 | 26724
39317 | 408.8197 | 26724
39318 | 411.4856 | 26724
39319 | 407.1204 | 26724
39320 | 406.1556 | 26724
39321 | 406.0701 | 26724
39322 | 404.8022 | 26724
39323 | 425.643 | 26724
39324 | 421.1034 | 26724
39325 | 411.4777 | 26724
39326 | 425.1247 | 26724
39327 | 415.3587 | 26724
39328 | 412.9971 | 26724
39329 | 402.6566 | 26724
39330 | 406.7626 | 26724
39331 | 401.0765 | 26724
39332 | 405.1319 | 26724
39333 | 416.1307 | 26724
39334 | 417.849 | 26724
39335 | 418.3343 | 26724
39336 | 411.3373 | 26724
39337 | 403.7893 | 26724
39338 | 415.079 | 26724
39339 | 416.9739 | 26724
39340 | 404.0429 | 26724
39341 | 417.5977 | 26724
39342 | 413.9764 | 26724
39343 | 412.1324 | 26724
39344 | 411.8483 | 26724
39345 | 415.008 | 26724
39346 | 419.3607 | 26724
39347 | 408.778 | 26724
39348 | 429.7794 | 26724
39349 | 407.913 | 26724
39350 | 413.5551 | 26724
39351 | 402.1951 | 26724
39352 | 401.8969 | 26724
39353 | 419.4576 | 26724
39354 | 411.699 | 26724
39355 | 416.4663 | 26724
39356 | 426.476 | 26724
39357 | 411.4342 | 26724
39358 | 405.6884 | 26724
39359 | 416.4732 | 26724
39360 | 419.4344 | 26724
39361 | 420.4742 | 26724
39362 | 419.4499 | 26724
39363 | 410.2026 | 26724
39364 | 410.8127 | 26724
39365 | 409.8539 | 26724
39366 | 411.9251 | 26724
39367 | 417.8607 | 26724
39368 | 414.3428 | 26724
39369 | 427.476 | 26724
39370 | 412.9243 | 26724
39371 | 419.4566 | 26724
39372 | 435.2902 | 26724
39373 | 425.1673 | 26724
39374 | 411.1045 | 26724
39375 | 407.4351 | 26724
39376 | 411.3302 | 26724
39377 | 410.9705 | 26724
39378 | 413.5339 | 26724
39379 | 421.02 | 26724
39380 | 415.6472 | 26724
39381 | 422.7474 | 26724
39382 | 418.8059 | 26724
39383 | 412.7815 | 26724
39384 | 408.8876 | 26724
39385 | 421.1983 | 26724
39386 | 411.6576 | 26724
39387 | 420.3079 | 26724
39388 | 417.5729 | 26724
39389 | 409.8148 | 26724
39390 | 410.664 | 26724
39391 | 414.3875 | 26724
39392 | 421.865 | 26724
39393 | 427.2423 | 26724
39394 | 411.4238 | 26724
39395 | 416.4031 | 26724
39396 | 418.8538 | 26724
39397 | 417.0986 | 26724
39398 | 429.1601 | 26724
39399 | 411.8768 | 26724
39400 | 417.292 | 26724
39401 | 424.7345 | 26724
39402 | 424.5223 | 26724
39403 | 418.3993 | 26724
39404 | 414.0986 | 26724
39405 | 400.9488 | 26724
39406 | 419.4745 | 26724
39407 | 419.6161 | 26724
39408 | 416.02 | 26724
39409 | 412.3169 | 26724
39410 | 419.1477 | 26724
39411 | 421.7842 | 26724
39412 | 417.7687 | 26724
39413 | 429.1328 | 26724
39414 | 410.5763 | 26724
39415 | 407.4335 | 26724
39416 | 421.9057 | 26724
39417 | 418.4558 | 26724
39418 | 423.2856 | 26724
39419 | 416.5117 | 26724
39420 | 410.1948 | 26724
39421 | 418.0668 | 26724
39422 | 417.6837 | 26724
39423 | 417.5851 | 26724
39424 | 408.872 | 26724
39425 | 410.5623 | 26724
39426 | 398.9419 | 26724
39427 | 412.5989 | 26724
39428 | 426.4389 | 26724
39429 | 413.7327 | 26724
39430 | 407.1486 | 26724
39431 | 428.2436 | 26724
39432 | 417.5375 | 26724
39433 | 421.6573 | 26724
39434 | 411.9512 | 26724
39435 | 414.2524 | 26724
39436 | 422.9289 | 26724
39437 | 422.7815 | 26724
39438 | 397.101 | 26724
39439 | 412.2856 | 26724
39440 | 414.936 | 26724
39441 | 417.8415 | 26724
39442 | 420.4031 | 26724
39443 | 406.4292 | 26724
39444 | 424.8934 | 26724
39445 | 427.1353 | 26724
39446 | 405.1485 | 26724
39447 | 417.924 | 26724
39448 | 418.4557 | 26724
39449 | 416.3934 | 26724
39450 | 427.3815 | 26724
39451 | 424.3124 | 26724
39452 | 415.1464 | 26724
39453 | 427.5158 | 26724
39454 | 417.849 | 26724
39455 | 423.3487 | 26724
39456 | 407.7266 | 26724
39457 | 419.646 | 26724
39458 | 434.6421 | 26724
39459 | 412.5976 | 26724
39460 | 414.7155 | 26724
39461 | 420.8008 | 26724
39462 | 421.9797 | 26724
39463 | 432.747 | 26724
39464 | 425.8239 | 26724
39465 | 419.8061 | 26724
39466 | 431.0679 | 26724
39467 | 409.1837 | 26724
39468 | 401.3774 | 26724
39469 | 427.5209 | 26724
39470 | 414.4974 | 26724
39471 | 412.203 | 26724
39472 | 411.2339 | 26724
39473 | 417.9681 | 26724
39474 | 426.6053 | 26724
39475 | 402.9141 | 26724
39476 | 405.4888 | 26724
39477 | 424.8745 | 26724
39478 | 426.5445 | 26724
39479 | 412.3615 | 26724
39480 | 403.8081 | 26724
39481 | 417.7952 | 26724
39482 | 411.7691 | 26724
39483 | 411.0592 | 26724
39484 | 404.9952 | 26724
39485 | 414.1126 | 26724
39486 | 409.2298 | 26724
39487 | 417.3718 | 26724
39488 | 425.4485 | 26724
39489 | 407.5391 | 26724
39490 | 412.5329 | 26724
39491 | 411.47 | 26724
39492 | 413.4584 | 26724
39493 | 409.868 | 26724
39494 | 416.59 | 26724
39495 | 425.7802 | 26724
39496 | 427.0361 | 26724
39497 | 423.5336 | 26724
39498 | 425.0548 | 26724
39499 | 416.4272 | 26724
39500 | 419.4337 | 26724
39501 | 420.939 | 26724
39502 | 420.4835 | 26724
39503 | 432.3546 | 26724
39504 | 414.0847 | 26724
39505 | 411.8624 | 26724
39506 | 418.4327 | 26724
39507 | 420.8717 | 26724
39508 | 416.0636 | 26724
39509 | 413.7855 | 26724
39510 | 416.4877 | 26724
39511 | 427.0233 | 26724
39512 | 423.3181 | 26724
39513 | 420.9068 | 26724
39514 | 429.9165 | 26724
39515 | 408.5988 | 26724
39516 | 431.3152 | 26724
39517 | 421.9946 | 26724
39518 | 417.5037 | 26724
39519 | 401.4735 | 26724
39520 | 421.2432 | 26724
39521 | 428.4936 | 26724
39522 | 419.1933 | 26724
39523 | 403.3128 | 26724
39524 | 415.1274 | 26724
39525 | 408.8684 | 26724
39526 | 420.1466 | 26724
39527 | 412.6909 | 26724
39528 | 440.1238 | 26724
39529 | 427.0423 | 26724
39530 | 412.7258 | 26724
39531 | 417.3082 | 26724
39532 | 426.5484 | 26724
39533 | 412.7645 | 26724
39534 | 410.732 | 26724
39535 | 414.739 | 26724
39536 | 406.5637 | 26724
39537 | 419.0202 | 26724
39538 | 409.0923 | 26724
39539 | 429.0718 | 26724
39540 | 421.3359 | 26724
39541 | 418.2553 | 26724
39542 | 410.1645 | 26724
39543 | 413.6607 | 26724
39544 | 418.5324 | 26724
39545 | 409.5988 | 26724
39546 | 417.3612 | 26724
39547 | 409.7985 | 26724
39548 | 416.4745 | 26724
39549 | 423.3123 | 26724
39550 | 421.6397 | 26724
39551 | 416.4476 | 26724
39552 | 399.8434 | 26724
39553 | 409.1641 | 26724
39554 | 419.3052 | 26724
39555 | 411.6643 | 26724
39556 | 414.7489 | 26724
39557 | 415.9285 | 26724
39558 | 418.0226 | 26724
39559 | 412.9732 | 26724
39560 | 413.0319 | 26724
39561 | 420.084 | 26724
39562 | 421.4937 | 26724
39563 | 417.7328 | 26724
39564 | 411.3306 | 26724
39565 | 425.2922 | 26724
39566 | 424.3404 | 26724
39567 | 416.2385 | 26724
39568 | 411.4791 | 26724
39569 | 418.2546 | 26724
39570 | 421.666 | 26724
39571 | 406.9094 | 26724
39572 | 430.8114 | 26724
39573 | 414.3664 | 26724
39574 | 409.1025 | 26724
39575 | 416.4738 | 26724
39576 | 415.6071 | 26724
39577 | 408.0205 | 26724
39578 | 424.0852 | 26724
39579 | 418.4331 | 26724
39580 | 403.1068 | 26724
39581 | 416.1471 | 26724
39582 | 417.3773 | 26724
39583 | 412.0291 | 26724
39584 | 407.1062 | 26724
39585 | 414.6208 | 26724
39586 | 429.7579 | 26724
39587 | 424.426 | 26724
39588 | 424.8051 | 26724
39589 | 413.1 | 26724
39590 | 419.8652 | 26724
39591 | 408.3632 | 26724
39592 | 412.1243 | 26724
39593 | 410.645 | 26724
39594 | 419.1694 | 26724
39595 | 426.4724 | 26724
39596 | 414.7291 | 26724
39597 | 398.1367 | 26724
39598 | 420.8518 | 26724
39599 | 425.3823 | 26724
39600 | 415.4573 | 26724
39601 | 409.4994 | 26724
39602 | 410.2885 | 26724
39603 | 424.3346 | 26724
39604 | 422.6433 | 26724
39605 | 429.5593 | 26724
39606 | 409.5828 | 26724
39607 | 407.9999 | 26724
39608 | 416.3187 | 26724
39609 | 418.2322 | 26724
39610 | 416.7971 | 26724
39611 | 418.2943 | 26724
39612 | 410.1365 | 26724
39613 | 406.6096 | 26724
39614 | 413.6214 | 26724
39615 | 426.9789 | 26724
39616 | 417.5786 | 26724
39617 | 407.0856 | 26724
39618 | 405.2116 | 26724
39619 | 417.7758 | 26724
39620 | 420.8893 | 26724
39621 | 437.3782 | 26724
39622 | 419.3787 | 26724
39623 | 428.3502 | 26724
39624 | 400.7038 | 26724
39625 | 413.9522 | 26724
39626 | 412.8266 | 26724
39627 | 423.3838 | 26724
39628 | 426.5572 | 26724
39629 | 413.9734 | 26724
39630 | 422.258 | 26724
39631 | 405.1111 | 26724
39632 | 415.8684 | 26724
39633 | 413.5345 | 26724
39634 | 413.9384 | 26724
39635 | 418.9937 | 26724
39636 | 409.9298 | 26724
39637 | 421.2318 | 26724
39638 | 409.6042 | 26724
39639 | 415.6275 | 26724
39640 | 420.1782 | 26724
39641 | 412.6882 | 26724
39642 | 430.8737 | 26724
39643 | 421.2177 | 26724
39644 | 404.2065 | 26724
39645 | 430.8206 | 26724
39646 | 432.1163 | 26724
39647 | 409.1929 | 26724
39648 | 426.3445 | 26724
39649 | 426.1637 | 26724
39650 | 423.4052 | 26724
39651 | 404.5983 | 26724
39652 | 418.8338 | 26724
39653 | 418.641 | 26724
39654 | 405.1555 | 26724
39655 | 424.9564 | 26724
39656 | 420.0056 | 26724
39657 | 423.5631 | 26724
39658 | 403.6432 | 26724
39659 | 403.0714 | 26724
39660 | 420.2294 | 26724
39661 | 416.4099 | 26724
39662 | 410.7055 | 26724
39663 | 411.1092 | 26724
39664 | 405.9588 | 26724
39665 | 417.4658 | 26724
39666 | 407.1235 | 26724
39667 | 419.9006 | 26724
39668 | 421.6216 | 26724
39669 | 406.1993 | 26724
39670 | 403.3171 | 26724
39671 | 408.0975 | 26724
39672 | 413.5981 | 26724
39673 | 417.1054 | 26724
39674 | 408.757 | 26724
39675 | 418.0285 | 26724
39676 | 408.3437 | 26724
39677 | 421.9072 | 26724
39678 | 405.8604 | 26724
39679 | 409.7502 | 26724
39680 | 414.822 | 26724
39681 | 408.6826 | 26724
39682 | 414.7602 | 26724
39683 | 419.2657 | 26724
39684 | 422.2868 | 26724
39685 | 430.0295 | 26724
39686 | 422.5082 | 26724
39687 | 418.2414 | 26724
39688 | 420.8297 | 26724
39689 | 422.1866 | 26724
39690 | 410.408 | 26724
39691 | 436.2417 | 26724
39692 | 418.5945 | 26724
39693 | 400.9982 | 26724
39694 | 419.7013 | 26724
39695 | 411.1714 | 26724
39696 | 423.3339 | 26724
39697 | 397.6972 | 26724
39698 | 411.623 | 26724
39699 | 423.098 | 26724
39700 | 411.7173 | 26724
39701 | 416.5392 | 26724
39702 | 408.2535 | 26724
39703 | 412.3193 | 26724
39704 | 416.8205 | 26724
39705 | 413.7731 | 26724
39706 | 412.3798 | 26724
39707 | 424.4778 | 26724
39708 | 421.1807 | 26724
39709 | 411.1893 | 26724
39710 | 415.4884 | 26724
39711 | 416.0276 | 26724
39712 | 401.0795 | 26724
39713 | 409.347 | 26724
39714 | 423.3823 | 26724
39715 | 412.9006 | 26724
39716 | 413.5047 | 26724
39717 | 415.4895 | 26724
39718 | 428.2185 | 26724
39719 | 407.6867 | 26724
39720 | 428.2457 | 26724
39721 | 408.1008 | 26724
39722 | 410.1653 | 26724
39723 | 423.7893 | 26724
39724 | 429.1055 | 26724
39725 | 418.2417 | 26724
39726 | 412.1094 | 26724
39727 | 419.1593 | 26724
39728 | 412.7105 | 26724
39729 | 423.2178 | 26724
39730 | 424.0484 | 26724
39731 | 428.0347 | 26724
39732 | 410.3806 | 26724
39733 | 429.3656 | 26724
39734 | 409.3824 | 26724
39735 | 413.0472 | 26724
39736 | 417.9147 | 26724
39737 | 410.3045 | 26724
39738 | 417.6803 | 26724
39739 | 420.0403 | 26724
39740 | 410.0251 | 26724
39741 | 427.841 | 26724
39742 | 416.0844 | 26724
39743 | 418.7245 | 26724
39744 | 414.4879 | 26724
39745 | 408.619 | 26724
39746 | 400.3603 | 26724
39747 | 392.6925 | 26724
39748 | 411.6551 | 26724
39749 | 409.7957 | 26724
39750 | 396.8657 | 26724
39751 | 441.0091 | 26724
39752 | 416.7702 | 26724
39753 | 408.9283 | 26724
39754 | 412.1444 | 26724
39755 | 411.2987 | 26724
39756 | 418.3091 | 26724
39757 | 429.4737 | 26724
39758 | 419.2687 | 26724
39759 | 421.3692 | 26724
39760 | 417.9925 | 26724
39761 | 422.4446 | 26724
39762 | 411.8952 | 26724
39763 | 422.7342 | 26724
39764 | 416.9068 | 26724
39765 | 424.2151 | 26724
39766 | 404.064 | 26724
39767 | 421.4311 | 26724
39768 | 416.4818 | 26724
39769 | 416.4493 | 26724
39770 | 421.7109 | 26724
39771 | 427.285 | 26724
39772 | 408.8204 | 26724
39773 | 404.4734 | 26724
39774 | 422.1975 | 26724
39775 | 412.9106 | 26724
39776 | 412.2805 | 26724
39777 | 432.1158 | 26724
39778 | 418.3616 | 26724
39779 | 421.4842 | 26724
39780 | 417.2479 | 26724
39781 | 402.2845 | 26724
39782 | 416.4393 | 26724
39783 | 407.9651 | 26724
39784 | 418.1474 | 26724
39785 | 424.6019 | 26724
39786 | 428.6593 | 26724
39787 | 420.3783 | 26724
39788 | 427.8085 | 26724
39789 | 419.8258 | 26724
39790 | 415.5442 | 26724
39791 | 424.2231 | 26724
39792 | 416.9919 | 26724
39793 | 418.4546 | 26724
39794 | 422.8198 | 26724
39795 | 417.3964 | 26724
39796 | 423.8863 | 26724
39797 | 415.8878 | 26724
39798 | 403.6183 | 26724
39799 | 420.1862 | 26724
39800 | 420.7845 | 26724
39801 | 410.0408 | 26724
39802 | 420.7536 | 26724
39803 | 427.5866 | 26724
39804 | 413.0483 | 26724
39805 | 425.8912 | 26724
39806 | 425.4267 | 26724
39807 | 414.9789 | 26724
39808 | 410.0473 | 26724
39809 | 413.9603 | 26724
39810 | 417.891 | 26724
39811 | 411.5123 | 26724
39812 | 395.1911 | 26724
39813 | 417.5394 | 26724
39814 | 417.1909 | 26724
39815 | 424.1431 | 26724
39816 | 415.7818 | 26724
39817 | 412.7172 | 26724
39818 | 416.0835 | 26724
39819 | 413.1548 | 26724
39820 | 408.1781 | 26724
39821 | 427.5299 | 26724
39822 | 412.4416 | 26724
39823 | 409.6427 | 26724
39824 | 415.9776 | 26724
39825 | 415.3155 | 26724
39826 | 412.3206 | 26724
39827 | 415.0541 | 26724
39828 | 424.1872 | 26724
39829 | 423.0867 | 26724
39830 | 424.0998 | 26724
39831 | 410.8735 | 26724
39832 | 413.2555 | 26724
39833 | 416.5144 | 26724
39834 | 417.9104 | 26724
39835 | 409.8425 | 26724
39836 | 423.1402 | 26724
39837 | 431.1059 | 26724
39838 | 413.5404 | 26724
39839 | 407.5832 | 26724
39840 | 420.4294 | 26724
39841 | 420.4034 | 26724
39842 | 403.7749 | 26724
39843 | 407.0228 | 26724
39844 | 422.7093 | 26724
39845 | 413.5473 | 26724
39846 | 409.1638 | 26724
39847 | 409.9461 | 26724
39848 | 417.1146 | 26724
39849 | 417.2428 | 26724
39850 | 409.3839 | 26724
39851 | 422.1875 | 26724
39852 | 429.1892 | 26724
39853 | 420.0704 | 26724
39854 | 403.0022 | 26724
39855 | 412.1579 | 26724
39856 | 416.9447 | 26724
39857 | 400.5574 | 26724
39858 | 424.3997 | 26724
39859 | 411.3772 | 26724
39860 | 412.5225 | 26724
39861 | 406.3317 | 26724
39862 | 408.2613 | 26724
39863 | 419.6104 | 26724
39864 | 411.4501 | 26724
39865 | 417.5264 | 26724
39866 | 429.4777 | 26724
39867 | 410.2877 | 26724
39868 | 423.1934 | 26724
39869 | 416.4016 | 26724
39870 | 420.4122 | 26724
39871 | 422.319 | 26724
39872 | 413.8474 | 26724
39873 | 416.0789 | 26724
39874 | 428.6361 | 26724
39875 | 413.6601 | 26724
39876 | 412.7697 | 26724
39877 | 401.2997 | 26724
39878 | 413.9786 | 26724
39879 | 420.9352 | 26724
39880 | 400.8633 | 26724
39881 | 412.173 | 26724
39882 | 418.798 | 26724
39883 | 429.6102 | 26724
39884 | 411.1617 | 26724
39885 | 397.4331 | 26724
39886 | 422.6051 | 26724
39887 | 417.9657 | 26724
39888 | 414.3379 | 26724
39889 | 422.948 | 26724
39890 | 416.628 | 26724
39891 | 432.3111 | 26724
39892 | 413.9767 | 26724
39893 | 425.7908 | 26724
39894 | 420.2534 | 26724
39895 | 423.1294 | 26724
39896 | 418.1712 | 26724
39897 | 407.731 | 26724
39898 | 414.1531 | 26724
39899 | 411.5144 | 26724
39900 | 409.3398 | 26724
39901 | 415.2006 | 26724
39902 | 420.6973 | 26724
39903 | 415.4738 | 26724
39904 | 402.1696 | 26724
39905 | 415.1839 | 26724
39906 | 421.0753 | 26724
39907 | 420.4521 | 26724
39908 | 426.434 | 26724
39909 | 411.8143 | 26724
39910 | 401.9517 | 26724
39911 | 407.6706 | 26724
39912 | 416.8428 | 26724
39913 | 421.2634 | 26724
39914 | 419.8969 | 26724
39915 | 438.4839 | 26724
39916 | 421.971 | 26724
39917 | 411.7642 | 26724
39918 | 413.2287 | 26724
39919 | 408.1811 | 26724
39920 | 415.0409 | 26724
39921 | 412.259 | 26724
39922 | 418.8266 | 26724
39923 | 431.6937 | 26724
39924 | 399.1445 | 26724
39925 | 418.546 | 26724
39926 | 425.4195 | 26724
39927 | 427.005 | 26724
39928 | 422.4351 | 26724
39929 | 409.9971 | 26724
39930 | 418.1353 | 26724
39931 | 404.0809 | 26724
39932 | 425.4798 | 26724
39933 | 403.0088 | 26724
39934 | 401.6476 | 26724
39935 | 413.4045 | 26724
39936 | 416.1083 | 26724
39937 | 415.7184 | 26724
39938 | 415.8618 | 26724
39939 | 405.3611 | 26724
39940 | 413.2678 | 26724
39941 | 413.0795 | 26724
39942 | 409.9784 | 26724
39943 | 411.9355 | 26724
39944 | 424.859 | 26724
39945 | 420.0307 | 26724
39946 | 418.8952 | 26724
39947 | 406.7968 | 26724
39948 | 422.9575 | 26724
39949 | 422.81 | 26724
39950 | 396.2307 | 26724
39951 | 419.1511 | 26724
39952 | 426.2386 | 26724
39953 | 419.196 | 26724
39954 | 412.8418 | 26724
39955 | 420.7729 | 26724
39956 | 413.6377 | 26724
39957 | 412.9611 | 26724
39958 | 433.5945 | 26724
39959 | 417.5665 | 26724
39960 | 416.6538 | 26724
39961 | 408.8984 | 26724
39962 | 413.0363 | 26724
39963 | 403.9185 | 26724
39964 | 405.228 | 26724
39965 | 415.4142 | 26724
39966 | 401.8662 | 26724
39967 | 418.2062 | 26724
39968 | 424.4323 | 26724
39969 | 432.2212 | 26724
39970 | 410.6398 | 26724
39971 | 423.4475 | 26724
39972 | 404.5848 | 26724
39973 | 418.1614 | 26724
39974 | 414.058 | 26724
39975 | 426.4883 | 26724
39976 | 412.8747 | 26724
39977 | 416.577 | 26724
39978 | 418.4666 | 26724
39979 | 407.5257 | 26724
39980 | 428.053 | 26724
39981 | 413.0081 | 26724
39982 | 411.442 | 26724
39983 | 421.5326 | 26724
39984 | 416.7119 | 26724
39985 | 426.9679 | 26724
39986 | 416.0304 | 26724
39987 | 416.226 | 26724
39988 | 412.2479 | 26724
39989 | 419.9701 | 26724
39990 | 416.1884 | 26724
39991 | 420.5693 | 26724
39992 | 406.731 | 26724
39993 | 424.2175 | 26724
39994 | 414.7576 | 26724
39995 | 403.8681 | 26724
39996 | 430.1752 | 26724
39997 | 412.2705 | 26724
39998 | 405.578 | 26724
39999 | 411.1832 | 26724
40000 | 412.1097 | 26724
40001 | 415.9509 | 26724
40002 | 426.7133 | 26724
40003 | 424.6294 | 26724
40004 | 424.7551 | 26724
40005 | 424.2119 | 26724
40006 | 413.3275 | 26724
40007 | 410.1145 | 26724
40008 | 417.1147 | 26724
40009 | 420.4415 | 26724
40010 | 410.5482 | 26724
40011 | 413.6218 | 26724
40012 | 410.8977 | 26724
40013 | 412.0662 | 26724
40014 | 421.854 | 26724
40015 | 426.2418 | 26724
40016 | 407.8526 | 26724
40017 | 410.1318 | 26724
40018 | 398.5068 | 26724
40019 | 417.6494 | 26724
40020 | 415.096 | 26724
40021 | 426.6755 | 26724
40022 | 415.4983 | 26724
40023 | 424.8997 | 26724
40024 | 423.7583 | 26724
40025 | 417.1034 | 26724
40026 | 413.8051 | 26724
40027 | 410.6766 | 26724
40028 | 430.7753 | 26724
40029 | 420.3513 | 26724
40030 | 421.9156 | 26724
40031 | 423.5082 | 26724
40032 | 422.3516 | 26724
40033 | 421.2123 | 26724
40034 | 422.4437 | 26724
40035 | 425.4122 | 26724
40036 | 426.75 | 26724
40037 | 421.9972 | 26724
40038 | 408.2645 | 26724
40039 | 421.513 | 26724
40040 | 426.5189 | 26724
40041 | 411.5125 | 26724
40042 | 416.1212 | 26724
40043 | 407.5201 | 26724
40044 | 408.6035 | 26724
40045 | 413.7299 | 26724
40046 | 434.1671 | 26724
40047 | 418.3325 | 26724
40048 | 415.5452 | 26724
40049 | 413.9494 | 26724
40050 | 404.9312 | 26724
40051 | 411.1948 | 26724
40052 | 412.5387 | 26724
40053 | 420.9332 | 26724
40054 | 417.8924 | 26724
40055 | 419.9569 | 26724
40056 | 408.8469 | 26724
40057 | 423.9531 | 26724
40058 | 404.8191 | 26724
40059 | 416.4151 | 26724
40060 | 417.9801 | 26724
40061 | 430.3459 | 26724
40062 | 421.9545 | 26724
40063 | 394.5428 | 26724
40064 | 407.9212 | 26724
40065 | 411.8919 | 26724
40066 | 431.0832 | 26724
40067 | 403.0639 | 26724
40068 | 415.4685 | 26724
40069 | 422.736 | 26724
40070 | 408.8704 | 26724
40071 | 412.0798 | 26724
40072 | 404.8892 | 26724
40073 | 412.1449 | 26724
40074 | 422.2633 | 26724
40075 | 412.8998 | 26724
40076 | 424.8628 | 26724
40077 | 412.6708 | 26724
40078 | 411.1614 | 26724
40079 | 406.6017 | 26724
40080 | 415.0506 | 26724
40081 | 417.9254 | 26724
40082 | 428.4071 | 26724
40083 | 423.5963 | 26724
40084 | 421.9852 | 26724
40085 | 422.5576 | 26724
40086 | 424.096 | 26724
40087 | 417.0303 | 26724
40088 | 420.9332 | 26724
40089 | 429.5683 | 26724
40090 | 415.3626 | 26724
40091 | 403.8065 | 26724
40092 | 427.1016 | 26724
40093 | 409.8428 | 26724
40094 | 417.2894 | 26724
40095 | 411.9503 | 26724
40096 | 412.5628 | 26724
40097 | 409.574 | 26724
40098 | 397.9358 | 26724
40099 | 412.7156 | 26724
40100 | 411.2278 | 26724
40101 | 424.1973 | 26724
40102 | 402.1408 | 26724
40103 | 415.2997 | 26724
40104 | 411.5328 | 26724
40105 | 424.3229 | 26724
40106 | 412.7665 | 26724
40107 | 420.5744 | 26724
40108 | 403.8718 | 26724
40109 | 410.3494 | 26724
40110 | 413.6388 | 26724
40111 | 407.8211 | 26724
40112 | 405.3306 | 26724
40113 | 409.1842 | 26724
40114 | 419.389 | 26724
40115 | 423.8612 | 26724
40116 | 412.6794 | 26724
40117 | 411.5779 | 26724
40118 | 418.4531 | 26724
40119 | 434.4953 | 26724
40120 | 428.9719 | 26724
40121 | 415.3044 | 26724
40122 | 415.2723 | 26724
40123 | 419.7597 | 26724
40124 | 411.4268 | 26724
40125 | 416.0397 | 26724
40126 | 402.7808 | 26724
40127 | 418.3109 | 26724
40128 | 408.8552 | 26724
40129 | 417.7547 | 26724
40130 | 417.788 | 26724
40131 | 406.5823 | 26724
40132 | 398.0314 | 26724
40133 | 398.4889 | 26724
40134 | 410.6904 | 26724
40135 | 412.4843 | 26724
40136 | 419.1805 | 26724
40137 | 418.7169 | 26724
40138 | 419.2752 | 26724
40139 | 418.4011 | 26724
40140 | 419.7425 | 26724
40141 | 422.6576 | 26724
40142 | 422.7853 | 26724
40143 | 426.4542 | 26724
40144 | 407.7981 | 26724
40145 | 411.2373 | 26724
40146 | 417.8032 | 26724
40147 | 412.0452 | 26724
40148 | 411.3198 | 26724
40149 | 424.395 | 26724
40150 | 423.9496 | 26724
40151 | 433.0644 | 26724
40152 | 406.2803 | 26724
40153 | 426.1689 | 26724
40154 | 426.9546 | 26724
40155 | 431.0169 | 26724
40156 | 433.7448 | 26724
40157 | 422.8368 | 26724
40158 | 421.5118 | 26724
40159 | 412.0956 | 26724
40160 | 431.3172 | 26724
40161 | 406.2864 | 26724
40162 | 416.8622 | 26724
40163 | 425.4354 | 26724
40164 | 408.3342 | 26724
40165 | 430.6306 | 26724
40166 | 423.0443 | 26724
40167 | 427.1017 | 26724
40168 | 414.3938 | 26724
40169 | 416.2296 | 26724
40170 | 410.5553 | 26724
40171 | 432.435 | 26724
40172 | 412.3851 | 26724
40173 | 422.0507 | 26724
40174 | 413.399 | 26724
40175 | 398.4081 | 26724
40176 | 414.4412 | 26724
40177 | 418.1089 | 26724
40178 | 414.2945 | 26724
40179 | 420.2533 | 26724
40180 | 412.9305 | 26724
40181 | 422.6366 | 26724
40182 | 408.3285 | 26724
40183 | 424.71 | 26724
40184 | 410.7043 | 26724
40185 | 414.0872 | 26724
40186 | 419.3436 | 26724
40187 | 419.4089 | 26724
40188 | 409.0426 | 26724
40189 | 422.9748 | 26724
40190 | 410.7517 | 26724
40191 | 409.6696 | 26724
40192 | 410.4123 | 26724
40193 | 416.8114 | 26724
40194 | 420.3417 | 26724
40195 | 398.4174 | 26724
40196 | 422.4178 | 26724
40197 | 407.9874 | 26724
40198 | 416.1396 | 26724
40199 | 421.5369 | 26724
40200 | 418.022 | 26724
40201 | 425.4709 | 26724
40202 | 410.8436 | 26724
40203 | 417.1664 | 26724
40204 | 429.6965 | 26724
40205 | 427.6458 | 26724
40206 | 418.8553 | 26724
40207 | 397.4904 | 26724
40208 | 413.6182 | 26724
40209 | 415.1539 | 26724
40210 | 423.389 | 26724
40211 | 415.7474 | 26724
40212 | 412.1633 | 26724
40213 | 433.4678 | 26724
40214 | 422.1411 | 26724
40215 | 420.1379 | 26724
40216 | 403.8867 | 26724
40217 | 421.8139 | 26724
40218 | 427.9887 | 26724
40219 | 423.1061 | 26724
40220 | 410.18 | 26724
40221 | 408.4244 | 26724
40222 | 420.3938 | 26724
40223 | 407.0498 | 26724
40224 | 419.8294 | 26724
40225 | 422.123 | 26724
40226 | 422.0379 | 26724
40227 | 407.5191 | 26724
40228 | 402.211 | 26724
40229 | 416.8952 | 26724
40230 | 407.7718 | 26724
40231 | 427.2014 | 26724
40232 | 403.2317 | 26724
40233 | 422.0923 | 26724
40234 | 427.9512 | 26724
40235 | 414.1817 | 26724
40236 | 421.0628 | 26724
40237 | 410.4172 | 26724
40238 | 412.685 | 26724
40239 | 419.1086 | 26724
40240 | 419.3369 | 26724
40241 | 430.7028 | 26724
40242 | 414.8231 | 26724
40243 | 421.9008 | 26724
40244 | 419.6933 | 26724
40245 | 419.7548 | 26724
40246 | 409.5431 | 26724
40247 | 401.2817 | 26724
40248 | 425.1497 | 26724
40249 | 408.2233 | 26724
40250 | 421.281 | 26724
40251 | 432.8551 | 26724
40252 | 428.7911 | 26724
40253 | 411.7504 | 26724
40254 | 431.3214 | 26724
40255 | 409.9069 | 26724
40256 | 417.5588 | 26724
40257 | 413.0797 | 26724
40258 | 423.3132 | 26724
40259 | 431.2578 | 26724
40260 | 420.0056 | 26724
40261 | 436.0102 | 26724
40262 | 425.5572 | 26724
40263 | 413.4408 | 26724
40264 | 408.0622 | 26724
40265 | 416.6834 | 26724
40266 | 420.0231 | 26724
40267 | 411.3334 | 26724
40268 | 398.0629 | 26724
40269 | 414.759 | 26724
40270 | 409.7845 | 26724
40271 | 428.7278 | 26724
40272 | 416.1597 | 26724
40273 | 411.4312 | 26724
40274 | 425.0466 | 26724
40275 | 409.6862 | 26724
40276 | 423.8104 | 26724
40277 | 422.2015 | 26724
40278 | 421.5662 | 26724
40279 | 433.6103 | 26724
40280 | 425.5755 | 26724
40281 | 421.2606 | 26724
40282 | 411.5761 | 26724
40283 | 415.6518 | 26724
40284 | 428.7581 | 26724
40285 | 396.6945 | 26724
40286 | 412.7354 | 26724
40287 | 399.3895 | 26724
40288 | 421.8912 | 26724
40289 | 417.8531 | 26724
40290 | 416.679 | 26724
40291 | 426.4936 | 26724
40292 | 422.0885 | 26724
40293 | 424.8565 | 26724
40294 | 429.6094 | 26724
40295 | 424.6993 | 26724
40296 | 423.8018 | 26724
40297 | 402.8184 | 26724
40298 | 417.7277 | 26724
40299 | 418.0668 | 26724
40300 | 411.925 | 26724
40301 | 421.1734 | 26724
40302 | 417.7773 | 26724
40303 | 420.1323 | 26724
40304 | 425.4927 | 26724
40305 | 411.0087 | 26724
40306 | 415.777 | 26724
40307 | 415.1352 | 26724
40308 | 412.8974 | 26724
40309 | 413.774 | 26724
40310 | 405.5846 | 26724
40311 | 420.629 | 26724
40312 | 423.1445 | 26724
40313 | 415.5065 | 26724
40314 | 412.2834 | 26724
40315 | 422.906 | 26724
40316 | 423.6198 | 26724
40317 | 410.7479 | 26724
40318 | 428.9766 | 26724
40319 | 413.1672 | 26724
40320 | 421.0806 | 26724
40321 | 414.3586 | 26724
40322 | 418.9301 | 26724
40323 | 410.0877 | 26724
40324 | 435.4729 | 26724
40325 | 416.7837 | 26724
40326 | 408.0354 | 26724
40327 | 409.6176 | 26724
40328 | 418.8517 | 26724
40329 | 415.224 | 26724
40330 | 407.0277 | 26724
40331 | 405.6403 | 26724
40332 | 406.3924 | 26724
40333 | 410.602 | 26724
40334 | 419.4463 | 26724
40335 | 420.1899 | 26724
40336 | 431.6415 | 26724
40337 | 402.7965 | 26724
40338 | 416.316 | 26724
40339 | 407.7862 | 26724
40340 | 406.8009 | 26724
40341 | 423.0547 | 26724
40342 | 414.6279 | 26724
40343 | 420.9701 | 26724
40344 | 423.3548 | 26724
40345 | 421.2749 | 26724
40346 | 427.6023 | 26724
40347 | 413.3268 | 26724
40348 | 410.6503 | 26724
40349 | 412.2549 | 26724
40350 | 413.1824 | 26724
40351 | 416.9111 | 26724
40352 | 417.9268 | 26724
40353 | 423.2888 | 26724
40354 | 415.7574 | 26724
40355 | 431.9032 | 26724
40356 | 409.3268 | 26724
40357 | 427.7057 | 26724
40358 | 427.8667 | 26724
40359 | 416.7875 | 26724
40360 | 407.0552 | 26724
40361 | 413.4703 | 26724
40362 | 410.1711 | 26724
40363 | 424.1918 | 26724
40364 | 404.3981 | 26724
40365 | 421.3816 | 26724
40366 | 419.2346 | 26724
40367 | 402.3621 | 26724
40368 | 413.5276 | 26724
40369 | 420.428 | 26724
40370 | 419.8015 | 26724
40371 | 423.6184 | 26724
40372 | 412.5533 | 26724
40373 | 433.9628 | 26724
40374 | 419.2447 | 26724
40375 | 435.6815 | 26724
40376 | 410.6538 | 26724
40377 | 404.9648 | 26724
40378 | 425.5238 | 26724
40379 | 428.8485 | 26724
40380 | 421.6109 | 26724
40381 | 404.4373 | 26724
40382 | 429.9838 | 26724
40383 | 417.0653 | 26724
40384 | 410.7097 | 26724
40385 | 420.517 | 26724
40386 | 419.8246 | 26724
40387 | 412.3468 | 26724
40388 | 410.7058 | 26724
40389 | 412.3788 | 26724
40390 | 414.3371 | 26724
40391 | 428.5789 | 26724
40392 | 426.8836 | 26724
40393 | 421.1049 | 26724
40394 | 423.9564 | 26724
40395 | 418.9416 | 26724
40396 | 420.7728 | 26724
40397 | 407.4814 | 26724
40398 | 404.5453 | 26724
40399 | 423.9316 | 26724
40400 | 404.6475 | 26724
40401 | 414.2589 | 26724
40402 | 423.8516 | 26724
40403 | 421.0757 | 26724
40404 | 405.9486 | 26724
40405 | 412.6005 | 26724
40406 | 414.5072 | 26724
40407 | 427.0906 | 26724
40408 | 424.1082 | 26724
40409 | 423.6976 | 26724
40410 | 408.9138 | 26724
40411 | 422.4184 | 26724
40412 | 422.8935 | 26724
40413 | 419.5038 | 26724
40414 | 415.6748 | 26724
40415 | 413.1709 | 26724
40416 | 409.4267 | 26724
40417 | 425.6014 | 26724
40418 | 416.7941 | 26724
40419 | 410.0213 | 26724
40420 | 418.8662 | 26724
40421 | 405.1891 | 26724
40422 | 401.388 | 26724
40423 | 423.9337 | 26724
40424 | 414.5891 | 26724
40425 | 409.3535 | 26724
40426 | 420.1462 | 26724
40427 | 416.9679 | 26724
40428 | 416.1048 | 26724
40429 | 407.6517 | 26724
40430 | 424.2946 | 26724
40431 | 415.2147 | 26724
40432 | 414.0151 | 26724
40433 | 416.9066 | 26724
40434 | 434.7935 | 26724
40435 | 401.3228 | 26724
40436 | 419.1119 | 26724
40437 | 412.3943 | 26724
40438 | 417.6843 | 26724
40439 | 408.6969 | 26724
40440 | 412.6228 | 26724
40441 | 416.6941 | 26724
40442 | 411.2448 | 26724
40443 | 415.0208 | 26724
40444 | 437.4248 | 26724
40445 | 410.0726 | 26724
40446 | 407.9005 | 26724
40447 | 415.8851 | 26724
40448 | 418.8014 | 26724
40449 | 402.4452 | 26724
40450 | 425.2617 | 26724
40451 | 427.718 | 26724
40452 | 418.4312 | 26724
40453 | 418.6334 | 26724
40454 | 424.2964 | 26724
40455 | 410.0213 | 26724
40456 | 431.9879 | 26724
40457 | 430.7319 | 26724
40458 | 431.9013 | 26724
40459 | 400.1628 | 26724
40460 | 425.5269 | 26724
40461 | 416.91 | 26724
40462 | 422.2053 | 26724
40463 | 425.892 | 26724
40464 | 410.9694 | 26724
40465 | 422.9817 | 26724
40466 | 425.7314 | 26724
40467 | 416.9028 | 26724
40468 | 411.8617 | 26724
40469 | 415.271 | 26724
40470 | 416.9938 | 26724
40471 | 413.7001 | 26724
40472 | 419.1951 | 26724
40473 | 425.9208 | 26724
40474 | 417.2338 | 26724
40475 | 421.325 | 26724
40476 | 416.4021 | 26724
40477 | 422.218 | 26724
40478 | 402.9534 | 26724
40479 | 414.211 | 26724
40480 | 420.7158 | 26724
40481 | 421.4414 | 26724
40482 | 425.268 | 26724
40483 | 405.6011 | 26724
40484 | 428.64 | 26724
40485 | 416.7576 | 26724
40486 | 413.5391 | 26724
40487 | 413.2157 | 26724
40488 | 424.9161 | 26724
40489 | 412.4942 | 26724
40490 | 403.2764 | 26724
40491 | 402.6918 | 26724
40492 | 411.7257 | 26724
40493 | 412.3295 | 26724
40494 | 416.4325 | 26724
40495 | 433.7059 | 26724
40496 | 408.7161 | 26724
40497 | 417.4065 | 26724
40498 | 402.1167 | 26724
40499 | 420.8313 | 26724
40500 | 412.9467 | 26724
40501 | 425.3939 | 26724
40502 | 422.4221 | 26724
40503 | 418.7181 | 26724
40504 | 408.1037 | 26724
40505 | 405.3959 | 26724
40506 | 423.8308 | 26724
40507 | 427.5574 | 26724
40508 | 412.6947 | 26724
40509 | 416.907 | 26724
40510 | 413.4807 | 26724
40511 | 413.6046 | 26724
40512 | 417.5033 | 26724
40513 | 408.4777 | 26724
40514 | 414.7806 | 26724
40515 | 402.7269 | 26724
40516 | 413.2931 | 26724
40517 | 418.0591 | 26724
40518 | 415.6166 | 26724
40519 | 414.6206 | 26724
40520 | 412.7114 | 26724
40521 | 416.2769 | 26724
40522 | 416.2378 | 26724
40523 | 432.6731 | 26724
40524 | 419.9572 | 26724
40525 | 427.4195 | 26724
40526 | 420.1361 | 26724
40527 | 414.5881 | 26724
40528 | 417.9654 | 26724
40529 | 403.8734 | 26724
40530 | 413.3303 | 26724
40531 | 420.4096 | 26724
40532 | 410.9396 | 26724
40533 | 425.3358 | 26724
40534 | 412.0689 | 26724
40535 | 426.6727 | 26724
40536 | 415.6303 | 26724
40537 | 426.7806 | 26724
40538 | 413.6954 | 26724
40539 | 416.9434 | 26724
40540 | 406.6554 | 26724
40541 | 408.6478 | 26724
40542 | 419.4179 | 26724
40543 | 407.7619 | 26724
40544 | 404.0814 | 26724
40545 | 413.8338 | 26724
40546 | 421.5586 | 26724
40547 | 422.031 | 26724
40548 | 428.5763 | 26724
40549 | 421.0054 | 26724
40550 | 414.3944 | 26724
40551 | 412.3237 | 26724
40552 | 407.9217 | 26724
40553 | 412.7359 | 26724
40554 | 415.4939 | 26724
40555 | 405.9121 | 26724
40556 | 397.3092 | 26724
40557 | 417.1509 | 26724
40558 | 424.4168 | 26724
40559 | 420.9556 | 26724
40560 | 427.9919 | 26724
40561 | 403.9375 | 26724
40562 | 416.8579 | 26724
40563 | 418.0129 | 26724
40564 | 406.3042 | 26724
40565 | 406.5148 | 26724
40566 | 422.5504 | 26724
40567 | 415.0967 | 26724
40568 | 407.2237 | 26724
40569 | 422.4036 | 26724
40570 | 407.3648 | 26724
40571 | 407.4218 | 26724
40572 | 420.0101 | 26724
40573 | 407.6381 | 26724
40574 | 412.3027 | 26724
40575 | 408.6412 | 26724
40576 | 401.3844 | 26724
40577 | 407.8545 | 26724
40578 | 414.2285 | 26724
40579 | 411.9912 | 26724
40580 | 414.4201 | 26724
40581 | 423.972 | 26724
40582 | 431.4763 | 26724
40583 | 401.4377 | 26724
40584 | 412.3405 | 26724
40585 | 416.3427 | 26724
40586 | 416.9407 | 26724
40587 | 420.8495 | 26724
40588 | 421.5013 | 26724
40589 | 417.7977 | 26724
40590 | 420.11 | 26724
40591 | 406.5828 | 26724
40592 | 403.1871 | 26724
40593 | 412.6451 | 26724
40594 | 419.4365 | 26724
40595 | 405.9977 | 26724
40596 | 424.5305 | 26724
40597 | 416.7713 | 26724
40598 | 426.7682 | 26724
40599 | 421.042 | 26724
40600 | 405.0778 | 26724
40601 | 425.1331 | 26724
40602 | 410.4541 | 26724
40603 | 404.6545 | 26724
40604 | 417.6795 | 26724
40605 | 408.5533 | 26724
40606 | 418.2302 | 26724
40607 | 413.6099 | 26724
40608 | 415.8018 | 26724
40609 | 410.2573 | 26724
40610 | 412.124 | 26724
40611 | 424.3051 | 26724
40612 | 414.086 | 26724
40613 | 430.3016 | 26724
40614 | 414.1945 | 26724
40615 | 420.7311 | 26724
40616 | 422.5444 | 26724
40617 | 415.6554 | 26724
40618 | 417.9373 | 26724
40619 | 428.3496 | 26724
40620 | 425.8304 | 26724
40621 | 415.007 | 26724
40622 | 412.8733 | 26724
40623 | 421.6171 | 26724
40624 | 419.3063 | 26724
40625 | 421.7152 | 26724
40626 | 406.2423 | 26724
40627 | 417.0258 | 26724
40628 | 411.2304 | 26724
40629 | 422.9564 | 26724
40630 | 407.8917 | 26724
40631 | 422.9721 | 26724
40632 | 418.6745 | 26724
40633 | 420.9802 | 26724
40634 | 425.9844 | 26724
40635 | 414.3597 | 26724
40636 | 410.7422 | 26724
40637 | 435.646 | 26724
40638 | 420.7258 | 26724
40639 | 424.9332 | 26724
40640 | 418.4645 | 26724
40641 | 411.3325 | 26724
40642 | 425.7022 | 26724
40643 | 420.2176 | 26724
40644 | 418.8697 | 26724
40645 | 430.9275 | 26724
40646 | 413.0221 | 26724
40647 | 409.6928 | 26724
40648 | 422.6781 | 26724
40649 | 418.639 | 26724
40650 | 413.0901 | 26724
40651 | 421.5964 | 26724
40652 | 408.4461 | 26724
40653 | 411.9486 | 26724
40654 | 409.6773 | 26724
40655 | 421.8289 | 26724
40656 | 430.1513 | 26724
40657 | 415.847 | 26724
40658 | 425.8113 | 26724
40659 | 418.3265 | 26724
40660 | 426.4976 | 26724
40661 | 411.4807 | 26724
40662 | 435.163 | 26724
40663 | 406.6377 | 26724
40664 | 421.8137 | 26724
40665 | 406.7593 | 26724
40666 | 419.0226 | 26724
40667 | 410.3491 | 26724
40668 | 423.7693 | 26724
40669 | 411.9197 | 26724
40670 | 415.4506 | 26724
40671 | 409.2277 | 26724
40672 | 418.196 | 26724
40673 | 419.8011 | 26724
40674 | 415.0049 | 26724
40675 | 414.0233 | 26724
40676 | 409.2122 | 26724
40677 | 430.4134 | 26724
40678 | 408.1023 | 26724
40679 | 412.1273 | 26724
40680 | 412.9249 | 26724
40681 | 428.2448 | 26724
40682 | 418.9598 | 26724
40683 | 421.5489 | 26724
40684 | 414.288 | 26724
40685 | 421.4629 | 26724
40686 | 411.8079 | 26724
40687 | 419.5798 | 26724
40688 | 407.9792 | 26724
40689 | 402.5584 | 26724
40690 | 423.2375 | 26724
40691 | 412.7461 | 26724
40692 | 411.7241 | 26724
40693 | 406.5308 | 26724
40694 | 414.429 | 26724
40695 | 401.4741 | 26724
40696 | 438.3492 | 26724
40697 | 426.6809 | 26724
40698 | 423.5123 | 26724
40699 | 410.9469 | 26724
40700 | 413.8344 | 26724
40701 | 425.8061 | 26724
40702 | 419.1644 | 26724
40703 | 427.081 | 26724
40704 | 399.7824 | 26724
40705 | 418.4258 | 26724
40706 | 402.2535 | 26724
40707 | 433.4613 | 26724
40708 | 410.5759 | 26724
40709 | 396.7762 | 26724
40710 | 428.3158 | 26724
40711 | 420.1465 | 26724
40712 | 411.3139 | 26724
40713 | 411.441 | 26724
40714 | 436.3425 | 26724
40715 | 419.8712 | 26724
40716 | 410.8198 | 26724
40717 | 418.8568 | 26724
40718 | 439.6794 | 26724
40719 | 411.0187 | 26724
40720 | 419.146 | 26724
40721 | 415.7207 | 26724
40722 | 405.4916 | 26724
40723 | 426.3938 | 26724
40724 | 430.2024 | 26724
40725 | 424.1742 | 26724
40726 | 396.885 | 26724
40727 | 433.0863 | 26724
40728 | 425.1513 | 26724
40729 | 421.6243 | 26724
40730 | 427.6147 | 26724
40731 | 409.2213 | 26724
40732 | 409.4898 | 26724
40733 | 412.0503 | 26724
40734 | 413.7969 | 26724
40735 | 422.0952 | 26724
40736 | 433.6989 | 26724
40737 | 418.329 | 26724
40738 | 416.3195 | 26724
40739 | 410.9319 | 26724
40740 | 436.7732 | 26724
40741 | 411.6012 | 26724
40742 | 413.8515 | 26724
40743 | 414.0045 | 26724
40744 | 416.8027 | 26724
40745 | 420.1738 | 26724
40746 | 395.3929 | 26724
40747 | 430.9565 | 26724
40748 | 417.4773 | 26724
40749 | 405.6276 | 26724
40750 | 430.2126 | 26724
40751 | 411.7601 | 26724
40752 | 423.0486 | 26724
40753 | 402.0599 | 26724
40754 | 411.1534 | 26724
40755 | 418.1668 | 26724
40756 | 426.546 | 26724
40757 | 416.333 | 26724
40758 | 404.2537 | 26724
40759 | 403.9412 | 26724
40760 | 410.3635 | 26724
40761 | 411.0247 | 26724
40762 | 424.9367 | 26724
40763 | 413.3429 | 26724
40764 | 424.0987 | 26724
40765 | 423.228 | 26724
40766 | 413.1676 | 26724
40767 | 410.1946 | 26724
40768 | 425.3226 | 26724
40769 | 416.9073 | 26724
40770 | 415.1559 | 26724
40771 | 417.1291 | 26724
40772 | 399.7488 | 26724
40773 | 425.3801 | 26724
40774 | 415.1238 | 26724
40775 | 418.6375 | 26724
40776 | 421.1777 | 26724
40777 | 421.9085 | 26724
40778 | 413.3944 | 26724
40779 | 423.1124 | 26724
40780 | 424.9597 | 26724
40781 | 415.7515 | 26724
40782 | 416.9582 | 26724
40783 | 422.5141 | 26724
40784 | 425.4896 | 26724
40785 | 415.8146 | 26724
40786 | 419.159 | 26724
40787 | 401.9868 | 26724
40788 | 418.4881 | 26724
40789 | 400.993 | 26724
40790 | 402.2764 | 26724
40791 | 412.5025 | 26724
40792 | 427.8171 | 26724
40793 | 415.4511 | 26724
40794 | 412.6906 | 26724
40795 | 421.3647 | 26724
40796 | 420.0715 | 26724
40797 | 419.1961 | 26724
40798 | 414.0638 | 26724
40799 | 401.9888 | 26724
40800 | 413.6858 | 26724
40801 | 425.8592 | 26724
40802 | 433.4581 | 26724
40803 | 423.4195 | 26724
40804 | 417.9959 | 26724
40805 | 419.4457 | 26724
40806 | 423.3386 | 26724
40807 | 412.9851 | 26724
40808 | 409.622 | 26724
40809 | 405.261 | 26724
40810 | 423.895 | 26724
40811 | 414.0308 | 26724
40812 | 417.7337 | 26724
40813 | 414.036 | 26724
40814 | 402.2442 | 26724
40815 | 411.2954 | 26724
40816 | 422.0792 | 26724
40817 | 404.292 | 26724
40818 | 424.8881 | 26724
40819 | 406.5798 | 26724
40820 | 412.1773 | 26724
40821 | 408.2215 | 26724
40822 | 422.4557 | 26724
40823 | 424.8426 | 26724
40824 | 421.6019 | 26724
40825 | 413.2805 | 26724
40826 | 415.6626 | 26724
40827 | 424.4557 | 26724
40828 | 413.4391 | 26724
40829 | 414.9627 | 26724
40830 | 420.4114 | 26724
40831 | 422.9382 | 26724
40832 | 418.3454 | 26724
40833 | 410.5578 | 26724
40834 | 409.9861 | 26724
40835 | 414.1274 | 26724
40836 | 420.3727 | 26724
40837 | 416.5554 | 26724
40838 | 416.2708 | 26724
40839 | 409.1845 | 26724
40840 | 412.7871 | 26724
40841 | 416.405 | 26724
40842 | 427.8664 | 26724
40843 | 424.6966 | 26724
40844 | 412.4857 | 26724
40845 | 406.6324 | 26724
40846 | 420.5137 | 26724
40847 | 403.3187 | 26724
40848 | 426.0713 | 26724
40849 | 418.8517 | 26724
40850 | 415.7235 | 26724
40851 | 411.7858 | 26724
40852 | 412.1454 | 26724
40853 | 398.6265 | 26724
40854 | 427.8582 | 26724
40855 | 415.1839 | 26724
40856 | 413.4773 | 26724
40857 | 437.0977 | 26724
40858 | 422.8817 | 26724
40859 | 410.2822 | 26724
40860 | 398.9313 | 26724
40861 | 404.3095 | 26724
40862 | 418.2306 | 26724
40863 | 409.7821 | 26724
40864 | 422.0491 | 26724
40865 | 402.683 | 26724
40866 | 423.3824 | 26724
40867 | 423.9619 | 26724
40868 | 401.0414 | 26724
40869 | 409.3997 | 26724
40870 | 411.4847 | 26724
40871 | 423.938 | 26724
40872 | 406.0451 | 26724
40873 | 426.0414 | 26724
40874 | 411.3152 | 26724
40875 | 420.8182 | 26724
40876 | 415.8854 | 26724
40877 | 413.9017 | 26724
40878 | 399.6405 | 26724
40879 | 399.1095 | 26724
40880 | 415.8323 | 26724
40881 | 413.2685 | 26724
40882 | 402.1951 | 26724
40883 | 419.0707 | 26724
40884 | 412.7435 | 26724
40885 | 414.1164 | 26724
40886 | 407.5283 | 26724
40887 | 411.173 | 26724
40888 | 424.2765 | 26724
40889 | 428.3114 | 26724
40890 | 426.1931 | 26724
40891 | 411.4933 | 26724
40892 | 417.8348 | 26724
40893 | 416.9591 | 26724
40894 | 434.2847 | 26724
40895 | 431.211 | 26724
40896 | 422.8985 | 26724
40897 | 427.1044 | 26724
40898 | 406.5065 | 26724
40899 | 418.8972 | 26724
40900 | 401.4142 | 26724
40901 | 428.0072 | 26724
40902 | 398.8335 | 26724
40903 | 424.6859 | 26724
40904 | 419.305 | 26724
40905 | 399.0176 | 26724
40906 | 424.2409 | 26724
40907 | 420.5944 | 26724
40908 | 416.0108 | 26724
40909 | 414.6774 | 26724
40910 | 413.457 | 26724
40911 | 414.7546 | 26724
40912 | 403.1815 | 26724
40913 | 405.4787 | 26724
40914 | 414.1177 | 26724
40915 | 421.2061 | 26724
40916 | 413.3536 | 26724
40917 | 424.4247 | 26724
40918 | 415.0313 | 26724
40919 | 401.7725 | 26724
40920 | 409.2467 | 26724
40921 | 405.6201 | 26724
40922 | 415.1525 | 26724
40923 | 412.281 | 26724
40924 | 416.8429 | 26724
40925 | 429.5469 | 26724
40926 | 415.6715 | 26724
40927 | 409.9776 | 26724
40928 | 425.1629 | 26724
40929 | 412.6002 | 26724
40930 | 408.4634 | 26724
40931 | 413.7565 | 26724
40932 | 407.7602 | 26724
40933 | 406.2239 | 26724
40934 | 406.3545 | 26724
40935 | 417.4219 | 26724
40936 | 419.8515 | 26724
40937 | 411.7848 | 26724
40938 | 419.5669 | 26724
40939 | 420.6633 | 26724
40940 | 409.4098 | 26724
40941 | 417.9584 | 26724
40942 | 411.839 | 26724
40943 | 403.4881 | 26724
40944 | 418.6617 | 26724
40945 | 418.6241 | 26724
40946 | 405.1784 | 26724
40947 | 423.107 | 26724
40948 | 423.0339 | 26724
40949 | 410.1437 | 26724
40950 | 426.7634 | 26724
40951 | 426.7552 | 26724
40952 | 407.1176 | 26724
40953 | 427.4291 | 26724
40954 | 432.3124 | 26724
40955 | 414.1533 | 26724
40956 | 434.6279 | 26724
40957 | 407.8627 | 26724
40958 | 415.1176 | 26724
40959 | 412.3145 | 26724
40960 | 411.209 | 26724
40961 | 428.0887 | 26724
40962 | 407.1766 | 26724
40963 | 434.4462 | 26724
40964 | 423.9026 | 26724
40965 | 422.8166 | 26724
40966 | 434.0769 | 26724
40967 | 414.8073 | 26724
40968 | 416.6445 | 26724
40969 | 425.4737 | 26724
40970 | 432.2661 | 26724
40971 | 429.1587 | 26724
40972 | 407.6616 | 26724
40973 | 404.493 | 26724
40974 | 418.15 | 26724
40975 | 431.4551 | 26724
40976 | 408.2285 | 26724
40977 | 421.0038 | 26724
40978 | 404.9716 | 26724
40979 | 409.9621 | 26724
40980 | 410.2716 | 26724
40981 | 421.4117 | 26724
40982 | 425.5321 | 26724
40983 | 418.048 | 26724
40984 | 416.1742 | 26724
40985 | 421.3475 | 26724
40986 | 403.7904 | 26724
40987 | 421.6598 | 26724
40988 | 419.6907 | 26724
40989 | 411.2427 | 26724
40990 | 425.3533 | 26724
40991 | 415.0312 | 26724
40992 | 427.0843 | 26724
40993 | 408.2231 | 26724
40994 | 410.7527 | 26724
40995 | 411.9137 | 26724
40996 | 427.179 | 26724
40997 | 418.3065 | 26724
40998 | 411.9143 | 26724
40999 | 404.1807 | 26724
41000 | 406.4641 | 26724
41001 | 417.1254 | 26724
41002 | 410.3986 | 26724
41003 | 411.1698 | 26724
41004 | 427.4728 | 26724
41005 | 432.0612 | 26724
41006 | 412.6416 | 26724
41007 | 411.66 | 26724
41008 | 403.8619 | 26724
41009 | 419.9242 | 26724
41010 | 415.2446 | 26724
41011 | 429.4437 | 26724
41012 | 415.2792 | 26724
41013 | 420.4409 | 26724
41014 | 427.443 | 26724
41015 | 397.3003 | 26724
41016 | 400.3294 | 26724
41017 | 408.2255 | 26724
41018 | 416.7115 | 26724
41019 | 425.9169 | 26724
41020 | 399.7688 | 26724
41021 | 402.7803 | 26724
41022 | 425.9337 | 26724
41023 | 407.3948 | 26724
41024 | 423.7113 | 26724
41025 | 427.6273 | 26724
41026 | 425.1405 | 26724
41027 | 409.3692 | 26724
41028 | 415.1961 | 26724
41029 | 420.1909 | 26724
41030 | 418.78 | 26724
41031 | 405.136 | 26724
41032 | 415.3598 | 26724
41033 | 421.5521 | 26724
41034 | 419.6845 | 26724
41035 | 421.6182 | 26724
41036 | 416.6252 | 26724
41037 | 403.0009 | 26724
41038 | 418.2748 | 26724
41039 | 412.5601 | 26724
41040 | 415.1928 | 26724
41041 | 421.0229 | 26724
41042 | 413.4245 | 26724
41043 | 417.4635 | 26724
41044 | 408.8234 | 26724
41045 | 421.2126 | 26724
41046 | 413.1804 | 26724
41047 | 418.5784 | 26724
41048 | 400.9039 | 26724
41049 | 403.3942 | 26724
41050 | 413.3223 | 26724
41051 | 418.6268 | 26724
41052 | 425.8812 | 26724
41053 | 413.1486 | 26724
41054 | 417.2569 | 26724
41055 | 423.4933 | 26724
41056 | 416.6412 | 26724
41057 | 418.5292 | 26724
41058 | 420.6749 | 26724
41059 | 420.761 | 26724
41060 | 419.4532 | 26724
41061 | 416.643 | 26724
41062 | 422.2399 | 26724
41063 | 432.2691 | 26724
41064 | 413.3138 | 26724
41065 | 413.1813 | 26724
41066 | 411.0136 | 26724
41067 | 425.2321 | 26724
41068 | 412.0955 | 26724
41069 | 417.1895 | 26724
41070 | 420.0106 | 26724
41071 | 428.5486 | 26724
41072 | 405.2112 | 26724
41073 | 428.2204 | 26724
41074 | 419.07 | 26724
41075 | 422.4733 | 26724
41076 | 420.096 | 26724
41077 | 429.2442 | 26724
41078 | 413.1846 | 26724
41079 | 420.9133 | 26724
41080 | 417.7989 | 26724
41081 | 410.3179 | 26724
41082 | 404.7977 | 26724
41083 | 421.6972 | 26724
41084 | 415.8495 | 26724
41085 | 424.1029 | 26724
41086 | 407.7266 | 26724
41087 | 420.9539 | 26724
41088 | 410.4349 | 26724
41089 | 426.9255 | 26724
41090 | 420.8433 | 26724
41091 | 426.0419 | 26724
41092 | 406.1622 | 26724
41093 | 413.6601 | 26724
41094 | 405.8508 | 26724
41095 | 416.8963 | 26724
41096 | 426.1411 | 26724
41097 | 427.7529 | 26724
41098 | 420.1241 | 26724
41099 | 416.4313 | 26724
41100 | 411.6852 | 26724
41101 | 430.3208 | 26724
41102 | 415.9497 | 26724
41103 | 411.5696 | 26724
41104 | 418.1386 | 26724
41105 | 411.1902 | 26724
41106 | 412.1008 | 26724
41107 | 428.9107 | 26724
41108 | 407.969 | 26724
41109 | 413.8387 | 26724
41110 | 409.9484 | 26724
41111 | 400.8917 | 26724
41112 | 418.507 | 26724
41113 | 408.7898 | 26724
41114 | 406.1296 | 26724
41115 | 412.9779 | 26724
41116 | 425.9708 | 26724
41117 | 420.4348 | 26724
41118 | 421.8565 | 26724
41119 | 418.1668 | 26724
41120 | 414.2479 | 26724
41121 | 416.3805 | 26724
41122 | 401.7967 | 26724
41123 | 424.1561 | 26724
41124 | 413.1879 | 26724
41125 | 411.1343 | 26724
41126 | 402.7838 | 26724
41127 | 418.4895 | 26724
41128 | 411.0798 | 26724
41129 | 419.3976 | 26724
41130 | 422.5005 | 26724
41131 | 416.853 | 26724
41132 | 419.3339 | 26724
41133 | 409.6011 | 26724
41134 | 423.1921 | 26724
41135 | 425.4448 | 26724
41136 | 421.0478 | 26724
41137 | 410.574 | 26724
41138 | 417.2064 | 26724
41139 | 423.147 | 26724
41140 | 428.083 | 26724
41141 | 418.5942 | 26724
41142 | 416.6521 | 26724
41143 | 417.7819 | 26724
41144 | 419.5659 | 26724
41145 | 419.943 | 26724
41146 | 430.4564 | 26724
41147 | 413.2739 | 26724
41148 | 399.9626 | 26724
41149 | 412.6513 | 26724
41150 | 413.9066 | 26724
41151 | 426.4616 | 26724
41152 | 403.4742 | 26724
41153 | 421.0603 | 26724
41154 | 425.0101 | 26724
41155 | 416.8542 | 26724
41156 | 415.4686 | 26724
41157 | 425.4717 | 26724
41158 | 402.9599 | 26724
41159 | 418.7364 | 26724
41160 | 416.9736 | 26724
41161 | 403.3576 | 26724
41162 | 407.9397 | 26724
41163 | 412.2518 | 26724
41164 | 419.8183 | 26724
41165 | 417.5289 | 26724
41166 | 427.4165 | 26724
41167 | 423.5787 | 26724
41168 | 422.1927 | 26724
41169 | 420.3469 | 26724
41170 | 412.8834 | 26724
41171 | 411.7095 | 26724
41172 | 410.3644 | 26724
41173 | 416.7152 | 26724
41174 | 410.6271 | 26724
41175 | 429.7281 | 26724
41176 | 417.1539 | 26724
41177 | 411.2557 | 26724
41178 | 418.2402 | 26724
41179 | 419.9562 | 26724
41180 | 422.8857 | 26724
41181 | 405.5592 | 26724
41182 | 413.0072 | 26724
41183 | 406.5425 | 26724
41184 | 409.1508 | 26724
41185 | 403.1157 | 26724
41186 | 431.0502 | 26724
41187 | 409.4347 | 26724
41188 | 421.5158 | 26724
41189 | 428.4866 | 26724
41190 | 418.519 | 26724
41191 | 408.1303 | 26724
41192 | 426.536 | 26724
41193 | 429.6549 | 26724
41194 | 415.9534 | 26724
41195 | 424.7521 | 26724
41196 | 417.3949 | 26724
41197 | 399.178 | 26724
41198 | 417.1362 | 26724
41199 | 426.5552 | 26724
41200 | 404.9522 | 26724
41201 | 410.5454 | 26724
41202 | 421.9167 | 26724
41203 | 411.7791 | 26724
41204 | 405.6042 | 26724
41205 | 399.2721 | 26724
41206 | 410.2485 | 26724
41207 | 404.7332 | 26724
41208 | 427.5994 | 26724
41209 | 407.6278 | 26724
41210 | 407.7736 | 26724
41211 | 421.0607 | 26724
41212 | 404.7198 | 26724
41213 | 429.2885 | 26724
41214 | 409.6258 | 26724
41215 | 419.7626 | 26724
41216 | 424.1536 | 26724
41217 | 425.5401 | 26724
41218 | 418.4371 | 26724
41219 | 412.243 | 26724
41220 | 419.8487 | 26724
41221 | 404.3452 | 26724
41222 | 413.5564 | 26724
41223 | 421.1961 | 26724
41224 | 402.0502 | 26724
41225 | 422.0686 | 26724
41226 | 434.8014 | 26724
41227 | 417.8531 | 26724
41228 | 413.4668 | 26724
41229 | 415.6617 | 26724
41230 | 420.9805 | 26724
41231 | 411.6583 | 26724
41232 | 426.0277 | 26724
41233 | 424.7064 | 26724
41234 | 420.2984 | 26724
41235 | 413.5966 | 26724
41236 | 432.3429 | 26724
41237 | 416.1538 | 26724
41238 | 411.1271 | 26724
41239 | 423.7335 | 26724
41240 | 412.0685 | 26724
41241 | 409.8785 | 26724
41242 | 421.7048 | 26724
41243 | 417.0413 | 26724
41244 | 427.533 | 26724
41245 | 414.0519 | 26724
41246 | 422.0163 | 26724
41247 | 408.9122 | 26724
41248 | 411.7798 | 26724
41249 | 410.4313 | 26724
41250 | 416.496 | 26724
41251 | 426.509 | 26724
41252 | 410.3314 | 26724
41253 | 416.0783 | 26724
41254 | 408.9803 | 26724
41255 | 422.2537 | 26724
41256 | 403.9551 | 26724
41257 | 417.1626 | 26724
41258 | 426.7071 | 26724
41259 | 405.5 | 26724
41260 | 417.0715 | 26724
41261 | 407.5928 | 26724
41262 | 408.1695 | 26724
41263 | 420.6799 | 26724
41264 | 413.1137 | 26724
41265 | 418.9004 | 26724
41266 | 417.006 | 26724
41267 | 421.7273 | 26724
41268 | 418.5873 | 26724
41269 | 419.5682 | 26724
41270 | 410.1996 | 26724
41271 | 425.0128 | 26724
41272 | 414.1447 | 26724
41273 | 420.8398 | 26724
41274 | 422.022 | 26724
41275 | 412.7526 | 26724
41276 | 412.7772 | 26724
41277 | 409.9357 | 26724
41278 | 427.5866 | 26724
41279 | 414.7287 | 26724
41280 | 418.6403 | 26724
41281 | 397.66 | 26724
41282 | 418.7462 | 26724
41283 | 413.8733 | 26724
41284 | 401.0023 | 26724
41285 | 410.5637 | 26724
41286 | 425.0605 | 26724
41287 | 408.3287 | 26724
41288 | 401.7011 | 26724
41289 | 411.9816 | 26724
41290 | 412.7753 | 26724
41291 | 410.1174 | 26724
41292 | 423.404 | 26724
41293 | 401.1205 | 26724
41294 | 420.0742 | 26724
41295 | 406.9295 | 26724
41296 | 431.1009 | 26724
41297 | 415.6721 | 26724
41298 | 402.813 | 26724
41299 | 425.407 | 26724
41300 | 426.676 | 26724
41301 | 432.9164 | 26724
41302 | 421.2446 | 26724
41303 | 413.9926 | 26724
41304 | 409.2017 | 26724
41305 | 417.0819 | 26724
41306 | 431.4602 | 26724
41307 | 420.9199 | 26724
41308 | 417.1966 | 26724
41309 | 408.7676 | 26724
41310 | 414.1603 | 26724
41311 | 418.9852 | 26724
41312 | 421.2167 | 26724
41313 | 402.9634 | 26724
41314 | 425.2921 | 26724
41315 | 418.5373 | 26724
41316 | 423.0659 | 26724
41317 | 416.7018 | 26724
41318 | 419.0554 | 26724
41319 | 434.5649 | 26724
41320 | 401.292 | 26724
41321 | 421.5414 | 26724
41322 | 427.3336 | 26724
41323 | 401.0264 | 26724
41324 | 423.7582 | 26724
41325 | 418.6514 | 26724
41326 | 420.0843 | 26724
41327 | 421.0901 | 26724
41328 | 425.1656 | 26724
41329 | 426.0224 | 26724
41330 | 424.7743 | 26724
41331 | 423.9723 | 26724
41332 | 429.2158 | 26724
41333 | 399.1169 | 26724
41334 | 396.1762 | 26724
41335 | 404.1084 | 26724
41336 | 414.2961 | 26724
41337 | 410.5143 | 26724
41338 | 413.6074 | 26724
41339 | 427.3604 | 26724
41340 | 410.2754 | 26724
41341 | 410.6807 | 26724
41342 | 437.0735 | 26724
41343 | 431.7434 | 26724
41344 | 412.9801 | 26724
41345 | 427.1822 | 26724
41346 | 412.9106 | 26724
41347 | 420.6918 | 26724
41348 | 427.7679 | 26724
41349 | 419.905 | 26724
41350 | 410.7944 | 26724
41351 | 416.5179 | 26724
41352 | 413.4974 | 26724
41353 | 415.7746 | 26724
41354 | 419.1166 | 26724
41355 | 422.392 | 26724
41356 | 420.3243 | 26724
41357 | 415.2151 | 26724
41358 | 417.4096 | 26724
41359 | 428.4544 | 26724
41360 | 419.1101 | 26724
41361 | 407.4223 | 26724
41362 | 435.4029 | 26724
41363 | 409.6548 | 26724
41364 | 409.2872 | 26724
41365 | 421.6777 | 26724
41366 | 418.1314 | 26724
41367 | 413.4856 | 26724
41368 | 420.353 | 26724
41369 | 427.4613 | 26724
41370 | 411.1959 | 26724
41371 | 418.6954 | 26724
41372 | 413.7379 | 26724
41373 | 407.9078 | 26724
41374 | 402.7084 | 26724
41375 | 425.4457 | 26724
41376 | 404.6635 | 26724
41377 | 405.1975 | 26724
41378 | 417.923 | 26724
41379 | 422.0226 | 26724
41380 | 406.7248 | 26724
41381 | 408.7103 | 26724
41382 | 418.5592 | 26724
41383 | 419.7663 | 26724
41384 | 422.6036 | 26724
41385 | 404.7096 | 26724
41386 | 424.9665 | 26724
41387 | 419.4361 | 26724
41388 | 422.3737 | 26724
41389 | 411.5678 | 26724
41390 | 404.759 | 26724
41391 | 429.8058 | 26724
41392 | 422.0108 | 26724
41393 | 420.3205 | 26724
41394 | 404.0279 | 26724
41395 | 424.1491 | 26724
41396 | 405.6992 | 26724
41397 | 422.8132 | 26724
41398 | 417.6812 | 26724
41399 | 425.1295 | 26724
41400 | 411.7978 | 26724
41401 | 405.7642 | 26724
41402 | 424.0599 | 26724
41403 | 400.8947 | 26724
41404 | 426.4194 | 26724
41405 | 426.8153 | 26724
41406 | 423.7008 | 26724
41407 | 419.1822 | 26724
41408 | 424.5824 | 26724
41409 | 413.6151 | 26724
41410 | 417.2095 | 26724
41411 | 413.6032 | 26724
41412 | 404.417 | 26724
41413 | 429.7879 | 26724
41414 | 423.632 | 26724
41415 | 419.2691 | 26724
41416 | 416.1654 | 26724
41417 | 421.7388 | 26724
41418 | 418.6383 | 26724
41419 | 430.8822 | 26724
41420 | 415.3185 | 26724
41421 | 406.2981 | 26724
41422 | 406.6389 | 26724
41423 | 432.6363 | 26724
41424 | 407.1751 | 26724
41425 | 401.8225 | 26724
41426 | 427.9328 | 26724
41427 | 417.2937 | 26724
41428 | 426.0721 | 26724
41429 | 415.0311 | 26724
41430 | 433.9005 | 26724
41431 | 418.3114 | 26724
41432 | 413.0496 | 26724
41433 | 418.5231 | 26724
41434 | 410.8587 | 26724
41435 | 415.82 | 26724
41436 | 416.3184 | 26724
41437 | 419.5289 | 26724
41438 | 414.0879 | 26724
41439 | 417.0579 | 26724
41440 | 407.8551 | 26724
41441 | 411.9737 | 26724
41442 | 414.0411 | 26724
41443 | 424.7873 | 26724
41444 | 404.3895 | 26724
41445 | 422.9624 | 26724
41446 | 417.5892 | 26724
41447 | 423.5811 | 26724
41448 | 429.0262 | 26724
41449 | 418.1191 | 26724
41450 | 407.2108 | 26724
41451 | 411.9564 | 26724
41452 | 412.9758 | 26724
41453 | 411.4099 | 26724
41454 | 412.0336 | 26724
41455 | 409.2781 | 26724
41456 | 410.3535 | 26724
41457 | 414.0782 | 26724
41458 | 417.1425 | 26724
41459 | 414.7073 | 26724
41460 | 414.5502 | 26724
41461 | 411.8416 | 26724
41462 | 415.9525 | 26724
41463 | 427.9371 | 26724
41464 | 417.8385 | 26724
41465 | 419.313 | 26724
41466 | 431.3992 | 26724
41467 | 417.8189 | 26724
41468 | 409.1108 | 26724
41469 | 401.9406 | 26724
41470 | 414.5762 | 26724
41471 | 408.0525 | 26724
41472 | 428.9555 | 26724
41473 | 431.0325 | 26724
41474 | 418.6012 | 26724
41475 | 420.3792 | 26724
41476 | 420.3951 | 26724
41477 | 410.0709 | 26724
41478 | 412.2578 | 26724
41479 | 419.7681 | 26724
41480 | 418.5217 | 26724
41481 | 402.8146 | 26724
41482 | 404.1913 | 26724
41483 | 408.7991 | 26724
41484 | 407.0601 | 26724
41485 | 412.9035 | 26724
41486 | 418.3798 | 26724
41487 | 408.3401 | 26724
41488 | 410.1639 | 26724
41489 | 406.6734 | 26724
41490 | 416.9945 | 26724
41491 | 408.5944 | 26724
41492 | 399.7397 | 26724
41493 | 417.2035 | 26724
41494 | 417.8388 | 26724
41495 | 409.9551 | 26724
41496 | 416.5735 | 26724
41497 | 423.4453 | 26724
41498 | 417.7359 | 26724
41499 | 422.3164 | 26724
41500 | 422.2518 | 26724
41501 | 408.6526 | 26724
41502 | 401.3791 | 26724
41503 | 421.0582 | 26724
41504 | 425.0113 | 26724
41505 | 412.5473 | 26724
41506 | 412.5826 | 26724
41507 | 406.0989 | 26724
41508 | 411.6004 | 26724
41509 | 418.957 | 26724
41510 | 434.2495 | 26724
41511 | 415.115 | 26724
41512 | 424.431 | 26724
41513 | 413.6028 | 26724
41514 | 409.9258 | 26724
41515 | 412.4855 | 26724
41516 | 426.4677 | 26724
41517 | 411.5874 | 26724
41518 | 409.867 | 26724
41519 | 415.9049 | 26724
41520 | 408.806 | 26724
41521 | 426.6228 | 26724
41522 | 416.4632 | 26724
41523 | 412.0722 | 26724
41524 | 424.7356 | 26724
41525 | 411.159 | 26724
41526 | 426.5844 | 26724
41527 | 424.1357 | 26724
41528 | 413.5268 | 26724
41529 | 413.5292 | 26724
41530 | 404.417 | 26724
41531 | 416.7386 | 26724
41532 | 425.2281 | 26724
41533 | 404.2236 | 26724
41534 | 426.9635 | 26724
41535 | 404.3256 | 26724
41536 | 416.5079 | 26724
41537 | 409.5194 | 26724
41538 | 435.96 | 26724
41539 | 420.5537 | 26724
41540 | 429.7661 | 26724
41541 | 419.5749 | 26724
41542 | 417.5146 | 26724
41543 | 404.1137 | 26724
41544 | 409.6702 | 26724
41545 | 404.0312 | 26724
41546 | 431.2882 | 26724
41547 | 408.7932 | 26724
41548 | 421.4894 | 26724
41549 | 410.0404 | 26724
41550 | 403.4381 | 26724
41551 | 415.3116 | 26724
41552 | 414.0791 | 26724
41553 | 428.1207 | 26724
41554 | 418.7958 | 26724
41555 | 416.3484 | 26724
41556 | 404.6643 | 26724
41557 | 418.921 | 26724
41558 | 407.8437 | 26724
41559 | 424.8888 | 26724
41560 | 431.916 | 26724
41561 | 408.7199 | 26724
41562 | 409.3293 | 26724
41563 | 425.6628 | 26724
41564 | 422.1413 | 26724
41565 | 414.2999 | 26724
41566 | 421.4698 | 26724
41567 | 413.6265 | 26724
41568 | 419.3899 | 26724
41569 | 413.7562 | 26724
41570 | 414.7655 | 26724
41571 | 412.1302 | 26724
41572 | 421.025 | 26724
41573 | 411.5109 | 26724
41574 | 408.775 | 26724
41575 | 416.8942 | 26724
41576 | 410.2555 | 26724
41577 | 428.1067 | 26724
41578 | 426.908 | 26724
41579 | 422.7188 | 26724
41580 | 426.5135 | 26724
41581 | 411.3577 | 26724
41582 | 427.841 | 26724
41583 | 417.3548 | 26724
41584 | 406.3292 | 26724
41585 | 421.5641 | 26724
41586 | 411.1902 | 26724
41587 | 399.2494 | 26724
41588 | 402.2229 | 26724
41589 | 421.7818 | 26724
41590 | 405.9232 | 26724
41591 | 423.2185 | 26724
41592 | 400.894 | 26724
41593 | 423.7432 | 26724
41594 | 414.8414 | 26724
41595 | 408.5566 | 26724
41596 | 417.4499 | 26724
41597 | 420.74 | 26724
41598 | 409.7216 | 26724
41599 | 427.8882 | 26724
41600 | 424.1778 | 26724
41601 | 412.1654 | 26724
41602 | 425.4836 | 26724
41603 | 415.6484 | 26724
41604 | 420.373 | 26724
41605 | 413.8757 | 26724
41606 | 418.4631 | 26724
41607 | 407.2928 | 26724
41608 | 416.7972 | 26724
41609 | 415.7952 | 26724
41610 | 411.3717 | 26724
41611 | 410.526 | 26724
41612 | 431.9031 | 26724
41613 | 405.6848 | 26724
41614 | 423.6766 | 26724
41615 | 420.987 | 26724
41616 | 420.0882 | 26724
41617 | 410.343 | 26724
41618 | 429.6762 | 26724
41619 | 410.9603 | 26724
41620 | 425.3999 | 26724
41621 | 418.8619 | 26724
41622 | 434.932 | 26724
41623 | 408.8638 | 26724
41624 | 410.6401 | 26724
41625 | 417.8928 | 26724
41626 | 423.6295 | 26724
41627 | 418.3505 | 26724
41628 | 432.7506 | 26724
41629 | 414.0715 | 26724
41630 | 415.7989 | 26724
41631 | 418.6608 | 26724
41632 | 420.3438 | 26724
41633 | 396.8611 | 26724
41634 | 417.1023 | 26724
41635 | 435.4899 | 26724
41636 | 405.6044 | 26724
41637 | 407.5389 | 26724
41638 | 427.0168 | 26724
41639 | 415.261 | 26724
41640 | 407.9497 | 26724
41641 | 419.3787 | 26724
41642 | 431.7886 | 26724
41643 | 423.0293 | 26724
41644 | 407.0936 | 26724
41645 | 407.7431 | 26724
41646 | 420.1551 | 26724
41647 | 409.6116 | 26724
41648 | 413.2167 | 26724
41649 | 396.1877 | 26724
41650 | 419.6293 | 26724
41651 | 414.4892 | 26724
41652 | 417.3468 | 26724
41653 | 406.6382 | 26724
41654 | 418.3121 | 26724
41655 | 413.6906 | 26724
41656 | 414.5964 | 26724
41657 | 416.3521 | 26724
41658 | 408.6095 | 26724
41659 | 411.8842 | 26724
41660 | 411.223 | 26724
41661 | 415.3857 | 26724
41662 | 418.6361 | 26724
41663 | 416.7356 | 26724
41664 | 412.5674 | 26724
41665 | 423.4748 | 26724
41666 | 421.8636 | 26724
41667 | 419.6406 | 26724
41668 | 410.7649 | 26724
41669 | 424.5094 | 26724
41670 | 421.6086 | 26724
41671 | 430.2027 | 26724
41672 | 417.9234 | 26724
41673 | 420.0875 | 26724
41674 | 422.8396 | 26724
41675 | 409.6607 | 26724
41676 | 417.6628 | 26724
41677 | 414.7568 | 26724
41678 | 416.0774 | 26724
41679 | 415.9689 | 26724
41680 | 422.7623 | 26724
41681 | 419.9014 | 26724
41682 | 427.9861 | 26724
41683 | 412.2083 | 26724
41684 | 403.7222 | 26724
41685 | 425.6432 | 26724
41686 | 425.9216 | 26724
41687 | 420.8765 | 26724
41688 | 408.9752 | 26724
41689 | 418.1028 | 26724
41690 | 423.0325 | 26724
41691 | 418.2289 | 26724
41692 | 413.9246 | 26724
41693 | 418.1151 | 26724
41694 | 406.2414 | 26724
41695 | 404.1017 | 26724
41696 | 430.6798 | 26724
41697 | 430.3423 | 26724
41698 | 422.513 | 26724
41699 | 409.4151 | 26724
41700 | 415.0027 | 26724
41701 | 418.7578 | 26724
41702 | 412.9445 | 26724
41703 | 410.1194 | 26724
41704 | 424.0644 | 26724
41705 | 417.5765 | 26724
41706 | 425.9476 | 26724
41707 | 404.7118 | 26724
41708 | 410.6057 | 26724
41709 | 418.3044 | 26724
41710 | 403.7689 | 26724
41711 | 413.8154 | 26724
41712 | 397.9568 | 26724
41713 | 418.5731 | 26724
41714 | 422.0817 | 26724
41715 | 420.7696 | 26724
41716 | 411.2082 | 26724
41717 | 424.7284 | 26724
41718 | 407.572 | 26724
41719 | 425.1061 | 26724
41720 | 422.9159 | 26724
41721 | 419.0487 | 26724
41722 | 416.9436 | 26724
41723 | 417.1364 | 26724
41724 | 429.7867 | 26724
41725 | 414.2517 | 26724
41726 | 416.8174 | 26724
41727 | 410.6303 | 26724
41728 | 419.0211 | 26724
41729 | 403.2802 | 26724
41730 | 407.537 | 26724
41731 | 425.842 | 26724
41732 | 415.0761 | 26724
41733 | 422.9792 | 26724
41734 | 403.3316 | 26724
41735 | 411.6405 | 26724
41736 | 413.8687 | 26724
41737 | 422.0258 | 26724
41738 | 423.9389 | 26724
41739 | 412.292 | 26724
41740 | 414.9346 | 26724
41741 | 418.5508 | 26724
41742 | 409.3988 | 26724
41743 | 409.1129 | 26724
41744 | 419.289 | 26724
41745 | 418.2281 | 26724
41746 | 410.7072 | 26724
41747 | 413.7867 | 26724
41748 | 404.0635 | 26724
41749 | 419.6394 | 26724
41750 | 418.4924 | 26724
41751 | 412.8037 | 26724
41752 | 418.9787 | 26724
41753 | 403.417 | 26724
41754 | 419.8254 | 26724
41755 | 417.2294 | 26724
41756 | 417.4848 | 26724
41757 | 406.1014 | 26724
41758 | 414.7443 | 26724
41759 | 413.1349 | 26724
41760 | 437.1743 | 26724
41761 | 403.4574 | 26724
41762 | 423.6657 | 26724
41763 | 413.6589 | 26724
41764 | 416.8382 | 26724
41765 | 423.8871 | 26724
41766 | 430.3255 | 26724
41767 | 422.3288 | 26724
41768 | 418.6122 | 26724
41769 | 412.8716 | 26724
41770 | 416.1748 | 26724
41771 | 424.7963 | 26724
41772 | 415.953 | 26724
41773 | 428.3025 | 26724
41774 | 421.8977 | 26724
41775 | 402.9768 | 26724
41776 | 401.2988 | 26724
41777 | 428.0441 | 26724
41778 | 416.3984 | 26724
41779 | 414.5287 | 26724
41780 | 409.1285 | 26724
41781 | 431.5192 | 26724
41782 | 419.4659 | 26724
41783 | 427.4946 | 26724
41784 | 405.8949 | 26724
41785 | 406.3621 | 26724
41786 | 417.2313 | 26724
41787 | 413.7211 | 26724
41788 | 412.919 | 26724
41789 | 415.2616 | 26724
41790 | 408.642 | 26724
41791 | 417.5184 | 26724
41792 | 408.9188 | 26724
41793 | 403.1653 | 26724
41794 | 412.0016 | 26724
41795 | 416.2602 | 26724
41796 | 426.6043 | 26724
41797 | 425.0179 | 26724
41798 | 417.7273 | 26724
41799 | 416.7803 | 26724
41800 | 415.0504 | 26724
41801 | 413.5045 | 26724
41802 | 412.9795 | 26724
41803 | 420.2412 | 26724
41804 | 414.8078 | 26724
41805 | 414.5644 | 26724
41806 | 412.7345 | 26724
41807 | 422.8772 | 26724
41808 | 417.7992 | 26724
41809 | 421.0976 | 26724
41810 | 424.3117 | 26724
41811 | 412.7031 | 26724
41812 | 405.8392 | 26724
41813 | 410.5593 | 26724
41814 | 415.8724 | 26724
41815 | 401.5766 | 26724
41816 | 418.3344 | 26724
41817 | 421.113 | 26724
41818 | 413.0854 | 26724
41819 | 408.0271 | 26724
41820 | 411.3672 | 26724
41821 | 413.8911 | 26724
41822 | 417.7289 | 26724
41823 | 412.5393 | 26724
41824 | 408.863 | 26724
41825 | 417.4164 | 26724
41826 | 427.5668 | 26724
41827 | 420.0864 | 26724
41828 | 420.8439 | 26724
41829 | 414.6236 | 26724
41830 | 426.1772 | 26724
41831 | 419.0267 | 26724
41832 | 411.7993 | 26724
41833 | 407.2073 | 26724
41834 | 398.0172 | 26724
41835 | 412.772 | 26724
41836 | 427.9161 | 26724
41837 | 411.0046 | 26724
41838 | 413.0468 | 26724
41839 | 429.746 | 26724
41840 | 422.3848 | 26724
41841 | 425.6803 | 26724
41842 | 411.3946 | 26724
41843 | 431.836 | 26724
41844 | 415.6648 | 26724
41845 | 424.8696 | 26724
41846 | 420.9474 | 26724
41847 | 419.482 | 26724
41848 | 411.8611 | 26724
41849 | 424.7328 | 26724
41850 | 427.0832 | 26724
41851 | 406.3572 | 26724
41852 | 412.2825 | 26724
41853 | 417.7906 | 26724
41854 | 413.7392 | 26724
41855 | 421.7051 | 26724
41856 | 406.1688 | 26724
41857 | 415.3804 | 26724
41858 | 417.279 | 26724
41859 | 407.958 | 26724
41860 | 420.3226 | 26724
41861 | 401.5028 | 26724
41862 | 416.9374 | 26724
41863 | 409.4907 | 26724
41864 | 409.7307 | 26724
41865 | 409.8134 | 26724
41866 | 420.5466 | 26724
41867 | 417.5479 | 26724
41868 | 426.6822 | 26724
41869 | 414.2344 | 26724
41870 | 407.057 | 26724
41871 | 410.7515 | 26724
41872 | 425.2422 | 26724
41873 | 413.8748 | 26724
41874 | 417.8457 | 26724
41875 | 424.0264 | 26724
41876 | 416.7784 | 26724
41877 | 410.8413 | 26724
41878 | 412.9611 | 26724
41879 | 403.6518 | 26724
41880 | 418.8948 | 26724
41881 | 419.2691 | 26724
41882 | 418.6909 | 26724
41883 | 403.345 | 26724
41884 | 426.4134 | 26724
41885 | 419.4407 | 26724
41886 | 410.7361 | 26724
41887 | 417.9774 | 26724
41888 | 417.1749 | 26724
41889 | 412.5419 | 26724
41890 | 420.3666 | 26724
41891 | 425.1079 | 26724
41892 | 398.5085 | 26724
41893 | 420.4007 | 26724
41894 | 405.5111 | 26724
41895 | 416.3623 | 26724
41896 | 412.2696 | 26724
41897 | 420.1711 | 26724
41898 | 400.484 | 26724
41899 | 400.0895 | 26724
41900 | 413.2718 | 26724
41901 | 416.1715 | 26724
41902 | 424.8152 | 26724
41903 | 422.5322 | 26724
41904 | 424.0912 | 26724
41905 | 417.4775 | 26724
41906 | 416.6587 | 26724
41907 | 431.5893 | 26724
41908 | 431.6649 | 26724
41909 | 419.3576 | 26724
41910 | 415.5345 | 26724
41911 | 417.3109 | 26724
41912 | 422.4293 | 26724
41913 | 419.1439 | 26724
41914 | 410.4078 | 26724
41915 | 398.2264 | 26724
41916 | 420.9805 | 26724
41917 | 416.8199 | 26724
41918 | 414.147 | 26724
41919 | 424.0576 | 26724
41920 | 424.8669 | 26724
41921 | 413.6697 | 26724
41922 | 418.0899 | 26724
41923 | 403.5415 | 26724
41924 | 413.9731 | 26724
41925 | 418.6807 | 26724
41926 | 418.5569 | 26724
41927 | 413.2726 | 26724
41928 | 417.7591 | 26724
41929 | 411.1615 | 26724
41930 | 415.2311 | 26724
41931 | 418.8278 | 26724
41932 | 425.0372 | 26724
41933 | 414.8631 | 26724
41934 | 414.9225 | 26724
41935 | 418.9165 | 26724
41936 | 426.9106 | 26724
41937 | 415.6189 | 26724
41938 | 420.0383 | 26724
41939 | 418.4423 | 26724
41940 | 428.0105 | 26724
41941 | 422.1153 | 26724
41942 | 426.8868 | 26724
41943 | 414.7151 | 26724
41944 | 421.6131 | 26724
41945 | 420.4151 | 26724
41946 | 404.432 | 26724
41947 | 404.7497 | 26724
41948 | 410.8526 | 26724
41949 | 420.175 | 26724
41950 | 405.3556 | 26724
41951 | 418.3111 | 26724
41952 | 408.4337 | 26724
41953 | 427.8982 | 26724
41954 | 419.0774 | 26724
41955 | 415.2064 | 26724
41956 | 413.1614 | 26724
41957 | 420.3752 | 26724
41958 | 406.926 | 26724
41959 | 423.933 | 26724
41960 | 406.1477 | 26724
41961 | 426.6679 | 26724
41962 | 415.614 | 26724
41963 | 410.4874 | 26724
41964 | 421.6385 | 26724
41965 | 432.5542 | 26724
41966 | 413.3395 | 26724
41967 | 414.8984 | 26724
41968 | 413.7151 | 26724
41969 | 420.6809 | 26724
41970 | 420.3856 | 26724
41971 | 416.4474 | 26724
41972 | 402.5949 | 26724
41973 | 415.061 | 26724
41974 | 423.3156 | 26724
41975 | 415.8675 | 26724
41976 | 425.5628 | 26724
41977 | 410.4995 | 26724
41978 | 406.304 | 26724
41979 | 418.3159 | 26724
41980 | 409.5819 | 26724
41981 | 428.077 | 26724
41982 | 437.1146 | 26724
41983 | 413.9048 | 26724
41984 | 417.3036 | 26724
41985 | 424.0237 | 26724
41986 | 423.0464 | 26724
41987 | 407.441 | 26724
41988 | 414.4952 | 26724
41989 | 424.1937 | 26724
41990 | 420.6447 | 26724
41991 | 412.6059 | 26724
41992 | 418.5871 | 26724
41993 | 426.6616 | 26724
41994 | 408.1238 | 26724
41995 | 420.8465 | 26724
41996 | 420.1925 | 26724
41997 | 405.7239 | 26724
41998 | 428.1505 | 26724
41999 | 430.6825 | 26724
42000 | 424.693 | 26724
42001 | 413.2276 | 26724
42002 | 415.2047 | 26724
42003 | 412.6573 | 26724
42004 | 430.6734 | 26724
42005 | 423.2017 | 26724
42006 | 414.7768 | 26724
42007 | 425.1738 | 26724
42008 | 429.3704 | 26724
42009 | 406.7178 | 26724
42010 | 411.5066 | 26724
42011 | 415.0109 | 26724
42012 | 417.7589 | 26724
42013 | 404.9358 | 26724
42014 | 404.0008 | 26724
42015 | 430.685 | 26724
42016 | 420.5666 | 26724
42017 | 423.4629 | 26724
42018 | 408.4074 | 26724
42019 | 416.2868 | 26724
42020 | 416.4492 | 26724
42021 | 409.7471 | 26724
42022 | 407.6158 | 26724
42023 | 426.0291 | 26724
42024 | 412.3039 | 26724
42025 | 416.0911 | 26724
42026 | 433.508 | 26724
42027 | 396.421 | 26724
42028 | 412.128 | 26724
42029 | 414.8958 | 26724
42030 | 423.3466 | 26724
42031 | 426.7337 | 26724
42032 | 412.9053 | 26724
42033 | 427.1763 | 26724
42034 | 410.8661 | 26724
42035 | 408.576 | 26724
42036 | 417.4932 | 26724
42037 | 412.6804 | 26724
42038 | 414.4519 | 26724
42039 | 405.366 | 26724
42040 | 414.1442 | 26724
42041 | 424.2552 | 26724
42042 | 408.3927 | 26724
42043 | 424.4818 | 26724
42044 | 419.7575 | 26724
42045 | 412.1044 | 26724
42046 | 429.1469 | 26724
42047 | 413.1427 | 26724
42048 | 414.2201 | 26724
42049 | 403.454 | 26724
42050 | 418.2439 | 26724
42051 | 420.8125 | 26724
42052 | 427.9569 | 26724
42053 | 432.5481 | 26724
42054 | 410.3544 | 26724
42055 | 416.1793 | 26724
42056 | 408.6382 | 26724
42057 | 425.7789 | 26724
42058 | 409.9845 | 26724
42059 | 419.7258 | 26724
42060 | 407.6853 | 26724
42061 | 412.0951 | 26724
42062 | 432.1335 | 26724
42063 | 408.462 | 26724
42064 | 416.5398 | 26724
42065 | 428.1667 | 26724
42066 | 415.3527 | 26724
42067 | 404.5346 | 26724
42068 | 409.1004 | 26724
42069 | 422.655 | 26724
42070 | 411.8494 | 26724
42071 | 425.8679 | 26724
42072 | 412.6017 | 26724
42073 | 407.9686 | 26724
42074 | 416.255 | 26724
42075 | 414.1349 | 26724
42076 | 412.975 | 26724
42077 | 427.4857 | 26724
42078 | 417.6452 | 26724
42079 | 422.9389 | 26724
42080 | 409.1829 | 26724
42081 | 421.697 | 26724
42082 | 425.6536 | 26724
42083 | 418.0387 | 26724
42084 | 415.1641 | 26724
42085 | 431.8525 | 26724
42086 | 416.9829 | 26724
42087 | 423.9357 | 26724
42088 | 413.697 | 26724
42089 | 427.6019 | 26724
42090 | 416.5626 | 26724
42091 | 402.1871 | 26724
42092 | 422.9567 | 26724
42093 | 418.5173 | 26724
42094 | 420.6079 | 26724
42095 | 407.6407 | 26724
42096 | 421.3233 | 26724
42097 | 411.633 | 26724
42098 | 419.4711 | 26724
42099 | 405.5143 | 26724
42100 | 397.5497 | 26724
42101 | 409.0627 | 26724
42102 | 403.1138 | 26724
42103 | 426.8404 | 26724
42104 | 419.0305 | 26724
42105 | 438.4723 | 26724
42106 | 422.1476 | 26724
42107 | 425.6926 | 26724
42108 | 413.9419 | 26724
42109 | 424.1784 | 26724
42110 | 427.6785 | 26724
42111 | 413.6294 | 26724
42112 | 410.2455 | 26724
42113 | 427.6767 | 26724
42114 | 426.0326 | 26724
42115 | 414.8881 | 26724
42116 | 418.8439 | 26724
42117 | 416.9837 | 26724
42118 | 419.386 | 26724
42119 | 417.3461 | 26724
42120 | 422.0985 | 26724
42121 | 408.5676 | 26724
42122 | 416.3518 | 26724
42123 | 413.7181 | 26724
42124 | 425.8308 | 26724
42125 | 401.0713 | 26724
42126 | 422.3598 | 26724
42127 | 410.579 | 26724
42128 | 405.4984 | 26724
42129 | 418.6878 | 26724
42130 | 407.5085 | 26724
42131 | 407.0383 | 26724
42132 | 407.7518 | 26724
42133 | 428.1504 | 26724
42134 | 413.5501 | 26724
42135 | 422.0783 | 26724
42136 | 407.0444 | 26724
42137 | 409.9082 | 26724
42138 | 417.4729 | 26724
42139 | 413.0228 | 26724
42140 | 411.0708 | 26724
42141 | 416.2084 | 26724
42142 | 410.3796 | 26724
42143 | 428.6921 | 26724
42144 | 422.5675 | 26724
42145 | 420.9174 | 26724
42146 | 414.0513 | 26724
42147 | 410.0265 | 26724
42148 | 422.6287 | 26724
42149 | 422.1028 | 26724
42150 | 418.8824 | 26724
42151 | 424.3069 | 26724
42152 | 404.8954 | 26724
42153 | 404.6114 | 26724
42154 | 412.8535 | 26724
42155 | 421.4444 | 26724
42156 | 408.7989 | 26724
42157 | 417.844 | 26724
42158 | 419.2275 | 26724
42159 | 403.9548 | 26724
42160 | 403.3768 | 26724
42161 | 419.7142 | 26724
42162 | 411.5586 | 26724
42163 | 409.6585 | 26724
42164 | 412.4912 | 26724
42165 | 414.0613 | 26724
42166 | 404.6941 | 26724
42167 | 400.5333 | 26724
42168 | 421.6366 | 26724
42169 | 403.5346 | 26724
42170 | 427.8437 | 26724
42171 | 418.9025 | 26724
42172 | 414.7257 | 26724
42173 | 425.1813 | 26724
42174 | 411.4906 | 26724
42175 | 420.8642 | 26724
42176 | 424.1414 | 26724
42177 | 416.9611 | 26724
42178 | 411.9121 | 26724
42179 | 421.1896 | 26724
42180 | 430.199 | 26724
42181 | 423.395 | 26724
42182 | 403.4699 | 26724
42183 | 414.2546 | 26724
42184 | 418.3441 | 26724
42185 | 421.6561 | 26724
42186 | 417.705 | 26724
42187 | 413.62 | 26724
42188 | 434.2815 | 26724
42189 | 403.3916 | 26724
42190 | 422.296 | 26724
42191 | 416.283 | 26724
42192 | 403.8 | 26724
42193 | 423.3102 | 26724
42194 | 422.0212 | 26724
42195 | 413.6581 | 26724
42196 | 417.7236 | 26724
42197 | 420.2165 | 26724
42198 | 409.9479 | 26724
42199 | 403.3551 | 26724
42200 | 399.0585 | 26724
42201 | 418.8748 | 26724
42202 | 398.5872 | 26724
42203 | 398.1298 | 26724
42204 | 423.446 | 26724
42205 | 406.7604 | 26724
42206 | 409.0833 | 26724
42207 | 415.5705 | 26724
42208 | 424.2274 | 26724
42209 | 409.3996 | 26724
42210 | 412.5222 | 26724
42211 | 423.0195 | 26724
42212 | 416.2912 | 26724
42213 | 424.7916 | 26724
42214 | 419.7312 | 26724
42215 | 428.7827 | 26724
42216 | 409.4924 | 26724
42217 | 417.3177 | 26724
42218 | 413.4712 | 26724
42219 | 404.2371 | 26724
42220 | 412.2024 | 26724
42221 | 418.3403 | 26724
42222 | 420.5264 | 26724
42223 | 428.4687 | 26724
42224 | 435.9078 | 26724
42225 | 420.829 | 26724
42226 | 424.6782 | 26724
42227 | 413.9146 | 26724
42228 | 418.219 | 26724
42229 | 415.3489 | 26724
42230 | 426.4247 | 26724
42231 | 408.105 | 26724
42232 | 408.8593 | 26724
42233 | 424.2575 | 26724
42234 | 412.1094 | 26724
42235 | 423.1396 | 26724
42236 | 419.9661 | 26724
42237 | 406.7353 | 26724
42238 | 406.8237 | 26724
42239 | 424.0343 | 26724
42240 | 411.8272 | 26724
42241 | 415.3526 | 26724
42242 | 417.9691 | 26724
42243 | 414.4211 | 26724
42244 | 410.6739 | 26724
42245 | 427.3028 | 26724
42246 | 410.6468 | 26724
42247 | 427.6745 | 26724
42248 | 416.7895 | 26724
42249 | 420.6237 | 26724
42250 | 402.7556 | 26724
42251 | 407.5955 | 26724
42252 | 407.5874 | 26724
42253 | 403.416 | 26724
42254 | 412.1592 | 26724
42255 | 409.767 | 26724
42256 | 425.428 | 26724
42257 | 421.2522 | 26724
42258 | 407.9582 | 26724
42259 | 422.5489 | 26724
42260 | 414.8303 | 26724
42261 | 406.4306 | 26724
42262 | 423.6969 | 26724
42263 | 415.4196 | 26724
42264 | 414.6629 | 26724
42265 | 403.7443 | 26724
42266 | 422.5841 | 26724
42267 | 420.3445 | 26724
42268 | 402.8754 | 26724
42269 | 420.0602 | 26724
42270 | 403.3616 | 26724
42271 | 420.7805 | 26724
42272 | 417.0914 | 26724
42273 | 425.4766 | 26724
42274 | 418.7246 | 26724
42275 | 418.5222 | 26724
42276 | 422.8009 | 26724
42277 | 414.89 | 26724
42278 | 409.3354 | 26724
42279 | 413.6259 | 26724
42280 | 409.4015 | 26724
42281 | 416.9637 | 26724
42282 | 408.2768 | 26724
42283 | 411.7081 | 26724
42284 | 428.9957 | 26724
42285 | 412.5301 | 26724
42286 | 423.8587 | 26724
42287 | 425.5718 | 26724
42288 | 415.2853 | 26724
42289 | 409.9514 | 26724
42290 | 420.8863 | 26724
42291 | 411.216 | 26724
42292 | 428.3417 | 26724
42293 | 418.0854 | 26724
42294 | 421.5683 | 26724
42295 | 417.2538 | 26724
42296 | 421.8107 | 26724
42297 | 416.121 | 26724
42298 | 409.7216 | 26724
42299 | 426.9904 | 26724
42300 | 412.2325 | 26724
42301 | 419.1238 | 26724
42302 | 418.1773 | 26724
42303 | 416.9851 | 26724
42304 | 403.8757 | 26724
42305 | 423.567 | 26724
42306 | 418.3014 | 26724
42307 | 400.0761 | 26724
42308 | 429.3164 | 26724
42309 | 411.404 | 26724
42310 | 411.1895 | 26724
42311 | 415.7126 | 26724
42312 | 405.6346 | 26724
42313 | 408.1082 | 26724
42314 | 417.0293 | 26724
42315 | 405.2478 | 26724
42316 | 405.2586 | 26724
42317 | 410.3095 | 26724
42318 | 411.7944 | 26724
42319 | 420.3306 | 26724
42320 | 412.4951 | 26724
42321 | 410.2221 | 26724
42322 | 420.093 | 26724
42323 | 417.594 | 26724
42324 | 431.1542 | 26724
42325 | 418.762 | 26724
42326 | 418.1013 | 26724
42327 | 404.0798 | 26724
42328 | 420.5727 | 26724
42329 | 408.0669 | 26724
42330 | 428.9669 | 26724
42331 | 403.1932 | 26724
42332 | 416.0414 | 26724
42333 | 418.8712 | 26724
42334 | 415.4222 | 26724
42335 | 421.5388 | 26724
42336 | 421.6015 | 26724
42337 | 409.0361 | 26724
42338 | 402.5631 | 26724
42339 | 417.7717 | 26724
42340 | 429.2014 | 26724
42341 | 409.6564 | 26724
42342 | 427.8951 | 26724
42343 | 406.1129 | 26724
42344 | 405.088 | 26724
42345 | 409.6334 | 26724
42346 | 413.7035 | 26724
42347 | 396.7218 | 26724
42348 | 397.088 | 26724
42349 | 410.4945 | 26724
42350 | 425.9978 | 26724
42351 | 418.4626 | 26724
42352 | 425.1036 | 26724
42353 | 411.8081 | 26724
42354 | 416.9446 | 26724
42355 | 429.0109 | 26724
42356 | 415.2063 | 26724
42357 | 418.3799 | 26724
42358 | 412.571 | 26724
42359 | 413.8997 | 26724
42360 | 411.0744 | 26724
42361 | 408.3818 | 26724
42362 | 424.7538 | 26724
42363 | 411.9791 | 26724
42364 | 407.8883 | 26724
42365 | 407.6017 | 26724
42366 | 413.2994 | 26724
42367 | 407.0508 | 26724
42368 | 412.1507 | 26724
42369 | 418.4696 | 26724
42370 | 418.1099 | 26724
42371 | 419.6989 | 26724
42372 | 416.8842 | 26724
42373 | 417.8601 | 26724
42374 | 412.7124 | 26724
42375 | 412.9585 | 26724
42376 | 412.6979 | 26724
42377 | 420.57 | 26724
42378 | 419.3869 | 26724
42379 | 435.1367 | 26724
42380 | 424.2453 | 26724
42381 | 396.5674 | 26724
42382 | 411.0641 | 26724
42383 | 416.9987 | 26724
42384 | 412.0144 | 26724
42385 | 414.2572 | 26724
42386 | 412.3149 | 26724
42387 | 412.8806 | 26724
42388 | 408.3902 | 26724
42389 | 416.4408 | 26724
42390 | 431.1511 | 26724
42391 | 408.5135 | 26724
42392 | 422.7461 | 26724
42393 | 420.8506 | 26724
42394 | 417.7396 | 26724
42395 | 423.4823 | 26724
42396 | 410.476 | 26724
42397 | 415.2326 | 26724
42398 | 420.089 | 26724
42399 | 428.0435 | 26724
42400 | 431.1739 | 26724
42401 | 416.4013 | 26724
42402 | 420.3764 | 26724
42403 | 410.0273 | 26724
42404 | 406.0791 | 26724
42405 | 417.0204 | 26724
42406 | 416.427 | 26724
42407 | 413.8457 | 26724
42408 | 428.8068 | 26724
42409 | 426.3305 | 26724
42410 | 426.9183 | 26724
42411 | 415.7454 | 26724
42412 | 433.8737 | 26724
42413 | 430.2833 | 26724
42414 | 417.2227 | 26724
42415 | 422.888 | 26724
42416 | 411.1449 | 26724
42417 | 416.4915 | 26724
42418 | 411.5986 | 26724
42419 | 432.4607 | 26724
42420 | 420.1516 | 26724
42421 | 407.6216 | 26724
42422 | 416.278 | 26724
42423 | 411.2533 | 26724
42424 | 419.5536 | 26724
42425 | 412.8103 | 26724
42426 | 412.6169 | 26724
42427 | 421.5535 | 26724
42428 | 427.7718 | 26724
42429 | 413.5979 | 26724
42430 | 435.1416 | 26724
42431 | 429.355 | 26724
42432 | 396.3145 | 26724
42433 | 425.6548 | 26724
42434 | 413.9247 | 26724
42435 | 413.2559 | 26724
42436 | 407.8298 | 26724
42437 | 421.0639 | 26724
42438 | 424.4614 | 26724
42439 | 420.1369 | 26724
42440 | 422.4657 | 26724
42441 | 412.2702 | 26724
42442 | 417.9941 | 26724
42443 | 422.3503 | 26724
42444 | 412.8785 | 26724
42445 | 412.0558 | 26724
42446 | 415.8583 | 26724
42447 | 408.5563 | 26724
42448 | 419.8794 | 26724
42449 | 417.0713 | 26724
42450 | 429.4619 | 26724
42451 | 417.415 | 26724
42452 | 419.939 | 26724
42453 | 415.7798 | 26724
42454 | 415.9958 | 26724
42455 | 407.9653 | 26724
42456 | 416.3153 | 26724
42457 | 402.0085 | 26724
42458 | 409.9819 | 26724
42459 | 417.055 | 26724
42460 | 432.0188 | 26724
42461 | 413.3131 | 26724
42462 | 426.6629 | 26724
42463 | 427.4438 | 26724
42464 | 424.5966 | 26724
42465 | 407.1542 | 26724
42466 | 402.5164 | 26724
42467 | 404.5751 | 26724
42468 | 422.7858 | 26724
42469 | 422.2342 | 26724
42470 | 422.0108 | 26724
42471 | 407.4869 | 26724
42472 | 423.6807 | 26724
42473 | 425.5811 | 26724
42474 | 406.4184 | 26724
42475 | 419.3787 | 26724
42476 | 398.5477 | 26724
42477 | 422.834 | 26724
42478 | 403.8935 | 26724
42479 | 418.2214 | 26724
42480 | 403.8368 | 26724
42481 | 415.6336 | 26724
42482 | 417.3933 | 26724
42483 | 430.2771 | 26724
42484 | 417.5111 | 26724
42485 | 429.2018 | 26724
42486 | 421.4435 | 26724
42487 | 416.1856 | 26724
42488 | 411.1393 | 26724
42489 | 415.185 | 26724
42490 | 430.9722 | 26724
42491 | 418.1303 | 26724
42492 | 413.9514 | 26724
42493 | 412.4386 | 26724
42494 | 414.1699 | 26724
42495 | 419.7277 | 26724
42496 | 429.2061 | 26724
42497 | 414.5331 | 26724
42498 | 416.8162 | 26724
42499 | 419.2106 | 26724
42500 | 405.1012 | 26724
42501 | 414.5838 | 26724
42502 | 411.4545 | 26724
42503 | 406.5346 | 26724
42504 | 417.9409 | 26724
42505 | 414.7853 | 26724
42506 | 413.5248 | 26724
42507 | 415.3171 | 26724
42508 | 418.0248 | 26724
42509 | 419.2188 | 26724
42510 | 410.0928 | 26724
42511 | 420.2834 | 26724
42512 | 431.0485 | 26724
42513 | 412.699 | 26724
42514 | 412.4307 | 26724
42515 | 405.1791 | 26724
42516 | 421.2773 | 26724
42517 | 409.5017 | 26724
42518 | 425.9588 | 26724
42519 | 413.7633 | 26724
42520 | 415.4053 | 26724
42521 | 409.9587 | 26724
42522 | 423.6288 | 26724
42523 | 424.8268 | 26724
42524 | 424.9786 | 26724
42525 | 429.0532 | 26724
42526 | 414.2222 | 26724
42527 | 420.2746 | 26724
42528 | 405.1242 | 26724
42529 | 417.8699 | 26724
42530 | 420.6839 | 26724
42531 | 417.8542 | 26724
42532 | 432.6129 | 26724
42533 | 412.1372 | 26724
42534 | 415.6402 | 26724
42535 | 404.9954 | 26724
42536 | 421.3538 | 26724
42537 | 415.9508 | 26724
42538 | 426.2611 | 26724
42539 | 429.6372 | 26724
42540 | 423.2891 | 26724
42541 | 418.5076 | 26724
42542 | 426.6302 | 26724
42543 | 404.0541 | 26724
42544 | 409.8187 | 26724
42545 | 413.399 | 26724
42546 | 419.4966 | 26724
42547 | 425.5742 | 26724
42548 | 408.6917 | 26724
42549 | 415.8152 | 26724
42550 | 401.5167 | 26724
42551 | 413.6521 | 26724
42552 | 404.107 | 26724
42553 | 413.3199 | 26724
42554 | 430.1534 | 26724
42555 | 405.7451 | 26724
42556 | 409.6764 | 26724
42557 | 401.2049 | 26724
42558 | 420.3342 | 26724
42559 | 422.9362 | 26724
42560 | 418.3947 | 26724
42561 | 423.7554 | 26724
42562 | 422.9662 | 26724
42563 | 422.6701 | 26724
42564 | 409.2073 | 26724
42565 | 407.5515 | 26724
42566 | 426.2076 | 26724
42567 | 410.0324 | 26724
42568 | 409.3499 | 26724
42569 | 411.4036 | 26724
42570 | 425.613 | 26724
42571 | 417.0524 | 26724
42572 | 422.6133 | 26724
42573 | 426.2129 | 26724
42574 | 415.2784 | 26724
42575 | 417.1182 | 26724
42576 | 410.1323 | 26724
42577 | 405.9089 | 26724
42578 | 413.059 | 26724
42579 | 411.5584 | 26724
42580 | 408.9475 | 26724
42581 | 408.1854 | 26724
42582 | 435.0249 | 26724
42583 | 403.4038 | 26724
42584 | 422.0761 | 26724
42585 | 415.4125 | 26724
42586 | 418.0667 | 26724
42587 | 429.5503 | 26724
42588 | 412.3242 | 26724
42589 | 417.5205 | 26724
42590 | 423.9155 | 26724
42591 | 413.6763 | 26724
42592 | 416.6486 | 26724
42593 | 415.7566 | 26724
42594 | 419.5445 | 26724
42595 | 418.0808 | 26724
42596 | 425.5084 | 26724
42597 | 417.0297 | 26724
42598 | 418.1292 | 26724
42599 | 433.2639 | 26724
42600 | 413.2206 | 26724
42601 | 413.2564 | 26724
42602 | 418.3324 | 26724
42603 | 406.1869 | 26724
42604 | 430.6598 | 26724
42605 | 410.4535 | 26724
42606 | 417.4966 | 26724
42607 | 412.4075 | 26724
42608 | 415.0041 | 26724
42609 | 426.0579 | 26724
42610 | 411.9582 | 26724
42611 | 425.72 | 26724
42612 | 411.8422 | 26724
42613 | 411.4321 | 26724
42614 | 420.5595 | 26724
42615 | 427.3494 | 26724
42616 | 431.7049 | 26724
42617 | 413.2973 | 26724
42618 | 414.9872 | 26724
42619 | 422.458 | 26724
42620 | 424.5306 | 26724
42621 | 418.6566 | 26724
42622 | 422.4239 | 26724
42623 | 418.3247 | 26724
42624 | 422.6075 | 26724
42625 | 419.6752 | 26724
42626 | 410.2843 | 26724
42627 | 405.0316 | 26724
42628 | 420.0373 | 26724
42629 | 422.594 | 26724
42630 | 407.9096 | 26724
42631 | 414.8972 | 26724
42632 | 408.5846 | 26724
42633 | 419.1603 | 26724
42634 | 415.1893 | 26724
42635 | 415.039 | 26724
42636 | 409.1193 | 26724
42637 | 416.0869 | 26724
42638 | 397.2841 | 26724
42639 | 423.6337 | 26724
42640 | 431.0341 | 26724
42641 | 432.0319 | 26724
42642 | 409.3095 | 26724
42643 | 409.7103 | 26724
42644 | 425.5081 | 26724
42645 | 417.5757 | 26724
42646 | 410.2911 | 26724
42647 | 406.0244 | 26724
42648 | 406.418 | 26724
42649 | 418.6784 | 26724
42650 | 414.0157 | 26724
42651 | 418.5589 | 26724
42652 | 422.2376 | 26724
42653 | 406.8914 | 26724
42654 | 425.6128 | 26724
42655 | 414.7442 | 26724
42656 | 408.1674 | 26724
42657 | 409.3402 | 26724
42658 | 411.3004 | 26724
42659 | 425.5322 | 26724
42660 | 406.9445 | 26724
42661 | 419.0594 | 26724
42662 | 413.9293 | 26724
42663 | 426.9365 | 26724
42664 | 417.2448 | 26724
42665 | 412.4581 | 26724
42666 | 420.4625 | 26724
42667 | 416.5178 | 26724
42668 | 405.2516 | 26724
42669 | 411.2437 | 26724
42670 | 420.8261 | 26724
42671 | 405.5207 | 26724
42672 | 422.2315 | 26724
42673 | 427.5899 | 26724
42674 | 404.2917 | 26724
42675 | 409.4856 | 26724
42676 | 420.1007 | 26724
42677 | 430.3517 | 26724
42678 | 412.2489 | 26724
42679 | 417.7562 | 26724
42680 | 409.4558 | 26724
42681 | 407.1122 | 26724
42682 | 420.681 | 26724
42683 | 413.3804 | 26724
42684 | 420.9081 | 26724
42685 | 409.7776 | 26724
42686 | 415.6792 | 26724
42687 | 425.9311 | 26724
42688 | 425.4824 | 26724
42689 | 422.7936 | 26724
42690 | 426.3223 | 26724
42691 | 418.463 | 26724
42692 | 432.2058 | 26724
42693 | 415.0601 | 26724
42694 | 418.1104 | 26724
42695 | 417.7424 | 26724
42696 | 422.9934 | 26724
42697 | 409.3864 | 26724
42698 | 429.5779 | 26724
42699 | 430.9891 | 26724
42700 | 406.4626 | 26724
42701 | 421.1639 | 26724
42702 | 424.3791 | 26724
42703 | 425.0009 | 26724
42704 | 415.8821 | 26724
42705 | 411.9938 | 26724
42706 | 412.929 | 26724
42707 | 425.26 | 26724
42708 | 422.4431 | 26724
42709 | 414.2175 | 26724
42710 | 435.0381 | 26724
42711 | 407.6627 | 26724
42712 | 406.5556 | 26724
42713 | 424.4083 | 26724
42714 | 421.9359 | 26724
42715 | 407.3899 | 26724
42716 | 422.454 | 26724
42717 | 418.2746 | 26724
42718 | 414.056 | 26724
42719 | 417.1043 | 26724
42720 | 402.32 | 26724
42721 | 418.8734 | 26724
42722 | 398.0796 | 26724
42723 | 407.5928 | 26724
42724 | 413.312 | 26724
42725 | 420.5889 | 26724
42726 | 415.9695 | 26724
42727 | 427.0358 | 26724
42728 | 425.5134 | 26724
42729 | 413.0647 | 26724
42730 | 403.7171 | 26724
42731 | 404.7092 | 26724
42732 | 414.2105 | 26724
42733 | 417.1055 | 26724
42734 | 416.9693 | 26724
42735 | 421.0951 | 26724
42736 | 423.2734 | 26724
42737 | 412.2544 | 26724
42738 | 419.5514 | 26724
42739 | 433.822 | 26724
42740 | 419.6406 | 26724
42741 | 433.1823 | 26724
42742 | 424.3802 | 26724
42743 | 422.4101 | 26724
42744 | 415.2583 | 26724
42745 | 413.8483 | 26724
42746 | 420.6664 | 26724
42747 | 426.0969 | 26724
42748 | 430.6475 | 26724
42749 | 413.7316 | 26724
42750 | 424.1781 | 26724
42751 | 415.033 | 26724
42752 | 413.4127 | 26724
42753 | 425.7491 | 26724
42754 | 430.2306 | 26724
42755 | 419.971 | 26724
42756 | 421.295 | 26724
42757 | 422.7694 | 26724
42758 | 408.2652 | 26724
42759 | 416.183 | 26724
42760 | 423.0608 | 26724
42761 | 422.1785 | 26724
42762 | 407.1623 | 26724
42763 | 419.0527 | 26724
42764 | 432.9861 | 26724
42765 | 419.3984 | 26724
42766 | 406.0808 | 26724
42767 | 422.0324 | 26724
42768 | 422.2519 | 26724
42769 | 398.2163 | 26724
42770 | 403.51 | 26724
42771 | 415.8082 | 26724
42772 | 410.5458 | 26724
42773 | 421.6605 | 26724
42774 | 407.8738 | 26724
42775 | 415.3787 | 26724
42776 | 417.2649 | 26724
42777 | 402.3886 | 26724
42778 | 426.0977 | 26724
42779 | 410.855 | 26724
42780 | 406.1414 | 26724
42781 | 402.703 | 26724
42782 | 421.6518 | 26724
42783 | 418.9808 | 26724
42784 | 415.0462 | 26724
42785 | 405.7738 | 26724
42786 | 410.4429 | 26724
42787 | 425.0286 | 26724
42788 | 415.511 | 26724
42789 | 419.2051 | 26724
42790 | 406.2282 | 26724
42791 | 413.5281 | 26724
42792 | 401.6497 | 26724
42793 | 409.0334 | 26724
42794 | 414.4944 | 26724
42795 | 408.6901 | 26724
42796 | 424.9103 | 26724
42797 | 424.031 | 26724
42798 | 418.9305 | 26724
42799 | 417.1358 | 26724
42800 | 412.2051 | 26724
42801 | 411.8404 | 26724
42802 | 409.2245 | 26724
42803 | 422.1962 | 26724
42804 | 424.8988 | 26724
42805 | 416.8351 | 26724
42806 | 402.2697 | 26724
42807 | 412.9463 | 26724
42808 | 402.0585 | 26724
42809 | 407.5946 | 26724
42810 | 415.2734 | 26724
42811 | 427.8395 | 26724
42812 | 432.6488 | 26724
42813 | 412.3875 | 26724
42814 | 425.0925 | 26724
42815 | 421.1283 | 26724
42816 | 419.4534 | 26724
42817 | 415.6541 | 26724
42818 | 427.2275 | 26724
42819 | 416.6977 | 26724
42820 | 407.7382 | 26724
42821 | 418.6038 | 26724
42822 | 410.8124 | 26724
42823 | 401.6399 | 26724
42824 | 424.9148 | 26724
42825 | 406.5631 | 26724
42826 | 415.4723 | 26724
42827 | 405.5185 | 26724
42828 | 421.6323 | 26724
42829 | 411.8719 | 26724
42830 | 412.805 | 26724
42831 | 418.401 | 26724
42832 | 421.8575 | 26724
42833 | 407.7006 | 26724
42834 | 421.4867 | 26724
42835 | 411.5286 | 26724
42836 | 424.9832 | 26724
42837 | 416.1822 | 26724
42838 | 427.1853 | 26724
42839 | 410.0457 | 26724
42840 | 424.2242 | 26724
42841 | 410.2302 | 26724
42842 | 402.5352 | 26724
42843 | 429.5391 | 26724
42844 | 410.3003 | 26724
42845 | 405.1439 | 26724
42846 | 413.3746 | 26724
42847 | 405.2237 | 26724
42848 | 422.7417 | 26724
42849 | 426.2597 | 26724
42850 | 405.6028 | 26724
42851 | 396.4493 | 26724
42852 | 409.6878 | 26724
42853 | 416.7178 | 26724
42854 | 420.6085 | 26724
42855 | 423.8517 | 26724
42856 | 413.5449 | 26724
42857 | 419.4875 | 26724
42858 | 427.4951 | 26724
42859 | 419.6248 | 26724
42860 | 425.2027 | 26724
42861 | 427.2235 | 26724
42862 | 412.2189 | 26724
42863 | 415.3144 | 26724
42864 | 411.9302 | 26724
42865 | 422.7775 | 26724
42866 | 414.9508 | 26724
42867 | 418.641 | 26724
42868 | 419.5295 | 26724
42869 | 414.4072 | 26724
42870 | 415.0563 | 26724
42871 | 407.7247 | 26724
42872 | 427.3266 | 26724
42873 | 434.5208 | 26724
42874 | 407.0459 | 26724
42875 | 414.9532 | 26724
42876 | 423.6056 | 26724
42877 | 412.7824 | 26724
42878 | 435.6411 | 26724
42879 | 425.9591 | 26724
42880 | 409.1564 | 26724
42881 | 418.0395 | 26724
42882 | 423.0206 | 26724
42883 | 425.479 | 26724
42884 | 415.2823 | 26724
42885 | 411.0429 | 26724
42886 | 410.8575 | 26724
42887 | 418.3894 | 26724
42888 | 409.4946 | 26724
42889 | 413.5283 | 26724
42890 | 414.6363 | 26724
42891 | 430.0418 | 26724
42892 | 414.8591 | 26724
42893 | 423.8021 | 26724
42894 | 408.8508 | 26724
42895 | 410.0963 | 26724
42896 | 417.6067 | 26724
42897 | 422.4374 | 26724
42898 | 407.554 | 26724
42899 | 413.0007 | 26724
42900 | 411.1772 | 26724
42901 | 413.5573 | 26724
42902 | 403.3242 | 26724
42903 | 428.9008 | 26724
42904 | 408.2006 | 26724
42905 | 412.5051 | 26724
42906 | 414.7176 | 26724
42907 | 419.0002 | 26724
42908 | 428.9729 | 26724
42909 | 435.9759 | 26724
42910 | 425.0459 | 26724
42911 | 429.4893 | 26724
42912 | 407.5698 | 26724
42913 | 424.9056 | 26724
42914 | 418.042 | 26724
42915 | 409.4827 | 26724
42916 | 412.119 | 26724
42917 | 432.5751 | 26724
42918 | 425.2597 | 26724
42919 | 420.3997 | 26724
42920 | 405.5435 | 26724
42921 | 426.0846 | 26724
42922 | 423.4649 | 26724
42923 | 403.7126 | 26724
42924 | 412.9098 | 26724
42925 | 419.0128 | 26724
42926 | 429.0676 | 26724
42927 | 421.3028 | 26724
42928 | 427.4389 | 26724
42929 | 408.6967 | 26724
42930 | 410.7177 | 26724
42931 | 405.4607 | 26724
42932 | 419.0972 | 26724
42933 | 404.4622 | 26724
42934 | 406.5345 | 26724
42935 | 411.3069 | 26724
42936 | 412.9809 | 26724
42937 | 419.0102 | 26724
42938 | 405.8463 | 26724
42939 | 428.2205 | 26724
42940 | 415.6953 | 26724
42941 | 417.5958 | 26724
42942 | 417.2872 | 26724
42943 | 425.6523 | 26724
42944 | 414.0585 | 26724
42945 | 420.4285 | 26724
42946 | 419.3951 | 26724
42947 | 417.0517 | 26724
42948 | 407.9961 | 26724
42949 | 418.6569 | 26724
42950 | 412.1394 | 26724
42951 | 418.9206 | 26724
42952 | 421.8865 | 26724
42953 | 413.5225 | 26724
42954 | 426.0014 | 26724
42955 | 416.8099 | 26724
42956 | 427.6744 | 26724
42957 | 407.5497 | 26724
42958 | 417.0416 | 26724
42959 | 413.8054 | 26724
42960 | 403.2471 | 26724
42961 | 410.9365 | 26724
42962 | 406.1384 | 26724
42963 | 409.3328 | 26724
42964 | 416.2537 | 26724
42965 | 425.2674 | 26724
42966 | 421.7535 | 26724
42967 | 415.4356 | 26724
42968 | 399.6735 | 26724
42969 | 401.9145 | 26724
42970 | 406.6742 | 26724
42971 | 411.3413 | 26724
42972 | 411.6065 | 26724
42973 | 419.7085 | 26724
42974 | 406.9824 | 26724
42975 | 420.234 | 26724
42976 | 421.1376 | 26724
42977 | 408.7913 | 26724
42978 | 411.6617 | 26724
42979 | 409.3288 | 26724
42980 | 411.7932 | 26724
42981 | 419.428 | 26724
42982 | 432.7927 | 26724
42983 | 426.4199 | 26724
42984 | 429.3559 | 26724
42985 | 412.0258 | 26724
42986 | 416.8489 | 26724
42987 | 415.9019 | 26724
42988 | 402.6529 | 26724
42989 | 409.921 | 26724
42990 | 417.1779 | 26724
42991 | 413.2165 | 26724
42992 | 430.2429 | 26724
42993 | 415.516 | 26724
42994 | 414.4251 | 26724
42995 | 413.3705 | 26724
42996 | 432.8144 | 26724
42997 | 433.3222 | 26724
42998 | 400.5777 | 26724
42999 | 427.8549 | 26724
43000 | 420.2245 | 26724
43001 | 412.4062 | 26724
43002 | 423.2415 | 26724
43003 | 419.7326 | 26724
43004 | 430.2576 | 26724
43005 | 426.8862 | 26724
43006 | 417.0802 | 26724
43007 | 417.1048 | 26724
43008 | 426.078 | 26724
43009 | 404.0429 | 26724
43010 | 415.3517 | 26724
43011 | 416.1291 | 26724
43012 | 413.5358 | 26724
43013 | 409.9607 | 26724
43014 | 407.3169 | 26724
43015 | 411.9342 | 26724
43016 | 430.0446 | 26724
43017 | 418.5284 | 26724
43018 | 413.4867 | 26724
43019 | 428.1046 | 26724
43020 | 410.0878 | 26724
43021 | 415.8577 | 26724
43022 | 415.0966 | 26724
43023 | 423.0596 | 26724
43024 | 422.992 | 26724
43025 | 420.2504 | 26724
43026 | 404.9701 | 26724
43027 | 430.5911 | 26724
43028 | 423.8908 | 26724
43029 | 424.8268 | 26724
43030 | 424.2716 | 26724
43031 | 427.2281 | 26724
43032 | 400.3573 | 26724
43033 | 416.6182 | 26724
43034 | 424.6451 | 26724
43035 | 407.3076 | 26724
43036 | 425.8792 | 26724
43037 | 410.3553 | 26724
43038 | 424.1289 | 26724
43039 | 409.8603 | 26724
43040 | 411.4364 | 26724
43041 | 423.0556 | 26724
43042 | 425.9437 | 26724
43043 | 410.8769 | 26724
43044 | 421.3388 | 26724
43045 | 417.1106 | 26724
43046 | 438.4222 | 26724
43047 | 428.6153 | 26724
43048 | 411.651 | 26724
43049 | 417.7437 | 26724
43050 | 417.6262 | 26724
43051 | 409.6786 | 26724
43052 | 409.5291 | 26724
43053 | 419.2776 | 26724
43054 | 413.4241 | 26724
43055 | 408.7481 | 26724
43056 | 401.1086 | 26724
43057 | 411.529 | 26724
43058 | 423.5317 | 26724
43059 | 418.7547 | 26724
43060 | 412.5416 | 26724
43061 | 426.3921 | 26724
43062 | 420.7296 | 26724
43063 | 413.2576 | 26724
43064 | 421.5214 | 26724
43065 | 418.7895 | 26724
43066 | 420.0225 | 26724
43067 | 416.9659 | 26724
43068 | 415.9859 | 26724
43069 | 423.9064 | 26724
43070 | 415.0045 | 26724
43071 | 408.2179 | 26724
43072 | 402.429 | 26724
43073 | 405.3902 | 26724
43074 | 423.1217 | 26724
43075 | 422.4497 | 26724
43076 | 408.0639 | 26724
43077 | 404.7453 | 26724
43078 | 417.3304 | 26724
43079 | 417.7386 | 26724
43080 | 427.9566 | 26724
43081 | 413.6905 | 26724
43082 | 410.0624 | 26724
43083 | 427.0912 | 26724
43084 | 418.3427 | 26724
43085 | 415.3376 | 26724
43086 | 411.4874 | 26724
43087 | 411.9374 | 26724
43088 | 414.6512 | 26724
43089 | 423.1306 | 26724
43090 | 404.4922 | 26724
43091 | 421.9945 | 26724
43092 | 406.8583 | 26724
43093 | 408.9108 | 26724
43094 | 411.7242 | 26724
43095 | 418.5643 | 26724
43096 | 425.4947 | 26724
43097 | 416.0167 | 26724
43098 | 405.7761 | 26724
43099 | 428.8824 | 26724
43100 | 410.6352 | 26724
43101 | 417.5372 | 26724
43102 | 420.8779 | 26724
43103 | 410.9289 | 26724
43104 | 420.1335 | 26724
43105 | 428.0038 | 26724
43106 | 410.0218 | 26724
43107 | 404.0872 | 26724
43108 | 426.5564 | 26724
43109 | 401.7016 | 26724
43110 | 403.1797 | 26724
43111 | 412.8638 | 26724
43112 | 416.017 | 26724
43113 | 422.0607 | 26724
43114 | 419.138 | 26724
43115 | 413.5666 | 26724
43116 | 420.8343 | 26724
43117 | 435.1609 | 26724
43118 | 414.302 | 26724
43119 | 416.4318 | 26724
43120 | 413.7425 | 26724
43121 | 418.3703 | 26724
43122 | 408.6372 | 26724
43123 | 415.0146 | 26724
43124 | 409.3103 | 26724
43125 | 408.8978 | 26724
43126 | 425.6411 | 26724
43127 | 410.8058 | 26724
43128 | 430.3062 | 26724
43129 | 411.4071 | 26724
43130 | 415.7038 | 26724
43131 | 405.2451 | 26724
43132 | 417.3469 | 26724
43133 | 414.2496 | 26724
43134 | 424.3296 | 26724
43135 | 418.0696 | 26724
43136 | 401.9346 | 26724
43137 | 404.1573 | 26724
43138 | 417.0488 | 26724
43139 | 419.7454 | 26724
43140 | 413.7665 | 26724
43141 | 421.5798 | 26724
43142 | 417.7102 | 26724
43143 | 416.4578 | 26724
43144 | 417.7325 | 26724
43145 | 427.5068 | 26724
43146 | 407.4155 | 26724
43147 | 422.1208 | 26724
43148 | 421.3589 | 26724
43149 | 422.037 | 26724
43150 | 410.0348 | 26724
43151 | 408.3734 | 26724
43152 | 418.1238 | 26724
43153 | 398.6141 | 26724
43154 | 427.3708 | 26724
43155 | 414.3045 | 26724
43156 | 404.7686 | 26724
43157 | 419.6879 | 26724
43158 | 420.8257 | 26724
43159 | 420.0629 | 26724
43160 | 435.3229 | 26724
43161 | 427.338 | 26724
43162 | 411.9867 | 26724
43163 | 415.8617 | 26724
43164 | 415.6289 | 26724
43165 | 410.5678 | 26724
43166 | 417.3287 | 26724
43167 | 426.8191 | 26724
43168 | 425.9062 | 26724
43169 | 414.5317 | 26724
43170 | 416.6237 | 26724
43171 | 421.5445 | 26724
43172 | 410.6397 | 26724
43173 | 418.9626 | 26724
43174 | 412.7352 | 26724
43175 | 412.5109 | 26724
43176 | 429.9372 | 26724
43177 | 420.811 | 26724
43178 | 425.13 | 26724
43179 | 421.0087 | 26724
43180 | 427.5545 | 26724
43181 | 413.9508 | 26724
43182 | 422.1699 | 26724
43183 | 401.916 | 26724
43184 | 403.5091 | 26724
43185 | 416.0854 | 26724
43186 | 423.7384 | 26724
43187 | 409.2676 | 26724
43188 | 416.6921 | 26724
43189 | 427.2071 | 26724
43190 | 409.0734 | 26724
43191 | 427.6631 | 26724
43192 | 421.7547 | 26724
43193 | 423.465 | 26724
43194 | 400.0159 | 26724
43195 | 410.611 | 26724
43196 | 428.391 | 26724
43197 | 414.2197 | 26724
43198 | 414.1535 | 26724
43199 | 408.3843 | 26724
43200 | 421.7255 | 26724
43201 | 418.5997 | 26724
43202 | 419.8404 | 26724
43203 | 428.0891 | 26724
43204 | 418.789 | 26724
43205 | 435.6742 | 26724
43206 | 426.8658 | 26724
43207 | 430.4883 | 26724
43208 | 399.0328 | 26724
43209 | 409.4922 | 26724
43210 | 421.2113 | 26724
43211 | 429.3296 | 26724
43212 | 416.5202 | 26724
43213 | 419.767 | 26724
43214 | 414.5386 | 26724
43215 | 426.6912 | 26724
43216 | 420.0998 | 26724
43217 | 424.2389 | 26724
43218 | 421.7382 | 26724
43219 | 415.3258 | 26724
43220 | 409.8741 | 26724
43221 | 425.5547 | 26724
43222 | 424.4854 | 26724
43223 | 410.2763 | 26724
43224 | 407.3121 | 26724
43225 | 416.3984 | 26724
43226 | 413.7846 | 26724
43227 | 415.7138 | 26724
43228 | 416.6167 | 26724
43229 | 402.3809 | 26724
43230 | 396.2409 | 26724
43231 | 412.8025 | 26724
43232 | 416.8234 | 26724
43233 | 416.6285 | 26724
43234 | 405.3555 | 26724
43235 | 414.6732 | 26724
43236 | 418.0328 | 26724
43237 | 411.5679 | 26724
43238 | 427.2888 | 26724
43239 | 427.2021 | 26724
43240 | 408.8768 | 26724
43241 | 413.6517 | 26724
43242 | 410.1918 | 26724
43243 | 418.3451 | 26724
43244 | 432.6617 | 26724
43245 | 421.3717 | 26724
43246 | 407.7806 | 26724
43247 | 419.9898 | 26724
43248 | 427.1352 | 26724
43249 | 420.6681 | 26724
43250 | 421.3065 | 26724
43251 | 424.8524 | 26724
43252 | 417.2105 | 26724
43253 | 411.8412 | 26724
43254 | 419.2574 | 26724
43255 | 423.1459 | 26724
43256 | 418.0764 | 26724
43257 | 400.8575 | 26724
43258 | 425.949 | 26724
43259 | 417.7771 | 26724
43260 | 412.3998 | 26724
43261 | 414.0788 | 26724
43262 | 416.9701 | 26724
43263 | 426.3501 | 26724
43264 | 421.1053 | 26724
43265 | 419.6503 | 26724
43266 | 415.7108 | 26724
43267 | 414.2092 | 26724
43268 | 411.5864 | 26724
43269 | 410.4237 | 26724
43270 | 421.1968 | 26724
43271 | 419.4595 | 26724
43272 | 427.0451 | 26724
43273 | 423.7564 | 26724
43274 | 420.9047 | 26724
43275 | 393.7705 | 26724
43276 | 418.6863 | 26724
43277 | 405.0952 | 26724
43278 | 414.508 | 26724
43279 | 424.6356 | 26724
43280 | 405.6818 | 26724
43281 | 418.4438 | 26724
43282 | 418.32 | 26724
43283 | 399.4458 | 26724
43284 | 407.7179 | 26724
43285 | 422.5894 | 26724
43286 | 402.5831 | 26724
43287 | 414.9239 | 26724
43288 | 410.1466 | 26724
43289 | 409.1602 | 26724
43290 | 407.5198 | 26724
43291 | 423.0721 | 26724
43292 | 413.9549 | 26724
43293 | 424.4156 | 26724
43294 | 397.2665 | 26724
43295 | 407.359 | 26724
43296 | 417.172 | 26724
43297 | 430.0621 | 26724
43298 | 422.6966 | 26724
43299 | 416.1038 | 26724
43300 | 410.896 | 26724
43301 | 408.1734 | 26724
43302 | 424.0629 | 26724
43303 | 410.7978 | 26724
43304 | 401.8129 | 26724
43305 | 418.1032 | 26724
43306 | 421.8703 | 26724
43307 | 402.2912 | 26724
43308 | 418.0894 | 26724
43309 | 423.6415 | 26724
43310 | 409.5665 | 26724
43311 | 415.5272 | 26724
43312 | 426.6361 | 26724
43313 | 413.266 | 26724
43314 | 408.7546 | 26724
43315 | 406.112 | 26724
43316 | 411.4193 | 26724
43317 | 414.3332 | 26724
43318 | 422.6577 | 26724
43319 | 423.762 | 26724
43320 | 415.4473 | 26724
43321 | 404.273 | 26724
43322 | 408.1932 | 26724
43323 | 416.4318 | 26724
43324 | 422.6228 | 26724
43325 | 409.3374 | 26724
43326 | 406.7656 | 26724
43327 | 409.0323 | 26724
43328 | 409.3152 | 26724
43329 | 431.5935 | 26724
43330 | 424.8223 | 26724
43331 | 411.5779 | 26724
43332 | 415.905 | 26724
43333 | 433.2423 | 26724
43334 | 419.7024 | 26724
43335 | 415.7243 | 26724
43336 | 411.4588 | 26724
43337 | 422.77 | 26724
43338 | 427.8014 | 26724
43339 | 405.5071 | 26724
43340 | 427.3734 | 26724
43341 | 418.1989 | 26724
43342 | 412.5734 | 26724
43343 | 415.2168 | 26724
43344 | 413.249 | 26724
43345 | 411.4601 | 26724
43346 | 423.3519 | 26724
43347 | 408.1279 | 26724
43348 | 402.611 | 26724
43349 | 414.7921 | 26724
43350 | 401.5267 | 26724
43351 | 414.2953 | 26724
43352 | 426.731 | 26724
43353 | 425.277 | 26724
43354 | 416.1867 | 26724
43355 | 428.4931 | 26724
43356 | 405.3864 | 26724
43357 | 417.0579 | 26724
43358 | 423.059 | 26724
43359 | 417.5098 | 26724
43360 | 413.861 | 26724
43361 | 405.9606 | 26724
43362 | 427.1623 | 26724
43363 | 418.8918 | 26724
43364 | 404.1921 | 26724
43365 | 413.6044 | 26724
43366 | 411.7926 | 26724
43367 | 407.5219 | 26724
43368 | 415.0525 | 26724
43369 | 413.2735 | 26724
43370 | 423.4276 | 26724
43371 | 419.1595 | 26724
43372 | 417.4546 | 26724
43373 | 424.334 | 26724
43374 | 408.0678 | 26724
43375 | 415.3334 | 26724
43376 | 413.7835 | 26724
43377 | 409.1417 | 26724
43378 | 416.0861 | 26724
43379 | 409.7741 | 26724
43380 | 417.275 | 26724
43381 | 412.1337 | 26724
43382 | 427.0521 | 26724
43383 | 418.8593 | 26724
43384 | 402.3983 | 26724
43385 | 401.6356 | 26724
43386 | 424.4781 | 26724
43387 | 415.0172 | 26724
43388 | 405.7787 | 26724
43389 | 432.3394 | 26724
43390 | 423.3328 | 26724
43391 | 415.0284 | 26724
43392 | 429.682 | 26724
43393 | 418.8063 | 26724
43394 | 411.929 | 26724
43395 | 414.8142 | 26724
43396 | 413.6631 | 26724
43397 | 410.3945 | 26724
43398 | 415.0738 | 26724
43399 | 415.5137 | 26724
43400 | 421.316 | 26724
43401 | 419.398 | 26724
43402 | 419.9842 | 26724
43403 | 423.4485 | 26724
43404 | 418.9984 | 26724
43405 | 431.3651 | 26724
43406 | 412.8672 | 26724
43407 | 416.0605 | 26724
43408 | 420.3499 | 26724
43409 | 410.2789 | 26724
43410 | 401.0477 | 26724
43411 | 411.947 | 26724
43412 | 407.4945 | 26724
43413 | 418.4192 | 26724
43414 | 413.9418 | 26724
43415 | 414.5574 | 26724
43416 | 407.0367 | 26724
43417 | 414.0048 | 26724
43418 | 422.0263 | 26724
43419 | 420.2136 | 26724
43420 | 404.7979 | 26724
43421 | 426.9249 | 26724
43422 | 413.6855 | 26724
43423 | 428.5431 | 26724
43424 | 408.9726 | 26724
43425 | 414.4545 | 26724
43426 | 415.2383 | 26724
43427 | 413.0598 | 26724
43428 | 428.9455 | 26724
43429 | 417.1782 | 26724
43430 | 430.3369 | 26724
43431 | 414.1774 | 26724
43432 | 421.1262 | 26724
43433 | 426.0912 | 26724
43434 | 417.769 | 26724
43435 | 394.4404 | 26724
43436 | 408.3054 | 26724
43437 | 428.9359 | 26724
43438 | 411.5741 | 26724
43439 | 410.4711 | 26724
43440 | 417.0358 | 26724
43441 | 424.8922 | 26724
43442 | 420.9721 | 26724
43443 | 407.5955 | 26724
43444 | 420.24 | 26724
43445 | 419.5491 | 26724
43446 | 408.7525 | 26724
43447 | 414.2429 | 26724
43448 | 427.5054 | 26724
43449 | 412.0233 | 26724
43450 | 420.1046 | 26724
43451 | 437.1844 | 26724
43452 | 423.2412 | 26724
43453 | 418.8164 | 26724
43454 | 408.6232 | 26724
43455 | 411.2413 | 26724
43456 | 415.7204 | 26724
43457 | 422.4228 | 26724
43458 | 411.8662 | 26724
43459 | 424.4705 | 26724
43460 | 413.4328 | 26724
43461 | 422.4927 | 26724
43462 | 407.7704 | 26724
43463 | 418.4614 | 26724
43464 | 413.7192 | 26724
43465 | 399.5678 | 26724
43466 | 421.2223 | 26724
43467 | 416.8032 | 26724
43468 | 418.6816 | 26724
43469 | 410.8112 | 26724
43470 | 412.8754 | 26724
43471 | 415.4936 | 26724
43472 | 417.8243 | 26724
43473 | 417.3895 | 26724
43474 | 417.6707 | 26724
43475 | 417.5034 | 26724
43476 | 410.3273 | 26724
43477 | 437.2795 | 26724
43478 | 411.848 | 26724
43479 | 429.7148 | 26724
43480 | 413.9986 | 26724
43481 | 422.9302 | 26724
43482 | 406.9492 | 26724
43483 | 426.277 | 26724
43484 | 413.6854 | 26724
43485 | 419.4789 | 26724
43486 | 427.2376 | 26724
43487 | 421.6824 | 26724
43488 | 419.5142 | 26724
43489 | 422.8093 | 26724
43490 | 425.3902 | 26724
43491 | 404.8672 | 26724
43492 | 420.9889 | 26724
43493 | 408.3646 | 26724
43494 | 422.5941 | 26724
43495 | 419.1689 | 26724
43496 | 427.1321 | 26724
43497 | 418.0394 | 26724
43498 | 419.4843 | 26724
43499 | 436.0381 | 26724
43500 | 437.601 | 26724
43501 | 418.5094 | 26724
43502 | 420.0426 | 26724
43503 | 422.7831 | 26724
43504 | 424.4566 | 26724
43505 | 418.5599 | 26724
43506 | 398.627 | 26724
43507 | 407.0467 | 26724
43508 | 409.2717 | 26724
43509 | 410.8697 | 26724
43510 | 407.1753 | 26724
43511 | 402.3133 | 26724
43512 | 424.4356 | 26724
43513 | 418.3956 | 26724
43514 | 416.7808 | 26724
43515 | 419.5253 | 26724
43516 | 422.6025 | 26724
43517 | 427.6591 | 26724
43518 | 418.0411 | 26724
43519 | 420.4045 | 26724
43520 | 423.4241 | 26724
43521 | 415.0078 | 26724
43522 | 403.0458 | 26724
43523 | 413.3121 | 26724
43524 | 411.5474 | 26724
43525 | 416.1647 | 26724
43526 | 411.9586 | 26724
43527 | 414.704 | 26724
43528 | 413.1478 | 26724
43529 | 432.8741 | 26724
43530 | 416.8602 | 26724
43531 | 424.0349 | 26724
43532 | 424.3734 | 26724
43533 | 409.1393 | 26724
43534 | 403.9758 | 26724
43535 | 406.4917 | 26724
43536 | 416.1006 | 26724
43537 | 418.7976 | 26724
43538 | 403.857 | 26724
43539 | 412.461 | 26724
43540 | 412.5737 | 26724
43541 | 421.5229 | 26724
43542 | 410.83 | 26724
43543 | 414.3414 | 26724
43544 | 438.7093 | 26724
43545 | 411.3417 | 26724
43546 | 419.196 | 26724
43547 | 420.9182 | 26724
43548 | 408.0577 | 26724
43549 | 420.5548 | 26724
43550 | 432.6849 | 26724
43551 | 418.5923 | 26724
43552 | 405.4555 | 26724
43553 | 417.9564 | 26724
43554 | 403.7333 | 26724
43555 | 419.9484 | 26724
43556 | 406.3285 | 26724
43557 | 417.8091 | 26724
43558 | 424.1466 | 26724
43559 | 408.6053 | 26724
43560 | 413.6441 | 26724
43561 | 416.2418 | 26724
43562 | 425.4747 | 26724
43563 | 404.5052 | 26724
43564 | 414.02 | 26724
43565 | 410.7863 | 26724
43566 | 425.3383 | 26724
43567 | 407.2081 | 26724
43568 | 422.7173 | 26724
43569 | 418.8546 | 26724
43570 | 421.873 | 26724
43571 | 414.6492 | 26724
43572 | 402.7377 | 26724
43573 | 410.0834 | 26724
43574 | 423.5382 | 26724
43575 | 415.9587 | 26724
43576 | 412.534 | 26724
43577 | 412.6667 | 26724
43578 | 425.8268 | 26724
43579 | 414.5335 | 26724
43580 | 415.7143 | 26724
43581 | 415.7551 | 26724
43582 | 407.2038 | 26724
43583 | 406.0115 | 26724
43584 | 420.7064 | 26724
43585 | 428.392 | 26724
43586 | 419.7747 | 26724
43587 | 410.1473 | 26724
43588 | 430.1417 | 26724
43589 | 420.5105 | 26724
43590 | 398.1969 | 26724
43591 | 407.153 | 26724
43592 | 412.9346 | 26724
43593 | 428.6897 | 26724
43594 | 417.4616 | 26724
43595 | 416.8065 | 26724
43596 | 419.5283 | 26724
43597 | 411.9382 | 26724
43598 | 425.6224 | 26724
43599 | 406.6534 | 26724
43600 | 423.933 | 26724
43601 | 424.1954 | 26724
43602 | 419.2636 | 26724
43603 | 420.1692 | 26724
43604 | 419.0736 | 26724
43605 | 421.0293 | 26724
43606 | 408.9249 | 26724
43607 | 422.1581 | 26724
43608 | 399.5658 | 26724
43609 | 410.5229 | 26724
43610 | 405.4363 | 26724
43611 | 415.4326 | 26724
43612 | 420.7995 | 26724
43613 | 421.2493 | 26724
43614 | 410.3571 | 26724
43615 | 405.083 | 26724
43616 | 403.2296 | 26724
43617 | 428.9914 | 26724
43618 | 417.7543 | 26724
43619 | 430.1793 | 26724
43620 | 420.6667 | 26724
43621 | 412.4704 | 26724
43622 | 412.8814 | 26724
43623 | 424.8833 | 26724
43624 | 424.2311 | 26724
43625 | 419.0635 | 26724
43626 | 428.9993 | 26724
43627 | 405.571 | 26724
43628 | 416.2028 | 26724
43629 | 406.7048 | 26724
43630 | 409.1666 | 26724
43631 | 435.7109 | 26724
43632 | 423.5735 | 26724
43633 | 421.8419 | 26724
43634 | 429.5301 | 26724
43635 | 414.7143 | 26724
43636 | 429.2665 | 26724
43637 | 406.9479 | 26724
43638 | 418.894 | 26724
43639 | 416.2083 | 26724
43640 | 414.7742 | 26724
43641 | 408.5756 | 26724
43642 | 422.5506 | 26724
43643 | 432.9199 | 26724
43644 | 429.931 | 26724
43645 | 420.0953 | 26724
43646 | 414.0931 | 26724
43647 | 402.5292 | 26724
43648 | 413.1469 | 26724
43649 | 419.094 | 26724
43650 | 410.9943 | 26724
43651 | 401.3533 | 26724
43652 | 418.9964 | 26724
43653 | 431.4547 | 26724
43654 | 438.0289 | 26724
43655 | 425.3099 | 26724
43656 | 414.7978 | 26724
43657 | 413.3267 | 26724
43658 | 409.4834 | 26724
43659 | 422.4662 | 26724
43660 | 409.5747 | 26724
43661 | 404.4789 | 26724
43662 | 420.9683 | 26724
43663 | 433.3198 | 26724
43664 | 419.3204 | 26724
43665 | 409.3373 | 26724
43666 | 406.4731 | 26724
43667 | 411.7795 | 26724
43668 | 421.0814 | 26724
43669 | 407.7561 | 26724
43670 | 418.2824 | 26724
43671 | 416.1847 | 26724
43672 | 428.4505 | 26724
43673 | 425.596 | 26724
43674 | 405.6756 | 26724
43675 | 424.115 | 26724
43676 | 414.9883 | 26724
43677 | 417.0734 | 26724
43678 | 419.9075 | 26724
43679 | 417.8727 | 26724
43680 | 418.0186 | 26724
43681 | 412.2863 | 26724
43682 | 414.1183 | 26724
43683 | 412.5239 | 26724
43684 | 417.2621 | 26724
43685 | 414.6537 | 26724
43686 | 428.0676 | 26724
43687 | 422.2769 | 26724
43688 | 417.1075 | 26724
43689 | 416.8799 | 26724
43690 | 425.167 | 26724
43691 | 422.1968 | 26724
43692 | 425.1705 | 26724
43693 | 415.1853 | 26724
43694 | 424.2165 | 26724
43695 | 419.2304 | 26724
43696 | 415.0107 | 26724
43697 | 405.0262 | 26724
43698 | 412.024 | 26724
43699 | 429.0639 | 26724
43700 | 419.0857 | 26724
43701 | 408.7606 | 26724
43702 | 399.4629 | 26724
43703 | 428.9795 | 26724
43704 | 406.2599 | 26724
43705 | 412.6046 | 26724
43706 | 426.4027 | 26724
43707 | 428.4084 | 26724
43708 | 424.1453 | 26724
43709 | 423.3288 | 26724
43710 | 410.6272 | 26724
43711 | 415.8676 | 26724
43712 | 408.6368 | 26724
43713 | 410.2977 | 26724
43714 | 411.5494 | 26724
43715 | 404.2791 | 26724
43716 | 410.234 | 26724
43717 | 418.0133 | 26724
43718 | 409.1267 | 26724
43719 | 418.2813 | 26724
43720 | 409.3649 | 26724
43721 | 404.9011 | 26724
43722 | 431.4527 | 26724
43723 | 416.7929 | 26724
43724 | 412.68 | 26724
43725 | 414.4991 | 26724
43726 | 408.6063 | 26724
43727 | 408.9831 | 26724
43728 | 415.4659 | 26724
43729 | 420.9924 | 26724
43730 | 420.9769 | 26724
43731 | 419.1193 | 26724
43732 | 427.5247 | 26724
43733 | 419.6786 | 26724
43734 | 416.3624 | 26724
43735 | 408.5928 | 26724
43736 | 425.172 | 26724
43737 | 416.6614 | 26724
43738 | 423.6642 | 26724
43739 | 414.0937 | 26724
43740 | 430.6091 | 26724
43741 | 405.5514 | 26724
43742 | 426.4834 | 26724
43743 | 424.6433 | 26724
43744 | 414.6908 | 26724
43745 | 411.0111 | 26724
43746 | 417.4414 | 26724
43747 | 421.3831 | 26724
43748 | 416.7162 | 26724
43749 | 430.604 | 26724
43750 | 409.9388 | 26724
43751 | 410.6551 | 26724
43752 | 413.6508 | 26724
43753 | 423.4717 | 26724
43754 | 416.5419 | 26724
43755 | 410.5539 | 26724
43756 | 414.3455 | 26724
43757 | 415.6526 | 26724
43758 | 416.7787 | 26724
43759 | 424.3448 | 26724
43760 | 412.5055 | 26724
43761 | 411.6321 | 26724
43762 | 421.4583 | 26724
43763 | 426.4144 | 26724
43764 | 401.7111 | 26724
43765 | 405.18 | 26724
43766 | 424.2672 | 26724
43767 | 393.7574 | 26724
43768 | 409.9763 | 26724
43769 | 412.1989 | 26724
43770 | 408.7884 | 26724
43771 | 426.5379 | 26724
43772 | 419.4271 | 26724
43773 | 417.7931 | 26724
43774 | 417.3798 | 26724
43775 | 410.5913 | 26724
43776 | 422.7544 | 26724
43777 | 427.9211 | 26724
43778 | 407.6906 | 26724
43779 | 430.3917 | 26724
43780 | 409.5045 | 26724
43781 | 417.9956 | 26724
43782 | 426.5054 | 26724
43783 | 418.5866 | 26724
43784 | 416.4661 | 26724
43785 | 414.1666 | 26724
43786 | 412.7991 | 26724
43787 | 417.3889 | 26724
43788 | 425.1077 | 26724
43789 | 426.7107 | 26724
43790 | 419.2615 | 26724
43791 | 421.3494 | 26724
43792 | 412.4228 | 26724
43793 | 415.959 | 26724
43794 | 404.8051 | 26724
43795 | 413.6778 | 26724
43796 | 424.4495 | 26724
43797 | 424.3312 | 26724
43798 | 431.0924 | 26724
43799 | 415.6301 | 26724
43800 | 414.5374 | 26724
43801 | 425.1607 | 26724
43802 | 404.6236 | 26724
43803 | 410.5875 | 26724
43804 | 417.275 | 26724
43805 | 401.243 | 26724
43806 | 410.874 | 26724
43807 | 407.8817 | 26724
43808 | 407.4635 | 26724
43809 | 424.8718 | 26724
43810 | 424.2563 | 26724
43811 | 408.6488 | 26724
43812 | 419.3493 | 26724
43813 | 427.937 | 26724
43814 | 418.2843 | 26724
43815 | 413.3968 | 26724
43816 | 402.9254 | 26724
43817 | 403.6686 | 26724
43818 | 421.5958 | 26724
43819 | 417.7892 | 26724
43820 | 417.158 | 26724
43821 | 416.4169 | 26724
43822 | 419.4329 | 26724
43823 | 423.6531 | 26724
43824 | 405.4241 | 26724
43825 | 408.0664 | 26724
43826 | 415.9304 | 26724
43827 | 427.2274 | 26724
43828 | 428.6637 | 26724
43829 | 411.6927 | 26724
43830 | 426.7512 | 26724
43831 | 413.6164 | 26724
43832 | 413.1319 | 26724
43833 | 419.341 | 26724
43834 | 410.588 | 26724
43835 | 413.4218 | 26724
43836 | 426.4742 | 26724
43837 | 402.426 | 26724
43838 | 405.9694 | 26724
43839 | 424.93 | 26724
43840 | 408.9312 | 26724
43841 | 423.6976 | 26724
43842 | 406.6824 | 26724
43843 | 403.5436 | 26724
43844 | 407.6712 | 26724
43845 | 424.8289 | 26724
43846 | 416.0393 | 26724
43847 | 429.1081 | 26724
43848 | 413.9069 | 26724
43849 | 422.7069 | 26724
43850 | 418.9494 | 26724
43851 | 410.5062 | 26724
43852 | 419.3746 | 26724
43853 | 420.3054 | 26724
43854 | 409.9184 | 26724
43855 | 418.5576 | 26724
43856 | 417.4324 | 26724
43857 | 406.1121 | 26724
43858 | 412.8679 | 26724
43859 | 434.1746 | 26724
43860 | 408.4784 | 26724
43861 | 411.2164 | 26724
43862 | 415.913 | 26724
43863 | 420.4176 | 26724
43864 | 419.6442 | 26724
43865 | 411.1393 | 26724
43866 | 415.3145 | 26724
43867 | 415.2882 | 26724
43868 | 415.5681 | 26724
43869 | 419.1767 | 26724
43870 | 409.149 | 26724
43871 | 413.9937 | 26724
43872 | 407.5868 | 26724
43873 | 422.9991 | 26724
43874 | 426.6158 | 26724
43875 | 424.8623 | 26724
43876 | 422.771 | 26724
43877 | 423.0805 | 26724
43878 | 420.7601 | 26724
43879 | 417.8775 | 26724
43880 | 417.0269 | 26724
43881 | 410.6895 | 26724
43882 | 412.7755 | 26724
43883 | 427.9663 | 26724
43884 | 423.4857 | 26724
43885 | 407.6962 | 26724
43886 | 410.9108 | 26724
43887 | 425.0547 | 26724
43888 | 412.3012 | 26724
43889 | 403.7253 | 26724
43890 | 412.8028 | 26724
43891 | 410.9682 | 26724
43892 | 401.145 | 26724
43893 | 416.0171 | 26724
43894 | 416.9972 | 26724
43895 | 418.907 | 26724
43896 | 424.424 | 26724
43897 | 429.9776 | 26724
43898 | 409.0967 | 26724
43899 | 410.5844 | 26724
43900 | 426.7848 | 26724
43901 | 405.7955 | 26724
43902 | 408.8612 | 26724
43903 | 416.2545 | 26724
43904 | 408.286 | 26724
43905 | 399.6691 | 26724
43906 | 419.151 | 26724
43907 | 425.5049 | 26724
43908 | 424.8147 | 26724
43909 | 409.891 | 26724
43910 | 423.566 | 26724
43911 | 412.8124 | 26724
43912 | 429.8831 | 26724
43913 | 408.3395 | 26724
43914 | 429.3378 | 26724
43915 | 417.4685 | 26724
43916 | 432.3961 | 26724
43917 | 406.5132 | 26724
43918 | 415.2275 | 26724
43919 | 423.2658 | 26724
43920 | 427.3415 | 26724
43921 | 418.9673 | 26724
43922 | 422.1598 | 26724
43923 | 433.6495 | 26724
43924 | 406.3861 | 26724
43925 | 420.2233 | 26724
43926 | 415.4903 | 26724
43927 | 409.6014 | 26724
43928 | 423.6743 | 26724
43929 | 416.7677 | 26724
43930 | 431.1069 | 26724
43931 | 420.2307 | 26724
43932 | 413.3109 | 26724
43933 | 415.7408 | 26724
43934 | 411.5176 | 26724
43935 | 418.0204 | 26724
43936 | 407.1614 | 26724
43937 | 410.5131 | 26724
43938 | 429.536 | 26724
43939 | 419.18 | 26724
43940 | 429.7758 | 26724
43941 | 411.8771 | 26724
43942 | 408.8472 | 26724
43943 | 411.8427 | 26724
43944 | 417.3487 | 26724
43945 | 408.5063 | 26724
43946 | 423.7193 | 26724
43947 | 419.0084 | 26724
43948 | 417.4818 | 26724
43949 | 423.1535 | 26724
43950 | 414.5211 | 26724
43951 | 422.0353 | 26724
43952 | 427.559 | 26724
43953 | 427.5022 | 26724
43954 | 415.996 | 26724
43955 | 425.6659 | 26724
43956 | 412.6907 | 26724
43957 | 418.6857 | 26724
43958 | 410.4111 | 26724
43959 | 427.9475 | 26724
43960 | 420.1025 | 26724
43961 | 414.0776 | 26724
43962 | 402.0025 | 26724
43963 | 413.536 | 26724
43964 | 417.9975 | 26724
43965 | 401.84 | 26724
43966 | 419.2889 | 26724
43967 | 426.2214 | 26724
43968 | 416.33 | 26724
43969 | 420.3941 | 26724
43970 | 412.2279 | 26724
43971 | 424.1152 | 26724
43972 | 411.674 | 26724
43973 | 420.3347 | 26724
43974 | 411.5015 | 26724
43975 | 400.57 | 26724
43976 | 428.2147 | 26724
43977 | 397.8295 | 26724
43978 | 400.8343 | 26724
43979 | 428.7006 | 26724
43980 | 410.0484 | 26724
43981 | 414.4821 | 26724
43982 | 426.3044 | 26724
43983 | 428.1106 | 26724
43984 | 420.9161 | 26724
43985 | 416.9041 | 26724
43986 | 419.604 | 26724
43987 | 422.5077 | 26724
43988 | 407.6562 | 26724
43989 | 425.2093 | 26724
43990 | 413.6671 | 26724
43991 | 411.6884 | 26724
43992 | 423.9721 | 26724
43993 | 424.3004 | 26724
43994 | 420.7304 | 26724
43995 | 420.8531 | 26724
43996 | 409.5002 | 26724
43997 | 413.3298 | 26724
43998 | 411.6813 | 26724
43999 | 428.1049 | 26724
44000 | 408.3635 | 26724
44001 | 426.6516 | 26724
44002 | 419.9864 | 26724
44003 | 415.9244 | 26724
44004 | 402.6789 | 26724
44005 | 421.7476 | 26724
44006 | 413.1403 | 26724
44007 | 402.5362 | 26724
44008 | 422.8544 | 26724
44009 | 414.0246 | 26724
44010 | 422.0522 | 26724
44011 | 421.967 | 26724
44012 | 407.9625 | 26724
44013 | 416.9304 | 26724
44014 | 413.4672 | 26724
44015 | 419.8838 | 26724
44016 | 427.1471 | 26724
44017 | 420.0732 | 26724
44018 | 417.8616 | 26724
44019 | 414.8596 | 26724
44020 | 416.9167 | 26724
44021 | 402.7134 | 26724
44022 | 395.4262 | 26724
44023 | 421.6758 | 26724
44024 | 424.0671 | 26724
44025 | 411.6261 | 26724
44026 | 420.6925 | 26724
44027 | 430.2243 | 26724
44028 | 416.7756 | 26724
44029 | 417.388 | 26724
44030 | 414.9866 | 26724
44031 | 398.0949 | 26724
44032 | 419.9163 | 26724
44033 | 421.7677 | 26724
44034 | 424.6117 | 26724
44035 | 418.3121 | 26724
44036 | 409.5402 | 26724
44037 | 413.6287 | 26724
44038 | 403.3978 | 26724
44039 | 420.466 | 26724
44040 | 432.4961 | 26724
44041 | 421.9264 | 26724
44042 | 424.7878 | 26724
44043 | 406.5444 | 26724
44044 | 420.4115 | 26724
44045 | 418.0619 | 26724
44046 | 406.0075 | 26724
44047 | 410.7285 | 26724
44048 | 419.2227 | 26724
44049 | 427.3962 | 26724
44050 | 429.587 | 26724
44051 | 412.0344 | 26724
44052 | 411.7223 | 26724
44053 | 427.3442 | 26724
44054 | 423.0035 | 26724
44055 | 407.0849 | 26724
44056 | 409.2267 | 26724
44057 | 415.9514 | 26724
44058 | 426.1493 | 26724
44059 | 428.9577 | 26724
44060 | 427.4771 | 26724
44061 | 422.958 | 26724
44062 | 417.8324 | 26724
44063 | 411.487 | 26724
44064 | 423.9024 | 26724
44065 | 402.5472 | 26724
44066 | 427.1054 | 26724
44067 | 420.4494 | 26724
44068 | 417.0213 | 26724
44069 | 409.1463 | 26724
44070 | 421.3075 | 26724
44071 | 423.0665 | 26724
44072 | 416.6824 | 26724
44073 | 407.6677 | 26724
44074 | 424.3258 | 26724
44075 | 424.9768 | 26724
44076 | 414.3544 | 26724
44077 | 420.7493 | 26724
44078 | 406.7625 | 26724
44079 | 426.7883 | 26724
44080 | 412.3739 | 26724
44081 | 426.6996 | 26724
44082 | 422.1646 | 26724
44083 | 426.9052 | 26724
44084 | 412.94 | 26724
44085 | 414.39 | 26724
44086 | 420.9385 | 26724
44087 | 414.8117 | 26724
44088 | 415.2843 | 26724
44089 | 413.4841 | 26724
44090 | 415.7493 | 26724
44091 | 414.8147 | 26724
44092 | 411.3904 | 26724
44093 | 430.1107 | 26724
44094 | 408.4231 | 26724
44095 | 429.5732 | 26724
44096 | 411.6707 | 26724
44097 | 420.6913 | 26724
44098 | 415.6317 | 26724
44099 | 416.6788 | 26724
44100 | 430.8473 | 26724
44101 | 426.5624 | 26724
44102 | 412.8535 | 26724
44103 | 425.9549 | 26724
44104 | 408.9979 | 26724
44105 | 411.3426 | 26724
44106 | 421.3202 | 26724
44107 | 414.5937 | 26724
44108 | 409.0659 | 26724
44109 | 420.1967 | 26724
44110 | 405.7634 | 26724
44111 | 408.8172 | 26724
44112 | 413.4593 | 26724
44113 | 427.9388 | 26724
44114 | 411.4266 | 26724
44115 | 414.3928 | 26724
44116 | 420.9293 | 26724
44117 | 415.5837 | 26724
44118 | 423.5775 | 26724
44119 | 430.3665 | 26724
44120 | 409.4521 | 26724
44121 | 410.6613 | 26724
44122 | 412.3349 | 26724
44123 | 427.427 | 26724
44124 | 406.4134 | 26724
44125 | 397.0119 | 26724
44126 | 430.154 | 26724
44127 | 405.7409 | 26724
44128 | 419.9388 | 26724
44129 | 413.7614 | 26724
44130 | 415.8495 | 26724
44131 | 411.5335 | 26724
44132 | 421.8952 | 26724
44133 | 412.7479 | 26724
44134 | 404.9455 | 26724
44135 | 411.6222 | 26724
44136 | 416.4994 | 26724
44137 | 414.0353 | 26724
44138 | 408.9596 | 26724
44139 | 408.2089 | 26724
44140 | 418.9059 | 26724
44141 | 412.6166 | 26724
44142 | 420.9246 | 26724
44143 | 411.5962 | 26724
44144 | 422.2534 | 26724
44145 | 404.851 | 26724
44146 | 415.6549 | 26724
44147 | 415.24 | 26724
44148 | 414.9892 | 26724
44149 | 407.9833 | 26724
44150 | 409.4591 | 26724
44151 | 415.3204 | 26724
44152 | 406.6296 | 26724
44153 | 411.1008 | 26724
44154 | 420.9379 | 26724
44155 | 415.3747 | 26724
44156 | 414.4954 | 26724
44157 | 417.794 | 26724
44158 | 431.6822 | 26724
44159 | 419.4225 | 26724
44160 | 420.6998 | 26724
44161 | 409.8958 | 26724
44162 | 411.4329 | 26724
44163 | 419.4281 | 26724
44164 | 417.8358 | 26724
44165 | 428.0752 | 26724
44166 | 406.0739 | 26724
44167 | 399.7202 | 26724
44168 | 416.9267 | 26724
44169 | 417.2966 | 26724
44170 | 419.5908 | 26724
44171 | 418.7685 | 26724
44172 | 418.3532 | 26724
44173 | 417.801 | 26724
44174 | 416.9622 | 26724
44175 | 407.7056 | 26724
44176 | 428.2759 | 26724
44177 | 424.5322 | 26724
44178 | 410.2172 | 26724
44179 | 418.2239 | 26724
44180 | 413.5566 | 26724
44181 | 430.0039 | 26724
44182 | 420.0522 | 26724
44183 | 420.392 | 26724
44184 | 423.2933 | 26724
44185 | 417.551 | 26724
44186 | 416.4289 | 26724
44187 | 414.8476 | 26724
44188 | 402.3725 | 26724
44189 | 409.6253 | 26724
44190 | 407.519 | 26724
44191 | 435.2056 | 26724
44192 | 401.9323 | 26724
44193 | 410.3295 | 26724
44194 | 411.1882 | 26724
44195 | 419.1528 | 26724
44196 | 420.6296 | 26724
44197 | 424.5937 | 26724
44198 | 423.1233 | 26724
44199 | 406.6103 | 26724
44200 | 406.1797 | 26724
44201 | 418.8096 | 26724
44202 | 405.4998 | 26724
44203 | 418.7411 | 26724
44204 | 418.4769 | 26724
44205 | 416.1455 | 26724
44206 | 427.4531 | 26724
44207 | 426.5678 | 26724
44208 | 421.2241 | 26724
44209 | 427.0854 | 26724
44210 | 411.4857 | 26724
44211 | 427.1445 | 26724
44212 | 415.121 | 26724
44213 | 409.7776 | 26724
44214 | 424.5565 | 26724
44215 | 417.7057 | 26724
44216 | 403.4972 | 26724
44217 | 398.8656 | 26724
44218 | 421.6053 | 26724
44219 | 407.4477 | 26724
44220 | 415.5601 | 26724
44221 | 427.5079 | 26724
44222 | 427.6149 | 26724
44223 | 427.8303 | 26724
44224 | 411.6834 | 26724
44225 | 434.7356 | 26724
44226 | 414.9889 | 26724
44227 | 409.2767 | 26724
44228 | 424.4842 | 26724
44229 | 415.5885 | 26724
44230 | 429.5781 | 26724
44231 | 419.8825 | 26724
44232 | 434.9183 | 26724
44233 | 415.6179 | 26724
44234 | 403.7669 | 26724
44235 | 419.9909 | 26724
44236 | 425.6868 | 26724
44237 | 405.9929 | 26724
44238 | 400.3159 | 26724
44239 | 408.0056 | 26724
44240 | 410.0125 | 26724
44241 | 416.4605 | 26724
44242 | 425.4945 | 26724
44243 | 415.5084 | 26724
44244 | 403.7242 | 26724
44245 | 426.5251 | 26724
44246 | 418.3992 | 26724
44247 | 419.4111 | 26724
44248 | 401.3748 | 26724
44249 | 419.9215 | 26724
44250 | 402.329 | 26724
44251 | 404.7554 | 26724
44252 | 414.5596 | 26724
44253 | 434.9086 | 26724
44254 | 408.3426 | 26724
44255 | 424.0583 | 26724
44256 | 419.3142 | 26724
44257 | 407.2438 | 26724
44258 | 411.141 | 26724
44259 | 412.2355 | 26724
44260 | 418.7456 | 26724
44261 | 431.4468 | 26724
44262 | 421.4234 | 26724
44263 | 410.0364 | 26724
44264 | 416.1516 | 26724
44265 | 417.3865 | 26724
44266 | 422.0212 | 26724
44267 | 418.531 | 26724
44268 | 414.8483 | 26724
44269 | 424.6535 | 26724
44270 | 410.0579 | 26724
44271 | 420.9992 | 26724
44272 | 438.8804 | 26724
44273 | 426.2497 | 26724
44274 | 416.0217 | 26724
44275 | 419.0529 | 26724
44276 | 409.0669 | 26724
44277 | 417.4569 | 26724
44278 | 412.8367 | 26724
44279 | 417.4057 | 26724
44280 | 411.5505 | 26724
44281 | 418.9249 | 26724
44282 | 407.1919 | 26724
44283 | 404.8972 | 26724
44284 | 408.206 | 26724
44285 | 402.7852 | 26724
44286 | 412.9889 | 26724
44287 | 423.4542 | 26724
44288 | 415.9133 | 26724
44289 | 416.838 | 26724
44290 | 417.6212 | 26724
44291 | 413.7537 | 26724
44292 | 425.7226 | 26724
44293 | 413.1868 | 26724
44294 | 404.1704 | 26724
44295 | 407.259 | 26724
44296 | 415.2228 | 26724
44297 | 418.7539 | 26724
44298 | 415.1803 | 26724
44299 | 421.6236 | 26724
44300 | 425.7215 | 26724
44301 | 416.97 | 26724
44302 | 405.4588 | 26724
44303 | 418.1364 | 26724
44304 | 424.6337 | 26724
44305 | 420.5077 | 26724
44306 | 416.8976 | 26724
44307 | 398.3371 | 26724
44308 | 421.1401 | 26724
44309 | 427.1541 | 26724
44310 | 417.7222 | 26724
44311 | 404.0996 | 26724
44312 | 410.5706 | 26724
44313 | 421.0296 | 26724
44314 | 418.7759 | 26724
44315 | 421.6272 | 26724
44316 | 411.9346 | 26724
44317 | 413.5485 | 26724
44318 | 402.4461 | 26724
44319 | 398.5319 | 26724
44320 | 427.1671 | 26724
44321 | 412.5314 | 26724
44322 | 415.2079 | 26724
44323 | 410.0882 | 26724
44324 | 415.3574 | 26724
44325 | 422.7866 | 26724
44326 | 399.4501 | 26724
44327 | 429.5278 | 26724
44328 | 415.4843 | 26724
44329 | 410.7565 | 26724
44330 | 430.459 | 26724
44331 | 412.5231 | 26724
44332 | 423.8666 | 26724
44333 | 415.4411 | 26724
44334 | 410.0137 | 26724
44335 | 424.9164 | 26724
44336 | 421.0408 | 26724
44337 | 417.5624 | 26724
44338 | 407.3156 | 26724
44339 | 423.1923 | 26724
44340 | 406.2064 | 26724
44341 | 422.0095 | 26724
44342 | 434.5792 | 26724
44343 | 431.8323 | 26724
44344 | 412.8479 | 26724
44345 | 417.0758 | 26724
44346 | 432.4406 | 26724
44347 | 408.0183 | 26724
44348 | 422.3334 | 26724
44349 | 424.4367 | 26724
44350 | 415.1647 | 26724
44351 | 426.7909 | 26724
44352 | 398.896 | 26724
44353 | 422.3546 | 26724
44354 | 409.3935 | 26724
44355 | 418.7119 | 26724
44356 | 418.189 | 26724
44357 | 419.7793 | 26724
44358 | 400.0338 | 26724
44359 | 417.0697 | 26724
44360 | 411.1542 | 26724
44361 | 416.0798 | 26724
44362 | 418.5076 | 26724
44363 | 412.3973 | 26724
44364 | 428.1966 | 26724
44365 | 414.9473 | 26724
44366 | 410.0421 | 26724
44367 | 424.4945 | 26724
44368 | 415.0809 | 26724
44369 | 419.078 | 26724
44370 | 424.2916 | 26724
44371 | 418.9205 | 26724
44372 | 399.9366 | 26724
44373 | 423.4585 | 26724
44374 | 421.0005 | 26724
44375 | 421.2768 | 26724
44376 | 423.7938 | 26724
44377 | 408.6011 | 26724
44378 | 423.119 | 26724
44379 | 423.903 | 26724
44380 | 425.932 | 26724
44381 | 412.9491 | 26724
44382 | 434.6073 | 26724
44383 | 414.8353 | 26724
44384 | 414.2055 | 26724
44385 | 413.7578 | 26724
44386 | 420.305 | 26724
44387 | 407.8822 | 26724
44388 | 432.8297 | 26724
44389 | 419.1525 | 26724
44390 | 429.2513 | 26724
44391 | 418.5441 | 26724
44392 | 406.9607 | 26724
44393 | 415.6269 | 26724
44394 | 399.3588 | 26724
44395 | 411.3581 | 26724
44396 | 422.0797 | 26724
44397 | 418.1071 | 26724
44398 | 418.52 | 26724
44399 | 420.1223 | 26724
44400 | 419.5455 | 26724
44401 | 424.9213 | 26724
44402 | 408.3382 | 26724
44403 | 424.7484 | 26724
44404 | 433.0657 | 26724
44405 | 409.2661 | 26724
44406 | 408.184 | 26724
44407 | 415.5815 | 26724
44408 | 421.0357 | 26724
44409 | 409.9292 | 26724
44410 | 407.6118 | 26724
44411 | 416.4506 | 26724
44412 | 415.1939 | 26724
44413 | 423.0484 | 26724
44414 | 415.9442 | 26724
44415 | 404.7719 | 26724
44416 | 428.3961 | 26724
44417 | 416.5478 | 26724
44418 | 416.549 | 26724
44419 | 425.9484 | 26724
44420 | 405.6927 | 26724
44421 | 410.839 | 26724
44422 | 418.1002 | 26724
44423 | 408.4668 | 26724
44424 | 419.7086 | 26724
44425 | 423.1092 | 26724
44426 | 419.8755 | 26724
44427 | 436.458 | 26724
44428 | 410.9055 | 26724
44429 | 417.0162 | 26724
44430 | 410.0561 | 26724
44431 | 422.9963 | 26724
44432 | 415.349 | 26724
44433 | 402.5478 | 26724
44434 | 417.9238 | 26724
44435 | 415.8519 | 26724
44436 | 406.5226 | 26724
44437 | 412.915 | 26724
44438 | 407.0837 | 26724
44439 | 421.4308 | 26724
44440 | 422.7469 | 26724
44441 | 413.479 | 26724
44442 | 430.9635 | 26724
44443 | 417.5567 | 26724
44444 | 409.8962 | 26724
44445 | 412.3613 | 26724
44446 | 419.7744 | 26724
44447 | 423.6114 | 26724
44448 | 407.5823 | 26724
44449 | 413.0922 | 26724
44450 | 402.3442 | 26724
44451 | 422.6959 | 26724
44452 | 401.9363 | 26724
44453 | 418.0097 | 26724
44454 | 413.1921 | 26724
44455 | 422.1506 | 26724
44456 | 423.6059 | 26724
44457 | 406.8189 | 26724
44458 | 417.9188 | 26724
44459 | 411.2128 | 26724
44460 | 415.8149 | 26724
44461 | 399.8446 | 26724
44462 | 419.5859 | 26724
44463 | 403.6341 | 26724
44464 | 412.8918 | 26724
44465 | 421.1234 | 26724
44466 | 416.0409 | 26724
44467 | 412.877 | 26724
44468 | 426.9053 | 26724
44469 | 407.2102 | 26724
44470 | 418.7225 | 26724
44471 | 429.7195 | 26724
44472 | 421.514 | 26724
44473 | 416.0308 | 26724
44474 | 408.7882 | 26724
44475 | 418.0662 | 26724
44476 | 397.5171 | 26724
44477 | 417.3752 | 26724
44478 | 411.3935 | 26724
44479 | 415.06 | 26724
44480 | 408.6297 | 26724
44481 | 416.6032 | 26724
44482 | 414.7597 | 26724
44483 | 420.4087 | 26724
44484 | 413.1946 | 26724
44485 | 423.6193 | 26724
44486 | 416.5632 | 26724
44487 | 419.8776 | 26724
44488 | 412.0212 | 26724
44489 | 419.5887 | 26724
44490 | 426.0816 | 26724
44491 | 410.3526 | 26724
44492 | 410.4774 | 26724
44493 | 419.4636 | 26724
44494 | 408.7805 | 26724
44495 | 430.7046 | 26724
44496 | 409.913 | 26724
44497 | 409.3588 | 26724
44498 | 430.6926 | 26724
44499 | 433.2088 | 26724
44500 | 423.24 | 26724
44501 | 422.6859 | 26724
44502 | 400.8804 | 26724
44503 | 405.1497 | 26724
44504 | 430.4935 | 26724
44505 | 425.014 | 26724
44506 | 429.1882 | 26724
44507 | 416.6015 | 26724
44508 | 423.7091 | 26724
44509 | 419.5677 | 26724
44510 | 410.4233 | 26724
44511 | 411.1965 | 26724
44512 | 419.0137 | 26724
44513 | 405.1556 | 26724
44514 | 425.4942 | 26724
44515 | 426.3053 | 26724
44516 | 405.7769 | 26724
44517 | 416.6389 | 26724
44518 | 395.0474 | 26724
44519 | 415.7115 | 26724
44520 | 412.3968 | 26724
44521 | 401.373 | 26724
44522 | 417.5059 | 26724
44523 | 419.3538 | 26724
44524 | 416.131 | 26724
44525 | 409.686 | 26724
44526 | 408.7854 | 26724
44527 | 408.4798 | 26724
44528 | 426.2661 | 26724
44529 | 430.5179 | 26724
44530 | 414.0507 | 26724
44531 | 411.332 | 26724
44532 | 425.7921 | 26724
44533 | 437.1999 | 26724
44534 | 410.5815 | 26724
44535 | 420.9957 | 26724
44536 | 412.0986 | 26724
44537 | 422.7431 | 26724
44538 | 426.8654 | 26724
44539 | 411.2219 | 26724
44540 | 416.8976 | 26724
44541 | 407.8327 | 26724
44542 | 406.8294 | 26724
44543 | 428.5205 | 26724
44544 | 414.5006 | 26724
44545 | 411.1923 | 26724
44546 | 416.9245 | 26724
44547 | 417.4977 | 26724
44548 | 426.2317 | 26724
44549 | 401.7711 | 26724
44550 | 414.129 | 26724
44551 | 410.7896 | 26724
44552 | 415.821 | 26724
44553 | 398.0841 | 26724
44554 | 415.4015 | 26724
44555 | 412.393 | 26724
44556 | 417.2188 | 26724
44557 | 418.3234 | 26724
44558 | 404.6512 | 26724
44559 | 424.8896 | 26724
44560 | 398.478 | 26724
44561 | 418.5007 | 26724
44562 | 420.8017 | 26724
44563 | 422.9262 | 26724
44564 | 405.8403 | 26724
44565 | 419.23 | 26724
44566 | 417.0354 | 26724
44567 | 402.8892 | 26724
44568 | 401.3175 | 26724
44569 | 409.1102 | 26724
44570 | 423.12 | 26724
44571 | 410.676 | 26724
44572 | 425.1238 | 26724
44573 | 409.8301 | 26724
44574 | 420.9078 | 26724
44575 | 422.0902 | 26724
44576 | 400.5238 | 26724
44577 | 424.3251 | 26724
44578 | 414.6227 | 26724
44579 | 416.319 | 26724
44580 | 409.1547 | 26724
44581 | 417.8761 | 26724
44582 | 421.6759 | 26724
44583 | 411.3256 | 26724
44584 | 411.7547 | 26724
44585 | 414.8175 | 26724
44586 | 424.0232 | 26724
44587 | 431.025 | 26724
44588 | 407.8023 | 26724
44589 | 418.1405 | 26724
44590 | 423.8558 | 26724
44591 | 419.6184 | 26724
44592 | 416.8506 | 26724
44593 | 420.3562 | 26724
44594 | 419.5035 | 26724
44595 | 406.499 | 26724
44596 | 406.1809 | 26724
44597 | 409.3837 | 26724
44598 | 422.8516 | 26724
44599 | 414.9593 | 26724
44600 | 409.0174 | 26724
44601 | 426.2225 | 26724
44602 | 423.7268 | 26724
44603 | 413.9992 | 26724
44604 | 421.5146 | 26724
44605 | 412.3021 | 26724
44606 | 425.871 | 26724
44607 | 404.1987 | 26724
44608 | 415.1949 | 26724
44609 | 413.0782 | 26724
44610 | 407.143 | 26724
44611 | 414.0876 | 26724
44612 | 418.5499 | 26724
44613 | 431.024 | 26724
44614 | 424.313 | 26724
44615 | 411.2583 | 26724
44616 | 408.6511 | 26724
44617 | 420.9672 | 26724
44618 | 412.8068 | 26724
44619 | 407.0041 | 26724
44620 | 417.1724 | 26724
44621 | 413.6554 | 26724
44622 | 418.7085 | 26724
44623 | 423.5686 | 26724
44624 | 417.8494 | 26724
44625 | 424.8008 | 26724
44626 | 409.9376 | 26724
44627 | 433.6396 | 26724
44628 | 430.4185 | 26724
44629 | 416.7161 | 26724
44630 | 416.3965 | 26724
44631 | 428.064 | 26724
44632 | 414.7591 | 26724
44633 | 420.1904 | 26724
44634 | 426.4938 | 26724
44635 | 410.9597 | 26724
44636 | 408.9265 | 26724
44637 | 419.2467 | 26724
44638 | 433.5591 | 26724
44639 | 416.9831 | 26724
44640 | 434.1739 | 26724
44641 | 422.9306 | 26724
44642 | 411.9719 | 26724
44643 | 418.7143 | 26724
44644 | 423.5948 | 26724
44645 | 409.891 | 26724
44646 | 407.4402 | 26724
44647 | 434.2255 | 26724
44648 | 407.1311 | 26724
44649 | 412.3273 | 26724
44650 | 413.9355 | 26724
44651 | 418.3385 | 26724
44652 | 408.5679 | 26724
44653 | 403.0124 | 26724
44654 | 400.1413 | 26724
44655 | 418.351 | 26724
44656 | 420.4196 | 26724
44657 | 409.7401 | 26724
44658 | 412.3545 | 26724
44659 | 418.1949 | 26724
44660 | 423.4904 | 26724
44661 | 412.5828 | 26724
44662 | 417.6528 | 26724
44663 | 417.5983 | 26724
44664 | 423.8297 | 26724
44665 | 424.783 | 26724
44666 | 414.0375 | 26724
44667 | 411.5486 | 26724
44668 | 419.1878 | 26724
44669 | 409.7781 | 26724
44670 | 418.6768 | 26724
44671 | 407.2985 | 26724
44672 | 424.8819 | 26724
44673 | 410.068 | 26724
44674 | 412.8859 | 26724
44675 | 419.051 | 26724
44676 | 418.0273 | 26724
44677 | 408.0391 | 26724
44678 | 414.4317 | 26724
44679 | 399.6445 | 26724
44680 | 426.5387 | 26724
44681 | 416.589 | 26724
44682 | 417.0986 | 26724
44683 | 415.2289 | 26724
44684 | 424.5032 | 26724
44685 | 417.3555 | 26724
44686 | 414.5259 | 26724
44687 | 423.3142 | 26724
44688 | 404.5358 | 26724
44689 | 402.8233 | 26724
44690 | 431.8217 | 26724
44691 | 420.6297 | 26724
44692 | 426.6742 | 26724
44693 | 413.7402 | 26724
44694 | 416.1136 | 26724
44695 | 417.4173 | 26724
44696 | 423.3979 | 26724
44697 | 404.2962 | 26724
44698 | 398.1339 | 26724
44699 | 429.1965 | 26724
44700 | 407.171 | 26724
44701 | 420.0194 | 26724
44702 | 424.9988 | 26724
44703 | 424.5823 | 26724
44704 | 414.1364 | 26724
44705 | 410.008 | 26724
44706 | 417.8558 | 26724
44707 | 415.825 | 26724
44708 | 419.4963 | 26724
44709 | 427.5132 | 26724
44710 | 412.4542 | 26724
44711 | 396.5298 | 26724
44712 | 414.1047 | 26724
44713 | 416.8647 | 26724
44714 | 423.7394 | 26724
44715 | 418.4294 | 26724
44716 | 422.2009 | 26724
44717 | 415.084 | 26724
44718 | 398.1667 | 26724
44719 | 416.8459 | 26724
44720 | 394.396 | 26724
44721 | 409.4994 | 26724
44722 | 427.4364 | 26724
44723 | 411.8712 | 26724
44724 | 420.4118 | 26724
44725 | 417.3452 | 26724
44726 | 415.0694 | 26724
44727 | 424.258 | 26724
44728 | 423.6061 | 26724
44729 | 424.1009 | 26724
44730 | 401.7572 | 26724
44731 | 416.6663 | 26724
44732 | 418.8936 | 26724
44733 | 419.0859 | 26724
44734 | 416.5751 | 26724
44735 | 411.0017 | 26724
44736 | 421.6567 | 26724
44737 | 417.5323 | 26724
44738 | 413.3474 | 26724
44739 | 410.4385 | 26724
44740 | 408.2987 | 26724
44741 | 425.7407 | 26724
44742 | 409.6568 | 26724
44743 | 402.5385 | 26724
44744 | 415.16 | 26724
44745 | 414.7846 | 26724
44746 | 408.07 | 26724
44747 | 430.0833 | 26724
44748 | 411.3868 | 26724
44749 | 415.4516 | 26724
44750 | 424.9927 | 26724
44751 | 415.6567 | 26724
44752 | 407.9613 | 26724
44753 | 410.0015 | 26724
44754 | 423.2312 | 26724
44755 | 436.9971 | 26724
44756 | 420.1583 | 26724
44757 | 410.5763 | 26724
44758 | 412.8721 | 26724
44759 | 423.0057 | 26724
44760 | 425.0814 | 26724
44761 | 414.0786 | 26724
44762 | 416.1716 | 26724
44763 | 413.2561 | 26724
44764 | 401.2406 | 26724
44765 | 415.5624 | 26724
44766 | 421.0979 | 26724
44767 | 405.5799 | 26724
44768 | 410.8213 | 26724
44769 | 425.4917 | 26724
44770 | 402.5366 | 26724
44771 | 411.3283 | 26724
44772 | 429.2004 | 26724
44773 | 422.0283 | 26724
44774 | 422.9982 | 26724
44775 | 417.295 | 26724
44776 | 414.9479 | 26724
44777 | 434.5578 | 26724
44778 | 408.927 | 26724
44779 | 415.9345 | 26724
44780 | 425.3807 | 26724
44781 | 411.0637 | 26724
44782 | 414.468 | 26724
44783 | 432.5151 | 26724
44784 | 411.9789 | 26724
44785 | 423.3494 | 26724
44786 | 420.5947 | 26724
44787 | 423.6868 | 26724
44788 | 415.8283 | 26724
44789 | 414.3752 | 26724
44790 | 416.6165 | 26724
44791 | 425.3848 | 26724
44792 | 421.4132 | 26724
44793 | 422.3892 | 26724
44794 | 421.3582 | 26724
44795 | 404.1577 | 26724
44796 | 403.8083 | 26724
44797 | 420.4841 | 26724
44798 | 407.5448 | 26724
44799 | 420.7463 | 26724
44800 | 402.8003 | 26724
44801 | 406.6357 | 26724
44802 | 400.362 | 26724
44803 | 404.9383 | 26724
44804 | 429.6651 | 26724
44805 | 427.6383 | 26724
44806 | 411.9825 | 26724
44807 | 411.3308 | 26724
44808 | 408.1193 | 26724
44809 | 408.965 | 26724
44810 | 416.9982 | 26724
44811 | 420.6674 | 26724
44812 | 422.4808 | 26724
44813 | 420.2635 | 26724
44814 | 417.2768 | 26724
44815 | 418.4522 | 26724
44816 | 408.6275 | 26724
44817 | 417.0898 | 26724
44818 | 405.7681 | 26724
44819 | 434.8035 | 26724
44820 | 424.8434 | 26724
44821 | 411.06 | 26724
44822 | 414.3627 | 26724
44823 | 417.7245 | 26724
44824 | 431.6047 | 26724
44825 | 408.1397 | 26724
44826 | 412.7942 | 26724
44827 | 414.1931 | 26724
44828 | 413.4122 | 26724
44829 | 413.5526 | 26724
44830 | 418.8956 | 26724
44831 | 407.1738 | 26724
44832 | 421.8772 | 26724
44833 | 424.8293 | 26724
44834 | 420.9537 | 26724
44835 | 425.3304 | 26724
44836 | 407.8176 | 26724
44837 | 405.7007 | 26724
44838 | 415.0286 | 26724
44839 | 416.2592 | 26724
44840 | 415.2172 | 26724
44841 | 424.3121 | 26724
44842 | 410.9355 | 26724
44843 | 413.5284 | 26724
44844 | 407.7476 | 26724
44845 | 416.3101 | 26724
44846 | 432.8764 | 26724
44847 | 415.8324 | 26724
44848 | 423.3053 | 26724
44849 | 409.3431 | 26724
44850 | 418.2424 | 26724
44851 | 419.9166 | 26724
44852 | 414.3091 | 26724
44853 | 416.6685 | 26724
44854 | 413.8202 | 26724
44855 | 409.0357 | 26724
44856 | 421.5607 | 26724
44857 | 405.3264 | 26724
44858 | 425.0088 | 26724
44859 | 406.2536 | 26724
44860 | 420.5505 | 26724
44861 | 406.1477 | 26724
44862 | 412.5609 | 26724
44863 | 422.4292 | 26724
44864 | 425.9039 | 26724
44865 | 409.1138 | 26724
44866 | 410.0677 | 26724
44867 | 407.5724 | 26724
44868 | 428.5725 | 26724
44869 | 419.2497 | 26724
44870 | 416.6376 | 26724
44871 | 412.6594 | 26724
44872 | 416.2591 | 26724
44873 | 420.788 | 26724
44874 | 409.4924 | 26724
44875 | 425.0452 | 26724
44876 | 424.9342 | 26724
44877 | 425.0275 | 26724
44878 | 415.245 | 26724
44879 | 427.2786 | 26724
44880 | 416.0866 | 26724
44881 | 416.646 | 26724
44882 | 421.7571 | 26724
44883 | 409.0156 | 26724
44884 | 411.4341 | 26724
44885 | 424.9637 | 26724
44886 | 427.4279 | 26724
44887 | 423.2591 | 26724
44888 | 430.9464 | 26724
44889 | 420.9603 | 26724
44890 | 421.0906 | 26724
44891 | 422.0708 | 26724
44892 | 416.5266 | 26724
44893 | 417.4732 | 26724
44894 | 408.0118 | 26724
44895 | 402.0604 | 26724
44896 | 417.0571 | 26724
44897 | 402.3662 | 26724
44898 | 411.4392 | 26724
44899 | 414.6796 | 26724
44900 | 431.7447 | 26724
44901 | 426.1001 | 26724
44902 | 421.2174 | 26724
44903 | 420.2026 | 26724
44904 | 427.0203 | 26724
44905 | 406.0325 | 26724
44906 | 428.688 | 26724
44907 | 427.7411 | 26724
44908 | 420.5925 | 26724
44909 | 417.4258 | 26724
44910 | 408.4695 | 26724
44911 | 408.9329 | 26724
44912 | 410.918 | 26724
44913 | 419.3403 | 26724
44914 | 411.8321 | 26724
44915 | 419.7489 | 26724
44916 | 423.1335 | 26724
44917 | 427.8676 | 26724
44918 | 407.816 | 26724
44919 | 431.6058 | 26724
44920 | 418.5408 | 26724
44921 | 419.4835 | 26724
44922 | 435.39 | 26724
44923 | 428.2981 | 26724
44924 | 419.0906 | 26724
44925 | 429.5736 | 26724
44926 | 412.8597 | 26724
44927 | 398.4335 | 26724
44928 | 415.8484 | 26724
44929 | 409.9967 | 26724
44930 | 411.5374 | 26724
44931 | 405.9757 | 26724
44932 | 431.9081 | 26724
44933 | 420.3698 | 26724
44934 | 414.0636 | 26724
44935 | 417.394 | 26724
44936 | 420.6504 | 26724
44937 | 414.0479 | 26724
44938 | 418.8575 | 26724
44939 | 404.407 | 26724
44940 | 413.0191 | 26724
44941 | 413.1222 | 26724
44942 | 419.6045 | 26724
44943 | 419.7124 | 26724
44944 | 419.1255 | 26724
44945 | 407.5595 | 26724
44946 | 408.6623 | 26724
44947 | 417.0688 | 26724
44948 | 438.4935 | 26724
44949 | 405.2632 | 26724
44950 | 415.8475 | 26724
44951 | 406.7439 | 26724
44952 | 424.9286 | 26724
44953 | 420.9621 | 26724
44954 | 434.8977 | 26724
44955 | 423.2977 | 26724
44956 | 428.1163 | 26724
44957 | 415.9434 | 26724
44958 | 403.2546 | 26724
44959 | 408.0909 | 26724
44960 | 425.7173 | 26724
44961 | 410.0115 | 26724
44962 | 419.8368 | 26724
44963 | 412.2497 | 26724
44964 | 409.8148 | 26724
44965 | 411.0259 | 26724
44966 | 410.8709 | 26724
44967 | 412.2961 | 26724
44968 | 410.7315 | 26724
44969 | 411.4078 | 26724
44970 | 418.7222 | 26724
44971 | 412.6609 | 26724
44972 | 410.6032 | 26724
44973 | 419.6195 | 26724
44974 | 412.4042 | 26724
44975 | 404.6209 | 26724
44976 | 407.6029 | 26724
44977 | 412.3078 | 26724
44978 | 412.9256 | 26724
44979 | 430.7764 | 26724
44980 | 425.5049 | 26724
44981 | 408.3418 | 26724
44982 | 406.4159 | 26724
44983 | 408.9466 | 26724
44984 | 429.6328 | 26724
44985 | 409.4307 | 26724
44986 | 417.6217 | 26724
44987 | 411.7214 | 26724
44988 | 414.6254 | 26724
44989 | 418.7943 | 26724
44990 | 416.6932 | 26724
44991 | 416.3533 | 26724
44992 | 425.1271 | 26724
44993 | 417.4608 | 26724
44994 | 428.178 | 26724
44995 | 412.0238 | 26724
44996 | 427.7489 | 26724
44997 | 413.7445 | 26724
44998 | 424.7984 | 26724
44999 | 433.5223 | 26724
45000 | 427.9532 | 26724
45001 | 401.1764 | 26724
45002 | 407.8736 | 26724
45003 | 429.769 | 26724
45004 | 424.8848 | 26724
45005 | 401.1558 | 26724
45006 | 421.6349 | 26724
45007 | 421.734 | 26724
45008 | 414.1902 | 26724
45009 | 414.2864 | 26724
45010 | 425.113 | 26724
45011 | 411.4361 | 26724
45012 | 413.1876 | 26724
45013 | 405.0669 | 26724
45014 | 423.9764 | 26724
45015 | 405.2324 | 26724
45016 | 425.5495 | 26724
45017 | 409.5734 | 26724
45018 | 419.137 | 26724
45019 | 406.9579 | 26724
45020 | 425.7164 | 26724
45021 | 421.0613 | 26724
45022 | 408.5651 | 26724
45023 | 410.1887 | 26724
45024 | 402.9699 | 26724
45025 | 414.2939 | 26724
45026 | 420.0508 | 26724
45027 | 427.2868 | 26724
45028 | 417.6979 | 26724
45029 | 424.9827 | 26724
45030 | 408.3324 | 26724
45031 | 413.2314 | 26724
45032 | 406.9885 | 26724
45033 | 419.8862 | 26724
45034 | 413.0404 | 26724
45035 | 399.7007 | 26724
45036 | 411.7467 | 26724
45037 | 424.1717 | 26724
45038 | 403.2023 | 26724
45039 | 424.0357 | 26724
45040 | 426.0548 | 26724
45041 | 415.5657 | 26724
45042 | 413.4764 | 26724
45043 | 421.2101 | 26724
45044 | 422.3233 | 26724
45045 | 414.9159 | 26724
45046 | 417.4828 | 26724
45047 | 416.201 | 26724
45048 | 430.4075 | 26724
45049 | 408.1547 | 26724
45050 | 429.8937 | 26724
45051 | 411.0899 | 26724
45052 | 416.0782 | 26724
45053 | 409.8896 | 26724
45054 | 421.9541 | 26724
45055 | 415.5069 | 26724
45056 | 426.2147 | 26724
45057 | 414.4259 | 26724
45058 | 405.4396 | 26724
45059 | 420.042 | 26724
45060 | 419.4104 | 26724
45061 | 424.642 | 26724
45062 | 422.0602 | 26724
45063 | 396.2106 | 26724
45064 | 414.8517 | 26724
45065 | 416.9329 | 26724
45066 | 417.3334 | 26724
45067 | 413.0989 | 26724
45068 | 411.1628 | 26724
45069 | 430.1731 | 26724
45070 | 417.5559 | 26724
45071 | 411.6075 | 26724
45072 | 415.6674 | 26724
45073 | 417.2284 | 26724
45074 | 412.4178 | 26724
45075 | 415.132 | 26724
45076 | 409.4463 | 26724
45077 | 407.8322 | 26724
45078 | 417.58 | 26724
45079 | 417.9055 | 26724
45080 | 418.0812 | 26724
45081 | 415.2515 | 26724
45082 | 418.4749 | 26724
45083 | 405.8206 | 26724
45084 | 412.2603 | 26724
45085 | 412.91 | 26724
45086 | 423.7656 | 26724
45087 | 415.9506 | 26724
45088 | 400.4861 | 26724
45089 | 406.7083 | 26724
45090 | 409.9462 | 26724
45091 | 415.243 | 26724
45092 | 420.7996 | 26724
45093 | 411.0101 | 26724
45094 | 427.5197 | 26724
45095 | 428.9186 | 26724
45096 | 410.1945 | 26724
45097 | 410.1093 | 26724
45098 | 414.3105 | 26724
45099 | 410.6645 | 26724
45100 | 422.528 | 26724
45101 | 423.2428 | 26724
45102 | 419.2158 | 26724
45103 | 423.158 | 26724
45104 | 423.4652 | 26724
45105 | 412.3362 | 26724
45106 | 410.5032 | 26724
45107 | 405.9806 | 26724
45108 | 416.56 | 26724
45109 | 431.7557 | 26724
45110 | 411.3521 | 26724
45111 | 408.7698 | 26724
45112 | 429.6773 | 26724
45113 | 422.988 | 26724
45114 | 416.2082 | 26724
45115 | 429.807 | 26724
45116 | 412.3516 | 26724
45117 | 424.0977 | 26724
45118 | 423.1072 | 26724
45119 | 414.841 | 26724
45120 | 425.4353 | 26724
45121 | 412.5659 | 26724
45122 | 417.2463 | 26724
45123 | 417.0445 | 26724
45124 | 421.565 | 26724
45125 | 428.1374 | 26724
45126 | 425.3905 | 26724
45127 | 412.2583 | 26724
45128 | 419.9386 | 26724
45129 | 427.3384 | 26724
45130 | 418.3175 | 26724
45131 | 409.1784 | 26724
45132 | 412.3593 | 26724
45133 | 422.1276 | 26724
45134 | 403.1852 | 26724
45135 | 410.0355 | 26724
45136 | 419.4139 | 26724
45137 | 411.7622 | 26724
45138 | 412.1784 | 26724
45139 | 413.0125 | 26724
45140 | 422.8987 | 26724
45141 | 427.0199 | 26724
45142 | 427.0556 | 26724
45143 | 427.1847 | 26724
45144 | 419.0006 | 26724
45145 | 420.6391 | 26724
45146 | 431.9593 | 26724
45147 | 424.989 | 26724
45148 | 416.8454 | 26724
45149 | 418.241 | 26724
45150 | 413.906 | 26724
45151 | 411.4272 | 26724
45152 | 418.1687 | 26724
45153 | 424.9512 | 26724
45154 | 429.1355 | 26724
45155 | 414.2715 | 26724
45156 | 418.8988 | 26724
45157 | 429.6316 | 26724
45158 | 418.0224 | 26724
45159 | 414.1725 | 26724
45160 | 414.9287 | 26724
45161 | 426.1845 | 26724
45162 | 412.2705 | 26724
45163 | 415.8083 | 26724
45164 | 412.572 | 26724
45165 | 407.7891 | 26724
45166 | 421.9505 | 26724
45167 | 413.308 | 26724
45168 | 415.7134 | 26724
45169 | 409.0807 | 26724
45170 | 408.5451 | 26724
45171 | 418.2628 | 26724
45172 | 422.9299 | 26724
45173 | 411.9561 | 26724
45174 | 417.6366 | 26724
45175 | 422.3018 | 26724
45176 | 412.9174 | 26724
45177 | 437.602 | 26724
45178 | 414.732 | 26724
45179 | 416.403 | 26724
45180 | 422.0782 | 26724
45181 | 415.0693 | 26724
45182 | 412.6756 | 26724
45183 | 420.9822 | 26724
45184 | 415.2883 | 26724
45185 | 421.1442 | 26724
45186 | 425.3394 | 26724
45187 | 438.5958 | 26724
45188 | 422.0356 | 26724
45189 | 417.5411 | 26724
45190 | 412.2218 | 26724
45191 | 412.0888 | 26724
45192 | 427.5969 | 26724
45193 | 419.0097 | 26724
45194 | 410.2644 | 26724
45195 | 418.4844 | 26724
45196 | 422.097 | 26724
45197 | 415.8162 | 26724
45198 | 400.9112 | 26724
45199 | 418.0777 | 26724
45200 | 420.7639 | 26724
45201 | 417.1553 | 26724
45202 | 419.3011 | 26724
45203 | 425.597 | 26724
45204 | 414.6123 | 26724
45205 | 426.5759 | 26724
45206 | 422.5251 | 26724
45207 | 421.8929 | 26724
45208 | 408.3909 | 26724
45209 | 407.7943 | 26724
45210 | 426.1837 | 26724
45211 | 412.3816 | 26724
45212 | 422.6414 | 26724
45213 | 427.824 | 26724
45214 | 415.5262 | 26724
45215 | 406.6318 | 26724
45216 | 433.8179 | 26724
45217 | 406.6872 | 26724
45218 | 414.3323 | 26724
45219 | 426.4168 | 26724
45220 | 412.7996 | 26724
45221 | 408.1891 | 26724
45222 | 422.1566 | 26724
45223 | 425.1964 | 26724
45224 | 418.1042 | 26724
45225 | 408.2869 | 26724
45226 | 417.1999 | 26724
45227 | 417.3092 | 26724
45228 | 427.158 | 26724
45229 | 418.489 | 26724
45230 | 403.4146 | 26724
45231 | 409.87 | 26724
45232 | 405.4277 | 26724
45233 | 412.1222 | 26724
45234 | 418.6656 | 26724
45235 | 409.7881 | 26724
45236 | 419.1638 | 26724
45237 | 421.6933 | 26724
45238 | 410.3007 | 26724
45239 | 416.2323 | 26724
45240 | 415.2103 | 26724
45241 | 418.9778 | 26724
45242 | 412.0388 | 26724
45243 | 416.6653 | 26724
45244 | 429.1359 | 26724
45245 | 409.183 | 26724
45246 | 423.9832 | 26724
45247 | 418.1338 | 26724
45248 | 402.4372 | 26724
45249 | 414.389 | 26724
45250 | 414.1388 | 26724
45251 | 409.9431 | 26724
45252 | 411.3778 | 26724
45253 | 425.3793 | 26724
45254 | 421.7651 | 26724
45255 | 425.9303 | 26724
45256 | 409.5188 | 26724
45257 | 424.3839 | 26724
45258 | 430.9172 | 26724
45259 | 416.8545 | 26724
45260 | 419.2283 | 26724
45261 | 412.3869 | 26724
45262 | 426.3139 | 26724
45263 | 412.5743 | 26724
45264 | 426.7166 | 26724
45265 | 426.8517 | 26724
45266 | 423.6767 | 26724
45267 | 417.7758 | 26724
45268 | 420.5367 | 26724
45269 | 411.4996 | 26724
45270 | 410.0945 | 26724
45271 | 416.3299 | 26724
45272 | 420.5239 | 26724
45273 | 422.6219 | 26724
45274 | 433.233 | 26724
45275 | 419.4399 | 26724
45276 | 412.4311 | 26724
45277 | 399.6904 | 26724
45278 | 423.2812 | 26724
45279 | 405.2219 | 26724
45280 | 412.797 | 26724
45281 | 418.9086 | 26724
45282 | 419.2977 | 26724
45283 | 405.5191 | 26724
45284 | 415.2164 | 26724
45285 | 429.811 | 26724
45286 | 411.1334 | 26724
45287 | 420.2271 | 26724
45288 | 428.3942 | 26724
45289 | 419.001 | 26724
45290 | 405.8771 | 26724
45291 | 431.6935 | 26724
45292 | 410.8138 | 26724
45293 | 411.5821 | 26724
45294 | 424.9702 | 26724
45295 | 397.9253 | 26724
45296 | 414.5123 | 26724
45297 | 422.0735 | 26724
45298 | 413.8341 | 26724
45299 | 420.4136 | 26724
45300 | 404.3944 | 26724
45301 | 427.7589 | 26724
45302 | 402.4051 | 26724
45303 | 419.8247 | 26724
45304 | 419.2573 | 26724
45305 | 419.5094 | 26724
45306 | 418.0835 | 26724
45307 | 413.2037 | 26724
45308 | 420.7587 | 26724
45309 | 410.3251 | 26724
45310 | 410.7004 | 26724
45311 | 411.5432 | 26724
45312 | 410.9191 | 26724
45313 | 417.2265 | 26724
45314 | 413.1353 | 26724
45315 | 417.6043 | 26724
45316 | 413.8482 | 26724
45317 | 420.137 | 26724
45318 | 393.5237 | 26724
45319 | 407.6272 | 26724
45320 | 407.1428 | 26724
45321 | 410.0639 | 26724
45322 | 410.0851 | 26724
45323 | 413.4023 | 26724
45324 | 403.3115 | 26724
45325 | 419.12 | 26724
45326 | 429.7136 | 26724
45327 | 411.3628 | 26724
45328 | 409.7777 | 26724
45329 | 412.7479 | 26724
45330 | 425.1348 | 26724
45331 | 424.9809 | 26724
45332 | 413.8802 | 26724
45333 | 420.9739 | 26724
45334 | 415.4361 | 26724
45335 | 411.4918 | 26724
45336 | 423.1065 | 26724
45337 | 410.3008 | 26724
45338 | 427.7706 | 26724
45339 | 435.9528 | 26724
45340 | 407.607 | 26724
45341 | 420.6258 | 26724
45342 | 418.624 | 26724
45343 | 413.3669 | 26724
45344 | 419.0896 | 26724
45345 | 417.1953 | 26724
45346 | 414.1065 | 26724
45347 | 419.2435 | 26724
45348 | 426.3276 | 26724
45349 | 422.3218 | 26724
45350 | 414.5207 | 26724
45351 | 410.5649 | 26724
45352 | 425.5226 | 26724
45353 | 420.0673 | 26724
45354 | 420.7465 | 26724
45355 | 421.4459 | 26724
45356 | 412.3678 | 26724
45357 | 413.9255 | 26724
45358 | 418.9987 | 26724
45359 | 415.4046 | 26724
45360 | 419.3156 | 26724
45361 | 416.9619 | 26724
45362 | 418.7946 | 26724
45363 | 430.0161 | 26724
45364 | 427.1504 | 26724
45365 | 419.6493 | 26724
45366 | 428.0485 | 26724
45367 | 406.7141 | 26724
45368 | 420.4284 | 26724
45369 | 421.4408 | 26724
45370 | 431.8973 | 26724
45371 | 423.0174 | 26724
45372 | 429.7274 | 26724
45373 | 427.098 | 26724
45374 | 417.1396 | 26724
45375 | 406.7176 | 26724
45376 | 424.1022 | 26724
45377 | 409.8105 | 26724
45378 | 423.9837 | 26724
45379 | 411.4496 | 26724
45380 | 409.466 | 26724
45381 | 418.8632 | 26724
45382 | 399.5166 | 26724
45383 | 410.8567 | 26724
45384 | 402.8254 | 26724
45385 | 427.8382 | 26724
45386 | 413.3521 | 26724
45387 | 422.0752 | 26724
45388 | 427.436 | 26724
45389 | 402.18 | 26724
45390 | 400.1188 | 26724
45391 | 408.1883 | 26724
45392 | 417.6765 | 26724
45393 | 431.5747 | 26724
45394 | 418.5075 | 26724
45395 | 415.8703 | 26724
45396 | 414.1665 | 26724
45397 | 421.2018 | 26724
45398 | 418.7101 | 26724
45399 | 421.5831 | 26724
45400 | 409.255 | 26724
45401 | 427.1867 | 26724
45402 | 417.9802 | 26724
45403 | 414.5733 | 26724
45404 | 414.5499 | 26724
45405 | 417.4355 | 26724
45406 | 417.9336 | 26724
45407 | 413.5141 | 26724
45408 | 403.3237 | 26724
45409 | 420.5849 | 26724
45410 | 409.8909 | 26724
45411 | 422.3812 | 26724
45412 | 413.2058 | 26724
45413 | 405.9305 | 26724
45414 | 421.3229 | 26724
45415 | 424.941 | 26724
45416 | 426.0555 | 26724
45417 | 414.4552 | 26724
45418 | 421.5188 | 26724
45419 | 418.2807 | 26724
45420 | 413.7047 | 26724
45421 | 439.6586 | 26724
45422 | 420.8961 | 26724
45423 | 408.6658 | 26724
45424 | 412.7286 | 26724
45425 | 406.0799 | 26724
45426 | 410.8119 | 26724
45427 | 413.8253 | 26724
45428 | 412.6632 | 26724
45429 | 404.9939 | 26724
45430 | 428.0074 | 26724
45431 | 415.4649 | 26724
45432 | 430.6149 | 26724
45433 | 423.6488 | 26724
45434 | 410.7577 | 26724
45435 | 421.7534 | 26724
45436 | 417.6834 | 26724
45437 | 402.0116 | 26724
45438 | 405.4292 | 26724
45439 | 412.7751 | 26724
45440 | 411.8953 | 26724
45441 | 415.3452 | 26724
45442 | 416.404 | 26724
45443 | 409.8591 | 26724
45444 | 401.5538 | 26724
45445 | 413.4015 | 26724
45446 | 412.6035 | 26724
45447 | 424.8021 | 26724
45448 | 409.1553 | 26724
45449 | 425.8731 | 26724
45450 | 422.93 | 26724
45451 | 404.5447 | 26724
45452 | 421.6993 | 26724
45453 | 413.2584 | 26724
45454 | 415.071 | 26724
45455 | 423.9432 | 26724
45456 | 420.7696 | 26724
45457 | 427.9397 | 26724
45458 | 422.7505 | 26724
45459 | 418.9368 | 26724
45460 | 413.3964 | 26724
45461 | 413.5052 | 26724
45462 | 404.3107 | 26724
45463 | 421.9341 | 26724
45464 | 415.8096 | 26724
45465 | 423.2362 | 26724
45466 | 434.1412 | 26724
45467 | 416.8549 | 26724
45468 | 423.9029 | 26724
45469 | 412.3243 | 26724
45470 | 423.9721 | 26724
45471 | 412.2423 | 26724
45472 | 418.1109 | 26724
45473 | 415.5906 | 26724
45474 | 409.9522 | 26724
45475 | 428.0619 | 26724
45476 | 407.7056 | 26724
45477 | 416.6568 | 26724
45478 | 423.5866 | 26724
45479 | 415.1579 | 26724
45480 | 422.7813 | 26724
45481 | 412.8698 | 26724
45482 | 422.3218 | 26724
45483 | 418.8758 | 26724
45484 | 409.1497 | 26724
45485 | 424 | 26724
45486 | 420.2849 | 26724
45487 | 407.668 | 26724
45488 | 410.9838 | 26724
45489 | 435.5836 | 26724
45490 | 424.0436 | 26724
45491 | 408.3707 | 26724
45492 | 402.7686 | 26724
45493 | 411.4294 | 26724
45494 | 412.9638 | 26724
45495 | 428.1011 | 26724
45496 | 394.9987 | 26724
45497 | 418.9722 | 26724
45498 | 415.735 | 26724
45499 | 420.252 | 26724
45500 | 425.9655 | 26724
45501 | 417.4927 | 26724
45502 | 406.597 | 26724
45503 | 414.6098 | 26724
45504 | 405.9722 | 26724
45505 | 419.0783 | 26724
45506 | 411.6921 | 26724
45507 | 416.7221 | 26724
45508 | 421.2202 | 26724
45509 | 413.4477 | 26724
45510 | 423.5529 | 26724
45511 | 421.3968 | 26724
45512 | 410.5842 | 26724
45513 | 407.6101 | 26724
45514 | 410.873 | 26724
45515 | 412.5336 | 26724
45516 | 422.8904 | 26724
45517 | 419.4881 | 26724
45518 | 418.9259 | 26724
45519 | 430.5493 | 26724
45520 | 419.6684 | 26724
45521 | 420.2418 | 26724
45522 | 415.8711 | 26724
45523 | 411.8726 | 26724
45524 | 410.9397 | 26724
45525 | 423.0275 | 26724
45526 | 414.6037 | 26724
45527 | 402.7058 | 26724
45528 | 401.2216 | 26724
45529 | 427.1076 | 26724
45530 | 412.8178 | 26724
45531 | 433.9471 | 26724
45532 | 404.0812 | 26724
45533 | 427.2898 | 26724
45534 | 420.3624 | 26724
45535 | 427.1087 | 26724
45536 | 425.209 | 26724
45537 | 418.1113 | 26724
45538 | 415.0371 | 26724
45539 | 421.1269 | 26724
45540 | 417.177 | 26724
45541 | 418.9326 | 26724
45542 | 415.2129 | 26724
45543 | 414.6925 | 26724
45544 | 415.9877 | 26724
45545 | 414.9409 | 26724
45546 | 414.6331 | 26724
45547 | 414.6385 | 26724
45548 | 427.6239 | 26724
45549 | 413.3633 | 26724
45550 | 415.0367 | 26724
45551 | 413.895 | 26724
45552 | 402.7831 | 26724
45553 | 407.5986 | 26724
45554 | 426.208 | 26724
45555 | 416.4134 | 26724
45556 | 429.77 | 26724
45557 | 422.0649 | 26724
45558 | 416.5682 | 26724
45559 | 422.3004 | 26724
45560 | 410.6781 | 26724
45561 | 411.9987 | 26724
45562 | 420.4339 | 26724
45563 | 421.3265 | 26724
45564 | 425.1992 | 26724
45565 | 413.2697 | 26724
45566 | 412.6869 | 26724
45567 | 406.9812 | 26724
45568 | 424.3582 | 26724
45569 | 434.3383 | 26724
45570 | 417.3252 | 26724
45571 | 411.6451 | 26724
45572 | 418.584 | 26724
45573 | 417.7353 | 26724
45574 | 421.9465 | 26724
45575 | 410.0978 | 26724
45576 | 417.1725 | 26724
45577 | 408.4635 | 26724
45578 | 411.6231 | 26724
45579 | 421.2256 | 26724
45580 | 416.7661 | 26724
45581 | 413.0361 | 26724
45582 | 410.0973 | 26724
45583 | 409.94 | 26724
45584 | 430.2903 | 26724
45585 | 426.6432 | 26724
45586 | 421.525 | 26724
45587 | 425.4494 | 26724
45588 | 419.4246 | 26724
45589 | 409.0786 | 26724
45590 | 427.7062 | 26724
45591 | 436.3649 | 26724
45592 | 402.3044 | 26724
45593 | 417.3476 | 26724
45594 | 419.711 | 26724
45595 | 402.2994 | 26724
45596 | 425.2926 | 26724
45597 | 422.0643 | 26724
45598 | 422.3196 | 26724
45599 | 415.3694 | 26724
45600 | 420.8971 | 26724
45601 | 422.5449 | 26724
45602 | 427.8818 | 26724
45603 | 417.5059 | 26724
45604 | 416.2922 | 26724
45605 | 417.7302 | 26724
45606 | 431.2482 | 26724
45607 | 413.7774 | 26724
45608 | 409.8816 | 26724
45609 | 409.879 | 26724
45610 | 408.8388 | 26724
45611 | 422.0197 | 26724
45612 | 406.0468 | 26724
45613 | 411.4244 | 26724
45614 | 411.2144 | 26724
45615 | 422.9313 | 26724
45616 | 423.0874 | 26724
45617 | 423.201 | 26724
45618 | 417.0338 | 26724
45619 | 411.7225 | 26724
45620 | 409.1769 | 26724
45621 | 418.2731 | 26724
45622 | 406.8619 | 26724
45623 | 411.3843 | 26724
45624 | 411.6356 | 26724
45625 | 404.6957 | 26724
45626 | 416.2325 | 26724
45627 | 421.5246 | 26724
45628 | 409.9918 | 26724
45629 | 415.414 | 26724
45630 | 424.8524 | 26724
45631 | 421.2314 | 26724
45632 | 415.5649 | 26724
45633 | 422.5633 | 26724
45634 | 419.8195 | 26724
45635 | 417.436 | 26724
45636 | 429.2622 | 26724
45637 | 420.0763 | 26724
45638 | 425.5543 | 26724
45639 | 424.6673 | 26724
45640 | 414.6743 | 26724
45641 | 410.2894 | 26724
45642 | 410.6972 | 26724
45643 | 406.3236 | 26724
45644 | 414.8358 | 26724
45645 | 416.9868 | 26724
45646 | 421.8075 | 26724
45647 | 411.5476 | 26724
45648 | 431.6498 | 26724
45649 | 421.9944 | 26724
45650 | 416.1711 | 26724
45651 | 410.5898 | 26724
45652 | 410.924 | 26724
45653 | 411.4575 | 26724
45654 | 424.6879 | 26724
45655 | 408.8982 | 26724
45656 | 423.1227 | 26724
45657 | 423.86 | 26724
45658 | 425.2447 | 26724
45659 | 413.0351 | 26724
45660 | 409.0569 | 26724
45661 | 414.1674 | 26724
45662 | 409.2897 | 26724
45663 | 409.7169 | 26724
45664 | 424.0834 | 26724
45665 | 434.49 | 26724
45666 | 404.9146 | 26724
45667 | 404.2724 | 26724
45668 | 399.4516 | 26724
45669 | 419.3363 | 26724
45670 | 420.6272 | 26724
45671 | 415.5285 | 26724
45672 | 434.2129 | 26724
45673 | 431.4763 | 26724
45674 | 414.7101 | 26724
45675 | 408.1105 | 26724
45676 | 415.7854 | 26724
45677 | 414.9318 | 26724
45678 | 425.5254 | 26724
45679 | 427.1516 | 26724
45680 | 417.5486 | 26724
45681 | 404.3678 | 26724
45682 | 410.7848 | 26724
45683 | 410.7738 | 26724
45684 | 429.8655 | 26724
45685 | 413.8544 | 26724
45686 | 418.5734 | 26724
45687 | 429.1389 | 26724
45688 | 415.4523 | 26724
45689 | 413.8524 | 26724
45690 | 408.9218 | 26724
45691 | 410.3535 | 26724
45692 | 412.8735 | 26724
45693 | 416.3897 | 26724
45694 | 410.0959 | 26724
45695 | 422.3417 | 26724
45696 | 429.3539 | 26724
45697 | 406.2302 | 26724
45698 | 416.2755 | 26724
45699 | 404.8128 | 26724
45700 | 429.0697 | 26724
45701 | 415.0396 | 26724
45702 | 407.4777 | 26724
45703 | 425.8399 | 26724
45704 | 418.5408 | 26724
45705 | 414.8558 | 26724
45706 | 414.6299 | 26724
45707 | 428.269 | 26724
45708 | 419.2734 | 26724
45709 | 409.8787 | 26724
45710 | 412.0681 | 26724
45711 | 416.0208 | 26724
45712 | 422.83 | 26724
45713 | 423.5267 | 26724
45714 | 425.8059 | 26724
45715 | 415.278 | 26724
45716 | 418.0536 | 26724
45717 | 416.9863 | 26724
45718 | 430.2202 | 26724
45719 | 433.8555 | 26724
45720 | 399.4222 | 26724
45721 | 405.8461 | 26724
45722 | 423.2526 | 26724
45723 | 423.3934 | 26724
45724 | 415.2403 | 26724
45725 | 420.143 | 26724
45726 | 424.0375 | 26724
45727 | 418.6884 | 26724
45728 | 425.1357 | 26724
45729 | 423.7823 | 26724
45730 | 428.4581 | 26724
45731 | 419.5721 | 26724
45732 | 428.9275 | 26724
45733 | 409.8358 | 26724
45734 | 417.8506 | 26724
45735 | 410.3688 | 26724
45736 | 407.3918 | 26724
45737 | 405.3977 | 26724
45738 | 410.4371 | 26724
45739 | 413.3617 | 26724
45740 | 415.8916 | 26724
45741 | 422.5507 | 26724
45742 | 407.8292 | 26724
45743 | 413.1378 | 26724
45744 | 415.2419 | 26724
45745 | 395.8531 | 26724
45746 | 419.1282 | 26724
45747 | 425.3703 | 26724
45748 | 424.5228 | 26724
45749 | 423.621 | 26724
45750 | 418.4706 | 26724
45751 | 425.9134 | 26724
45752 | 424.9433 | 26724
45753 | 419.629 | 26724
45754 | 405.9921 | 26724
45755 | 399.4846 | 26724
45756 | 425.5811 | 26724
45757 | 413.6512 | 26724
45758 | 425.744 | 26724
45759 | 420.0907 | 26724
45760 | 422.3307 | 26724
45761 | 406.2754 | 26724
45762 | 422.8194 | 26724
45763 | 410.5759 | 26724
45764 | 418.768 | 26724
45765 | 411.7359 | 26724
45766 | 422.7217 | 26724
45767 | 414.1194 | 26724
45768 | 414.9623 | 26724
45769 | 425.7334 | 26724
45770 | 407.6731 | 26724
45771 | 408.3852 | 26724
45772 | 407.4859 | 26724
45773 | 419.8615 | 26724
45774 | 414.0239 | 26724
45775 | 430.712 | 26724
45776 | 419.8738 | 26724
45777 | 417.4783 | 26724
45778 | 420.6678 | 26724
45779 | 413.6157 | 26724
45780 | 427.8814 | 26724
45781 | 426.5164 | 26724
45782 | 424.353 | 26724
45783 | 401.9109 | 26724
45784 | 424.504 | 26724
45785 | 421.3954 | 26724
45786 | 414.1692 | 26724
45787 | 407.7715 | 26724
45788 | 403.493 | 26724
45789 | 424.4869 | 26724
45790 | 411.1624 | 26724
45791 | 419.3243 | 26724
45792 | 418.0925 | 26724
45793 | 413.1896 | 26724
45794 | 400.3646 | 26724
45795 | 415.9296 | 26724
45796 | 411.9492 | 26724
45797 | 409.0332 | 26724
45798 | 411.1437 | 26724
45799 | 428.3578 | 26724
45800 | 402.5456 | 26724
45801 | 432.9497 | 26724
45802 | 409.6717 | 26724
45803 | 416.216 | 26724
45804 | 405.2483 | 26724
45805 | 422.9956 | 26724
45806 | 421.485 | 26724
45807 | 429.7313 | 26724
45808 | 414.9707 | 26724
45809 | 402.378 | 26724
45810 | 413.8643 | 26724
45811 | 426.0781 | 26724
45812 | 416.9159 | 26724
45813 | 415.5359 | 26724
45814 | 404.601 | 26724
45815 | 411.5418 | 26724
45816 | 419.5068 | 26724
45817 | 409.5417 | 26724
45818 | 420.569 | 26724
45819 | 420.4186 | 26724
45820 | 423.2715 | 26724
45821 | 423.6305 | 26724
45822 | 408.838 | 26724
45823 | 404.3917 | 26724
45824 | 431.1071 | 26724
45825 | 417.8587 | 26724
45826 | 431.7512 | 26724
45827 | 432.5427 | 26724
45828 | 430.3461 | 26724
45829 | 411.326 | 26724
45830 | 403.3958 | 26724
45831 | 419.8117 | 26724
45832 | 424.3711 | 26724
45833 | 402.3304 | 26724
45834 | 417.618 | 26724
45835 | 407.2853 | 26724
45836 | 408.0525 | 26724
45837 | 403.9943 | 26724
45838 | 427.1308 | 26724
45839 | 401.0986 | 26724
45840 | 420.461 | 26724
45841 | 406.8655 | 26724
45842 | 427.256 | 26724
45843 | 414.0278 | 26724
45844 | 422.2087 | 26724
45845 | 407.7178 | 26724
45846 | 416.4088 | 26724
45847 | 425.1111 | 26724
45848 | 404.203 | 26724
45849 | 419.3362 | 26724
45850 | 424.7756 | 26724
45851 | 407.6641 | 26724
45852 | 433.103 | 26724
45853 | 421.7857 | 26724
45854 | 410.6592 | 26724
45855 | 405.756 | 26724
45856 | 409.7909 | 26724
45857 | 413.7453 | 26724
45858 | 420.5918 | 26724
45859 | 412.07 | 26724
45860 | 412.717 | 26724
45861 | 414.4682 | 26724
45862 | 408.0184 | 26724
45863 | 425.7262 | 26724
45864 | 406.0963 | 26724
45865 | 422.2422 | 26724
45866 | 406.565 | 26724
45867 | 417.5179 | 26724
45868 | 406.69 | 26724
45869 | 426.0284 | 26724
45870 | 427.0817 | 26724
45871 | 408.6734 | 26724
45872 | 415.2387 | 26724
45873 | 405.9065 | 26724
45874 | 411.9875 | 26724
45875 | 422.0089 | 26724
45876 | 405.5067 | 26724
45877 | 420.9161 | 26724
45878 | 398.5353 | 26724
45879 | 419.5617 | 26724
45880 | 409.6935 | 26724
45881 | 412.9235 | 26724
45882 | 418.7992 | 26724
45883 | 408.5782 | 26724
45884 | 413.1035 | 26724
45885 | 398.6317 | 26724
45886 | 426.3428 | 26724
45887 | 406.68 | 26724
45888 | 420.7492 | 26724
45889 | 420.2475 | 26724
45890 | 427.7483 | 26724
45891 | 407.8823 | 26724
45892 | 418.2712 | 26724
45893 | 429.7942 | 26724
45894 | 403.5886 | 26724
45895 | 406.0361 | 26724
45896 | 414.7786 | 26724
45897 | 421.6842 | 26724
45898 | 424.2291 | 26724
45899 | 404.1296 | 26724
45900 | 408.101 | 26724
45901 | 413.3672 | 26724
45902 | 410.4893 | 26724
45903 | 410.6524 | 26724
45904 | 419.5025 | 26724
45905 | 419.0871 | 26724
45906 | 414.204 | 26724
45907 | 416.6453 | 26724
45908 | 416.8858 | 26724
45909 | 409.9916 | 26724
45910 | 409.9281 | 26724
45911 | 417.8287 | 26724
45912 | 429.0726 | 26724
45913 | 409.9273 | 26724
45914 | 412.2777 | 26724
45915 | 414.2139 | 26724
45916 | 401.6206 | 26724
45917 | 413.8214 | 26724
45918 | 424.0542 | 26724
45919 | 411.5504 | 26724
45920 | 417.425 | 26724
45921 | 414.2785 | 26724
45922 | 408.9609 | 26724
45923 | 426.6404 | 26724
45924 | 417.2846 | 26724
45925 | 411.4977 | 26724
45926 | 420.2018 | 26724
45927 | 428.5935 | 26724
45928 | 405.7748 | 26724
45929 | 424.8773 | 26724
45930 | 427.4514 | 26724
45931 | 421.521 | 26724
45932 | 406.6103 | 26724
45933 | 428.7599 | 26724
45934 | 421.655 | 26724
45935 | 404.9138 | 26724
45936 | 417.2975 | 26724
45937 | 417.2719 | 26724
45938 | 411.2448 | 26724
45939 | 430.4957 | 26724
45940 | 416.2257 | 26724
45941 | 408.9319 | 26724
45942 | 417.2906 | 26724
45943 | 418.8782 | 26724
45944 | 421.8169 | 26724
45945 | 413.3553 | 26724
45946 | 425.6963 | 26724
45947 | 417.6412 | 26724
45948 | 424.1753 | 26724
45949 | 415.1922 | 26724
45950 | 414.4019 | 26724
45951 | 422.2712 | 26724
45952 | 425.2246 | 26724
45953 | 404.6366 | 26724
45954 | 416.6088 | 26724
45955 | 410.5859 | 26724
45956 | 430.4571 | 26724
45957 | 417.8581 | 26724
45958 | 417.0246 | 26724
45959 | 422.6389 | 26724
45960 | 420.0411 | 26724
45961 | 433.0658 | 26724
45962 | 423.7994 | 26724
45963 | 399.7838 | 26724
45964 | 424.7323 | 26724
45965 | 420.5584 | 26724
45966 | 411.742 | 26724
45967 | 410.2161 | 26724
45968 | 412.0707 | 26724
45969 | 427.3976 | 26724
45970 | 409.0984 | 26724
45971 | 423.7054 | 26724
45972 | 419.9607 | 26724
45973 | 416.1403 | 26724
45974 | 409.255 | 26724
45975 | 415.8723 | 26724
45976 | 408.8995 | 26724
45977 | 416.8766 | 26724
45978 | 410.7568 | 26724
45979 | 414.3009 | 26724
45980 | 428.356 | 26724
45981 | 420.7922 | 26724
45982 | 422.8788 | 26724
45983 | 418.0487 | 26724
45984 | 412.6556 | 26724
45985 | 420.7747 | 26724
45986 | 420.8808 | 26724
45987 | 411.2004 | 26724
45988 | 405.1064 | 26724
45989 | 407.6665 | 26724
45990 | 413.8515 | 26724
45991 | 429.5893 | 26724
45992 | 428.503 | 26724
45993 | 412.3378 | 26724
45994 | 394.0512 | 26724
45995 | 415.5066 | 26724
45996 | 437.0242 | 26724
45997 | 415.8832 | 26724
45998 | 415.1411 | 26724
45999 | 421.0974 | 26724
46000 | 413.5244 | 26724
46001 | 416.7995 | 26724
46002 | 405.6506 | 26724
46003 | 406.4255 | 26724
46004 | 410.3111 | 26724
46005 | 417.3725 | 26724
46006 | 412.3289 | 26724
46007 | 426.8495 | 26724
46008 | 407.856 | 26724
46009 | 410.0375 | 26724
46010 | 423.7254 | 26724
46011 | 411.2242 | 26724
46012 | 419.6222 | 26724
46013 | 417.6392 | 26724
46014 | 399.1094 | 26724
46015 | 424.5162 | 26724
46016 | 416.7147 | 26724
46017 | 425.3523 | 26724
46018 | 417.49 | 26724
46019 | 422.6025 | 26724
46020 | 430.1463 | 26724
46021 | 411.3895 | 26724
46022 | 423.8295 | 26724
46023 | 429.5348 | 26724
46024 | 408.2064 | 26724
46025 | 412.0004 | 26724
46026 | 407.0918 | 26724
46027 | 419.9266 | 26724
46028 | 415.3299 | 26724
46029 | 403.5732 | 26724
46030 | 413.8039 | 26724
46031 | 420.0648 | 26724
46032 | 423.4117 | 26724
46033 | 422.4881 | 26724
46034 | 415.2377 | 26724
46035 | 404.6575 | 26724
46036 | 409.9194 | 26724
46037 | 415.7983 | 26724
46038 | 419.9022 | 26724
46039 | 409.0112 | 26724
46040 | 420.2115 | 26724
46041 | 426.7266 | 26724
46042 | 420.2911 | 26724
46043 | 417.6645 | 26724
46044 | 413.0222 | 26724
46045 | 402.3533 | 26724
46046 | 435.0195 | 26724
46047 | 425.221 | 26724
46048 | 425.6194 | 26724
46049 | 411.7757 | 26724
46050 | 418.5687 | 26724
46051 | 424.3178 | 26724
46052 | 418.8104 | 26724
46053 | 421.335 | 26724
46054 | 408.6465 | 26724
46055 | 410.4781 | 26724
46056 | 436.541 | 26724
46057 | 416.5402 | 26724
46058 | 425.4629 | 26724
46059 | 414.9987 | 26724
46060 | 419.7545 | 26724
46061 | 435.4627 | 26724
46062 | 418.4632 | 26724
46063 | 420.2228 | 26724
46064 | 419.3105 | 26724
46065 | 404.1964 | 26724
46066 | 406.3849 | 26724
46067 | 409.5011 | 26724
46068 | 415.3556 | 26724
46069 | 422.4061 | 26724
46070 | 421.6153 | 26724
46071 | 416.8452 | 26724
46072 | 407.3815 | 26724
46073 | 422.1703 | 26724
46074 | 417.1728 | 26724
46075 | 405.778 | 26724
46076 | 420.418 | 26724
46077 | 412.3083 | 26724
46078 | 433.6078 | 26724
46079 | 404.8418 | 26724
46080 | 410.821 | 26724
46081 | 430.2631 | 26724
46082 | 420.9489 | 26724
46083 | 401.9956 | 26724
46084 | 416.7617 | 26724
46085 | 416.471 | 26724
46086 | 419.528 | 26724
46087 | 420.7883 | 26724
46088 | 422.5885 | 26724
46089 | 420.8658 | 26724
46090 | 405.8714 | 26724
46091 | 416.257 | 26724
46092 | 421.1713 | 26724
46093 | 420.8463 | 26724
46094 | 413.8455 | 26724
46095 | 414.415 | 26724
46096 | 423.9935 | 26724
46097 | 420.2274 | 26724
46098 | 395.7608 | 26724
46099 | 419.3034 | 26724
46100 | 415.297 | 26724
46101 | 422.5281 | 26724
46102 | 404.7791 | 26724
46103 | 412.5284 | 26724
46104 | 410.3327 | 26724
46105 | 420.6012 | 26724
46106 | 406.4052 | 26724
46107 | 410.7592 | 26724
46108 | 414.9517 | 26724
46109 | 423.0311 | 26724
46110 | 412.3097 | 26724
46111 | 415.6522 | 26724
46112 | 413.2607 | 26724
46113 | 419.9924 | 26724
46114 | 421.4086 | 26724
46115 | 411.8945 | 26724
46116 | 412.3184 | 26724
46117 | 409.092 | 26724
46118 | 418.3998 | 26724
46119 | 417.1502 | 26724
46120 | 417.8956 | 26724
46121 | 433.8499 | 26724
46122 | 407.5873 | 26724
46123 | 408.3185 | 26724
46124 | 411.7811 | 26724
46125 | 424.6676 | 26724
46126 | 431.6415 | 26724
46127 | 428.4958 | 26724
46128 | 410.4135 | 26724
46129 | 423.5835 | 26724
46130 | 402.0132 | 26724
46131 | 415.6694 | 26724
46132 | 418.3972 | 26724
46133 | 419.8529 | 26724
46134 | 419.3583 | 26724
46135 | 420.327 | 26724
46136 | 420.709 | 26724
46137 | 433.3296 | 26724
46138 | 413.2265 | 26724
46139 | 415.6859 | 26724
46140 | 424.5246 | 26724
46141 | 425.3109 | 26724
46142 | 419.3542 | 26724
46143 | 416.0289 | 26724
46144 | 414.6099 | 26724
46145 | 410.7587 | 26724
46146 | 414.4045 | 26724
46147 | 414.3949 | 26724
46148 | 422.4362 | 26724
46149 | 416.0429 | 26724
46150 | 414.703 | 26724
46151 | 415.3316 | 26724
46152 | 402.0206 | 26724
46153 | 413.5482 | 26724
46154 | 426.1793 | 26724
46155 | 414.3694 | 26724
46156 | 415.6218 | 26724
46157 | 425.9572 | 26724
46158 | 409.7469 | 26724
46159 | 427.73 | 26724
46160 | 402.2997 | 26724
46161 | 423.5524 | 26724
46162 | 408.9545 | 26724
46163 | 427.1442 | 26724
46164 | 412.4908 | 26724
46165 | 425.1941 | 26724
46166 | 418.4061 | 26724
46167 | 415.3869 | 26724
46168 | 417.6294 | 26724
46169 | 421.0667 | 26724
46170 | 418.0579 | 26724
46171 | 429.2896 | 26724
46172 | 405.0668 | 26724
46173 | 433.0229 | 26724
46174 | 414.2139 | 26724
46175 | 404.0732 | 26724
46176 | 412.1959 | 26724
46177 | 423.709 | 26724
46178 | 409.1182 | 26724
46179 | 406.2969 | 26724
46180 | 416.9773 | 26724
46181 | 410.2827 | 26724
46182 | 406.3182 | 26724
46183 | 415.8933 | 26724
46184 | 409.2911 | 26724
46185 | 425.0105 | 26724
46186 | 420.9953 | 26724
46187 | 423.4741 | 26724
46188 | 415.9035 | 26724
46189 | 422.6604 | 26724
46190 | 415.0368 | 26724
46191 | 407.0586 | 26724
46192 | 414.3876 | 26724
46193 | 425.2807 | 26724
46194 | 407.5883 | 26724
46195 | 406.3362 | 26724
46196 | 417.4775 | 26724
46197 | 419.4745 | 26724
46198 | 423.7515 | 26724
46199 | 404.936 | 26724
46200 | 411.5955 | 26724
46201 | 410.1869 | 26724
46202 | 412.57 | 26724
46203 | 431.9554 | 26724
46204 | 412.5597 | 26724
46205 | 424.9962 | 26724
46206 | 409.6149 | 26724
46207 | 423.495 | 26724
46208 | 406.7411 | 26724
46209 | 413.7423 | 26724
46210 | 426.5355 | 26724
46211 | 409.6633 | 26724
46212 | 416.1852 | 26724
46213 | 401.3717 | 26724
46214 | 421.4277 | 26724
46215 | 407.5049 | 26724
46216 | 416.4399 | 26724
46217 | 409.3309 | 26724
46218 | 408.1361 | 26724
46219 | 422.9257 | 26724
46220 | 425.6042 | 26724
46221 | 419.5984 | 26724
46222 | 418.1223 | 26724
46223 | 409.094 | 26724
46224 | 423.6088 | 26724
46225 | 427.1142 | 26724
46226 | 423.595 | 26724
46227 | 429.5741 | 26724
46228 | 420.6855 | 26724
46229 | 424.6909 | 26724
46230 | 420.4503 | 26724
46231 | 421.3414 | 26724
46232 | 420.7337 | 26724
46233 | 412.8626 | 26724
46234 | 416.2147 | 26724
46235 | 421.3115 | 26724
46236 | 413.5077 | 26724
46237 | 416.4454 | 26724
46238 | 424.507 | 26724
46239 | 408.5442 | 26724
46240 | 420.906 | 26724
46241 | 427.0121 | 26724
46242 | 416.216 | 26724
46243 | 414.9369 | 26724
46244 | 411.818 | 26724
46245 | 409.6859 | 26724
46246 | 420.7684 | 26724
46247 | 407.2141 | 26724
46248 | 417.535 | 26724
46249 | 413.0869 | 26724
46250 | 424.7874 | 26724
46251 | 417.7816 | 26724
46252 | 409.4214 | 26724
46253 | 425.0589 | 26724
46254 | 407.318 | 26724
46255 | 406.6328 | 26724
46256 | 418.4569 | 26724
46257 | 399.8601 | 26724
46258 | 421.2445 | 26724
46259 | 409.1538 | 26724
46260 | 419.9175 | 26724
46261 | 416.7893 | 26724
46262 | 432.2226 | 26724
46263 | 407.8631 | 26724
46264 | 416.7905 | 26724
46265 | 424.0166 | 26724
46266 | 422.321 | 26724
46267 | 412.4488 | 26724
46268 | 432.8352 | 26724
46269 | 422.5675 | 26724
46270 | 419.4995 | 26724
46271 | 422.434 | 26724
46272 | 427.306 | 26724
46273 | 411.8459 | 26724
46274 | 405.3919 | 26724
46275 | 421.769 | 26724
46276 | 424.9512 | 26724
46277 | 414.5024 | 26724
46278 | 413.7473 | 26724
46279 | 404.7676 | 26724
46280 | 416.9716 | 26724
46281 | 409.6335 | 26724
46282 | 417.3508 | 26724
46283 | 430.9703 | 26724
46284 | 398.3102 | 26724
46285 | 427.9477 | 26724
46286 | 420.5928 | 26724
46287 | 413.7659 | 26724
46288 | 409.3262 | 26724
46289 | 424.0414 | 26724
46290 | 429.0871 | 26724
46291 | 429.3783 | 26724
46292 | 411.4187 | 26724
46293 | 409.9031 | 26724
46294 | 421.2613 | 26724
46295 | 437.2768 | 26724
46296 | 420.3035 | 26724
46297 | 403.0785 | 26724
46298 | 399.5832 | 26724
46299 | 421.8978 | 26724
46300 | 418.4442 | 26724
46301 | 415.22 | 26724
46302 | 418.9366 | 26724
46303 | 414.7103 | 26724
46304 | 403.1759 | 26724
46305 | 420.5742 | 26724
46306 | 424.672 | 26724
46307 | 407.0186 | 26724
46308 | 411.4636 | 26724
46309 | 424.24 | 26724
46310 | 414.0351 | 26724
46311 | 431.5535 | 26724
46312 | 416.7432 | 26724
46313 | 433.1352 | 26724
46314 | 411.4406 | 26724
46315 | 418.9554 | 26724
46316 | 405.975 | 26724
46317 | 430.2276 | 26724
46318 | 430.8997 | 26724
46319 | 430.9871 | 26724
46320 | 422.4758 | 26724
46321 | 417.1843 | 26724
46322 | 421.4638 | 26724
46323 | 409.0717 | 26724
46324 | 407.3488 | 26724
46325 | 416.8963 | 26724
46326 | 413.7561 | 26724
46327 | 415.8789 | 26724
46328 | 404.7725 | 26724
46329 | 429.4312 | 26724
46330 | 423.9602 | 26724
46331 | 409.2087 | 26724
46332 | 410.9853 | 26724
46333 | 408.3184 | 26724
46334 | 422.3156 | 26724
46335 | 421.3783 | 26724
46336 | 413.4765 | 26724
46337 | 407.2974 | 26724
46338 | 437.5252 | 26724
46339 | 406.7836 | 26724
46340 | 420.2712 | 26724
46341 | 415.1552 | 26724
46342 | 412.8332 | 26724
46343 | 418.8889 | 26724
46344 | 421.173 | 26724
46345 | 421.2793 | 26724
46346 | 408.2632 | 26724
46347 | 413.143 | 26724
46348 | 420.0675 | 26724
46349 | 409.8722 | 26724
46350 | 414.3652 | 26724
46351 | 426.4853 | 26724
46352 | 407.0728 | 26724
46353 | 410.6679 | 26724
46354 | 416.4117 | 26724
46355 | 431.8717 | 26724
46356 | 418.3563 | 26724
46357 | 410.8282 | 26724
46358 | 430.4689 | 26724
46359 | 408.319 | 26724
46360 | 398.8811 | 26724
46361 | 435.1983 | 26724
46362 | 414.8823 | 26724
46363 | 414.5247 | 26724
46364 | 410.4997 | 26724
46365 | 426.7718 | 26724
46366 | 426.4115 | 26724
46367 | 412.7942 | 26724
46368 | 402.3852 | 26724
46369 | 403.3357 | 26724
46370 | 418.6186 | 26724
46371 | 422.3936 | 26724
46372 | 429.9592 | 26724
46373 | 415.6496 | 26724
46374 | 422.5999 | 26724
46375 | 420.3689 | 26724
46376 | 418.0377 | 26724
46377 | 413.4137 | 26724
46378 | 408.2162 | 26724
46379 | 414.7864 | 26724
46380 | 420.7045 | 26724
46381 | 401.4215 | 26724
46382 | 421.1664 | 26724
46383 | 422.1113 | 26724
46384 | 414.1564 | 26724
46385 | 405.0778 | 26724
46386 | 425.3847 | 26724
46387 | 414.7105 | 26724
46388 | 417.4718 | 26724
46389 | 401.0512 | 26724
46390 | 411.4538 | 26724
46391 | 417.3432 | 26724
46392 | 412.1923 | 26724
46393 | 410.6224 | 26724
46394 | 418.8888 | 26724
46395 | 409.3404 | 26724
46396 | 422.4008 | 26724
46397 | 419.6166 | 26724
46398 | 409.6729 | 26724
46399 | 418.4805 | 26724
46400 | 428.6309 | 26724
46401 | 408.5699 | 26724
46402 | 430.9809 | 26724
46403 | 422.2093 | 26724
46404 | 421.4113 | 26724
46405 | 420.2911 | 26724
46406 | 426.1549 | 26724
46407 | 416.0774 | 26724
46408 | 420.456 | 26724
46409 | 405.9754 | 26724
46410 | 415.6276 | 26724
46411 | 429.0128 | 26724
46412 | 415.8686 | 26724
46413 | 421.1005 | 26724
46414 | 430.954 | 26724
46415 | 413.6667 | 26724
46416 | 409.2555 | 26724
46417 | 422.584 | 26724
46418 | 419.8104 | 26724
46419 | 429.5085 | 26724
46420 | 418.9757 | 26724
46421 | 418.6751 | 26724
46422 | 394.6488 | 26724
46423 | 417.1693 | 26724
46424 | 399.7769 | 26724
46425 | 426.7286 | 26724
46426 | 415.2823 | 26724
46427 | 428.5636 | 26724
46428 | 421.4446 | 26724
46429 | 421.1857 | 26724
46430 | 419.5361 | 26724
46431 | 410.335 | 26724
46432 | 412.3001 | 26724
46433 | 412.6307 | 26724
46434 | 412.0311 | 26724
46435 | 425.8948 | 26724
46436 | 415.4881 | 26724
46437 | 407.1193 | 26724
46438 | 422.3558 | 26724
46439 | 409.9761 | 26724
46440 | 416.1926 | 26724
46441 | 410.1907 | 26724
46442 | 430.5493 | 26724
46443 | 415.6604 | 26724
46444 | 415.5256 | 26724
46445 | 412.9133 | 26724
46446 | 420.18 | 26724
46447 | 417.119 | 26724
46448 | 418.1044 | 26724
46449 | 415.6025 | 26724
46450 | 413.1601 | 26724
46451 | 418.7017 | 26724
46452 | 415.8898 | 26724
46453 | 411.851 | 26724
46454 | 421.826 | 26724
46455 | 410.4508 | 26724
46456 | 418.8296 | 26724
46457 | 423.1779 | 26724
46458 | 421.2473 | 26724
46459 | 416.3748 | 26724
46460 | 416.3883 | 26724
46461 | 408.6986 | 26724
46462 | 426.3715 | 26724
46463 | 417.7604 | 26724
46464 | 418.1012 | 26724
46465 | 426.2641 | 26724
46466 | 415.5872 | 26724
46467 | 409.4468 | 26724
46468 | 418.3569 | 26724
46469 | 410.3882 | 26724
46470 | 425.4351 | 26724
46471 | 423.8244 | 26724
46472 | 431.0456 | 26724
46473 | 427.3084 | 26724
46474 | 408.7484 | 26724
46475 | 413.4887 | 26724
46476 | 404.6698 | 26724
46477 | 422.7826 | 26724
46478 | 412.2708 | 26724
46479 | 423.1595 | 26724
46480 | 420.0206 | 26724
46481 | 423.1071 | 26724
46482 | 425.9338 | 26724
46483 | 412.4526 | 26724
46484 | 405.8293 | 26724
46485 | 412.097 | 26724
46486 | 396.7755 | 26724
46487 | 407.1421 | 26724
46488 | 413.2841 | 26724
46489 | 432.796 | 26724
46490 | 412.0607 | 26724
46491 | 416.5786 | 26724
46492 | 426.9632 | 26724
46493 | 410.6342 | 26724
46494 | 408.5333 | 26724
46495 | 416.33 | 26724
46496 | 412.4569 | 26724
46497 | 414.3781 | 26724
46498 | 413.2196 | 26724
46499 | 407.9186 | 26724
46500 | 424.5029 | 26724
46501 | 413.6042 | 26724
46502 | 414.8478 | 26724
46503 | 421.1529 | 26724
46504 | 420.4567 | 26724
46505 | 421.927 | 26724
46506 | 425.8348 | 26724
46507 | 414.7736 | 26724
46508 | 411.5496 | 26724
46509 | 428.8069 | 26724
46510 | 417.5981 | 26724
46511 | 419.6379 | 26724
46512 | 415.1091 | 26724
46513 | 417.164 | 26724
46514 | 414.3312 | 26724
46515 | 417.7848 | 26724
46516 | 414.0067 | 26724
46517 | 418.3431 | 26724
46518 | 405.5683 | 26724
46519 | 419.9934 | 26724
46520 | 413.892 | 26724
46521 | 423.8516 | 26724
46522 | 427.4155 | 26724
46523 | 423.3673 | 26724
46524 | 416.4974 | 26724
46525 | 404.4973 | 26724
46526 | 415.9857 | 26724
46527 | 417.4785 | 26724
46528 | 407.8536 | 26724
46529 | 419.6754 | 26724
46530 | 402.646 | 26724
46531 | 415.3932 | 26724
46532 | 426.7208 | 26724
46533 | 417.1735 | 26724
46534 | 407.8514 | 26724
46535 | 414.5472 | 26724
46536 | 400.6854 | 26724
46537 | 426.5593 | 26724
46538 | 420.3723 | 26724
46539 | 419.9921 | 26724
46540 | 409.8537 | 26724
46541 | 404.3752 | 26724
46542 | 404.0164 | 26724
46543 | 400.6494 | 26724
46544 | 405.5013 | 26724
46545 | 421.8337 | 26724
46546 | 411.0394 | 26724
46547 | 423.6394 | 26724
46548 | 410.9152 | 26724
46549 | 412.5446 | 26724
46550 | 410.4337 | 26724
46551 | 410.1691 | 26724
46552 | 398.2582 | 26724
46553 | 415.3326 | 26724
46554 | 418.9972 | 26724
46555 | 411.8875 | 26724
46556 | 409.3303 | 26724
46557 | 425.7841 | 26724
46558 | 410.438 | 26724
46559 | 410.186 | 26724
46560 | 415.1706 | 26724
46561 | 410.7285 | 26724
46562 | 419.4516 | 26724
46563 | 421.8613 | 26724
46564 | 415.7079 | 26724
46565 | 425.4201 | 26724
46566 | 402.9986 | 26724
46567 | 422.0293 | 26724
46568 | 407.2854 | 26724
46569 | 410.0201 | 26724
46570 | 424.5913 | 26724
46571 | 403.1674 | 26724
46572 | 411.9512 | 26724
46573 | 422.3552 | 26724
46574 | 417.9112 | 26724
46575 | 421.5786 | 26724
46576 | 407.0624 | 26724
46577 | 416.3844 | 26724
46578 | 414.2875 | 26724
46579 | 405.4603 | 26724
46580 | 407.4126 | 26724
46581 | 428.0535 | 26724
46582 | 425.403 | 26724
46583 | 426.8902 | 26724
46584 | 409.069 | 26724
46585 | 422.0032 | 26724
46586 | 413.8814 | 26724
46587 | 413.4908 | 26724
46588 | 411.7405 | 26724
46589 | 414.0858 | 26724
46590 | 419.8498 | 26724
46591 | 411.8163 | 26724
46592 | 415.3222 | 26724
46593 | 427.8263 | 26724
46594 | 432.2078 | 26724
46595 | 403.382 | 26724
46596 | 413.3601 | 26724
46597 | 414.7806 | 26724
46598 | 412.4096 | 26724
46599 | 405.0873 | 26724
46600 | 404.8274 | 26724
46601 | 412.6734 | 26724
46602 | 419.2272 | 26724
46603 | 417.8926 | 26724
46604 | 414.1184 | 26724
46605 | 408.2534 | 26724
46606 | 403.5559 | 26724
46607 | 405.1217 | 26724
46608 | 405.623 | 26724
46609 | 417.0783 | 26724
46610 | 413.538 | 26724
46611 | 410.0099 | 26724
46612 | 421.8689 | 26724
46613 | 424.7239 | 26724
46614 | 406.6644 | 26724
46615 | 422.0349 | 26724
46616 | 411.9299 | 26724
46617 | 412.0904 | 26724
46618 | 413.3753 | 26724
46619 | 408.4168 | 26724
46620 | 418.2443 | 26724
46621 | 400.8067 | 26724
46622 | 418.767 | 26724
46623 | 416.0118 | 26724
46624 | 418.6876 | 26724
46625 | 417.0823 | 26724
46626 | 437.246 | 26724
46627 | 400.4884 | 26724
46628 | 414.3844 | 26724
46629 | 418.6997 | 26724
46630 | 417.1652 | 26724
46631 | 434.0514 | 26724
46632 | 407.2023 | 26724
46633 | 429.104 | 26724
46634 | 416.7091 | 26724
46635 | 413.879 | 26724
46636 | 423.9622 | 26724
46637 | 402.0496 | 26724
46638 | 413.4399 | 26724
46639 | 418.5553 | 26724
46640 | 419.5162 | 26724
46641 | 410.6511 | 26724
46642 | 406.6247 | 26724
46643 | 421.5799 | 26724
46644 | 411.3169 | 26724
46645 | 410.9439 | 26724
46646 | 413.996 | 26724
46647 | 419.5493 | 26724
46648 | 425.9004 | 26724
46649 | 414.0449 | 26724
46650 | 402.2642 | 26724
46651 | 405.958 | 26724
46652 | 405.5245 | 26724
46653 | 423.4817 | 26724
46654 | 425.5745 | 26724
46655 | 415.0228 | 26724
46656 | 405.7953 | 26724
46657 | 412.5708 | 26724
46658 | 403.035 | 26724
46659 | 406.6402 | 26724
46660 | 415.5854 | 26724
46661 | 419.2497 | 26724
46662 | 424.4946 | 26724
46663 | 426.414 | 26724
46664 | 410.7558 | 26724
46665 | 418.8126 | 26724
46666 | 424.7232 | 26724
46667 | 411.0497 | 26724
46668 | 410.211 | 26724
46669 | 418.6117 | 26724
46670 | 422.1357 | 26724
46671 | 424.0306 | 26724
46672 | 412.7499 | 26724
46673 | 409.3649 | 26724
46674 | 415.9463 | 26724
46675 | 406.9199 | 26724
46676 | 423.0347 | 26724
46677 | 415.9073 | 26724
46678 | 398.6646 | 26724
46679 | 404.4466 | 26724
46680 | 421.1841 | 26724
46681 | 408.4701 | 26724
46682 | 423.248 | 26724
46683 | 412.1903 | 26724
46684 | 419.3179 | 26724
46685 | 416.084 | 26724
46686 | 424.2849 | 26724
46687 | 407.6373 | 26724
46688 | 416.3866 | 26724
46689 | 414.5713 | 26724
46690 | 417.65 | 26724
46691 | 410.3605 | 26724
46692 | 417.5952 | 26724
46693 | 424.1998 | 26724
46694 | 403.056 | 26724
46695 | 415.4437 | 26724
46696 | 411.8019 | 26724
46697 | 420.8822 | 26724
46698 | 424.2987 | 26724
46699 | 417.6173 | 26724
46700 | 411.5963 | 26724
46701 | 402.663 | 26724
46702 | 406.7628 | 26724
46703 | 437.9073 | 26724
46704 | 404.0073 | 26724
46705 | 427.5603 | 26724
46706 | 413.3515 | 26724
46707 | 400.7314 | 26724
46708 | 399.409 | 26724
46709 | 406.1035 | 26724
46710 | 419.5562 | 26724
46711 | 404.6403 | 26724
46712 | 422.2533 | 26724
46713 | 414.5848 | 26724
46714 | 409.1133 | 26724
46715 | 403.7524 | 26724
46716 | 425.0887 | 26724
46717 | 434.0502 | 26724
46718 | 411.4274 | 26724
46719 | 431.7937 | 26724
46720 | 398.3265 | 26724
46721 | 419.8993 | 26724
46722 | 428.0402 | 26724
46723 | 416.3847 | 26724
46724 | 420.8012 | 26724
46725 | 409.243 | 26724
46726 | 426.4364 | 26724
46727 | 420.2445 | 26724
46728 | 414.5816 | 26724
46729 | 416.1203 | 26724
46730 | 414.7728 | 26724
46731 | 425.5841 | 26724
46732 | 416.4688 | 26724
46733 | 401.057 | 26724
46734 | 409.9261 | 26724
46735 | 426.4188 | 26724
46736 | 410.4871 | 26724
46737 | 405.6217 | 26724
46738 | 410.9287 | 26724
46739 | 414.8768 | 26724
46740 | 413.2186 | 26724
46741 | 417.4637 | 26724
46742 | 402.0485 | 26724
46743 | 409.8272 | 26724
46744 | 409.3011 | 26724
46745 | 414.7217 | 26724
46746 | 405.5805 | 26724
46747 | 428.7223 | 26724
46748 | 422.4815 | 26724
46749 | 422.5752 | 26724
46750 | 417.7773 | 26724
46751 | 416.0769 | 26724
46752 | 425.8152 | 26724
46753 | 409.7195 | 26724
46754 | 415.8872 | 26724
46755 | 406.5391 | 26724
46756 | 430.7776 | 26724
46757 | 427.3526 | 26724
46758 | 413.4116 | 26724
46759 | 413.3557 | 26724
46760 | 410.7981 | 26724
46761 | 420.6369 | 26724
46762 | 406.3779 | 26724
46763 | 415.5935 | 26724
46764 | 396.0919 | 26724
46765 | 409.1129 | 26724
46766 | 413.1813 | 26724
46767 | 416.5373 | 26724
46768 | 422.7811 | 26724
46769 | 415.6112 | 26724
46770 | 405.201 | 26724
46771 | 421.4964 | 26724
46772 | 415.3217 | 26724
46773 | 429.8836 | 26724
46774 | 416.6368 | 26724
46775 | 414.9409 | 26724
46776 | 423.9642 | 26724
46777 | 424.9556 | 26724
46778 | 426.7257 | 26724
46779 | 415.9546 | 26724
46780 | 406.793 | 26724
46781 | 418.3735 | 26724
46782 | 414.577 | 26724
46783 | 429.5967 | 26724
46784 | 416.0342 | 26724
46785 | 405.3599 | 26724
46786 | 420.5606 | 26724
46787 | 413.3001 | 26724
46788 | 415.0222 | 26724
46789 | 426.0717 | 26724
46790 | 416.042 | 26724
46791 | 406.3128 | 26724
46792 | 415.2689 | 26724
46793 | 418.5464 | 26724
46794 | 412.7041 | 26724
46795 | 413.3856 | 26724
46796 | 418.0318 | 26724
46797 | 412.8073 | 26724
46798 | 422.7639 | 26724
46799 | 405.9106 | 26724
46800 | 412.5042 | 26724
46801 | 416.634 | 26724
46802 | 417.7451 | 26724
46803 | 403.2751 | 26724
46804 | 398.0476 | 26724
46805 | 413.0399 | 26724
46806 | 430.1739 | 26724
46807 | 409.2135 | 26724
46808 | 420.7394 | 26724
46809 | 412.0072 | 26724
46810 | 421.7641 | 26724
46811 | 415.8075 | 26724
46812 | 424.4353 | 26724
46813 | 411.8564 | 26724
46814 | 419.0643 | 26724
46815 | 420.8293 | 26724
46816 | 427.8403 | 26724
46817 | 417.4022 | 26724
46818 | 417.3993 | 26724
46819 | 419.0922 | 26724
46820 | 417.5401 | 26724
46821 | 425.7428 | 26724
46822 | 419.5481 | 26724
46823 | 412.322 | 26724
46824 | 405.9857 | 26724
46825 | 417.8445 | 26724
46826 | 415.7818 | 26724
46827 | 416.5132 | 26724
46828 | 428.051 | 26724
46829 | 421.2356 | 26724
46830 | 406.6044 | 26724
46831 | 422.7485 | 26724
46832 | 426.2847 | 26724
46833 | 410.9432 | 26724
46834 | 411.1251 | 26724
46835 | 422.4055 | 26724
46836 | 427.4143 | 26724
46837 | 425.4334 | 26724
46838 | 414.1149 | 26724
46839 | 407.1136 | 26724
46840 | 416.9891 | 26724
46841 | 415.2848 | 26724
46842 | 426.056 | 26724
46843 | 419.2193 | 26724
46844 | 415.2123 | 26724
46845 | 405.7412 | 26724
46846 | 409.9045 | 26724
46847 | 429.7903 | 26724
46848 | 422.618 | 26724
46849 | 410.977 | 26724
46850 | 420.5041 | 26724
46851 | 419.3557 | 26724
46852 | 420.257 | 26724
46853 | 414.1696 | 26724
46854 | 413.9109 | 26724
46855 | 408.6064 | 26724
46856 | 415.7494 | 26724
46857 | 412.3856 | 26724
46858 | 408.5107 | 26724
46859 | 422.8896 | 26724
46860 | 422.1678 | 26724
46861 | 412.4146 | 26724
46862 | 404.7474 | 26724
46863 | 413.3798 | 26724
46864 | 413.2609 | 26724
46865 | 419.9572 | 26724
46866 | 422.1084 | 26724
46867 | 417.3147 | 26724
46868 | 410.4894 | 26724
46869 | 420.6545 | 26724
46870 | 409.5712 | 26724
46871 | 412.3283 | 26724
46872 | 408.3725 | 26724
46873 | 418.0353 | 26724
46874 | 401.043 | 26724
46875 | 422.5511 | 26724
46876 | 411.3277 | 26724
46877 | 434.7495 | 26724
46878 | 421.559 | 26724
46879 | 415.3044 | 26724
46880 | 422.2374 | 26724
46881 | 404.4448 | 26724
46882 | 430.3851 | 26724
46883 | 420.1073 | 26724
46884 | 419.5149 | 26724
46885 | 415.9892 | 26724
46886 | 416.0727 | 26724
46887 | 421.5247 | 26724
46888 | 404.009 | 26724
46889 | 410.0672 | 26724
46890 | 405.5272 | 26724
46891 | 409.3213 | 26724
46892 | 417.914 | 26724
46893 | 412.1137 | 26724
46894 | 418.6887 | 26724
46895 | 410.2391 | 26724
46896 | 410.9704 | 26724
46897 | 420.3492 | 26724
46898 | 417.2008 | 26724
46899 | 410.6919 | 26724
46900 | 430.2105 | 26724
46901 | 412.6101 | 26724
46902 | 418.4858 | 26724
46903 | 410.4713 | 26724
46904 | 425.7542 | 26724
46905 | 418.4032 | 26724
46906 | 409.6705 | 26724
46907 | 407.5023 | 26724
46908 | 415.2344 | 26724
46909 | 427.4452 | 26724
46910 | 418.6403 | 26724
46911 | 406.5309 | 26724
46912 | 423.9463 | 26724
46913 | 415.44 | 26724
46914 | 423.2197 | 26724
46915 | 408.5321 | 26724
46916 | 414.7652 | 26724
46917 | 401.1613 | 26724
46918 | 419.1708 | 26724
46919 | 414.9118 | 26724
46920 | 422.9528 | 26724
46921 | 420.4042 | 26724
46922 | 421.6849 | 26724
46923 | 409.7402 | 26724
46924 | 405.6068 | 26724
46925 | 414.2731 | 26724
46926 | 413.6413 | 26724
46927 | 420.0505 | 26724
46928 | 412.4741 | 26724
46929 | 419.5084 | 26724
46930 | 407.6806 | 26724
46931 | 433.7972 | 26724
46932 | 434.541 | 26724
46933 | 410.3363 | 26724
46934 | 402.6241 | 26724
46935 | 410.8523 | 26724
46936 | 428.8015 | 26724
46937 | 416.3858 | 26724
46938 | 412.5366 | 26724
46939 | 413.6409 | 26724
46940 | 412.8143 | 26724
46941 | 420.645 | 26724
46942 | 423.5352 | 26724
46943 | 430.0887 | 26724
46944 | 422.4113 | 26724
46945 | 411.3457 | 26724
46946 | 424.0257 | 26724
46947 | 419.5477 | 26724
46948 | 405.9083 | 26724
46949 | 424.4884 | 26724
46950 | 427.7504 | 26724
46951 | 405.877 | 26724
46952 | 426.5796 | 26724
46953 | 420.3826 | 26724
46954 | 417.7728 | 26724
46955 | 417.1328 | 26724
46956 | 414.7312 | 26724
46957 | 422.0518 | 26724
46958 | 412.9192 | 26724
46959 | 415.874 | 26724
46960 | 408.7809 | 26724
46961 | 406.0139 | 26724
46962 | 424.9534 | 26724
46963 | 409.7926 | 26724
46964 | 419.7578 | 26724
46965 | 417.3724 | 26724
46966 | 413.067 | 26724
46967 | 421.3031 | 26724
46968 | 412.009 | 26724
46969 | 411.0555 | 26724
46970 | 408.7579 | 26724
46971 | 430.0734 | 26724
46972 | 414.1894 | 26724
46973 | 409.678 | 26724
46974 | 411.1892 | 26724
46975 | 408.0054 | 26724
46976 | 409.5696 | 26724
46977 | 423.8162 | 26724
46978 | 405.1349 | 26724
46979 | 400.6403 | 26724
46980 | 412.725 | 26724
46981 | 418.9361 | 26724
46982 | 408.6401 | 26724
46983 | 422.7299 | 26724
46984 | 411.6986 | 26724
46985 | 411.9942 | 26724
46986 | 419.0084 | 26724
46987 | 411.3099 | 26724
46988 | 420.2986 | 26724
46989 | 416.3831 | 26724
46990 | 416.5614 | 26724
46991 | 404.4652 | 26724
46992 | 411.7195 | 26724
46993 | 412.896 | 26724
46994 | 415.3839 | 26724
46995 | 426.0278 | 26724
46996 | 431.0659 | 26724
46997 | 400.2412 | 26724
46998 | 421.4978 | 26724
46999 | 403.298 | 26724
47000 | 408.5074 | 26724
47001 | 418.0234 | 26724
47002 | 415.1808 | 26724
47003 | 429.5061 | 26724
47004 | 412.7311 | 26724
47005 | 426.3152 | 26724
47006 | 417.564 | 26724
47007 | 404.5613 | 26724
47008 | 405.3824 | 26724
47009 | 406.2022 | 26724
47010 | 407.419 | 26724
47011 | 416.799 | 26724
47012 | 418.8329 | 26724
47013 | 418.8159 | 26724
47014 | 413.0799 | 26724
47015 | 418.0964 | 26724
47016 | 414.339 | 26724
47017 | 419.0913 | 26724
47018 | 421.4029 | 26724
47019 | 409.4981 | 26724
47020 | 415.908 | 26724
47021 | 410.4079 | 26724
47022 | 416.028 | 26724
47023 | 426.6693 | 26724
47024 | 419.1523 | 26724
47025 | 412.5274 | 26724
47026 | 410.7874 | 26724
47027 | 407.0666 | 26724
47028 | 417.5431 | 26724
47029 | 407.8942 | 26724
47030 | 401.1639 | 26724
47031 | 416.5268 | 26724
47032 | 419.2079 | 26724
47033 | 413.6143 | 26724
47034 | 420.1123 | 26724
47035 | 403.6231 | 26724
47036 | 397.6929 | 26724
47037 | 417.6254 | 26724
47038 | 411.5916 | 26724
47039 | 412.6126 | 26724
47040 | 414.7789 | 26724
47041 | 426.2033 | 26724
47042 | 413.9967 | 26724
47043 | 410.2077 | 26724
47044 | 405.6216 | 26724
47045 | 410.725 | 26724
47046 | 400.2202 | 26724
47047 | 433.4838 | 26724
47048 | 426.7826 | 26724
47049 | 411.8029 | 26724
47050 | 425.3494 | 26724
47051 | 423.9611 | 26724
47052 | 407.5552 | 26724
47053 | 414.9887 | 26724
47054 | 423.6666 | 26724
47055 | 410.5074 | 26724
47056 | 414.188 | 26724
47057 | 413.4428 | 26724
47058 | 409.3956 | 26724
47059 | 429.562 | 26724
47060 | 409.2014 | 26724
47061 | 409.4541 | 26724
47062 | 412.1895 | 26724
47063 | 416.8574 | 26724
47064 | 427.0797 | 26724
47065 | 400.2304 | 26724
47066 | 411.9238 | 26724
47067 | 407.09 | 26724
47068 | 419.1349 | 26724
47069 | 425.2128 | 26724
47070 | 420.0729 | 26724
47071 | 412.3161 | 26724
47072 | 409.079 | 26724
47073 | 407.7439 | 26724
47074 | 411.2906 | 26724
47075 | 397.3079 | 26724
47076 | 414.6435 | 26724
47077 | 433.7814 | 26724
47078 | 410.7721 | 26724
47079 | 419.6815 | 26724
47080 | 416.1903 | 26724
47081 | 409.9523 | 26724
47082 | 399.1416 | 26724
47083 | 422.9894 | 26724
47084 | 416.974 | 26724
47085 | 402.4572 | 26724
47086 | 419.8479 | 26724
47087 | 409.7227 | 26724
47088 | 405.1168 | 26724
47089 | 407.4705 | 26724
47090 | 415.8231 | 26724
47091 | 415.5151 | 26724
47092 | 404.7283 | 26724
47093 | 420.9403 | 26724
47094 | 411.3339 | 26724
47095 | 399.373 | 26724
47096 | 429.0707 | 26724
47097 | 419.3724 | 26724
47098 | 419.7727 | 26724
47099 | 407.846 | 26724
47100 | 429.442 | 26724
47101 | 409.5287 | 26724
47102 | 417.077 | 26724
47103 | 427.485 | 26724
47104 | 423.4676 | 26724
47105 | 412.9412 | 26724
47106 | 420.554 | 26724
47107 | 427.1805 | 26724
47108 | 422.4959 | 26724
47109 | 407.3549 | 26724
47110 | 414.4703 | 26724
47111 | 428.8651 | 26724
47112 | 406.1254 | 26724
47113 | 427.0679 | 26724
47114 | 415.0519 | 26724
47115 | 408.7031 | 26724
47116 | 413.1817 | 26724
47117 | 426.4599 | 26724
47118 | 414.6459 | 26724
47119 | 419.987 | 26724
47120 | 425.5839 | 26724
47121 | 416.6463 | 26724
47122 | 418.702 | 26724
47123 | 423.7716 | 26724
47124 | 415.3017 | 26724
47125 | 413.4743 | 26724
47126 | 418.747 | 26724
47127 | 424.0009 | 26724
47128 | 403.2618 | 26724
47129 | 419.126 | 26724
47130 | 424.0284 | 26724
47131 | 433.2545 | 26724
47132 | 427.282 | 26724
47133 | 415.6774 | 26724
47134 | 426.3197 | 26724
47135 | 410.7688 | 26724
47136 | 426.0836 | 26724
47137 | 415.376 | 26724
47138 | 417.2028 | 26724
47139 | 414.606 | 26724
47140 | 419.0304 | 26724
47141 | 420.0234 | 26724
47142 | 412.3464 | 26724
47143 | 410.8474 | 26724
47144 | 399.6836 | 26724
47145 | 421.4966 | 26724
47146 | 428.9729 | 26724
47147 | 422.2426 | 26724
47148 | 414.9112 | 26724
47149 | 429.4792 | 26724
47150 | 411.0443 | 26724
47151 | 424.0071 | 26724
47152 | 400.8655 | 26724
47153 | 412.9125 | 26724
47154 | 414.4853 | 26724
47155 | 399.9544 | 26724
47156 | 424.2071 | 26724
47157 | 405.0243 | 26724
47158 | 412.2244 | 26724
47159 | 414.4723 | 26724
47160 | 411.5791 | 26724
47161 | 411.6674 | 26724
47162 | 413.4229 | 26724
47163 | 412.6602 | 26724
47164 | 419.2169 | 26724
47165 | 416.6171 | 26724
47166 | 411.4232 | 26724
47167 | 415.1715 | 26724
47168 | 426.8603 | 26724
47169 | 407.1866 | 26724
47170 | 415.4796 | 26724
47171 | 423.1817 | 26724
47172 | 397.7696 | 26724
47173 | 432.0757 | 26724
47174 | 414.5076 | 26724
47175 | 422.4934 | 26724
47176 | 427.6047 | 26724
47177 | 420.0589 | 26724
47178 | 411.6423 | 26724
47179 | 424.7354 | 26724
47180 | 410.6814 | 26724
47181 | 420.351 | 26724
47182 | 416.4822 | 26724
47183 | 416.1905 | 26724
47184 | 414.6868 | 26724
47185 | 430.7667 | 26724
47186 | 414.8062 | 26724
47187 | 417.0063 | 26724
47188 | 418.1903 | 26724
47189 | 438.7054 | 26724
47190 | 408.2724 | 26724
47191 | 422.5482 | 26724
47192 | 418.7414 | 26724
47193 | 411.8918 | 26724
47194 | 409.9469 | 26724
47195 | 412.9681 | 26724
47196 | 411.6196 | 26724
47197 | 412.0202 | 26724
47198 | 415.3163 | 26724
47199 | 416.0647 | 26724
47200 | 408.6743 | 26724
47201 | 411.1994 | 26724
47202 | 405.6538 | 26724
47203 | 417.3369 | 26724
47204 | 425.1554 | 26724
47205 | 409.1776 | 26724
47206 | 414.7537 | 26724
47207 | 418.298 | 26724
47208 | 418.7722 | 26724
47209 | 419.6427 | 26724
47210 | 418.1224 | 26724
47211 | 406.9482 | 26724
47212 | 423.0919 | 26724
47213 | 426.3594 | 26724
47214 | 399.2368 | 26724
47215 | 425.2423 | 26724
47216 | 409.1201 | 26724
47217 | 421.9103 | 26724
47218 | 409.302 | 26724
47219 | 411.3109 | 26724
47220 | 426.8132 | 26724
47221 | 424.8752 | 26724
47222 | 413.3382 | 26724
47223 | 425.0073 | 26724
47224 | 417.301 | 26724
47225 | 407.083 | 26724
47226 | 419.4129 | 26724
47227 | 427.5932 | 26724
47228 | 403.773 | 26724
47229 | 407.9666 | 26724
47230 | 419.2775 | 26724
47231 | 418.2616 | 26724
47232 | 419.5929 | 26724
47233 | 406.2356 | 26724
47234 | 413.3281 | 26724
47235 | 404.3968 | 26724
47236 | 405.2102 | 26724
47237 | 416.5 | 26724
47238 | 416.1711 | 26724
47239 | 424.0207 | 26724
47240 | 417.5535 | 26724
47241 | 413.3675 | 26724
47242 | 410.3647 | 26724
47243 | 427.1047 | 26724
47244 | 412.9045 | 26724
47245 | 400.7343 | 26724
47246 | 426.2698 | 26724
47247 | 417.1992 | 26724
47248 | 421.0033 | 26724
47249 | 429.4581 | 26724
47250 | 426.0436 | 26724
47251 | 422.719 | 26724
47252 | 418.4126 | 26724
47253 | 402.0566 | 26724
47254 | 405.422 | 26724
47255 | 414.2476 | 26724
47256 | 413.5323 | 26724
47257 | 401.7755 | 26724
47258 | 426.3672 | 26724
47259 | 413.4565 | 26724
47260 | 418.0412 | 26724
47261 | 408.9947 | 26724
47262 | 407.7007 | 26724
47263 | 409.1489 | 26724
47264 | 425.4839 | 26724
47265 | 421.8571 | 26724
47266 | 413.876 | 26724
47267 | 411.8995 | 26724
47268 | 407.5521 | 26724
47269 | 412.1189 | 26724
47270 | 421.8924 | 26724
47271 | 411.0707 | 26724
47272 | 413.9361 | 26724
47273 | 418.0951 | 26724
47274 | 417.1173 | 26724
47275 | 413.1937 | 26724
47276 | 413.397 | 26724
47277 | 424.3829 | 26724
47278 | 416.1786 | 26724
47279 | 408.5705 | 26724
47280 | 416.5378 | 26724
47281 | 417.9001 | 26724
47282 | 409.3045 | 26724
47283 | 416.4583 | 26724
47284 | 407.4793 | 26724
47285 | 428.2989 | 26724
47286 | 431.8581 | 26724
47287 | 417.1189 | 26724
47288 | 413.3768 | 26724
47289 | 410.7545 | 26724
47290 | 420.2586 | 26724
47291 | 425.864 | 26724
47292 | 413.03 | 26724
47293 | 423.7407 | 26724
47294 | 404.702 | 26724
47295 | 409.8951 | 26724
47296 | 425.567 | 26724
47297 | 434.7039 | 26724
47298 | 410.9298 | 26724
47299 | 431.5887 | 26724
47300 | 424.3494 | 26724
47301 | 427.2748 | 26724
47302 | 412.7936 | 26724
47303 | 401.8174 | 26724
47304 | 428.477 | 26724
47305 | 411.9244 | 26724
47306 | 428.4039 | 26724
47307 | 421.3647 | 26724
47308 | 413.1481 | 26724
47309 | 407.0045 | 26724
47310 | 411.2364 | 26724
47311 | 415.7773 | 26724
47312 | 401.1922 | 26724
47313 | 409.3338 | 26724
47314 | 414.4722 | 26724
47315 | 419.1985 | 26724
47316 | 402.171 | 26724
47317 | 402.7608 | 26724
47318 | 425.7424 | 26724
47319 | 409.466 | 26724
47320 | 420.5034 | 26724
47321 | 418.8263 | 26724
47322 | 407.0783 | 26724
47323 | 431.0223 | 26724
47324 | 421.8007 | 26724
47325 | 419.6135 | 26724
47326 | 428.393 | 26724
47327 | 409.4007 | 26724
47328 | 413.0707 | 26724
47329 | 414.6357 | 26724
47330 | 408.1614 | 26724
47331 | 412.4487 | 26724
47332 | 418.9744 | 26724
47333 | 411.5915 | 26724
47334 | 426.4568 | 26724
47335 | 423.6129 | 26724
47336 | 419.7962 | 26724
47337 | 421.4179 | 26724
47338 | 412.6566 | 26724
47339 | 410.7136 | 26724
47340 | 416.0812 | 26724
47341 | 417.555 | 26724
47342 | 405.6806 | 26724
47343 | 425.2995 | 26724
47344 | 407.8727 | 26724
47345 | 427.2384 | 26724
47346 | 423.471 | 26724
47347 | 428.1302 | 26724
47348 | 427.1766 | 26724
47349 | 421.1027 | 26724
47350 | 425.1319 | 26724
47351 | 409.0288 | 26724
47352 | 428.0104 | 26724
47353 | 421.8521 | 26724
47354 | 407.277 | 26724
47355 | 403.2069 | 26724
47356 | 415.7264 | 26724
47357 | 410.3009 | 26724
47358 | 427.6209 | 26724
47359 | 401.7947 | 26724
47360 | 415.7925 | 26724
47361 | 412.8809 | 26724
47362 | 415.4949 | 26724
47363 | 409.6085 | 26724
47364 | 399.4415 | 26724
47365 | 424.5291 | 26724
47366 | 406.754 | 26724
47367 | 412.1336 | 26724
47368 | 412.9132 | 26724
47369 | 420.8714 | 26724
47370 | 394.4168 | 26724
47371 | 426.9572 | 26724
47372 | 410.2861 | 26724
47373 | 416.665 | 26724
47374 | 421.2482 | 26724
47375 | 415.1471 | 26724
47376 | 415.7172 | 26724
47377 | 410.0271 | 26724
47378 | 432.9025 | 26724
47379 | 416.9578 | 26724
47380 | 404.7726 | 26724
47381 | 424.3858 | 26724
47382 | 420.0954 | 26724
47383 | 425.1939 | 26724
47384 | 414.1478 | 26724
47385 | 407.8426 | 26724
47386 | 418.8652 | 26724
47387 | 420.8389 | 26724
47388 | 420.9557 | 26724
47389 | 412.3004 | 26724
47390 | 424.1082 | 26724
47391 | 414.1646 | 26724
47392 | 416.3078 | 26724
47393 | 433.0786 | 26724
47394 | 415.0224 | 26724
47395 | 418.3276 | 26724
47396 | 428.5693 | 26724
47397 | 413.0988 | 26724
47398 | 404.631 | 26724
47399 | 413.1191 | 26724
47400 | 410.6253 | 26724
47401 | 416.8633 | 26724
47402 | 401.753 | 26724
47403 | 404.6469 | 26724
47404 | 411.1087 | 26724
47405 | 416.5664 | 26724
47406 | 416.5859 | 26724
47407 | 401.7819 | 26724
47408 | 416.3371 | 26724
47409 | 430.8795 | 26724
47410 | 411.3812 | 26724
47411 | 407.6474 | 26724
47412 | 407.4344 | 26724
47413 | 419.6385 | 26724
47414 | 419.8788 | 26724
47415 | 413.4639 | 26724
47416 | 413.9396 | 26724
47417 | 410.8092 | 26724
47418 | 415.5814 | 26724
47419 | 423.4952 | 26724
47420 | 418.8607 | 26724
47421 | 408.6196 | 26724
47422 | 420.0174 | 26724
47423 | 427.5153 | 26724
47424 | 420.3034 | 26724
47425 | 419.8628 | 26724
47426 | 409.485 | 26724
47427 | 424.3543 | 26724
47428 | 425.0767 | 26724
47429 | 423.3095 | 26724
47430 | 411.9516 | 26724
47431 | 412.5482 | 26724
47432 | 418.0149 | 26724
47433 | 416.98 | 26724
47434 | 407.4149 | 26724
47435 | 419.4577 | 26724
47436 | 416.6045 | 26724
47437 | 407.7787 | 26724
47438 | 407.3117 | 26724
47439 | 421.7685 | 26724
47440 | 422.867 | 26724
47441 | 418.6877 | 26724
47442 | 405.5342 | 26724
47443 | 424.2992 | 26724
47444 | 426.6682 | 26724
47445 | 412.2522 | 26724
47446 | 414.3439 | 26724
47447 | 426.0285 | 26724
47448 | 420.6549 | 26724
47449 | 416.857 | 26724
47450 | 416.1232 | 26724
47451 | 411.636 | 26724
47452 | 417.7018 | 26724
47453 | 406.1171 | 26724
47454 | 425.5033 | 26724
47455 | 424.8243 | 26724
47456 | 420.8485 | 26724
47457 | 401.7168 | 26724
47458 | 424.4241 | 26724
47459 | 425.5797 | 26724
47460 | 408.0669 | 26724
47461 | 427.2202 | 26724
47462 | 427.1185 | 26724
47463 | 413.5235 | 26724
47464 | 420.7046 | 26724
47465 | 411.5533 | 26724
47466 | 406.077 | 26724
47467 | 417.5293 | 26724
47468 | 404.8102 | 26724
47469 | 419.8984 | 26724
47470 | 418.4246 | 26724
47471 | 427.504 | 26724
47472 | 409.0033 | 26724
47473 | 416.947 | 26724
47474 | 414.7442 | 26724
47475 | 412.6515 | 26724
47476 | 417.8818 | 26724
47477 | 417.3563 | 26724
47478 | 411.0431 | 26724
47479 | 398.2869 | 26724
47480 | 415.475 | 26724
47481 | 408.0322 | 26724
47482 | 407.8365 | 26724
47483 | 419.888 | 26724
47484 | 414.7098 | 26724
47485 | 420.0641 | 26724
47486 | 426.3761 | 26724
47487 | 402.8096 | 26724
47488 | 428.2053 | 26724
47489 | 418.5912 | 26724
47490 | 434.1009 | 26724
47491 | 404.3082 | 26724
47492 | 432.2752 | 26724
47493 | 426.991 | 26724
47494 | 414.4659 | 26724
47495 | 419.2929 | 26724
47496 | 412.8591 | 26724
47497 | 422.4741 | 26724
47498 | 429.9435 | 26724
47499 | 424.1795 | 26724
47500 | 421.972 | 26724
47501 | 403.935 | 26724
47502 | 407.2764 | 26724
47503 | 415.229 | 26724
47504 | 430.1935 | 26724
47505 | 406.513 | 26724
47506 | 416.7002 | 26724
47507 | 409.8112 | 26724
47508 | 404.9641 | 26724
47509 | 436.5407 | 26724
47510 | 417.6794 | 26724
47511 | 410.7215 | 26724
47512 | 421.4501 | 26724
47513 | 412.5333 | 26724
47514 | 426.3508 | 26724
47515 | 407.795 | 26724
47516 | 421.4042 | 26724
47517 | 415.8794 | 26724
47518 | 412.4621 | 26724
47519 | 411.9491 | 26724
47520 | 423.8757 | 26724
47521 | 417.3023 | 26724
47522 | 414.6602 | 26724
47523 | 408.9484 | 26724
47524 | 414.0095 | 26724
47525 | 415.0481 | 26724
47526 | 419.9132 | 26724
47527 | 416.8516 | 26724
47528 | 426.1343 | 26724
47529 | 413.3214 | 26724
47530 | 429.1797 | 26724
47531 | 403.6176 | 26724
47532 | 416.253 | 26724
47533 | 405.7602 | 26724
47534 | 419.5276 | 26724
47535 | 406.1301 | 26724
47536 | 416.9121 | 26724
47537 | 408.6186 | 26724
47538 | 424.0966 | 26724
47539 | 409.3091 | 26724
47540 | 418.5611 | 26724
47541 | 424.2614 | 26724
47542 | 410.4633 | 26724
47543 | 421.1155 | 26724
47544 | 412.9362 | 26724
47545 | 417.0158 | 26724
47546 | 415.9516 | 26724
47547 | 426.755 | 26724
47548 | 412.5723 | 26724
47549 | 406.376 | 26724
47550 | 417.1685 | 26724
47551 | 402.681 | 26724
47552 | 408.8567 | 26724
47553 | 408.0751 | 26724
47554 | 405.8465 | 26724
47555 | 404.4582 | 26724
47556 | 426.1788 | 26724
47557 | 401.5501 | 26724
47558 | 426.8201 | 26724
47559 | 433.0025 | 26724
47560 | 423.3988 | 26724
47561 | 425.9374 | 26724
47562 | 410.5531 | 26724
47563 | 428.6412 | 26724
47564 | 402.5198 | 26724
47565 | 409.421 | 26724
47566 | 417.2926 | 26724
47567 | 408.0329 | 26724
47568 | 421.3737 | 26724
47569 | 409.5523 | 26724
47570 | 416.4642 | 26724
47571 | 426.1738 | 26724
47572 | 399.4193 | 26724
47573 | 422.2606 | 26724
47574 | 411.8214 | 26724
47575 | 418.3046 | 26724
47576 | 433.3251 | 26724
47577 | 416.0882 | 26724
47578 | 415.5685 | 26724
47579 | 425.0744 | 26724
47580 | 415.07 | 26724
47581 | 416.7112 | 26724
47582 | 424.926 | 26724
47583 | 410.7855 | 26724
47584 | 416.682 | 26724
47585 | 429.4618 | 26724
47586 | 405.9545 | 26724
47587 | 419.4552 | 26724
47588 | 421.5868 | 26724
47589 | 409.8658 | 26724
47590 | 419.0476 | 26724
47591 | 416.9769 | 26724
47592 | 407.2143 | 26724
47593 | 422.5533 | 26724
47594 | 412.054 | 26724
47595 | 423.8973 | 26724
47596 | 429.4019 | 26724
47597 | 411.1397 | 26724
47598 | 417.4181 | 26724
47599 | 409.6362 | 26724
47600 | 419.4056 | 26724
47601 | 419.7433 | 26724
47602 | 426.9345 | 26724
47603 | 421.288 | 26724
47604 | 413.7172 | 26724
47605 | 406.7676 | 26724
47606 | 418.4758 | 26724
47607 | 410.5114 | 26724
47608 | 413.9111 | 26724
47609 | 418.6429 | 26724
47610 | 410.0571 | 26724
47611 | 427.7209 | 26724
47612 | 412.8693 | 26724
47613 | 407.2583 | 26724
47614 | 427.6144 | 26724
47615 | 420.7123 | 26724
47616 | 412.2792 | 26724
47617 | 418.2802 | 26724
47618 | 433.6941 | 26724
47619 | 404.436 | 26724
47620 | 411.6661 | 26724
47621 | 412.5238 | 26724
47622 | 407.7853 | 26724
47623 | 421.3704 | 26724
47624 | 419.2744 | 26724
47625 | 412.0311 | 26724
47626 | 406.9917 | 26724
47627 | 412.9441 | 26724
47628 | 408.1434 | 26724
47629 | 414.6387 | 26724
47630 | 418.1917 | 26724
47631 | 424.2087 | 26724
47632 | 427.4296 | 26724
47633 | 435.9018 | 26724
47634 | 416.5055 | 26724
47635 | 423.016 | 26724
47636 | 419.1194 | 26724
47637 | 422.3128 | 26724
47638 | 420.778 | 26724
47639 | 407.3777 | 26724
47640 | 412.8196 | 26724
47641 | 416.4038 | 26724
47642 | 432.9293 | 26724
47643 | 416.0182 | 26724
47644 | 414.2932 | 26724
47645 | 405.666 | 26724
47646 | 408.6799 | 26724
47647 | 402.7297 | 26724
47648 | 429.9297 | 26724
47649 | 402.5828 | 26724
47650 | 422.2475 | 26724
47651 | 425.6283 | 26724
47652 | 417.4477 | 26724
47653 | 415.6509 | 26724
47654 | 415.326 | 26724
47655 | 411.5724 | 26724
47656 | 408.3857 | 26724
47657 | 429.2616 | 26724
47658 | 419.1817 | 26724
47659 | 401.7228 | 26724
47660 | 430.2916 | 26724
47661 | 421.6747 | 26724
47662 | 420.0853 | 26724
47663 | 423.5452 | 26724
47664 | 421.5037 | 26724
47665 | 429.6449 | 26724
47666 | 411.8818 | 26724
47667 | 421.4684 | 26724
47668 | 402.3553 | 26724
47669 | 427.9442 | 26724
47670 | 409.566 | 26724
47671 | 428.2662 | 26724
47672 | 406.5796 | 26724
47673 | 413.5916 | 26724
47674 | 416.6293 | 26724
47675 | 405.529 | 26724
47676 | 418.6044 | 26724
47677 | 411.5536 | 26724
47678 | 404.3719 | 26724
47679 | 415.7903 | 26724
47680 | 405.4425 | 26724
47681 | 426.5142 | 26724
47682 | 417.7726 | 26724
47683 | 409.3137 | 26724
47684 | 424.5128 | 26724
47685 | 412.1169 | 26724
47686 | 416.1667 | 26724
47687 | 413.5727 | 26724
47688 | 409.6486 | 26724
47689 | 424.94 | 26724
47690 | 411.8647 | 26724
47691 | 411.1585 | 26724
47692 | 411.959 | 26724
47693 | 412.737 | 26724
47694 | 411.3134 | 26724
47695 | 418.7194 | 26724
47696 | 412.9324 | 26724
47697 | 402.9602 | 26724
47698 | 418.8993 | 26724
47699 | 434.5895 | 26724
47700 | 411.5537 | 26724
47701 | 430.2164 | 26724
47702 | 426.1558 | 26724
47703 | 411.1845 | 26724
47704 | 422.1342 | 26724
47705 | 413.791 | 26724
47706 | 424.4092 | 26724
47707 | 406.7275 | 26724
47708 | 412.1454 | 26724
47709 | 420.5926 | 26724
47710 | 424.6861 | 26724
47711 | 412.3205 | 26724
47712 | 409.5369 | 26724
47713 | 408.3599 | 26724
47714 | 408.4892 | 26724
47715 | 430.8378 | 26724
47716 | 417.7092 | 26724
47717 | 412.2506 | 26724
47718 | 404.5444 | 26724
47719 | 411.5842 | 26724
47720 | 420.5637 | 26724
47721 | 407.3225 | 26724
47722 | 415.5892 | 26724
47723 | 405.8642 | 26724
47724 | 412.471 | 26724
47725 | 426.6396 | 26724
47726 | 417.5771 | 26724
47727 | 417.4594 | 26724
47728 | 409.9255 | 26724
47729 | 418.6389 | 26724
47730 | 411.6431 | 26724
47731 | 414.4068 | 26724
47732 | 408.2238 | 26724
47733 | 416.3661 | 26724
47734 | 426.62 | 26724
47735 | 412.6105 | 26724
47736 | 395.3548 | 26724
47737 | 416.708 | 26724
47738 | 420.1148 | 26724
47739 | 414.6337 | 26724
47740 | 422.1942 | 26724
47741 | 407.1095 | 26724
47742 | 415.862 | 26724
47743 | 425.4738 | 26724
47744 | 427.0727 | 26724
47745 | 418.0701 | 26724
47746 | 432.531 | 26724
47747 | 417.3532 | 26724
47748 | 423.0129 | 26724
47749 | 402.601 | 26724
47750 | 427.5365 | 26724
47751 | 422.4499 | 26724
47752 | 423.7619 | 26724
47753 | 419.7085 | 26724
47754 | 420.6983 | 26724
47755 | 419.151 | 26724
47756 | 407.3702 | 26724
47757 | 416.0042 | 26724
47758 | 420.3476 | 26724
47759 | 428.6612 | 26724
47760 | 418.0211 | 26724
47761 | 406.4731 | 26724
47762 | 420.5796 | 26724
47763 | 412.691 | 26724
47764 | 423.2499 | 26724
47765 | 413.0675 | 26724
47766 | 405.7159 | 26724
47767 | 411.3961 | 26724
47768 | 414.2747 | 26724
47769 | 402.7756 | 26724
47770 | 410.2617 | 26724
47771 | 404.6455 | 26724
47772 | 404.9584 | 26724
47773 | 399.1763 | 26724
47774 | 426.3456 | 26724
47775 | 413.5697 | 26724
47776 | 414.4163 | 26724
47777 | 427.2081 | 26724
47778 | 419.3457 | 26724
47779 | 409.6652 | 26724
47780 | 430.509 | 26724
47781 | 433.5606 | 26724
47782 | 430.1324 | 26724
47783 | 417.7734 | 26724
47784 | 407.101 | 26724
47785 | 428.2634 | 26724
47786 | 422.2129 | 26724
47787 | 421.4178 | 26724
47788 | 405.9421 | 26724
47789 | 430.7734 | 26724
47790 | 411.1596 | 26724
47791 | 419.4972 | 26724
47792 | 417.5841 | 26724
47793 | 414.1179 | 26724
47794 | 405.2102 | 26724
47795 | 412.255 | 26724
47796 | 414.0558 | 26724
47797 | 415.0193 | 26724
47798 | 423.3059 | 26724
47799 | 426.0344 | 26724
47800 | 424.033 | 26724
47801 | 424.6562 | 26724
47802 | 412.9796 | 26724
47803 | 419.8519 | 26724
47804 | 408.6448 | 26724
47805 | 423.2819 | 26724
47806 | 413.3099 | 26724
47807 | 413.372 | 26724
47808 | 420.3049 | 26724
47809 | 418.0821 | 26724
47810 | 428.6655 | 26724
47811 | 432.7867 | 26724
47812 | 400.3117 | 26724
47813 | 426.9112 | 26724
47814 | 407.4577 | 26724
47815 | 429.224 | 26724
47816 | 415.7724 | 26724
47817 | 414.0571 | 26724
47818 | 418.5156 | 26724
47819 | 415.8044 | 26724
47820 | 417.1659 | 26724
47821 | 416.5503 | 26724
47822 | 410.7003 | 26724
47823 | 427.9343 | 26724
47824 | 409.0901 | 26724
47825 | 427.8328 | 26724
47826 | 407.5749 | 26724
47827 | 410.6514 | 26724
47828 | 422.1351 | 26724
47829 | 417.1547 | 26724
47830 | 415.2997 | 26724
47831 | 426.3189 | 26724
47832 | 415.5883 | 26724
47833 | 412.9207 | 26724
47834 | 412.9194 | 26724
47835 | 408.4719 | 26724
47836 | 421.0102 | 26724
47837 | 421.2449 | 26724
47838 | 417.499 | 26724
47839 | 428.616 | 26724
47840 | 424.3126 | 26724
47841 | 411.2316 | 26724
47842 | 418.0655 | 26724
47843 | 415.648 | 26724
47844 | 412.3629 | 26724
47845 | 420.8545 | 26724
47846 | 413.6078 | 26724
47847 | 414.007 | 26724
47848 | 432.6205 | 26724
47849 | 419.2921 | 26724
47850 | 410.6145 | 26724
47851 | 422.3455 | 26724
47852 | 417.408 | 26724
47853 | 414.2324 | 26724
47854 | 424.4923 | 26724
47855 | 413.9947 | 26724
47856 | 407.2678 | 26724
47857 | 398.0633 | 26724
47858 | 419.6542 | 26724
47859 | 411.3727 | 26724
47860 | 413.4989 | 26724
47861 | 413.1693 | 26724
47862 | 422.2047 | 26724
47863 | 432.7067 | 26724
47864 | 414.8585 | 26724
47865 | 425.2746 | 26724
47866 | 423.6471 | 26724
47867 | 417.6377 | 26724
47868 | 403.6503 | 26724
47869 | 416.4702 | 26724
47870 | 416.1739 | 26724
47871 | 422.6713 | 26724
47872 | 421.2217 | 26724
47873 | 423.5913 | 26724
47874 | 412.0742 | 26724
47875 | 423.2896 | 26724
47876 | 409.05 | 26724
47877 | 409.3166 | 26724
47878 | 416.0786 | 26724
47879 | 431.2068 | 26724
47880 | 414.8077 | 26724
47881 | 413.9216 | 26724
47882 | 414.2195 | 26724
47883 | 421.8024 | 26724
47884 | 413.8868 | 26724
47885 | 420.1273 | 26724
47886 | 418.4023 | 26724
47887 | 404.1666 | 26724
47888 | 426.0403 | 26724
47889 | 420.1596 | 26724
47890 | 419.1794 | 26724
47891 | 418.7609 | 26724
47892 | 410.8425 | 26724
47893 | 413.4581 | 26724
47894 | 411.2664 | 26724
47895 | 432.9045 | 26724
47896 | 419.3182 | 26724
47897 | 424.4037 | 26724
47898 | 401.1785 | 26724
47899 | 426.5671 | 26724
47900 | 414.3821 | 26724
47901 | 424.4819 | 26724
47902 | 407.8968 | 26724
47903 | 415.1285 | 26724
47904 | 410.1997 | 26724
47905 | 418.7876 | 26724
47906 | 426.4265 | 26724
47907 | 417.9841 | 26724
47908 | 408.3584 | 26724
47909 | 423.0023 | 26724
47910 | 408.0996 | 26724
47911 | 423.909 | 26724
47912 | 412.0971 | 26724
47913 | 410.9386 | 26724
47914 | 420.2667 | 26724
47915 | 417.5768 | 26724
47916 | 413.7202 | 26724
47917 | 428.3073 | 26724
47918 | 415.4433 | 26724
47919 | 407.942 | 26724
47920 | 412.3968 | 26724
47921 | 430.0246 | 26724
47922 | 417.0347 | 26724
47923 | 421.9142 | 26724
47924 | 420.6468 | 26724
47925 | 419.5705 | 26724
47926 | 422.5691 | 26724
47927 | 414.7683 | 26724
47928 | 417.4265 | 26724
47929 | 406.0005 | 26724
47930 | 420.0029 | 26724
47931 | 415.0552 | 26724
47932 | 433.1632 | 26724
47933 | 421.1384 | 26724
47934 | 408.5662 | 26724
47935 | 416.4708 | 26724
47936 | 427.5604 | 26724
47937 | 414.1894 | 26724
47938 | 408.6657 | 26724
47939 | 406.8825 | 26724
47940 | 423.7599 | 26724
47941 | 433.3809 | 26724
47942 | 405.8494 | 26724
47943 | 429.0192 | 26724
47944 | 404.0059 | 26724
47945 | 426.1748 | 26724
47946 | 408.158 | 26724
47947 | 414.494 | 26724
47948 | 400.703 | 26724
47949 | 409.0029 | 26724
47950 | 415.3996 | 26724
47951 | 426.8287 | 26724
47952 | 412.0982 | 26724
47953 | 405.0108 | 26724
47954 | 414.2825 | 26724
47955 | 421.8225 | 26724
47956 | 424.9585 | 26724
47957 | 417.2152 | 26724
47958 | 411.7427 | 26724
47959 | 411.8631 | 26724
47960 | 421.7644 | 26724
47961 | 418.4514 | 26724
47962 | 414.2771 | 26724
47963 | 406.1936 | 26724
47964 | 417.4788 | 26724
47965 | 404.9975 | 26724
47966 | 428.7501 | 26724
47967 | 422.581 | 26724
47968 | 419.213 | 26724
47969 | 423.7933 | 26724
47970 | 410.8785 | 26724
47971 | 418.6247 | 26724
47972 | 421.9573 | 26724
47973 | 407.6183 | 26724
47974 | 407.8202 | 26724
47975 | 420.0165 | 26724
47976 | 421.8617 | 26724
47977 | 426.7717 | 26724
47978 | 421.8612 | 26724
47979 | 421.6106 | 26724
47980 | 423.7816 | 26724
47981 | 403.3359 | 26724
47982 | 423.5914 | 26724
47983 | 424.4842 | 26724
47984 | 412.1183 | 26724
47985 | 423.2958 | 26724
47986 | 410.731 | 26724
47987 | 400.162 | 26724
47988 | 415.8722 | 26724
47989 | 420.4779 | 26724
47990 | 411.4499 | 26724
47991 | 408.6225 | 26724
47992 | 412.0019 | 26724
47993 | 413.7749 | 26724
47994 | 404.5943 | 26724
47995 | 419.7572 | 26724
47996 | 414.461 | 26724
47997 | 418.522 | 26724
47998 | 433.5626 | 26724
47999 | 430.8984 | 26724
48000 | 420.9377 | 26724
48001 | 424.5234 | 26724
48002 | 420.137 | 26724
48003 | 419.3285 | 26724
48004 | 419.322 | 26724
48005 | 416.3931 | 26724
48006 | 416.0401 | 26724
48007 | 404.3567 | 26724
48008 | 414.9902 | 26724
48009 | 419.3909 | 26724
48010 | 418.2995 | 26724
48011 | 417.1078 | 26724
48012 | 410.8597 | 26724
48013 | 412.3186 | 26724
48014 | 415.6483 | 26724
48015 | 422.098 | 26724
48016 | 413.9558 | 26724
48017 | 417.4232 | 26724
48018 | 420.7785 | 26724
48019 | 426.7815 | 26724
48020 | 413.6982 | 26724
48021 | 414.5477 | 26724
48022 | 407.3321 | 26724
48023 | 409.3468 | 26724
48024 | 417.1177 | 26724
48025 | 423.1186 | 26724
48026 | 403.312 | 26724
48027 | 405.8104 | 26724
48028 | 399.4501 | 26724
48029 | 413.0972 | 26724
48030 | 412.6609 | 26724
48031 | 414.4966 | 26724
48032 | 403.7578 | 26724
48033 | 420.8133 | 26724
48034 | 415.9022 | 26724
48035 | 420.6687 | 26724
48036 | 435.0899 | 26724
48037 | 418.4997 | 26724
48038 | 423.3459 | 26724
48039 | 417.4557 | 26724
48040 | 407.5046 | 26724
48041 | 409.7506 | 26724
48042 | 408.8687 | 26724
48043 | 403.8871 | 26724
48044 | 415.2856 | 26724
48045 | 432.8537 | 26724
48046 | 420.4119 | 26724
48047 | 418.9628 | 26724
48048 | 407.1161 | 26724
48049 | 412.9172 | 26724
48050 | 409.7121 | 26724
48051 | 399.0986 | 26724
48052 | 431.9398 | 26724
48053 | 415.3557 | 26724
48054 | 417.755 | 26724
48055 | 404.0487 | 26724
48056 | 414.0979 | 26724
48057 | 433.432 | 26724
48058 | 409.4531 | 26724
48059 | 422.1266 | 26724
48060 | 424.6532 | 26724
48061 | 406.2269 | 26724
48062 | 415.7682 | 26724
48063 | 405.0029 | 26724
48064 | 415.1708 | 26724
48065 | 415.7232 | 26724
48066 | 413.5191 | 26724
48067 | 428.6446 | 26724
48068 | 419.2092 | 26724
48069 | 417.5798 | 26724
48070 | 419.5054 | 26724
48071 | 400.4189 | 26724
48072 | 406.7693 | 26724
48073 | 413.7361 | 26724
48074 | 416.1443 | 26724
48075 | 404.9246 | 26724
48076 | 408.8518 | 26724
48077 | 434.6307 | 26724
48078 | 415.12 | 26724
48079 | 410.9719 | 26724
48080 | 416.0768 | 26724
48081 | 422.1709 | 26724
48082 | 413.4048 | 26724
48083 | 421.4792 | 26724
48084 | 407.5964 | 26724
48085 | 403.8431 | 26724
48086 | 411.9493 | 26724
48087 | 425.6183 | 26724
48088 | 421.0406 | 26724
48089 | 417.2713 | 26724
48090 | 429.3929 | 26724
48091 | 414.94 | 26724
48092 | 424.7472 | 26724
48093 | 428.8854 | 26724
48094 | 408.2502 | 26724
48095 | 425.8947 | 26724
48096 | 406.1226 | 26724
48097 | 424.7666 | 26724
48098 | 412.6801 | 26724
48099 | 402.6741 | 26724
48100 | 429.8531 | 26724
48101 | 413.9134 | 26724
48102 | 414.4892 | 26724
48103 | 410.2069 | 26724
48104 | 425.7187 | 26724
48105 | 419.9011 | 26724
48106 | 429.8103 | 26724
48107 | 415.0109 | 26724
48108 | 403.19 | 26724
48109 | 436.8044 | 26724
48110 | 406.5637 | 26724
48111 | 411.8726 | 26724
48112 | 407.3919 | 26724
48113 | 418.5986 | 26724
48114 | 421.3122 | 26724
48115 | 426.2551 | 26724
48116 | 410.0419 | 26724
48117 | 414.6545 | 26724
48118 | 420.7457 | 26724
48119 | 421.2087 | 26724
48120 | 420.0686 | 26724
48121 | 418.7059 | 26724
48122 | 421.3545 | 26724
48123 | 414.591 | 26724
48124 | 409.8777 | 26724
48125 | 413.2919 | 26724
48126 | 411.3187 | 26724
48127 | 421.647 | 26724
48128 | 406.8769 | 26724
48129 | 403.8468 | 26724
48130 | 416.7448 | 26724
48131 | 406.3756 | 26724
48132 | 405.8394 | 26724
48133 | 422.9712 | 26724
48134 | 423.535 | 26724
48135 | 426.0366 | 26724
48136 | 399.7797 | 26724
48137 | 413.7223 | 26724
48138 | 427.1877 | 26724
48139 | 433.1792 | 26724
48140 | 423.7341 | 26724
48141 | 412.6866 | 26724
48142 | 423.884 | 26724
48143 | 426.8686 | 26724
48144 | 421.1425 | 26724
48145 | 415.6644 | 26724
48146 | 421.5535 | 26724
48147 | 417.3546 | 26724
48148 | 423.4172 | 26724
48149 | 421.3036 | 26724
48150 | 427.904 | 26724
48151 | 406.8815 | 26724
48152 | 421.3079 | 26724
48153 | 414.4647 | 26724
48154 | 408.3959 | 26724
48155 | 422.8823 | 26724
48156 | 426.2678 | 26724
48157 | 410.4576 | 26724
48158 | 412.1438 | 26724
48159 | 418.9802 | 26724
48160 | 422.4792 | 26724
48161 | 407.9758 | 26724
48162 | 417.6104 | 26724
48163 | 419.9993 | 26724
48164 | 427.0924 | 26724
48165 | 403.298 | 26724
48166 | 407.5995 | 26724
48167 | 411.6794 | 26724
48168 | 433.6491 | 26724
48169 | 423.6295 | 26724
48170 | 410.6917 | 26724
48171 | 408.5487 | 26724
48172 | 426.0552 | 26724
48173 | 424.2584 | 26724
48174 | 423.621 | 26724
48175 | 414.133 | 26724
48176 | 427.0148 | 26724
48177 | 418.5918 | 26724
48178 | 407.9768 | 26724
48179 | 424.3918 | 26724
48180 | 409.8934 | 26724
48181 | 404.1313 | 26724
48182 | 414.9162 | 26724
48183 | 415.2507 | 26724
48184 | 401.8012 | 26724
48185 | 416.1456 | 26724
48186 | 423.2072 | 26724
48187 | 413.1879 | 26724
48188 | 414.444 | 26724
48189 | 426.0746 | 26724
48190 | 406.4628 | 26724
48191 | 406.8803 | 26724
48192 | 417.2485 | 26724
48193 | 406.099 | 26724
48194 | 420.7692 | 26724
48195 | 418.5878 | 26724
48196 | 424.0691 | 26724
48197 | 406.6984 | 26724
48198 | 422.1962 | 26724
48199 | 421.2247 | 26724
48200 | 411.4992 | 26724
48201 | 429.0578 | 26724
48202 | 408.8218 | 26724
48203 | 415.3935 | 26724
48204 | 418.5842 | 26724
48205 | 402.5717 | 26724
48206 | 410.1616 | 26724
48207 | 399.9244 | 26724
48208 | 423.8288 | 26724
48209 | 420.8463 | 26724
48210 | 430.9839 | 26724
48211 | 421.1252 | 26724
48212 | 411.3495 | 26724
48213 | 421.46 | 26724
48214 | 408.6667 | 26724
48215 | 408.4046 | 26724
48216 | 417.1885 | 26724
48217 | 420.4143 | 26724
48218 | 412.2004 | 26724
48219 | 409.6566 | 26724
48220 | 421.8707 | 26724
48221 | 420.9359 | 26724
48222 | 406.3511 | 26724
48223 | 421.1591 | 26724
48224 | 417.9505 | 26724
48225 | 410.7209 | 26724
48226 | 406.6897 | 26724
48227 | 429.0646 | 26724
48228 | 415.6855 | 26724
48229 | 403.1933 | 26724
48230 | 402.0811 | 26724
48231 | 420.6006 | 26724
48232 | 428.6722 | 26724
48233 | 402.811 | 26724
48234 | 423.4163 | 26724
48235 | 422.5356 | 26724
48236 | 431.1951 | 26724
48237 | 402.0977 | 26724
48238 | 405.9303 | 26724
48239 | 422.8445 | 26724
48240 | 421.9566 | 26724
48241 | 415.7474 | 26724
48242 | 422.5107 | 26724
48243 | 425.5821 | 26724
48244 | 417.5321 | 26724
48245 | 434.5131 | 26724
48246 | 415.2327 | 26724
48247 | 417.1065 | 26724
48248 | 411.3531 | 26724
48249 | 411.3228 | 26724
48250 | 420.6974 | 26724
48251 | 410.2957 | 26724
48252 | 419.9219 | 26724
48253 | 419.927 | 26724
48254 | 413.2127 | 26724
48255 | 421.7092 | 26724
48256 | 420.6276 | 26724
48257 | 406.0532 | 26724
48258 | 422.3486 | 26724
48259 | 406.6659 | 26724
48260 | 405.5999 | 26724
48261 | 427.8698 | 26724
48262 | 414.3842 | 26724
48263 | 418.8992 | 26724
48264 | 431.8906 | 26724
48265 | 410.8523 | 26724
48266 | 425.1951 | 26724
48267 | 411.9913 | 26724
48268 | 402.8197 | 26724
48269 | 416.3035 | 26724
48270 | 422.3176 | 26724
48271 | 424.4217 | 26724
48272 | 416.8232 | 26724
48273 | 415.9762 | 26724
48274 | 412.0924 | 26724
48275 | 424.2009 | 26724
48276 | 421.5702 | 26724
48277 | 410.7338 | 26724
48278 | 413.6248 | 26724
48279 | 415.2936 | 26724
48280 | 426.4545 | 26724
48281 | 417.7908 | 26724
48282 | 406.6823 | 26724
48283 | 406.5883 | 26724
48284 | 408.2956 | 26724
48285 | 405.2897 | 26724
48286 | 417.2825 | 26724
48287 | 404.6598 | 26724
48288 | 412.2906 | 26724
48289 | 431.855 | 26724
48290 | 406.207 | 26724
48291 | 397.9082 | 26724
48292 | 429.7678 | 26724
48293 | 423.2539 | 26724
48294 | 411.3608 | 26724
48295 | 412.9927 | 26724
48296 | 416.0234 | 26724
48297 | 413.1973 | 26724
48298 | 423.3649 | 26724
48299 | 423.5092 | 26724
48300 | 408.2052 | 26724
48301 | 416.7952 | 26724
48302 | 411.0784 | 26724
48303 | 425.7089 | 26724
48304 | 425.7251 | 26724
48305 | 420.0406 | 26724
48306 | 427.4333 | 26724
48307 | 408.0477 | 26724
48308 | 418.5468 | 26724
48309 | 402.8445 | 26724
48310 | 415.7554 | 26724
48311 | 422.2997 | 26724
48312 | 429.0336 | 26724
48313 | 415.0011 | 26724
48314 | 412.9768 | 26724
48315 | 409.7501 | 26724
48316 | 415.7325 | 26724
48317 | 425.3771 | 26724
48318 | 422.6107 | 26724
48319 | 414.6444 | 26724
48320 | 429.1378 | 26724
48321 | 408.6944 | 26724
48322 | 416.0686 | 26724
48323 | 399.9252 | 26724
48324 | 415.757 | 26724
48325 | 435.2561 | 26724
48326 | 419.8739 | 26724
48327 | 416.2358 | 26724
48328 | 415.6127 | 26724
48329 | 413.4131 | 26724
48330 | 402.8012 | 26724
48331 | 407.525 | 26724
48332 | 411.6672 | 26724
48333 | 409.2431 | 26724
48334 | 408.3854 | 26724
48335 | 423.4606 | 26724
48336 | 404.1385 | 26724
48337 | 418.0211 | 26724
48338 | 431.3335 | 26724
48339 | 410.708 | 26724
48340 | 421.8884 | 26724
48341 | 416.0651 | 26724
48342 | 406.0885 | 26724
48343 | 423.8613 | 26724
48344 | 410.9304 | 26724
48345 | 413.0598 | 26724
48346 | 416.5894 | 26724
48347 | 419.5675 | 26724
48348 | 404.0794 | 26724
48349 | 410.1888 | 26724
48350 | 428.4061 | 26724
48351 | 412.6008 | 26724
48352 | 416.498 | 26724
48353 | 419.3493 | 26724
48354 | 419.7601 | 26724
48355 | 412.9759 | 26724
48356 | 425.1487 | 26724
48357 | 409.641 | 26724
48358 | 407.6086 | 26724
48359 | 406.832 | 26724
48360 | 403.4728 | 26724
48361 | 415.4653 | 26724
48362 | 402.2419 | 26724
48363 | 406.0365 | 26724
48364 | 394.5204 | 26724
48365 | 404.6074 | 26724
48366 | 422.0669 | 26724
48367 | 420.1875 | 26724
48368 | 426.7109 | 26724
48369 | 418.2303 | 26724
48370 | 430.101 | 26724
48371 | 413.4029 | 26724
48372 | 426.9403 | 26724
48373 | 409.5588 | 26724
48374 | 405.7915 | 26724
48375 | 415.8249 | 26724
48376 | 419.4196 | 26724
48377 | 417.6868 | 26724
48378 | 411.7254 | 26724
48379 | 417.626 | 26724
48380 | 420.1417 | 26724
48381 | 424.6087 | 26724
48382 | 415.699 | 26724
48383 | 409.6519 | 26724
48384 | 407.2681 | 26724
48385 | 427.3506 | 26724
48386 | 417.7971 | 26724
48387 | 418.4488 | 26724
48388 | 418.397 | 26724
48389 | 431.2253 | 26724
48390 | 411.8942 | 26724
48391 | 430.9692 | 26724
48392 | 420.8336 | 26724
48393 | 418.339 | 26724
48394 | 427.712 | 26724
48395 | 417.5146 | 26724
48396 | 412.2494 | 26724
48397 | 417.7452 | 26724
48398 | 411.1108 | 26724
48399 | 414.9192 | 26724
48400 | 431.4057 | 26724
48401 | 417.4453 | 26724
48402 | 431.6785 | 26724
48403 | 409.8787 | 26724
48404 | 412.5386 | 26724
48405 | 423.0505 | 26724
48406 | 414.2182 | 26724
48407 | 417.3236 | 26724
48408 | 422.3032 | 26724
48409 | 424.9996 | 26724
48410 | 405.3614 | 26724
48411 | 418.4975 | 26724
48412 | 409.7718 | 26724
48413 | 424.4733 | 26724
48414 | 423.3723 | 26724
48415 | 422.5269 | 26724
48416 | 424.7404 | 26724
48417 | 410.0463 | 26724
48418 | 431.9735 | 26724
48419 | 412.4064 | 26724
48420 | 412.6104 | 26724
48421 | 415.7618 | 26724
48422 | 417.7803 | 26724
48423 | 412.9224 | 26724
48424 | 422.8746 | 26724
48425 | 422.3065 | 26724
48426 | 423.0019 | 26724
48427 | 412.3627 | 26724
48428 | 433.0224 | 26724
48429 | 421.4088 | 26724
48430 | 406.1214 | 26724
48431 | 405.1837 | 26724
48432 | 427.4251 | 26724
48433 | 407.9718 | 26724
48434 | 406.3799 | 26724
48435 | 417.2552 | 26724
48436 | 418.9453 | 26724
48437 | 409.1824 | 26724
48438 | 421.7726 | 26724
48439 | 415.109 | 26724
48440 | 428.3082 | 26724
48441 | 422.337 | 26724
48442 | 415.8684 | 26724
48443 | 423.4085 | 26724
48444 | 414.367 | 26724
48445 | 421.3501 | 26724
48446 | 412.8799 | 26724
48447 | 416.6369 | 26724
48448 | 419.9946 | 26724
48449 | 422.8299 | 26724
48450 | 403.8772 | 26724
48451 | 404.364 | 26724
48452 | 431.4697 | 26724
48453 | 426.5221 | 26724
48454 | 421.6061 | 26724
48455 | 417.501 | 26724
48456 | 416.9104 | 26724
48457 | 412.4439 | 26724
48458 | 421.4803 | 26724
48459 | 402.4359 | 26724
48460 | 418.7529 | 26724
48461 | 412.1456 | 26724
48462 | 411.2551 | 26724
48463 | 410.0566 | 26724
48464 | 405.1027 | 26724
48465 | 402.5894 | 26724
48466 | 406.4799 | 26724
48467 | 415.7407 | 26724
48468 | 414.4115 | 26724
48469 | 423.2036 | 26724
48470 | 419.6777 | 26724
48471 | 427.2463 | 26724
48472 | 422.808 | 26724
48473 | 414.2617 | 26724
48474 | 420.747 | 26724
48475 | 405.5811 | 26724
48476 | 419.092 | 26724
48477 | 414.662 | 26724
48478 | 425.5326 | 26724
48479 | 430.4397 | 26724
48480 | 410.5923 | 26724
48481 | 420.0554 | 26724
48482 | 404.9971 | 26724
48483 | 420.8404 | 26724
48484 | 414.482 | 26724
48485 | 406.2996 | 26724
48486 | 417.9967 | 26724
48487 | 410.1881 | 26724
48488 | 404.5201 | 26724
48489 | 415.7222 | 26724
48490 | 412.7192 | 26724
48491 | 408.1532 | 26724
48492 | 413.184 | 26724
48493 | 417.4394 | 26724
48494 | 415.3673 | 26724
48495 | 423.8144 | 26724
48496 | 419.965 | 26724
48497 | 396.8096 | 26724
48498 | 415.0292 | 26724
48499 | 417.8631 | 26724
48500 | 424.1733 | 26724
48501 | 415.6164 | 26724
48502 | 431.2482 | 26724
48503 | 434.7901 | 26724
48504 | 425.0492 | 26724
48505 | 421.2208 | 26724
48506 | 401.6396 | 26724
48507 | 426.183 | 26724
48508 | 427.9351 | 26724
48509 | 403.7624 | 26724
48510 | 423.8349 | 26724
48511 | 415.6964 | 26724
48512 | 397.2291 | 26724
48513 | 419.049 | 26724
48514 | 401.6466 | 26724
48515 | 409.8082 | 26724
48516 | 419.3234 | 26724
48517 | 410.05 | 26724
48518 | 417.7155 | 26724
48519 | 413.872 | 26724
48520 | 425.219 | 26724
48521 | 416.4752 | 26724
48522 | 410.1844 | 26724
48523 | 423.2921 | 26724
48524 | 415.4111 | 26724
48525 | 414.3747 | 26724
48526 | 412.8685 | 26724
48527 | 409.337 | 26724
48528 | 407.4615 | 26724
48529 | 397.8014 | 26724
48530 | 408.8964 | 26724
48531 | 415.1612 | 26724
48532 | 401.1593 | 26724
48533 | 416.8042 | 26724
48534 | 418.6864 | 26724
48535 | 415.0531 | 26724
48536 | 422.4917 | 26724
48537 | 404.0106 | 26724
48538 | 409.0272 | 26724
48539 | 419.9353 | 26724
48540 | 412.9284 | 26724
48541 | 411.0345 | 26724
48542 | 423.9824 | 26724
48543 | 430.2796 | 26724
48544 | 415.6866 | 26724
48545 | 436.7658 | 26724
48546 | 405.1918 | 26724
48547 | 420.9718 | 26724
48548 | 406.6722 | 26724
48549 | 413.9158 | 26724
48550 | 416.47 | 26724
48551 | 414.8704 | 26724
48552 | 428.9029 | 26724
48553 | 427.2344 | 26724
48554 | 416.221 | 26724
48555 | 418.9446 | 26724
48556 | 410.122 | 26724
48557 | 421.2261 | 26724
48558 | 416.0924 | 26724
48559 | 414.0343 | 26724
48560 | 424.9805 | 26724
48561 | 421.8534 | 26724
48562 | 426.3183 | 26724
48563 | 426.0075 | 26724
48564 | 412.054 | 26724
48565 | 398.4804 | 26724
48566 | 400.5257 | 26724
48567 | 418.6714 | 26724
48568 | 410.3386 | 26724
48569 | 428.709 | 26724
48570 | 425.5501 | 26724
48571 | 419.6831 | 26724
48572 | 427.3332 | 26724
48573 | 412.7437 | 26724
48574 | 419.1658 | 26724
48575 | 406.1494 | 26724
48576 | 409.9132 | 26724
48577 | 420.8097 | 26724
48578 | 419.3471 | 26724
48579 | 410.8262 | 26724
48580 | 429.135 | 26724
48581 | 422.3634 | 26724
48582 | 414.1243 | 26724
48583 | 417.7547 | 26724
48584 | 409.9778 | 26724
48585 | 429.1225 | 26724
48586 | 420.5299 | 26724
48587 | 418.5698 | 26724
48588 | 422.9964 | 26724
48589 | 411.754 | 26724
48590 | 413.4114 | 26724
48591 | 404.052 | 26724
48592 | 414.4189 | 26724
48593 | 410.7854 | 26724
48594 | 416.9617 | 26724
48595 | 410.4002 | 26724
48596 | 413.9517 | 26724
48597 | 423.0435 | 26724
48598 | 423.8849 | 26724
48599 | 423.1744 | 26724
48600 | 410.4598 | 26724
48601 | 427.1657 | 26724
48602 | 423.1819 | 26724
48603 | 420.9413 | 26724
48604 | 419.6114 | 26724
48605 | 405.1065 | 26724
48606 | 405.3392 | 26724
48607 | 430.7905 | 26724
48608 | 415.3805 | 26724
48609 | 413.5823 | 26724
48610 | 406.9067 | 26724
48611 | 415.7527 | 26724
48612 | 413.5984 | 26724
48613 | 419.2628 | 26724
48614 | 414.9148 | 26724
48615 | 423.9808 | 26724
48616 | 423.4225 | 26724
48617 | 418.9588 | 26724
48618 | 419.6948 | 26724
48619 | 422.0673 | 26724
48620 | 421.0357 | 26724
48621 | 428.4711 | 26724
48622 | 421.3224 | 26724
48623 | 428.2 | 26724
48624 | 426.2844 | 26724
48625 | 411.6475 | 26724
48626 | 410.7804 | 26724
48627 | 426.6063 | 26724
48628 | 409.9178 | 26724
48629 | 412.4452 | 26724
48630 | 428.7593 | 26724
48631 | 426.6514 | 26724
48632 | 421.4573 | 26724
48633 | 419.2967 | 26724
48634 | 410.1921 | 26724
48635 | 413.6864 | 26724
48636 | 415.2529 | 26724
48637 | 430.5212 | 26724
48638 | 410.8488 | 26724
48639 | 423.4372 | 26724
48640 | 413.8162 | 26724
48641 | 403.2703 | 26724
48642 | 410.641 | 26724
48643 | 403.4346 | 26724
48644 | 425.1567 | 26724
48645 | 403.1924 | 26724
48646 | 409.6352 | 26724
48647 | 428.5911 | 26724
48648 | 421.4479 | 26724
48649 | 411.178 | 26724
48650 | 410.7757 | 26724
48651 | 417.6569 | 26724
48652 | 417.835 | 26724
48653 | 409.8182 | 26724
48654 | 405.9154 | 26724
48655 | 416.9642 | 26724
48656 | 418.9467 | 26724
48657 | 411.6121 | 26724
48658 | 406.3341 | 26724
48659 | 408.9777 | 26724
48660 | 413.1762 | 26724
48661 | 414.8958 | 26724
48662 | 413.7805 | 26724
48663 | 417.6003 | 26724
48664 | 428.0281 | 26724
48665 | 421.4875 | 26724
48666 | 414.9088 | 26724
48667 | 419.8946 | 26724
48668 | 411.0469 | 26724
48669 | 413.8414 | 26724
48670 | 425.5636 | 26724
48671 | 419.9929 | 26724
48672 | 405.0614 | 26724
48673 | 416.0137 | 26724
48674 | 414.3751 | 26724
48675 | 406.6033 | 26724
48676 | 423.9828 | 26724
48677 | 420.2725 | 26724
48678 | 417.8148 | 26724
48679 | 419.2179 | 26724
48680 | 407.9587 | 26724
48681 | 410.6689 | 26724
48682 | 415.7817 | 26724
48683 | 407.9038 | 26724
48684 | 407.4563 | 26724
48685 | 430.7989 | 26724
48686 | 406.9193 | 26724
48687 | 412.622 | 26724
48688 | 421.7385 | 26724
48689 | 416.1063 | 26724
48690 | 408.0137 | 26724
48691 | 423.1755 | 26724
48692 | 429.2932 | 26724
48693 | 422.3199 | 26724
48694 | 404.0111 | 26724
48695 | 412.0789 | 26724
48696 | 421.0357 | 26724
48697 | 414.1391 | 26724
48698 | 417.5556 | 26724
48699 | 412.7906 | 26724
48700 | 406.0437 | 26724
48701 | 423.5278 | 26724
48702 | 418.2287 | 26724
48703 | 402.9319 | 26724
48704 | 422.4406 | 26724
48705 | 425.1257 | 26724
48706 | 413.7249 | 26724
48707 | 417.4129 | 26724
48708 | 432.546 | 26724
48709 | 420.5062 | 26724
48710 | 398.9795 | 26724
48711 | 408.7908 | 26724
48712 | 408.8119 | 26724
48713 | 423.0934 | 26724
48714 | 422.6425 | 26724
48715 | 439.0172 | 26724
48716 | 418.5039 | 26724
48717 | 416.5036 | 26724
48718 | 433.6835 | 26724
48719 | 423.787 | 26724
48720 | 417.0109 | 26724
48721 | 410.0897 | 26724
48722 | 420.9863 | 26724
48723 | 417.1816 | 26724
48724 | 417.0074 | 26724
48725 | 410.5017 | 26724
48726 | 403.1791 | 26724
48727 | 422.4185 | 26724
48728 | 421.5984 | 26724
48729 | 413.9532 | 26724
48730 | 415.5242 | 26724
48731 | 410.5291 | 26724
48732 | 407.4032 | 26724
48733 | 410.3997 | 26724
48734 | 397.0578 | 26724
48735 | 415.6867 | 26724
48736 | 427.3289 | 26724
48737 | 439.4007 | 26724
48738 | 414.4376 | 26724
48739 | 407.6094 | 26724
48740 | 421.3685 | 26724
48741 | 414.6193 | 26724
48742 | 430.999 | 26724
48743 | 409.3081 | 26724
48744 | 436.0023 | 26724
48745 | 401.1224 | 26724
48746 | 413.9717 | 26724
48747 | 429.1257 | 26724
48748 | 420.0053 | 26724
48749 | 413.0355 | 26724
48750 | 427.876 | 26724
48751 | 412.37 | 26724
48752 | 418.8106 | 26724
48753 | 408.4874 | 26724
48754 | 426.9766 | 26724
48755 | 409.04 | 26724
48756 | 410.9141 | 26724
48757 | 411.7717 | 26724
48758 | 423.4664 | 26724
48759 | 424.4549 | 26724
48760 | 410.2278 | 26724
48761 | 418.6949 | 26724
48762 | 417.0026 | 26724
48763 | 418.6664 | 26724
48764 | 410.514 | 26724
48765 | 415.0265 | 26724
48766 | 421.6937 | 26724
48767 | 417.2127 | 26724
48768 | 411.8081 | 26724
48769 | 420.6128 | 26724
48770 | 411.5174 | 26724
48771 | 418.7984 | 26724
48772 | 410.5462 | 26724
48773 | 430.9507 | 26724
48774 | 426.4602 | 26724
48775 | 400.509 | 26724
48776 | 428.3464 | 26724
48777 | 413.9383 | 26724
48778 | 422.4849 | 26724
48779 | 420.8131 | 26724
48780 | 412.9301 | 26724
48781 | 407.4341 | 26724
48782 | 413.4575 | 26724
48783 | 425.2046 | 26724
48784 | 406.1027 | 26724
48785 | 417.3566 | 26724
48786 | 419.6902 | 26724
48787 | 427.003 | 26724
48788 | 420.9028 | 26724
48789 | 429.0118 | 26724
48790 | 415.7647 | 26724
48791 | 420.7734 | 26724
48792 | 418.256 | 26724
48793 | 418.3898 | 26724
48794 | 413.2543 | 26724
48795 | 428.7011 | 26724
48796 | 419.111 | 26724
48797 | 412.041 | 26724
48798 | 402.3334 | 26724
48799 | 413.3301 | 26724
48800 | 416.6336 | 26724
48801 | 430.0882 | 26724
48802 | 413.8832 | 26724
48803 | 404.4164 | 26724
48804 | 408.0438 | 26724
48805 | 421.4787 | 26724
48806 | 414.2085 | 26724
48807 | 410.2539 | 26724
48808 | 413.8037 | 26724
48809 | 429.7829 | 26724
48810 | 408.718 | 26724
48811 | 408.0865 | 26724
48812 | 413.7863 | 26724
48813 | 414.3086 | 26724
48814 | 424.31 | 26724
48815 | 420.8058 | 26724
48816 | 423.5425 | 26724
48817 | 423.5546 | 26724
48818 | 420.7009 | 26724
48819 | 404.1127 | 26724
48820 | 418.9591 | 26724
48821 | 417.7424 | 26724
48822 | 425.9144 | 26724
48823 | 420.7957 | 26724
48824 | 404.8778 | 26724
48825 | 422.7179 | 26724
48826 | 422.6221 | 26724
48827 | 411.4564 | 26724
48828 | 438.103 | 26724
48829 | 413.7774 | 26724
48830 | 417.9354 | 26724
48831 | 420.9028 | 26724
48832 | 417.2451 | 26724
48833 | 407.3096 | 26724
48834 | 417.3096 | 26724
48835 | 406.219 | 26724
48836 | 407.2943 | 26724
48837 | 415.7344 | 26724
48838 | 407.5522 | 26724
48839 | 425.5415 | 26724
48840 | 418.185 | 26724
48841 | 412.9393 | 26724
48842 | 418.2949 | 26724
48843 | 409.1278 | 26724
48844 | 425.4868 | 26724
48845 | 407.4551 | 26724
48846 | 412.2042 | 26724
48847 | 409.8014 | 26724
48848 | 410.5107 | 26724
48849 | 427.1356 | 26724
48850 | 411.5854 | 26724
48851 | 409.694 | 26724
48852 | 417.974 | 26724
48853 | 418.9327 | 26724
48854 | 410.4085 | 26724
48855 | 415.9012 | 26724
48856 | 423.6304 | 26724
48857 | 405.9698 | 26724
48858 | 413.8839 | 26724
48859 | 417.0934 | 26724
48860 | 417.8108 | 26724
48861 | 423.8469 | 26724
48862 | 416.5458 | 26724
48863 | 411.532 | 26724
48864 | 417.3484 | 26724
48865 | 418.5794 | 26724
48866 | 422.5384 | 26724
48867 | 410.0893 | 26724
48868 | 419.5956 | 26724
48869 | 414.6004 | 26724
48870 | 426.793 | 26724
48871 | 407.9671 | 26724
48872 | 424.0262 | 26724
48873 | 424.654 | 26724
48874 | 421.5818 | 26724
48875 | 416.0232 | 26724
48876 | 399.6539 | 26724
48877 | 415.1577 | 26724
48878 | 409.675 | 26724
48879 | 410.6809 | 26724
48880 | 412.6929 | 26724
48881 | 407.1003 | 26724
48882 | 417.1542 | 26724
48883 | 420.7993 | 26724
48884 | 424.2091 | 26724
48885 | 420.1883 | 26724
48886 | 412.0247 | 26724
48887 | 416.7894 | 26724
48888 | 412.4589 | 26724
48889 | 415.4812 | 26724
48890 | 409.6409 | 26724
48891 | 425.5324 | 26724
48892 | 410.3743 | 26724
48893 | 418.1076 | 26724
48894 | 416.1444 | 26724
48895 | 422.1226 | 26724
48896 | 406.4875 | 26724
48897 | 410.6338 | 26724
48898 | 420.2737 | 26724
48899 | 400.3149 | 26724
48900 | 410.3422 | 26724
48901 | 419.3489 | 26724
48902 | 422.4988 | 26724
48903 | 426.3589 | 26724
48904 | 413.607 | 26724
48905 | 416.8749 | 26724
48906 | 408.6894 | 26724
48907 | 419.6747 | 26724
48908 | 423.9622 | 26724
48909 | 418.652 | 26724
48910 | 418.1615 | 26724
48911 | 403.4847 | 26724
48912 | 437.0148 | 26724
48913 | 408.2253 | 26724
48914 | 407.0592 | 26724
48915 | 415.5439 | 26724
48916 | 420.0082 | 26724
48917 | 407.1625 | 26724
48918 | 420.4846 | 26724
48919 | 420.7064 | 26724
48920 | 427.1574 | 26724
48921 | 424.9647 | 26724
48922 | 412.5798 | 26724
48923 | 415.9932 | 26724
48924 | 414.1539 | 26724
48925 | 411.5388 | 26724
48926 | 406.821 | 26724
48927 | 423.3738 | 26724
48928 | 430.3375 | 26724
48929 | 425.3741 | 26724
48930 | 425.26 | 26724
48931 | 416.0381 | 26724
48932 | 418.0183 | 26724
48933 | 410.3574 | 26724
48934 | 410.3541 | 26724
48935 | 419.2477 | 26724
48936 | 406.3402 | 26724
48937 | 423.2779 | 26724
48938 | 427.1067 | 26724
48939 | 409.3984 | 26724
48940 | 416.187 | 26724
48941 | 422.3629 | 26724
48942 | 421.454 | 26724
48943 | 417.5474 | 26724
48944 | 414.4751 | 26724
48945 | 416.563 | 26724
48946 | 413.9861 | 26724
48947 | 430.9041 | 26724
48948 | 416.844 | 26724
48949 | 411.4036 | 26724
48950 | 401.9594 | 26724
48951 | 427.4575 | 26724
48952 | 417.3305 | 26724
48953 | 423.169 | 26724
48954 | 402.8114 | 26724
48955 | 415.9935 | 26724
48956 | 418.7412 | 26724
48957 | 407.5976 | 26724
48958 | 431.4982 | 26724
48959 | 417.7473 | 26724
48960 | 414.046 | 26724
48961 | 422.1635 | 26724
48962 | 414.5054 | 26724
48963 | 419.7284 | 26724
48964 | 427.5022 | 26724
48965 | 414.7586 | 26724
48966 | 421.8267 | 26724
48967 | 420.0359 | 26724
48968 | 415.9333 | 26724
48969 | 417.8538 | 26724
48970 | 419.631 | 26724
48971 | 423.2782 | 26724
48972 | 436.1158 | 26724
48973 | 422.3243 | 26724
48974 | 410.22 | 26724
48975 | 404.0764 | 26724
48976 | 407.6721 | 26724
48977 | 410.3671 | 26724
48978 | 416.7593 | 26724
48979 | 428.8808 | 26724
48980 | 422.1558 | 26724
48981 | 419.7468 | 26724
48982 | 414.7446 | 26724
48983 | 425.7342 | 26724
48984 | 421.8506 | 26724
48985 | 426.681 | 26724
48986 | 428.3964 | 26724
48987 | 412.6835 | 26724
48988 | 410.257 | 26724
48989 | 419.5079 | 26724
48990 | 414.461 | 26724
48991 | 425.015 | 26724
48992 | 422.8976 | 26724
48993 | 420.9209 | 26724
48994 | 416.7872 | 26724
48995 | 421.1707 | 26724
48996 | 412.2993 | 26724
48997 | 418.6189 | 26724
48998 | 405.3937 | 26724
48999 | 422.2741 | 26724
49000 | 422.3252 | 26724
49001 | 412.1982 | 26724
49002 | 428.7152 | 26724
49003 | 420.7461 | 26724
49004 | 420.7655 | 26724
49005 | 417.1707 | 26724
49006 | 417.8181 | 26724
49007 | 423.2222 | 26724
49008 | 415.021 | 26724
49009 | 421.7903 | 26724
49010 | 416.1868 | 26724
49011 | 412.2292 | 26724
49012 | 418.584 | 26724
49013 | 416.026 | 26724
49014 | 418.6747 | 26724
49015 | 429.1533 | 26724
49016 | 409.7111 | 26724
49017 | 419.3927 | 26724
49018 | 417.1198 | 26724
49019 | 406.3469 | 26724
49020 | 408.004 | 26724
49021 | 420.2519 | 26724
49022 | 411.2506 | 26724
49023 | 400.6045 | 26724
49024 | 420.8949 | 26724
49025 | 414.3997 | 26724
49026 | 413.5623 | 26724
49027 | 427.2767 | 26724
49028 | 433.0352 | 26724
49029 | 412.2516 | 26724
49030 | 427.1359 | 26724
49031 | 429.5967 | 26724
49032 | 406.2382 | 26724
49033 | 423.8877 | 26724
49034 | 402.2243 | 26724
49035 | 403.4347 | 26724
49036 | 417.5639 | 26724
49037 | 413.7019 | 26724
49038 | 427.0055 | 26724
49039 | 409.1325 | 26724
49040 | 415.2739 | 26724
49041 | 420.721 | 26724
49042 | 416.6102 | 26724
49043 | 417.794 | 26724
49044 | 409.9611 | 26724
49045 | 428.5797 | 26724
49046 | 422.0752 | 26724
49047 | 405.4418 | 26724
49048 | 411.7379 | 26724
49049 | 422.6972 | 26724
49050 | 405.7649 | 26724
49051 | 422.8298 | 26724
49052 | 413.9968 | 26724
49053 | 409.5118 | 26724
49054 | 419.6278 | 26724
49055 | 410.3441 | 26724
49056 | 425.974 | 26724
49057 | 409.3748 | 26724
49058 | 432.5376 | 26724
49059 | 418.46 | 26724
49060 | 419.3685 | 26724
49061 | 406.9993 | 26724
49062 | 415.9455 | 26724
49063 | 410.9213 | 26724
49064 | 419.8641 | 26724
49065 | 417.4573 | 26724
49066 | 401.176 | 26724
49067 | 434.2393 | 26724
49068 | 415.1932 | 26724
49069 | 425.2141 | 26724
49070 | 407.3664 | 26724
49071 | 413.6286 | 26724
49072 | 421.2214 | 26724
49073 | 418.283 | 26724
49074 | 405.147 | 26724
49075 | 409.8124 | 26724
49076 | 411.9522 | 26724
49077 | 414.3734 | 26724
49078 | 422.9162 | 26724
49079 | 402.9145 | 26724
49080 | 415.9154 | 26724
49081 | 403.0846 | 26724
49082 | 415.2847 | 26724
49083 | 407.5787 | 26724
49084 | 417.0915 | 26724
49085 | 420.4579 | 26724
49086 | 420.5131 | 26724
49087 | 411.8685 | 26724
49088 | 416.3306 | 26724
49089 | 422.3152 | 26724
49090 | 419.1391 | 26724
49091 | 408.6328 | 26724
49092 | 410.823 | 26724
49093 | 405.7862 | 26724
49094 | 419.8092 | 26724
49095 | 413.5699 | 26724
49096 | 428.3203 | 26724
49097 | 418.0375 | 26724
49098 | 418.3807 | 26724
49099 | 413.7003 | 26724
49100 | 421.0789 | 26724
49101 | 406.5048 | 26724
49102 | 423.4082 | 26724
49103 | 413.0704 | 26724
49104 | 422.567 | 26724
49105 | 418.4295 | 26724
49106 | 402.5051 | 26724
49107 | 410.6657 | 26724
49108 | 430.2977 | 26724
49109 | 417.9438 | 26724
49110 | 421.2227 | 26724
49111 | 430.6808 | 26724
49112 | 421.9774 | 26724
49113 | 413.5894 | 26724
49114 | 416.5808 | 26724
49115 | 412.9774 | 26724
49116 | 418.9103 | 26724
49117 | 410.9252 | 26724
49118 | 414.4394 | 26724
49119 | 422.0262 | 26724
49120 | 436.0763 | 26724
49121 | 435.8137 | 26724
49122 | 411.0901 | 26724
49123 | 425.057 | 26724
49124 | 408.2798 | 26724
49125 | 423.3528 | 26724
49126 | 427.0685 | 26724
49127 | 403.644 | 26724
49128 | 424.9331 | 26724
49129 | 415.5947 | 26724
49130 | 415.8422 | 26724
49131 | 432.9663 | 26724
49132 | 407.8723 | 26724
49133 | 412.5861 | 26724
49134 | 427.6708 | 26724
49135 | 412.5145 | 26724
49136 | 422.9508 | 26724
49137 | 421.1835 | 26724
49138 | 424.0985 | 26724
49139 | 415.0189 | 26724
49140 | 406.7592 | 26724
49141 | 415.2962 | 26724
49142 | 422.7857 | 26724
49143 | 427.8839 | 26724
49144 | 412.8289 | 26724
49145 | 416.2268 | 26724
49146 | 412.1484 | 26724
49147 | 423.4579 | 26724
49148 | 408.4024 | 26724
49149 | 419.648 | 26724
49150 | 415.6393 | 26724
49151 | 420.6699 | 26724
49152 | 435.1563 | 26724
49153 | 410.1527 | 26724
49154 | 415.2303 | 26724
49155 | 417.3969 | 26724
49156 | 420.2722 | 26724
49157 | 409.8436 | 26724
49158 | 422.3023 | 26724
49159 | 406.8109 | 26724
49160 | 422.8776 | 26724
49161 | 426.5724 | 26724
49162 | 415.3815 | 26724
49163 | 405.366 | 26724
49164 | 419.1401 | 26724
49165 | 400.5727 | 26724
49166 | 425.8809 | 26724
49167 | 420.1434 | 26724
49168 | 421.4343 | 26724
49169 | 419.6616 | 26724
49170 | 400.3608 | 26724
49171 | 424.5715 | 26724
49172 | 406.243 | 26724
49173 | 411.8137 | 26724
49174 | 424.4587 | 26724
49175 | 417.7233 | 26724
49176 | 432.1881 | 26724
49177 | 420.7266 | 26724
49178 | 429.8737 | 26724
49179 | 412.2525 | 26724
49180 | 419.104 | 26724
49181 | 416.4175 | 26724
49182 | 429.0094 | 26724
49183 | 408.5332 | 26724
49184 | 427.4788 | 26724
49185 | 413.4019 | 26724
49186 | 424.3404 | 26724
49187 | 401.2122 | 26724
49188 | 417.808 | 26724
49189 | 423.0395 | 26724
49190 | 401.0016 | 26724
49191 | 424.1422 | 26724
49192 | 412.2706 | 26724
49193 | 414.18 | 26724
49194 | 427.4671 | 26724
49195 | 409.1697 | 26724
49196 | 404.3514 | 26724
49197 | 425.9569 | 26724
49198 | 422.3454 | 26724
49199 | 422.0704 | 26724
49200 | 436.6209 | 26724
49201 | 401.8786 | 26724
49202 | 421.403 | 26724
49203 | 415.6875 | 26724
49204 | 429.9581 | 26724
49205 | 408.7486 | 26724
49206 | 419.5926 | 26724
49207 | 429.8176 | 26724
49208 | 415.2167 | 26724
49209 | 421.2062 | 26724
49210 | 426.7093 | 26724
49211 | 419.1077 | 26724
49212 | 414.8507 | 26724
49213 | 417.1372 | 26724
49214 | 414.2707 | 26724
49215 | 421.3179 | 26724
49216 | 411.5825 | 26724
49217 | 434.6195 | 26724
49218 | 416.4362 | 26724
49219 | 413.2269 | 26724
49220 | 409.5377 | 26724
49221 | 410.0473 | 26724
49222 | 426.5366 | 26724
49223 | 407.0603 | 26724
49224 | 406.36 | 26724
49225 | 411.0508 | 26724
49226 | 416.9761 | 26724
49227 | 426.5002 | 26724
49228 | 412.0641 | 26724
49229 | 411.6431 | 26724
49230 | 408.5154 | 26724
49231 | 418.0237 | 26724
49232 | 416.8809 | 26724
49233 | 421.5816 | 26724
49234 | 411.6191 | 26724
49235 | 397.7983 | 26724
49236 | 414.1325 | 26724
49237 | 416.2758 | 26724
49238 | 415.5847 | 26724
49239 | 405.2501 | 26724
49240 | 413.5145 | 26724
49241 | 416.0488 | 26724
49242 | 429.446 | 26724
49243 | 424.5685 | 26724
49244 | 414.5833 | 26724
49245 | 421.8558 | 26724
49246 | 420.8349 | 26724
49247 | 431.0888 | 26724
49248 | 412.425 | 26724
49249 | 417.2683 | 26724
49250 | 418.3917 | 26724
49251 | 418.6218 | 26724
49252 | 419.1605 | 26724
49253 | 423.9682 | 26724
49254 | 403.2631 | 26724
49255 | 408.8229 | 26724
49256 | 405.8798 | 26724
49257 | 420.9779 | 26724
49258 | 409.3849 | 26724
49259 | 408.0152 | 26724
49260 | 413.5131 | 26724
49261 | 407.2512 | 26724
49262 | 416.4531 | 26724
49263 | 407.3078 | 26724
49264 | 416.6189 | 26724
49265 | 434.0876 | 26724
49266 | 414.9539 | 26724
49267 | 414.6495 | 26724
49268 | 420.2235 | 26724
49269 | 420.2867 | 26724
49270 | 426.6795 | 26724
49271 | 409.608 | 26724
49272 | 414.7203 | 26724
49273 | 415.0289 | 26724
49274 | 427.398 | 26724
49275 | 403.0241 | 26724
49276 | 411.8335 | 26724
49277 | 430.8897 | 26724
49278 | 419.1539 | 26724
49279 | 417.2978 | 26724
49280 | 416.0228 | 26724
49281 | 431.4512 | 26724
49282 | 425.829 | 26724
49283 | 409.002 | 26724
49284 | 422.6034 | 26724
49285 | 417.5287 | 26724
49286 | 399.4236 | 26724
49287 | 430.3691 | 26724
49288 | 422.9146 | 26724
49289 | 421.5917 | 26724
49290 | 415.5945 | 26724
49291 | 417.6002 | 26724
49292 | 407.4167 | 26724
49293 | 424.0792 | 26724
49294 | 405.8704 | 26724
49295 | 428.2771 | 26724
49296 | 419.9702 | 26724
49297 | 412.6942 | 26724
49298 | 412.8317 | 26724
49299 | 415.0557 | 26724
49300 | 403.4042 | 26724
49301 | 430.2557 | 26724
49302 | 417.3993 | 26724
49303 | 408.2098 | 26724
49304 | 419.4883 | 26724
49305 | 429.6586 | 26724
49306 | 433.7121 | 26724
49307 | 421.9012 | 26724
49308 | 410.7446 | 26724
49309 | 421.0818 | 26724
49310 | 424.2837 | 26724
49311 | 423.0132 | 26724
49312 | 413.2369 | 26724
49313 | 416.9243 | 26724
49314 | 413.6138 | 26724
49315 | 405.5153 | 26724
49316 | 421.2457 | 26724
49317 | 418.3406 | 26724
49318 | 415.5751 | 26724
49319 | 427.2679 | 26724
49320 | 404.3447 | 26724
49321 | 423.4846 | 26724
49322 | 430.4203 | 26724
49323 | 413.6676 | 26724
49324 | 407.1463 | 26724
49325 | 404.4851 | 26724
49326 | 414.7062 | 26724
49327 | 420.4343 | 26724
49328 | 414.5147 | 26724
49329 | 401.5235 | 26724
49330 | 420.8461 | 26724
49331 | 424.1715 | 26724
49332 | 420.5902 | 26724
49333 | 412.6148 | 26724
49334 | 421.1559 | 26724
49335 | 400.3874 | 26724
49336 | 414.8196 | 26724
49337 | 425.6689 | 26724
49338 | 415.2634 | 26724
49339 | 426.1218 | 26724
49340 | 416.9215 | 26724
49341 | 428.0915 | 26724
49342 | 411.7047 | 26724
49343 | 413.2262 | 26724
49344 | 412.0006 | 26724
49345 | 411.6868 | 26724
49346 | 412.11 | 26724
49347 | 413.4727 | 26724
49348 | 409.2096 | 26724
49349 | 417.2385 | 26724
49350 | 417.8861 | 26724
49351 | 407.5013 | 26724
49352 | 418.2288 | 26724
49353 | 420.1781 | 26724
49354 | 411.4521 | 26724
49355 | 420.6394 | 26724
49356 | 437.3779 | 26724
49357 | 415.1435 | 26724
49358 | 415.3773 | 26724
49359 | 407.8806 | 26724
49360 | 405.5589 | 26724
49361 | 420.6833 | 26724
49362 | 413.135 | 26724
49363 | 423.6507 | 26724
49364 | 418.9057 | 26724
49365 | 427.9442 | 26724
49366 | 424.4549 | 26724
49367 | 415.4776 | 26724
49368 | 419.9011 | 26724
49369 | 412.8929 | 26724
49370 | 401.4068 | 26724
49371 | 406.5817 | 26724
49372 | 414.6919 | 26724
49373 | 417.4224 | 26724
49374 | 423.3931 | 26724
49375 | 403.1037 | 26724
49376 | 422.7643 | 26724
49377 | 408.305 | 26724
49378 | 408.868 | 26724
49379 | 420.8537 | 26724
49380 | 416.0566 | 26724
49381 | 401.7398 | 26724
49382 | 423.7287 | 26724
49383 | 419.8269 | 26724
49384 | 421.8887 | 26724
49385 | 417.7951 | 26724
49386 | 397.2151 | 26724
49387 | 421.902 | 26724
49388 | 405.6573 | 26724
49389 | 413.2522 | 26724
49390 | 418.3061 | 26724
49391 | 428.5277 | 26724
49392 | 411.5264 | 26724
49393 | 413.7786 | 26724
49394 | 426.552 | 26724
49395 | 421.9712 | 26724
49396 | 423.9472 | 26724
49397 | 409.1873 | 26724
49398 | 431.7669 | 26724
49399 | 434.1117 | 26724
49400 | 416.2995 | 26724
49401 | 404.3773 | 26724
49402 | 417.4989 | 26724
49403 | 427.8424 | 26724
49404 | 404.6657 | 26724
49405 | 425.1409 | 26724
49406 | 423.3803 | 26724
49407 | 415.9822 | 26724
49408 | 421.439 | 26724
49409 | 416.4617 | 26724
49410 | 413.1774 | 26724
49411 | 417.8239 | 26724
49412 | 407.0119 | 26724
49413 | 418.1508 | 26724
49414 | 417.8412 | 26724
49415 | 415.377 | 26724
49416 | 422.9053 | 26724
49417 | 428.1566 | 26724
49418 | 413.066 | 26724
49419 | 403.6122 | 26724
49420 | 429.1613 | 26724
49421 | 410.5427 | 26724
49422 | 416.0099 | 26724
49423 | 441.9121 | 26724
49424 | 413.4343 | 26724
49425 | 411.2489 | 26724
49426 | 406.8045 | 26724
49427 | 408.7277 | 26724
49428 | 411.6689 | 26724
49429 | 403.178 | 26724
49430 | 421.5707 | 26724
49431 | 416.8266 | 26724
49432 | 408.8938 | 26724
49433 | 411.5642 | 26724
49434 | 404.8992 | 26724
49435 | 410.1264 | 26724
49436 | 410.0318 | 26724
49437 | 413.502 | 26724
49438 | 408.8086 | 26724
49439 | 417.1453 | 26724
49440 | 405.2067 | 26724
49441 | 423.1925 | 26724
49442 | 419.1447 | 26724
49443 | 414.3684 | 26724
49444 | 433.8918 | 26724
49445 | 406.9222 | 26724
49446 | 395.4909 | 26724
49447 | 413.3761 | 26724
49448 | 404.0927 | 26724
49449 | 413.9314 | 26724
49450 | 418.0167 | 26724
49451 | 431.5044 | 26724
49452 | 425.7616 | 26724
49453 | 428.1049 | 26724
49454 | 411.9654 | 26724
49455 | 407.282 | 26724
49456 | 419.4118 | 26724
49457 | 412.4131 | 26724
49458 | 426.434 | 26724
49459 | 418.5107 | 26724
49460 | 417.8568 | 26724
49461 | 419.194 | 26724
49462 | 430.2281 | 26724
49463 | 427.7687 | 26724
49464 | 399.5078 | 26724
49465 | 426.996 | 26724
49466 | 405.7107 | 26724
49467 | 411.1067 | 26724
49468 | 427.6787 | 26724
49469 | 414.6975 | 26724
49470 | 408.7478 | 26724
49471 | 412.8343 | 26724
49472 | 408.588 | 26724
49473 | 414.2127 | 26724
49474 | 415.401 | 26724
49475 | 419.5438 | 26724
49476 | 402.1773 | 26724
49477 | 412.6295 | 26724
49478 | 422.0617 | 26724
49479 | 428.1205 | 26724
49480 | 402.469 | 26724
49481 | 423.4932 | 26724
49482 | 410.0161 | 26724
49483 | 420.9614 | 26724
49484 | 416.6356 | 26724
49485 | 412.2319 | 26724
49486 | 430.1597 | 26724
49487 | 408.2947 | 26724
49488 | 435.3363 | 26724
49489 | 407.8919 | 26724
49490 | 418.572 | 26724
49491 | 410.141 | 26724
49492 | 429.0069 | 26724
49493 | 416.9114 | 26724
49494 | 401.3032 | 26724
49495 | 408.4225 | 26724
49496 | 422.862 | 26724
49497 | 427.3984 | 26724
49498 | 416.2135 | 26724
49499 | 413.4881 | 26724
49500 | 433.0802 | 26724
49501 | 409.378 | 26724
49502 | 412.9542 | 26724
49503 | 412.3711 | 26724
49504 | 419.5496 | 26724
49505 | 414.5284 | 26724
49506 | 403.8634 | 26724
49507 | 423.2272 | 26724
49508 | 400.9337 | 26724
49509 | 400.4253 | 26724
49510 | 417.5214 | 26724
49511 | 411.7891 | 26724
49512 | 405.0735 | 26724
49513 | 416.4071 | 26724
49514 | 410.8688 | 26724
49515 | 415.6419 | 26724
49516 | 408.9533 | 26724
49517 | 416.5865 | 26724
49518 | 406.2111 | 26724
49519 | 418.2653 | 26724
49520 | 416.858 | 26724
49521 | 424.9551 | 26724
49522 | 419.1284 | 26724
49523 | 423.169 | 26724
49524 | 403.7598 | 26724
49525 | 397.2345 | 26724
49526 | 425.5725 | 26724
49527 | 421.7086 | 26724
49528 | 416.3035 | 26724
49529 | 416.7837 | 26724
49530 | 420.2625 | 26724
49531 | 424.775 | 26724
49532 | 434.0301 | 26724
49533 | 398.9346 | 26724
49534 | 423.1981 | 26724
49535 | 425.6458 | 26724
49536 | 421.381 | 26724
49537 | 418.2705 | 26724
49538 | 420.1536 | 26724
49539 | 423.9027 | 26724
49540 | 429.191 | 26724
49541 | 414.8567 | 26724
49542 | 401.8758 | 26724
49543 | 428.8915 | 26724
49544 | 431.9802 | 26724
49545 | 424.311 | 26724
49546 | 433.5704 | 26724
49547 | 421.2776 | 26724
49548 | 423.9299 | 26724
49549 | 409.0226 | 26724
49550 | 417.8405 | 26724
49551 | 411.1685 | 26724
49552 | 407.6382 | 26724
49553 | 431.9336 | 26724
49554 | 412.6826 | 26724
49555 | 425.4654 | 26724
49556 | 412.4765 | 26724
49557 | 416.3371 | 26724
49558 | 405.8374 | 26724
49559 | 420.6556 | 26724
49560 | 431.3166 | 26724
49561 | 431.4646 | 26724
49562 | 407.667 | 26724
49563 | 425.5533 | 26724
49564 | 409.7856 | 26724
49565 | 426.467 | 26724
49566 | 408.4314 | 26724
49567 | 416.7045 | 26724
49568 | 426.8334 | 26724
49569 | 414.4785 | 26724
49570 | 411.293 | 26724
49571 | 414.877 | 26724
49572 | 408.1444 | 26724
49573 | 427.9024 | 26724
49574 | 417.8948 | 26724
49575 | 414.7559 | 26724
49576 | 403.0721 | 26724
49577 | 411.7321 | 26724
49578 | 416.8481 | 26724
49579 | 431.8618 | 26724
49580 | 411.551 | 26724
49581 | 428.6184 | 26724
49582 | 405.8214 | 26724
49583 | 426.2339 | 26724
49584 | 422.0359 | 26724
49585 | 407.7964 | 26724
49586 | 421.5033 | 26724
49587 | 405.1623 | 26724
49588 | 425.7809 | 26724
49589 | 406.4041 | 26724
49590 | 412.5239 | 26724
49591 | 400.3171 | 26724
49592 | 404.8149 | 26724
49593 | 408.4634 | 26724
49594 | 417.5705 | 26724
49595 | 419.2364 | 26724
49596 | 415.6492 | 26724
49597 | 408.7022 | 26724
49598 | 415.6189 | 26724
49599 | 432.0604 | 26724
49600 | 413.6727 | 26724
49601 | 407.9009 | 26724
49602 | 409.9813 | 26724
49603 | 402.2314 | 26724
49604 | 424.8164 | 26724
49605 | 426.1767 | 26724
49606 | 408.0195 | 26724
49607 | 412.4953 | 26724
49608 | 413.2506 | 26724
49609 | 423.0776 | 26724
49610 | 428.489 | 26724
49611 | 418.0235 | 26724
49612 | 406.9525 | 26724
49613 | 411.4545 | 26724
49614 | 415.1069 | 26724
49615 | 416.3186 | 26724
49616 | 420.4378 | 26724
49617 | 428.8854 | 26724
49618 | 428.0844 | 26724
49619 | 414.1381 | 26724
49620 | 417.3983 | 26724
49621 | 430.121 | 26724
49622 | 406.593 | 26724
49623 | 421.4917 | 26724
49624 | 418.5296 | 26724
49625 | 402.7669 | 26724
49626 | 431.7972 | 26724
49627 | 419.678 | 26724
49628 | 424.8491 | 26724
49629 | 420.2212 | 26724
49630 | 428.6062 | 26724
49631 | 422.7205 | 26724
49632 | 432.1688 | 26724
49633 | 421.5118 | 26724
49634 | 413.5139 | 26724
49635 | 410.1253 | 26724
49636 | 428.7977 | 26724
49637 | 403.6777 | 26724
49638 | 421.2467 | 26724
49639 | 410.8009 | 26724
49640 | 405.3128 | 26724
49641 | 413.9265 | 26724
49642 | 415.3664 | 26724
49643 | 414.737 | 26724
49644 | 414.961 | 26724
49645 | 403.6235 | 26724
49646 | 423.0909 | 26724
49647 | 414.8793 | 26724
49648 | 415.0796 | 26724
49649 | 412.4933 | 26724
49650 | 410.1068 | 26724
49651 | 413.0601 | 26724
49652 | 413.2053 | 26724
49653 | 417.6306 | 26724
49654 | 428.1079 | 26724
49655 | 418.7857 | 26724
49656 | 428.9694 | 26724
49657 | 423.6934 | 26724
49658 | 427.2369 | 26724
49659 | 404.5056 | 26724
49660 | 416.7223 | 26724
49661 | 429.9525 | 26724
49662 | 420.7439 | 26724
49663 | 410.8379 | 26724
49664 | 408.7294 | 26724
49665 | 426.5504 | 26724
49666 | 421.8267 | 26724
49667 | 419.5927 | 26724
49668 | 415.9735 | 26724
49669 | 420.6285 | 26724
49670 | 409.138 | 26724
49671 | 408.7119 | 26724
49672 | 419.1674 | 26724
49673 | 420.8942 | 26724
49674 | 414.2684 | 26724
49675 | 422.3239 | 26724
49676 | 414.3928 | 26724
49677 | 401.7071 | 26724
49678 | 410.71 | 26724
49679 | 418.2131 | 26724
49680 | 432.1526 | 26724
49681 | 417.9412 | 26724
49682 | 424.286 | 26724
49683 | 419.9235 | 26724
49684 | 418.6773 | 26724
49685 | 426.5772 | 26724
49686 | 409.9155 | 26724
49687 | 410.9187 | 26724
49688 | 423.3538 | 26724
49689 | 425.8898 | 26724
49690 | 418.8944 | 26724
49691 | 427.0887 | 26724
49692 | 410.0162 | 26724
49693 | 428.1975 | 26724
49694 | 410.6423 | 26724
49695 | 421.3105 | 26724
49696 | 404.7113 | 26724
49697 | 428.2268 | 26724
49698 | 413.8614 | 26724
49699 | 406.6035 | 26724
49700 | 409.8691 | 26724
49701 | 409.0702 | 26724
49702 | 432.8226 | 26724
49703 | 428.3665 | 26724
49704 | 406.3156 | 26724
49705 | 409.817 | 26724
49706 | 404.7433 | 26724
49707 | 427.1526 | 26724
49708 | 415.7158 | 26724
49709 | 415.7357 | 26724
49710 | 415.6609 | 26724
49711 | 418.9442 | 26724
49712 | 409.2756 | 26724
49713 | 412.2567 | 26724
49714 | 422.9301 | 26724
49715 | 420.0239 | 26724
49716 | 429.5272 | 26724
49717 | 414.4499 | 26724
49718 | 405.1012 | 26724
49719 | 426.7407 | 26724
49720 | 406.0549 | 26724
49721 | 420.7778 | 26724
49722 | 432.4511 | 26724
49723 | 414.5689 | 26724
49724 | 412.9966 | 26724
49725 | 420.0979 | 26724
49726 | 416.7302 | 26724
49727 | 423.264 | 26724
49728 | 410.5499 | 26724
49729 | 406.47 | 26724
49730 | 401.3103 | 26724
49731 | 410.8379 | 26724
49732 | 418.4688 | 26724
49733 | 427.4871 | 26724
49734 | 426.0386 | 26724
49735 | 426.9594 | 26724
49736 | 425.5172 | 26724
49737 | 400.1035 | 26724
49738 | 412.2767 | 26724
49739 | 415.4466 | 26724
49740 | 406.5172 | 26724
49741 | 402.553 | 26724
49742 | 421.0292 | 26724
49743 | 420.7157 | 26724
49744 | 421.8587 | 26724
49745 | 412.2008 | 26724
49746 | 417.6586 | 26724
49747 | 418.3254 | 26724
49748 | 408.1351 | 26724
49749 | 415.5106 | 26724
49750 | 423.35 | 26724
49751 | 413.506 | 26724
49752 | 424.6577 | 26724
49753 | 425.7309 | 26724
49754 | 400.4233 | 26724
49755 | 425.3208 | 26724
49756 | 417.5484 | 26724
49757 | 418.3721 | 26724
49758 | 422.6076 | 26724
49759 | 419.9647 | 26724
49760 | 416.3323 | 26724
49761 | 425.7581 | 26724
49762 | 419.8941 | 26724
49763 | 423.7879 | 26724
49764 | 417.2183 | 26724
49765 | 433.0283 | 26724
49766 | 421.0401 | 26724
49767 | 417.0048 | 26724
49768 | 414.4685 | 26724
49769 | 408.0836 | 26724
49770 | 413.5525 | 26724
49771 | 418.2165 | 26724
49772 | 423.5672 | 26724
49773 | 418.8527 | 26724
49774 | 427.5114 | 26724
49775 | 418.6865 | 26724
49776 | 419.5035 | 26724
49777 | 410.0861 | 26724
49778 | 417.9035 | 26724
49779 | 430.7213 | 26724
49780 | 416.5117 | 26724
49781 | 411.6589 | 26724
49782 | 415.7832 | 26724
49783 | 432.237 | 26724
49784 | 417.2417 | 26724
49785 | 417.7468 | 26724
49786 | 424.1915 | 26724
49787 | 426.7566 | 26724
49788 | 411.4081 | 26724
49789 | 411.0251 | 26724
49790 | 415.4707 | 26724
49791 | 420.2483 | 26724
49792 | 415.4937 | 26724
49793 | 404.7341 | 26724
49794 | 429.0444 | 26724
49795 | 407.0531 | 26724
49796 | 431.8104 | 26724
49797 | 405.7648 | 26724
49798 | 412.4689 | 26724
49799 | 419.0291 | 26724
49800 | 414.074 | 26724
49801 | 407.7999 | 26724
49802 | 434.1387 | 26724
49803 | 408.7343 | 26724
49804 | 417.9631 | 26724
49805 | 417.6307 | 26724
49806 | 398.1731 | 26724
49807 | 421.3455 | 26724
49808 | 413.1819 | 26724
49809 | 417.8085 | 26724
49810 | 419.8466 | 26724
49811 | 414.3856 | 26724
49812 | 433.415 | 26724
49813 | 406.8354 | 26724
49814 | 416.8792 | 26724
49815 | 420.1061 | 26724
49816 | 423.9739 | 26724
49817 | 418.751 | 26724
49818 | 408.2385 | 26724
49819 | 403.8468 | 26724
49820 | 430.5214 | 26724
49821 | 413.4039 | 26724
49822 | 420.0721 | 26724
49823 | 418.272 | 26724
49824 | 404.4641 | 26724
49825 | 409.0408 | 26724
49826 | 412.9882 | 26724
49827 | 419.5518 | 26724
49828 | 434.9386 | 26724
49829 | 433.6998 | 26724
49830 | 421.9899 | 26724
49831 | 425.9199 | 26724
49832 | 428.3622 | 26724
49833 | 433.3196 | 26724
49834 | 424.4442 | 26724
49835 | 414.9023 | 26724
49836 | 409.4933 | 26724
49837 | 405.7622 | 26724
49838 | 412.4541 | 26724
49839 | 400.7272 | 26724
49840 | 432.0796 | 26724
49841 | 430.4725 | 26724
49842 | 397.0719 | 26724
49843 | 406.6843 | 26724
49844 | 427.5262 | 26724
49845 | 424.7843 | 26724
49846 | 429.172 | 26724
49847 | 419.4567 | 26724
49848 | 409.6632 | 26724
49849 | 406.9924 | 26724
49850 | 416.812 | 26724
49851 | 421.4663 | 26724
49852 | 424.1999 | 26724
49853 | 408.3171 | 26724
49854 | 403.0826 | 26724
49855 | 418.1205 | 26724
49856 | 412.8686 | 26724
49857 | 405.1652 | 26724
49858 | 421.4053 | 26724
49859 | 408.9123 | 26724
49860 | 407.8578 | 26724
49861 | 412.9846 | 26724
49862 | 419.8147 | 26724
49863 | 413.4103 | 26724
49864 | 410.4406 | 26724
49865 | 408.3716 | 26724
49866 | 406.684 | 26724
49867 | 435.6206 | 26724
49868 | 420.8577 | 26724
49869 | 411.0618 | 26724
49870 | 404.035 | 26724
49871 | 423.9547 | 26724
49872 | 417.1342 | 26724
49873 | 414.7777 | 26724
49874 | 415.2624 | 26724
49875 | 419.204 | 26724
49876 | 414.1711 | 26724
49877 | 416.8718 | 26724
49878 | 409.0092 | 26724
49879 | 413.0409 | 26724
49880 | 414.9654 | 26724
49881 | 420.5312 | 26724
49882 | 416.4534 | 26724
49883 | 426.676 | 26724
49884 | 413.6893 | 26724
49885 | 404.0743 | 26724
49886 | 425.3008 | 26724
49887 | 418.7526 | 26724
49888 | 413.266 | 26724
49889 | 427.6368 | 26724
49890 | 415.5734 | 26724
49891 | 410.9356 | 26724
49892 | 406.413 | 26724
49893 | 428.3946 | 26724
49894 | 401.6037 | 26724
49895 | 430.1855 | 26724
49896 | 405.7352 | 26724
49897 | 407.7808 | 26724
49898 | 424.3824 | 26724
49899 | 416.798 | 26724
49900 | 413.0352 | 26724
49901 | 414.4231 | 26724
49902 | 405.306 | 26724
49903 | 403.768 | 26724
49904 | 424.4201 | 26724
49905 | 425.2184 | 26724
49906 | 414.2696 | 26724
49907 | 409.6222 | 26724
49908 | 398.0777 | 26724
49909 | 430.6846 | 26724
49910 | 413.925 | 26724
49911 | 413.7301 | 26724
49912 | 416.4929 | 26724
49913 | 412.9645 | 26724
49914 | 417.0575 | 26724
49915 | 419.5756 | 26724
49916 | 426.6934 | 26724
49917 | 417.4677 | 26724
49918 | 409.0521 | 26724
49919 | 414.0274 | 26724
49920 | 407.4606 | 26724
49921 | 408.0868 | 26724
49922 | 418.8731 | 26724
49923 | 410.5924 | 26724
49924 | 405.9849 | 26724
49925 | 416.8251 | 26724
49926 | 414.6844 | 26724
49927 | 426.1982 | 26724
49928 | 422.1655 | 26724
49929 | 421.0082 | 26724
49930 | 409.571 | 26724
49931 | 425.6819 | 26724
49932 | 421.3535 | 26724
49933 | 401.1128 | 26724
49934 | 425.3512 | 26724
49935 | 419.7319 | 26724
49936 | 401.7342 | 26724
49937 | 419.996 | 26724
49938 | 430.7989 | 26724
49939 | 417.345 | 26724
49940 | 433.3581 | 26724
49941 | 423.8687 | 26724
49942 | 418.6319 | 26724
49943 | 417.8963 | 26724
49944 | 426.3005 | 26724
49945 | 426.0801 | 26724
49946 | 418.0746 | 26724
49947 | 405.2151 | 26724
49948 | 418.3306 | 26724
49949 | 411.1925 | 26724
49950 | 401.7369 | 26724
49951 | 428.4372 | 26724
49952 | 421.0484 | 26724
49953 | 406.4862 | 26724
49954 | 427.6487 | 26724
49955 | 416.5702 | 26724
49956 | 406.6094 | 26724
49957 | 414.1856 | 26724
49958 | 413.4727 | 26724
49959 | 428.3998 | 26724
49960 | 407.7292 | 26724
49961 | 404.6398 | 26724
49962 | 414.8024 | 26724
49963 | 416.5647 | 26724
49964 | 421.4116 | 26724
49965 | 418.8556 | 26724
49966 | 423.1163 | 26724
49967 | 420.0534 | 26724
49968 | 422.2673 | 26724
49969 | 403.9264 | 26724
49970 | 422.4546 | 26724
49971 | 403.0484 | 26724
49972 | 424.8433 | 26724
49973 | 421.8391 | 26724
49974 | 414.9777 | 26724
49975 | 431.5838 | 26724
49976 | 406.6535 | 26724
49977 | 413.2253 | 26724
49978 | 415.3424 | 26724
49979 | 412.3152 | 26724
49980 | 423.547 | 26724
49981 | 427.2354 | 26724
49982 | 413.2128 | 26724
49983 | 429.7948 | 26724
49984 | 414.173 | 26724
49985 | 424.5097 | 26724
49986 | 430.3379 | 26724
49987 | 432.1787 | 26724
49988 | 408.4319 | 26724
49989 | 417.1001 | 26724
49990 | 411.0668 | 26724
49991 | 418.4751 | 26724
49992 | 426.6478 | 26724
49993 | 416.769 | 26724
49994 | 424.7688 | 26724
49995 | 419.0699 | 26724
49996 | 409.7801 | 26724
49997 | 423.3758 | 26724
49998 | 425.6175 | 26724
49999 | 419.1952 | 26724
50000 | 423.1705 | 26724

## Key Findings
KEY FINDINGS
• Mean duration: 417 days • Deterministic model underestimated by 134 days. • 100% probability of exceeding 281-day target. • Realistic range: 390 to 443 days. • Expected cost impact: $26724

## Decision Tree
DECISION: How to handle the 'Unavailability of Materials' risk for Activity E?
Risk Details:
• Risk: Unavailability of Materials (E1)
• Probability: 30%
• Impact: $5,935
• EMV: $1,780.50
Decision Options: 1. Accept Risk 2. Mitigate Risk (Backup Supplier) 3. Transfer Risk (Insurance)
Decision Option | Cost if Risk Occurs | Cost if No Risk | Prob Risk Occurs | Prob No Risk | EMV
Accept Risk | 5935 | 0 | 0.3 | 0.7 | 1780.5
Mitigate ($1,000) | 6935 | 1000 | 0.1 | 0.9 | 1593.5
Transfer ($1,500) | 1687 | 1500 | 0.3 | 0.7 | 1556.1
Optimal Decision: Transfer ($1,500)
Expected Cost: $1556.1
EVPI (Value of Perfect Information):
224.4